## TS-0001 v1.0.0
Section | Title | # | Editors Note ID | Editor' Note | Reccommendation | Action |  |  | Complete | Owner/Contributor | CR
[6 empty] | Revise | Delete | Other
|  | 29 | 29 | [Count of Editor's Note references in v1.0.0 Doc]
1 | Scope |  |  | - | -
2 | References |  |  | - | -
3 | Definitions, abbreviations, and acronyms |  |  | - | -
4 | Conventions |  |  | - | -
5 | Architecture Model |  |  | - | -
6 | Configurations supported by oneM2M Architecture |  |  | - | -
7 | M2M Identification and addressing
8 | Description and Flows of Reference Points
8.1 | General Communication Flow Scheme on Mca and Mcc Reference Points
8.1.2 | Request | 1 | 8.1.2_0a | Need to figure out the impact of Role in different procedures
|  | 2 | 8.1.2.f_0 | Editor's Note: Example usage of all rc enumerated values needed. What is the use case for "nothing"?
|  | 3 | 8.1.2.f_1 | Editor's Note: Do we need to support use case for "no response expected" in this release.
|  | 4 | 8.1.2.g | Editors Note: This may be impacted by the management of access control policy which will be enhanced to take into account Hierarchical and non-Hierarchical URI.
|  | 5 | - | Rapportuer Note: Discussions during ARC#10bis. Contribution expected for the resolution of the above stated Editor's Note. | Remove
8.4 | Device Triggering
8.4.2 | General Procedure for Device Triggering |  |  | - | -
8.4.2.1 | Triggering procedure for targeting ASN/MN-CSE | 6 | 8.4.2.1.a | Editor's Note: M2M-Ext-ID is set on registration, how the IN-CSE gets it is FFS | FFS - Clarify or Find Technical Solution?
9 | Resource Management
9.5 | Resource Type Specification Conventions |  |  | Clean-up: Verify use of string delimited with '[' and ']'
9.6 | Resource Types
9.6.1 |  |  |  | Clean-up: Issue raised in discussion of ARC-2014-1491R01 Update table to match specification. Clairify use of [sq brackets] convention. | [5 empty] | Josef Blanz - Qualcomm
9.6.3 | Resource Type CSEBase
|  |  |  | Clean-up: Issues raised in discussion of ARC-2014-1477R01: <schedule> information in CSE. Also: Clarify what zero multiplicity means… | [5 empty] | Heedong Choi, LG Electronics
9.6.16 | Resource Type mgmtCmd | 7 | 9.6.16.a | Editor's Note: The types of management operations (e.g. cmdType) to be used by mgmtCmd are FFS. | FFS - Clarify or Find Technical Solution?
|  | 8 | 9.6.16.b | Editor’s Note: It is FFS for how to use execTarget for group management | FFS - Clarify or Find Technical Solution?
10 | Information Flows
10.1 | Basic Procedures
10.1.1 | CREATE ( C)
10.1.1.1 | Non-registration related CREATE procedure | 9 | 10.1.1.1.b | Editor's Note: AE or CSE may not have the ID upon its registration request. Alternative information for fr is FFS. | Discuss w/WG4 SEC and Clarify. FFS - Find Technical Solution?
|  | 10 | 10.1.1.1.c | Editor's Note: which parameters are deducted to be mandatory/optional in the request is for FFS. Clause 8.1 should provide a generic mechanism to identify mandatory params for a request by looking at how the resource is defined. E.g. If the attribute in the resource definition is identified as mandatory and it is of type RW, then it is also intended as mandatory in the request. | Discuss w/WG4 SEC and Clarify. FFS - Find Technical Solution?
|  | 11 | 10.1.1.1.d | Editor's Note: references to elements defined in sect 8 have been added here. They may be removed if we decide to move sect 8.1.2-4 to stage 3 doc. In this case, these references will be removed and sect 1 of this document would replace sect 8.1.2-4 in the TS-0001. | Discuss Sect 8 structure and Clarify.
|  | 12 | 10.1.1.1.e | Editor's Note: how far should the Receiver go back to a parent to look for an accessControlPolicyIDs is FFS | FFS - Clarify or Find Technical Solution?
10.1.1.2 | Registration related CREATE procedure |  |  | - | -
10.1.1.2.1 | CSE Registration procedure |  |  | Rappoterur Note: The picture designed for CSE is referenced also for AE in 10.1.1.2, but for AE is incorrect. Duplicate and correct it in 10.1.1.2 ?
Rapporteur Observation: The above stated Rapporteur Note added via contribution ARC-2014-1427. We need to have a contribution to correct the picture for clause 10.1.1.2. Fix the associated descriptions as well.
10.1.5 | NOTIFY (N) | 13 | 10.1.5.a | Editor's Note: not sure how to align this procedure with the other ones. The Receiver should also have a local processing, but if the address of the resource in the to is not one of the defined resource types what the receiver does is out of scope. However if the NOTIFY will corresponds to a create instance then the procedures described in the create should apply. This operation needs more refining. | Discuss and Clarify
|  | 14 | 10.1.5.b | Editor's note: General exceptions are FFS in particular for notification failures. | FFS - Clarify or Find Technical Solution?
10.2 | Resource Type-Specific Procedures
10.2.6 | Resource Discovery Procedure
10.2.6.2 | Discovery procedure via Retrieve Operation | 15 | 10.2.6.2.a | Editor's Note: It is FFS about discovery propagation mechanism, i.e. multi-hop discovery propagation and its policies | FFS - Clarify or Find Technical Solution?
10.2.9 | External Management Operations through <mgmtCmd>
10.2.9.3 | Retrieve <mgmtCmd> | 16 | 10.2.9.3.a | Editor's Note: We need to agree on a terminology on how to refer to a specific instance of a resource type. | Clarify notation
10.2.8.4 | Update <mgmtCmd> |  |  | - | -
10.2.8.5 | Delete <mgmtCmd> |  |  | - | -
10.2.9.6 | Execute <mgmtCmd> | 17 | 10.2.9.6.a | Editor's note: The definition of Execute is to be for FFS in clause 10.1. | Define / Align with Sect 10.1
|  | 18 | 10.2.8.6.b | Editor's Note: Reference to setps 004 and 005 needed. | Clarify / reference
10.2.9.7 | Cancel <execInstance> | 19 | 10.2.9.7.a | Editor's Note: The Cancel flow shall be updated based on the definition of EXEC procedure. | Clarify and Align with EXEC text
10.2.12 | Notification Procedures for Resource Subscription | 20 | 10.2.12.a | Editor's Note: The notification policy enforcement between subscription resource hosting CSE and the notification target CSE need to be FFS | FFS - Clarify or Find Technical Solution? |  | CR |  | TP 12 | Cisco, Ericsson, Huawei, LG | ARC-2014-1458R01
|  | 21 | 10.2.12.b | Editor's Note: How the latestNotify is carried in the notification is FFS | FFS - Clarify or Find Technical Solution? |  | CR |  | TP 12 | Cisco, Ericsson, Huawei, LG | ARC-2014-1458R01
|  | 22 | 10.2.12.c | Editor's Note: The specific threshold mentioned above needs to be added as an attribute in the <CSEBase> resource type. | Clarify threshold |  | CR |  | TP 12 | Cisco, Ericsson, Huawei, LG | ARC-2014-1458R01
11 | Trust Enabling Architecture
12 | Information Recording
12.2 | Offline Charging
12.2.1 | Architecture | 23 | 12.2.1.a | Editors Note: Update Figure 5.2.1-1 to include this new interface. | Align Architecture Figures
|  | 24 | 12.2.1.b | Editor's Note: Once this picture is moved to clause 5.5; need to remove the picture from here. | Align with Sect 5.2.2.5
12.2.4 | Correlation between charging information of M2M IN and charging in the access network | 25 | 12.2.4.a | Editor's Note: <<FFS>> | FFS - provide text for Technical Solution?
12.2.5 | Definition of Charging Information
12.2.5.3 | Structure of the Accounting Message Formats
12.2.5.3.1 | Accounting-Request Message | 26 | 12.2.5.3.1.b | Editors Note: The inclusion of additional information is FFS | FFS - provide text for Technical Solution?
Annex A | (informative): Mapping of Requirements with CSFs |  |  | - | -
Annex B | (informative): oneM2M System and 3GPP MTC Release-11 Underlying Network Interworking |  |  | - | -
Annex C | (informative): Interworking between oneM2M System and 3GPP2 Underlying Networks |  |  | - | -
Annex D | (normative): <mgmtObj> Resource Instances Description |  |  | - | -
Annex E | (informative): CSE Minimum Provisioning |  |  | - | -
Annex F | (informative): Interworking / Integration of non-oneM2M solutions and protocols |  |  | - | -
F.1 | Introduction |  |  | - | -
F.2 | Interworking with non-oneM2M solutions through specialized interworking applications | 27 | F.2.a | Editor’s note: Figure title needed | Add Figure Title
|  | 28 | F.2.b | Editor's Note: Retargeting mechanisms may also be mentioned, if and when defined | Clarify or Find Technical Solution?
F.4 | Entity-relation representation of an non-IP based M2M Area network |  |  | - | -
F.4.1 | Responsibilities of the Interworking Proxy Application Entity (IPE) | 29 | F.4.1.a | Editor's Note: Mapping principles of the none-oneM2M information model into oneM2M resources is FFS. | FFS - Clarify or Find Technical Solution?
Annex G | (informative): List of M2M Services |  |  | - | -
Annex H | (informative): Object Identifier Based M2M Device Identifier |  |  | - | -