| INPUT CONTRIBUTION |
| --- |
| Group Name:* | Work Programme Management AHG |
| Title:* | Input to Work Programme Documentation |
| Source:* | Joachim Koss, Gemalto M2M joachim.koss@gemalto.com |
| Contact: | Joachim Koss, Gemalto M2M joachim.koss@gemalto.com |
| Date:* | 2014-05-16 |
| Abstract:* | This contribution provides inputs to the textual part of ADM-0001-oneM2M_Work_Programme |
| Agenda Item:* | 6 |
| Work item(s): | None |
| Document(s) Impacted* | None |
| Intended purpose of document:* | Decision Discussion Information Other <specify> |
| Decision requested or recommendation:* |  |

oneM2M Notice

The document to which this cover statement is attached is submitted to oneM2M.  Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by terms of the Working Procedures and the Partnership Agreement, including the Intellectual Property Rights (IPR) Principles Governing oneM2M Work found in Annex 1 of the Partnership Agreement.

1	Rational

Action A-WPM-2013-0008 requests all WPM participants to provide contributions on enhancing the ADM skeleton with content. This contribution on hand proposes some text.

2	Proposed text

- Definitions, symbols, abbreviations and acronyms
For the present document the following apply:

  - Definitions

Approval	means the decision of the Technical Plenary that a deliverable is ready for getting ratified in order to publish it (see process description in [2]).

Change Control	means the decision of a Working Group that the content of a draft deliverable is sufficiently advanced that it will utilize the Change Control process (see process description in [2]).

Drafting	means the editorial phase of a deliverable until it is placed under Change Control (see process description in [2]).

Forecast	means the date estimation (best guess) for the required milestones of a deliverable based on the current state of it taking into account the level of completeness, risks and uncertainties

Freeze	means the decision of a Working Group that the technical content of a draft deliverable is complete (given consideration of the Work Item scope and workplan), and it is frozen for further technical input (see process description in [2])

Level of completeness	means the estimation of how much of a deliverable has been already drafted in relation to the expected total amount being necessary for the approval

Milestone dates	means dates for the main process corner stones of a deliverable specified in the respective Work Item documents (see process description in [2])

Start	means the beginning of drafting a deliverable

Target	means a requested date for a deliverable which is specified in the respective Work Item document for all its main milestones

TP#n-1	means the last Technical Plenary meeting before the current one. The current one is the basis for an update of the Work Programme.

  - Symbols

none

  - Abbreviations, acronyms

ARC	Architecture
Doc_ID	Document Identifier
MAS	Management, Abstraction and Semantics
REQ	Requirements
SEC	Security
TP	Technical Plenary
TS	Technical Specification
WI	Work Item
WG	Working Group

- Conventions

Work Programme updates

Annex C - Form for updating planning (Register D) - serves for updating forecasts of milestone dates and level of completeness by the respective rapporteurs of the deliverables. For this purpose only the green marked entry cells are used. The dates in the target columns are taken from the actual revisions of the approved respective Work Item documents.

Scaling of level of completeness

- Value range from 0% - 100%, no special scaling requested.
Highest level achievable in a WG is 95%.

- Measurement will be against milestone “Approval” listed in the agreed respective Work Item (meaning that 100% completeness must be achieved for reaching this milestone)

- Expected levels of completeness at milestones:

- Start	-	   0%
First draft / skeleton	-	10% 
Freeze	-	90%
WG decision: “ready for approval”	 	95%

(shall be achieved for the deliverable being presented to Technical Plenary for approval, rest of 5 % is considered as remaining editorial effort for producing the final revision, which is candidate for TP ratification, candidate for getting published by the Partners Type 1)

- Approval (by TP)	-	100%