| INPUT CONTRIBUTION |
| --- |
| Group Name:* | Work Programme Management AHG |
| Title:* | Minutes of ETSI M2M Workshop PC conference call |
| Source:* | Joachim Koss, Gemalto M2M joachim.koss@gemalto.com |
| Contact: | Joachim Koss, Gemalto M2M joachim.koss@gemalto.com |
| Date:* | 2014-06-20 |
| Abstract:* | This contribution provides the minutes of the last ETSI M2M Workshop Programme Committee conference call of 2014-06-17 |
| Agenda Item:* | 6 |
| Work item(s): | None |
| Document(s) Impacted* | None |
| Intended purpose of document:* | Decision Discussion Information Other <specify> |
| Decision requested or recommendation:* |  |

oneM2M Notice

The document to which this cover statement is attached is submitted to oneM2M.  Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by terms of the Working Procedures and the Partnership Agreement, including the Intellectual Property Rights (IPR) Principles Governing oneM2M Work found in Annex 1 of the Partnership Agreement.

1	Rational

On 2014-06-17 the ETSI M2M Workshop Programme Committee had a conference call. The convenor of oneM2M TP ad-hoc group WPM participated as a new member of this Programme Committee representing the TP topics for the launch event as part of the 3-days M2M Workshop.

2	Minutes of December M2M Workshop – conference call 17 June 2014 taken by Nathalie Guinet (ETSI)

Objective of the call

The objective of the call was to discuss how to best integrate the oneM2M release 1 launch event into the already launched ETSI workshop on Machine to Machine (event endorsed by oneM2M).

- Participants present on call :

marylin.arndt@ORANGE.COM         Marylin ARNDT

gerry.mcauley@ETSI.ORG           Gerry Mc Auley

aurelie.sfez@ETSI.ORG            Aurélie SFEZ

omar.elloumi@ALCATEL-LUCENT.COM  Omar ELLOUMI

raymond.forbes@ERICSSON.COM      Ray FORBES

Francois.Ennesser@GEMALTO.COM    François ENNESSER

jean-luc.freisse@ETSI.ORG        Jean-luc FREISSE

nathalie.guinet@ETSI.ORG         Nathalie GUINET

karen.hughes@ETSI.ORG            Karen Hughes

seungmyeong.jeong@LGE.COM        Seoungmyeong JEONG

Joachim.Koss@GEMALTO.COM         Joachim KOSS

patricia.martigne@ORANGE.COM     Patricia MARTIGNE

ultan.mulligan@ETSI.ORG          Ultan MULLIGAN

Enrico.Scarrone@TELECOMITALIA.IT Enrico SCARRONE

joerg.swetina@NECLAB.EU          Joerg SWETINA

laurent.velez@ETSI.ORG           Laurent VELEZ

laurent.vreck@ETSI.ORG           Laurent VRECK

- Workshop Format validation:

09 Dec: “oneM2M Release 1 Launch event” handled by oneM2M WPM

10-11 Dec: agenda populated via the ongoing call for presentation and demonstrations

Joachim Koss presented the oneM2M Release 1 Launch event: this event is still to be formally approved by oneM2M, should be done by the end of June.

Planning has started within WPM sub group (Every 2 week conference calls), WPM has the task to proceed this as a big project and was asked to coordinate with ETSI M2M Workshop Programme Committee to ensure good coordination and consistency over the three days.

The “launch event” would be split into two parts:

- Morning dedicated to invited presentations on oneM2M aspects (no call, WPM invite the speakers they want).

- The afternoon would be showcases. Demos will illustrate various oneM2M architecture features

Nathalie Guinet suggested to have Luis Jorge Romero, the ETSI DG to open the launch event with an introduction speech. This was agreed.

Joachim is drafting a tender for demos to be sent to oneM2M (not showcase on company product) this is totally separated from the ongoing call for demos within the M2M workshop, however, it would be most welcome to allow the demos to stay over the next two days.

Ray: clarified that what is called demos is more “showcase” of a demo. Equipment could be set up in another room + video link.  Laurent Vreck proposed a recorded video of the demos + presentation by the presenter.

Agreements

- WPM is populating the oneM2M release 1 speaking part (speakers invited) and the demos for the day.

- From TWP, one from marcom and one person from WPM (demos and presentations) will join the M2M workshop Programme committee. Invite was sent to Richard Brennan (tbc) to liaise with the workshop organization.

- Logistically, Nathalie Guinet will take over WPM in getting the speakers to register, send their bios and presentations once WPM has provided their agenda for the speakers.

- From the proposals they receive, WPM will decide which demos go in the amphi, those outside.

- Details and Requirements in terms of IT infrastructure regarding the demos will be required as soon as possible to ensure that the ETSI Secretariat is able to evaluate the logistical and budgetary feasibility. The tender deadline is in 2 weeks, so in 2 weeks we will know more.

- Laurent Velez/ Aurélie Sfez will register to WPM group in order to ensure smooth coordination on the demos parts.

- Aurélie Sfez has offered to help with the provision of a questionnaire to help finding out the demo requirements.

- Demos could stay over the M2M workshop.

Action WPM : to input clear requirements on the demos to ETSI

Action ETSI:  evaluate feasibility and associated costs to meet the requirements

Next WPM call on 24 June, feedback after.

- Event timelines

Nathalie Guinet introduced the timelines that were agreed for the M2M workshop with the PC.

Joachim need to discuss this on 24 June.

M2M WORKSHOP:

First two weeks July:  select proposals and build draft agenda (one call, 2nd week of July, another one 3rd week of July)

M2M WS agenda finalization during oneM2M meeting in Sophia:  28 July – 1st August

1/08/2014: draft agenda online + speaker notification

It was proposed to use the opportunity of the oneM2M meeting to synchronize the two parts of the event.  So TWP should have their very stable draft agenda by the oneM2M meeting in July.

It was agreed to meet during the oneM2M meeting in July Wed.30 July : 13:00 to 14:00

Mid Sept: a massive communication with final agendas online will be sent.
OneM2M day should be fixed at that date (early September)

Communication aspects:

- No formal decision of oneM2M until 2 weeks.

- Reminder on the agreed timelines for M2M workshop agenda publication: deadline to contribute 30th June 2014 – no mention of the oneM2M launch event at this point in time.

Etsi has however to send a reminder to contribute to the M2M workshop in order not to hinder its smooth running.

- The launch event needs to be announced by the oneM2M partners through oneM2M MARCOM

- From the ETSI side, ETSI will send a CL and internal communication to its members, pr and news release as part of the ETSI M2M workshop.

- ETSI is hosting the event, most people will want to attend the oneM2M launch event and M2M workshop, ETSI is proposing to handle that.

- OneM2M MARCOM is responsible for all oneM2M visuals  (flyer, roll up, brochures etc…)

- The launch event day is a good opportunity for oneM2M to have brochures, pop ups. ETSI will not organize that directly. Budget is with the other partners and not with ETSI.

- Who is doing what

- OneM2M launch event

WPM defines the agenda of the 1st morning + work on demos (handle the demos proposals + speakers fishing)

Demos: in close contact with Laurent Velez/Aurélie Sfez

Decisions are made in WPM but shown to the ETSI M2M WS PC to ensure good coordination.

Joachim Koss: “transportation unit” for oneM2M WPM to M2M PC

WPM is composed of everyone registered to WPM, focusing on the launch event.

Joachim will send the agenda and minutes of WPM to the M2M WS mailing list.

Laurent Velez will be at the WPM call to handle demos.

Nathalie Guinet would like to assume the full responsibility of speakers follow  up for both events.

Aurélie Sfez would handle the organization of demos from the ETSI side.

M2M PC handles the ETSI M2M Workshop and is being kept informed of the oneM2M launch event.

AOB

No other business was raised during the call.