| INPUT CONTRIBUTION |
| --- |
| Group Name:* | Work Programme Management Ad Hoc Group; WPM#12.2 |
| Title:* | Showcase Demo Status |
| Source:* | Nicolas Damour, WPM Convenor (ndamour@sierrawireless.com) |
| Contact: | Nicolas Damour, WPM Convenor (ndamour@sierrawireless.com) |
| Date:* | 2014-09-02 |
| Abstract:* | Overview of the status of the organization of the demos planned during the oneM2M showcase event on December 9th 2014 |
| Agenda Item:* | 6.1. oneM2M Showcase agenda |
| Work item(s): | n/a |
| Document(s) Impacted* | None |
| Intended purpose of document:* | Decision Discussion Information Other <specify> |
| Decision requested or recommendation:* | To formally agree on the consolidated status presented in this document |

oneM2M Notice

The document to which this cover statement is attached is submitted to oneM2M.  Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by terms of the Working Procedures and the Partnership Agreement, including the Intellectual Property Rights (IPR) Principles Governing oneM2M Work found in Annex 1 of the Partnership Agreement.

1	Context of the two separate events

1.1	oneM2M Showcase Event

The oneM2M Showcase Event will take place on December 9th, 2014.

This event is kindly hosted by the ETSI in their Sophia Antipolis headquarters.

This event is co-organized by ETSI (as a host) and the oneM2M MARCOM group.

The detailed agenda of the oneM2M Showcase Event is under the responsibility of the oneM2M MARCOM group, who has delegated to the oneM2M TP WPM Ad-Hoc group the task of organizing the oneM2M Showcase Presentations, the oneM2M Showcase Demos and the oneM2M Exhibit Demos.

1.2	ETSI M2M Workshop

The ETSI M2M Workshop is a closely related yet separate event that will take place in the same location (ETSI Sophia Antipolis HQ) on December 10th and 11th, 2014.

The organization of the ETSI M2M Workshop is solely managed by the ETSI

Details of the ETSI M2M Workshop can be found on the dedicated ETSI event page:

http://www.etsi.org/news-events/events/768-2014-12-etsi-workshop-on-m2m

2	oneM2M Demos - Planning

On July 11th (UTC time), the oneM2M secretariat has sent to the email exploder lists oneM2M_TP@list.oneM2M.org and oneM2M_Marketing@LIST.ONEM2M.ORG a mail calling for showcase demonstrations for the oneM2M Event, to be submitted by interested member companies and partners, with a deadline set to August 8th 2014.

Following this call for submissions, nine submissions have been received by the oneM2M secretariat.

On August 13th 2014, during the WPM#12.1 conference call, these nine submissions have been disclosed and reviewed. All of them appeared to be within the scope of the tender for this event.

On August 14th, in accordance with the decision taken during WPM#12.1, Joachim Koss, in his capacity of WPM Acting Convenor, has sent an email to the email exploder list oneM2M_WP_Management@list.oneM2M.org to disclose the nine received submissions and ask for further comments by September 1st.

Time was also given to original submitters to discuss until September 1st and to merge some of the showcases if they wished to, in particular the submitters of the showcases 1+2 and 6, as it was felt that these may have been intended to be the same showcase (see action point A-WPM -12.1-003).

On September 2nd, during the WPM#12.2 conference call, we need to endorse the definite list of showcases that will receive both a speaking slot in the afternoon of the oneM2M Showcase Event as well as space to actually display their showcase.

This list will then be formally communicated by WPM to the oneM2M secretariat, and then via the same lists that the original tender was sent. It should be made clear in this mail that Exhibit Demos may still be considered (see next item).

MARCOM confirmed that there are three stages of information requested from the submitters of showcases:

Phase 1: Participating companies that will be named in the first oneM2M press release announcing the event mid-September – submitters must provide an up-to-date list of participant companies to each showcase before Monday September 8th.

Phase 2: Title and one-liner description of the showcases for the second press release around mid-October

Phase 3: Detailed description of the showcase and confirmed participants for the third press release and for the show catalog (deadline mid-November)

Up until September 30th, other proposals for Exhibit Demos may be received by the oneM2M secretariat. These will also be reviewed by WPM to check if they are following the expected guidelines, and will be considered for display on the same exhibit floor as the Showcase Demos, under the same conditions.

All submitters of Showcase Demos and/or Exhibit Demos may update their demo description as they progress in their work and shall make sure that on September 30th at the latest, they have sent a detailed description to the oneM2M secretariat as well as a final title and final one-liner description.

According to MARCOM’s requirements, participants have until October 31st (tbc by MARCOM) to “freeze” the detailed description of their showcase.

3	List of oneM2M Showcase Demos and Presentations

Out of the initial 9 contributions of showcase demos and presentations, after some proposals have been merged, we have the following list of seven showcase demos and presentations:

Showcase A: oneM2M/ESMIG Home Energy Management showcase

Submitted by ESMIG and other companies (to be listed later)

Merged from the original showcases #1, #2 and #6

Showcase B: Vehicle to Home Solution – Cross Vertical Application via Horizontal oneM2M Platform

Submitted by LG Electronics and LG U+; originally numbered showcase #3

Showcase C: Smart City Services and Multiple Service Layer Platforms Interworking

Submitted by KETI, InterDigital, NEC & Fraunhofer; originally numbered showcase #4

Showcase D: oneM2M enabled housekeeper with management and semantic support

Submitted by Huawei and China Unicom; originally numbered showcase #5

Showcase E: A oneM2M-based Continua Compliant Healthcare System and Interworking of Multiple oneM2M Service Layer Platforms

Submitted by Lamprey Networks; originally numbered showcase #7

Showcase F: Connected Vehicle Cloud based on oneM2M platform

Submitted by Ericsson; originally numbered showcase #8

Showcase G: OneM2M Business Application(s) for Smart Energy and Building Monitoring for Predictive Maintenance

Submitted by TELIT / ILS Technology LLC; originally numbered showcase #9

4	List of oneM2M Exhibit Demos

There are currently no candidates for oneM2M Exhibit Demos.