## Showcase
2014-09-24 | Owner | July |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  |  | January
startdate of week |  | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8 | 15 | 22 | 29 | 5 | 12 | 19 | 26
Calender Week |  | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 36 | 38 | 39 | 40 | 41 | 4142 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5
Coordinated Events |  | September 22 39: TP13; November 10 46: TP14; December 8 50: E; January 19 4: TP15; January 26 5: M2M-e
Actions
Showcase Demonstrations
Tender calling for demos | oneM2M secretariat | bar: July 7 28
Deadline for receiving commitments & draft demo description | oneM2M secretariat | bar: July 14 29 to August 4 32
Deadline for receiving description (one-line) of demo | oneM2M secretariat | September 29 40: 30
Deadline for receiving FINAL description of demo | oneM2M secretariat | October 27 44: 31
Demo hardware available on-site at ETSI (as applicable) | Demo Companies+ETSI CTI | December 1 49: tbd
Demo Display available on-site at ETSI | Demo Companies+MARCOM | bar: December 1 49
Demo run through | Demo Companies+ETSI CTI | December 8 50: 8
Demo Display set-up (Iris G2/G3) | Demo Companies | December 8 50: 8~9
oneM2M Showcase | oneM2M + ETSI | December 8 50: 9
ETSI M2M Workshop | ETSI | December 8 50: 10~11
Demo & Display tear-down (Iris G2/G3) | Demo Companies | December 8 50: 11
Showcase Presentations
detail suggestion for the agenda by email discussion | WPM & MARCOM | bar: July 7 28
final decision on agenda and speakers (Session 1 Business Focus) | MARCOM | August 25 35: 29; September 1 36: 02; September 15 38: 17; September 29 40: 30
final decision on agenda and speakers (Session 2 Technical Focus) | WPM (MARCOM involved) | August 25 35: 29; September 1 36: 02; September 15 38: 17; September 29 40: 30
Communicate Tender result to list | WPM | September 1 36: 05
agenda and speakers for demo presentations (Session 3, 4) | WPM (MARCOM involved) | September 22 39: 26
action plan available for further updates | MARCOM | July 7 28: 8; July 28 31: 28; August 4 32: 05©
Speaker Nominations (for Web publication) | WPM (MARCOM involved) | July 7 28: 8; July 28 31: 28>; August 4 32: >; August 11 33: >; August 18 34: >; August 25 35: 29; September 22 39: 26
Speaker Confirmations (for External PR) | WPM (MARCOM involved) | July 28 31: 28; September 8 36: 3; October 6 41: 10
Demo Presentation PPT Template Available | oneM2M secretariat | October 13 4142: 15
deadline for final presentations | Programme Committee | November 10 46: Draft 15; November 24 48: Final 30; December 8 50: 9
Session Dry Run (at TP14) | Joint WPM/Marcom | November 10 46: 12??
Media Communications
outline Communication Plan (This document) | MARCOM | July 28 31: 28; August 4 32: R01; September 15 38: R03; September 22 39: R05
create / update event ETSI Web page | ETSI | August 4 32: 8; August 11 33: >; August 18 34: >; August 25 35: >; September 1 36: 5; September 29 40: 29
create / update event oneM2M Web page | MARCOM | August 4 32: 8; August 11 33: >; August 18 34: >; August 25 35: >; September 1 36: 5; September 29 40: 29
Detailed Communication Plan (e.g. interviews) | MARCOM | July 28 31: 28; August 11 33: 15
[[ TP Press Release - Release 1 Announcement ]] | MARCOM (with TP) | August 4 32: 07©
Press Release #1 - Draft & Approve | MARCOM (with ETSI) | August 18 34: 18; August 25 35: 29; September 1 36: 05; September 22 39: 24
Press Release #1 - Event announcment | MARCOM (with ETSI) | September 1 36: 1 > 05; September 22 39: >; September 29 40: 29
Press Briefings - as scheduled | MARCOM | September 1 36: ???
Analyst Briefings - as scheduled | MARCOM | September 15 38: ???
Press Release #2 - Draft & Approve | MARCOM (with ETSI) | September 29 40: 29 - 3; October 13 4142: 15
Press Release #2 - Planned Agenda, Speakers, Demos | MARCOM (with ETSI) | October 6 41: 6; October 13 4142: >; October 20 43: 21
Press Release #3 - Draft & Approve | MARCOM (with ETSI) | November 3 45: 3 - 7
Press Release #3 - Final Agenda, Speakers, Demos | MARCOM (with ETSI) | November 10 46: 13
Salesware / Collateral
Identify/Engage Graphic Designer | MARCOM | August 4 32: 8; September 15 38: 15
Basic oneM2M Graphics update | Designer+MARCOM | August 11 33: 11; August 18 34: 22; September 29 40: 3
Update Brochure Content | MARCOM | August 11 33: 11; August 18 34: 22; September 29 40: 3
Update Single Sheet graphics(rev2) | Designer+MARCOM | August 18 34: 18; August 25 35: 29; October 6 41: 10
Distribute Single Sheet (rev2) for Regional use | MARCOM | August 25 35: 29; October 6 41: 10
Print Single Sheet (rev2) | MARCOM+Printer | September 1 36: 5; October 13 4142: 17
Update Brochure Content (rev2.1) | MARCOM
Update Single Sheet design (rev2.1) | Designer+MARCOM | November 3 45: 3; November 17 47: 21
Distribute Single Sheet (rev2.1) for Regional use | MARCOM | November 24 48: 28
Print Single Sheet (rev2.1) | MARCOM+Printer | November 24 48: 28
Single Sheet rev 2.1 - Deliver to Event site | MARCOM | December 1 49: 5
Identify/Engage Writer | MARCOM | August 18 34: 22; September 15 38: 15
Brochure Content Authoring | Writer+MARCOM | August 25 35: 25; September 15 38: 19; October 6 41: 10
Brochure design | Designer+MARCOM | September 22 39: 22; October 6 41: 10; October 20 43: 24
Brochure final version available | MARCOM | October 13 4142: 17; October 27 44: 31
Brochure - Print | MARCOM+Printer | October 27 44: 17; November 3 45: 7
Brochure - Deliver to Event site | MARCOM | December 1 49: 5
Event Brochure - Preparation | Program Committee+MARCOM | August 18 34: 18; August 25 35: 29; October 27 44: 27; November 10 46: 10
Event Brochure - Distribute (PDF / PUB) | Program Committee+MARCOM | September 1 36: 1; November 10 46: 14
Event Brochure - Print (Locally?) | MARCOM+Printer | September 1 36: a / r; November 10 46: a / r; December 1 49: 5
Catalogue for Demos - collect information | WPM (MARCOM involved) | September 29 40: 30
Catalogue for Demos - Cover Design | Designer+MARCOM | bar: October 13 4142; November 10 46
Catalogue for Demos - send to designer | ETSI (WPM involved) | October 13 4142: 13; November 10 46: 14
Catalogue for Demos - Content Integration | Designer+MARCOM | bar: October 13 4142; November 10 46
Catalogue for Demos - final version available for review | ETSI Program Committee | November 17 47: 21
Catalogue for Demos - send to printer | ETSI Program Committee | November 24 48: 28
Catalog - Print | ETSI Program Committee | bar: December 1 49
Catalog - Deliver to Event site | ETSI Program Committee | December 1 49: 5
Banners - decide theme/message | MARCOM | September 29 40: 29; October 13 4142: 17
Banners - Graphic Design | MARCOM | October 13 4142: 13; October 27 44: 31
Banners - Production | MARCOM | November 10 46: 10 - 14
Banners - Deliver to Event site | MARCOM | December 1 49: 5
Paid Article Placement | MARCOM | September 15 38: ???
Event Coordination
generate invitation list | Program Committee | July 28 31: (tbd)
open participant registration | Program Committee | July 28 31: (tbd); September 29 40: 3
send invitations | Program Committee+MARCOM | July 28 31: (tbd)
close participant registration | Program Committee | December 1 49: 5
Coordinated Communications
Identify & Engage White Paper Author | MARCOM + Proactive PR | August 11 33: 11; August 18 34: 22; September 22 39: 26; September 29 40: 29
Define White Paper Scope and Messaging | MARCOM + Author | August 18 34: 18; September 1 36: 5; September 29 40: 3
Work on White Paper | Author | September 8 36: 8; November 10 46: 14
Publish White Paper | MARCOM | November 17 47: 21
Develop Webinar Series Plans and Schedule | MARCOM | July 28 31: 28
Select Webinar Service (e.g. BrightTalk?) | MARCOM | August 4 32: 4; August 11 33: 15; September 15 38: >; September 22 39: 26
Identify & Engage Webinar Presenters | MARCOM | July 28 31: 1; September 22 39: 26
oneM2M Overview Webinar Series Announcement & Registration | MARCOM (with TP/WPM) | August 4 32: 4; August 18 34: 22; September 29 40: 3?; October 6 41: ??
Webinar #1 Business Focus - Preperation | MARCOM (with TP/WPM) | bar: September 22 39 to October 6 41
Webinar #1 Business Focus - Announcement | MARCOM | September 29 40: 3
Webinar #1 Business Focus - Session & Recording | MARCOM | October 13 4142: 15?
Webinar #1 Business Focus - Upload & Availability | MARCOM | October 13 4142: 17
Webinar #2 (Arch + topics tbc) Preparation | MARCOM (with TP/WPM) | bar: September 29 40 to October 13 4142
Webinar #2 (Arch + topics tbc) Announcement | MARCOM | October 6 41: 8
Webinar #2 (Arch + topics tbc) Session & Recording | MARCOM | October 20 43: 22?
Webinar #2 (Arch + topics tbc) Upload & Availability | MARCOM | October 20 43: 24
Webinar #3 (Sec + topics tbc) Preparation | MARCOM (with TP/WPM) | bar: October 13 4142 to October 27 44
Webinar #3 (Sec + topics tbc) Announcement | MARCOM | bar: October 20 43
Webinar #3 (Sec + topics tbc) Session & Recording | MARCOM | bar: November 3 45
Webinar #3 (Sec + topics tbc) Upload & Availability | MARCOM | November 3 45: 7
Webinar #4 (MAS + topics tbc) Preparation | MARCOM (with TP/WPM) | bar: October 27 44 to November 10 46
Webinar #4 (MAS + topics tbc) Announcement | MARCOM | bar: November 3 45 to November 10 46
Webinar #4 (MAS + topics tbc) Session & Recording | MARCOM | November 17 47: 19?
Webinar #4 (MAS + topics tbc) Upload & Availability | MARCOM | November 17 47: 21
Webinar #5 (a/r topics tbc) Preparation | MARCOM (with TP/WPM) | bar: November 3 45 to November 17 47
Webinar #5 (a/r topics tbc) Announcement | MARCOM | bar: November 10 46 to November 17 47
Webinar #5 (a/r topics tbc) Session & Recording | MARCOM | November 24 48: 26?
Webinar #5 (a/r topics tbc) Upload & Availability | MARCOM | November 24 48: 28
Showcase Live Webinar (tbd) | MARCOM (with TP/WPM) | December 8 50: 9
Live Webinar Post Production (tbd) | MARCOM (with TP/WPM) | December 8 50: 12
Other
Launch new website | MARCOM | July 14 29: 15; September 22 39: 26; September 29 40: ???
Decision on PR Firm | MARCOM (with SC/FC) | August 4 32: 4; August 11 33: 15; August 25 35: 27 ©
Decision on Web Advertizing (e.g. AdWords) | MARCOM (with SC/FC) | August 4 32: 4; August 11 33: 15; October 6 41: 10
Plan and schedule Video content | MARCOM
oneM2M Video preparation | MARCOM | September 22 39: PR; October 6 41: ???
oneM2M Video filming / post-production | MARCOM | October 27 44: ???
oneM2M Video on-line launch | MARCOM | November 10 46: ???
Note on L25: WPM 12.2