## Showcase
| 2014-08-05 | ACTOR | Owner | Cost | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October |  |  |  | November |  |  |  | December
| startdate of week |  |  | (Est USD) | 30 | 7 | 14 | 21 | 28 | 4 | 11 | 18 | 25 | 1 | 8 | 15 | 22 | 29 | 6 | 13 | 20 | 27 | 3 | 10 | 17 | 24 | 1 | 8
No. | Calender Week |  |  |  | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 4142 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50
Actions
A | Showcase Demonstrations
A1 | Tender calling for demos | oneM2M secretariat |  | 0 | July 7 28: 8
A2 | Deadline for receiving commitments & draft demo description | oneM2M secretariat |  | 0 | August 4 32: 8
A3 | Deadline for receiving detailed description of demo | oneM2M secretariat |  | 0 | September 29 40: 30
A17 | Demo hardware available on-site at ETSI (as applicable) | Demo Companies+ETSI CTI |  | 0 | December 1 49: tbd
| Demo Display available on-site at ETSI | Demo Companies+MARCOM |  | 0 | bar: December 1 49
A18 | Demo run through | Demo Companies+ETSI CTI |  | 0 | December 8 50: 8
| Demo Display set-up (Iris G2/G3) | Demo Companies |  | 0 | December 8 50: 8~9
A19 | oneM2M Showcase | oneM2M + ETSI |  | 0 | December 8 50: 9
| ETSI M2M Workshop | ETSI |  | 0 | December 8 50: 10~11
| Demo & Display tear-down (Iris G2/G3) | Demo Companies |  | 0 | December 8 50: 11
B | Showcase Presentations
B4 | detail suggestion for the agenda by email discussion | WPM & MARCOM |  | 0 | July 7 28: 8
B5a | final decision on agenda and speakers (Session 1 Business Focus) | MARCOM (WPM involved) |  | 0 | August 25 35: 29
B5b | final decision on agenda and speakers (Session 2 Technical Focus) | WPM (MARCOM involved) |  | 0 | August 25 35: 29
B6 | agenda and speakers for demo presentations (Session 3, 4) | WPM (MARCOM involved) |  | 0 | October 6 41: 10
B7 | action plan available for further updates | MARCOM |  | 0 | July 7 28: 8; July 28 31: 28
| Speaker Nominations | WPM (MARCOM involved) |  | 0 | July 7 28: 8; July 28 31: 28
| Speaker Confirmations | WPM (MARCOM involved) |  | 0 | July 28 31: 28; September 8 37: 3
B15 | deadline for draft presentations (Session 1 and 2) | Programme Committee |  | 0 | October 20 43: tbd
B16 | deadline for final presentations (Session 1 and 2) | Programme Committee |  | 0 | November 24 48: 28
| deadline for final demo presentations (Session 3 and 4) | Programme Committee |  | 0 | November 24 48: 28
5
C | Media Communications
C8 | outline Communication Plan | MARCOM |  | 0 | July 28 31: 28
C9 | create / update event ETSI Web page | ETSI |  | 0 | August 4 32: 8
| create / update event oneM2M Web page | MARCOM |  | 0 | August 4 32: 8
C14 | Detailed Communication Plan (e.g. interviews) | MARCOM |  | 0 | July 28 31: 28; August 11 33: 15
| [[ TP Press Release - Release 1 Announcement ]] | MARCOM (with TP) |  | 0 | August 18 34: ???
| Press Release #1 - Draft & Approve | MARCOM (with ETSI) |  | 0 | August 18 34: 18; August 25 35: 29
C21 | Press Release #1 - Event announcment | MARCOM (with ETSI) |  | 0 | bar: September 1 36
C22 | Publicise event | MARCOM (with ETSI) |  | 0
| Wire Service? | MARCOM |  | 250 | August 4 32: ???; September 1 36: ???
| Press Briefings - as scheduled | MARCOM |  | 0 | September 1 36: ???
| Analyst Briefings - as scheduled | MARCOM |  | 0 | September 15 38: ???
| Press Release #2 - Draft & Approve | MARCOM (with ETSI) |  | 0 | September 29 40: 29 - 3
C23 | Press Release #2 - Planned Agenda, Speakers, Demos | MARCOM (with ETSI) |  | 0 | October 6 41: 6
| Press Release #3 - Draft & Approve | MARCOM (with ETSI) |  | 0 | November 3 45: 3 - 7
C24 | Press Release #3 - Final Agenda, Speakers, Demos | MARCOM (with ETSI) |  | 0 | November 10 46: 10
D | Salesware / Collateral
| Identify/Engage Graphic Designer | MARCOM |  | 0 | August 4 32: 8
| Basic oneM2M Graphics update | Designer+MARCOM |  | 1000 | August 11 33: 11; August 18 34: 22
| Update Brochure Content | MARCOM |  | 0 | August 11 33: 11; August 18 34: 22
| Update Single Sheet graphics(rev2) | Designer+MARCOM |  | 1000 | August 18 34: 18; August 25 35: 29
| Distribute Single Sheet (rev2) for Regional use | MARCOM |  | 0 | August 25 35: 29
| Print Single Sheet (rev2) | MARCOM+Printer |  | 250 | September 1 36: 5
| Update Brochure Content (rev2.1) | MARCOM |  | 0
| Update Single Sheet design (rev2.1) | Designer+MARCOM |  | 500 | November 3 45: 3; November 17 47: 21
| Distribute Single Sheet (rev2.1) for Regional use | MARCOM |  | 0 | November 24 48: 28
| Print Single Sheet (rev2.1) | MARCOM+Printer |  | 500 | November 24 48: 28
| Single Sheet rev 2.1 - Deliver to Event site | MARCOM |  | 50 | December 1 49: 5
| Identify/Engage Writer | MARCOM |  | 0 | August 18 34: 22
| Brochure Content Authoring | Writer+MARCOM |  | 2000 | August 25 35: 25; September 15 38: 19
D39 | Brochure design | Designer+MARCOM |  | 1000 | September 22 39: 22; October 6 41: 10
D40 | Brochure final version available | MARCOM |  | 0 | October 13 4142: 17
D41 | Brochure - Print | MARCOM+Printer |  | 500 | October 27 44: 17
| Brochure - Deliver to Event site | MARCOM |  | 50 | December 1 49: 5
| Event Brochure - Preparation | Program Committee+MARCOM |  | 0 | August 18 34: 18; August 25 35: 29
| Event Brochure - Distribute (PDF / PUB) | Program Committee+MARCOM |  | 0 | bar: September 1 36; December 1 49
| Event Brochure - Print (Locally?) | MARCOM+Printer |  | 250 | September 1 36: a / r; December 1 49: 5
D42 | Catalogue for Demos - collect information | WPM (MARCOM involved) |  | 0 | September 29 40: 30
| Catalogue for Demos - Cover Design | Designer+MARCOM |  | 500 | bar: October 13 4142; November 10 46
D43 | Catalogue for Demos - send to designer | ETSI (WPM involved) |  | 0 | October 13 4142: 13; November 10 46: 14
| Catalogue for Demos - Content Integration | Designer+MARCOM |  | 500 | bar: October 13 4142; November 10 46
| Catalogue for Demos - final version available for review | ETSI Program Committee |  | 0 | November 17 47: 21
D44 | Catalogue for Demos - send to printer | ETSI Program Committee |  | 0 | November 24 48: 28
| Catalog - Print | ETSI Program Committee |  | 50 | bar: December 1 49
| Catalog - Deliver to Event site | ETSI Program Committee |  | 50 | December 1 49: 5
D45 | Banners - decide theme/message | MARCOM |  | 0 | September 29 40: 29; October 13 4142: 17
D46 | Banners - Graphic Design | MARCOM |  | 500 | October 13 4142: 13; October 27 44: 31
| Banners - Production | MARCOM |  | 500 | November 10 46: 10 - 14
| Banners - Deliver to Event site | MARCOM |  | 50 | December 1 49: 5
| Paid Article Placement | MARCOM |  | 2500 | September 15 38: ???
E | Event Coordination
E10 | generate invitation list | Program Committee |  | 0 | July 28 31: (tbd)
E11 | open participant registration | Program Committee |  | 0 | July 28 31: (tbd)
E12 | send invitations | Program Committee+MARCOM |  | 0 | July 28 31: (tbd)
E13 | close participant registration | Program Committee |  | 0 | December 1 49: 5
F | Coordinated Communications
| Identify & Engage White Paper Author | MARCOM |  | 0 | August 11 33: 11; August 18 34: 22
| Define White Paper Scope and Messaging | MARCOM + Author |  | 0 | August 18 34: 18; September 1 36: 5
F25 | Work on White Paper | Author |  | 2000 | September 8 37: 8; November 10 46: 14
F26 | Publish White Paper | MARCOM |  | 0 | November 17 47: 21
| Develop Webinar Series Plans and Schedule | MARCOM |  | 0 | July 28 31: 28
| Select Webinar Service (e.g. BrightTalk?) | MARCOM |  | 2550 | August 4 32: 4; August 11 33: 15
| Identify & Engage Webinar Presenters | MARCOM |  | 0 | bar: July 28 31
| Business Outreach Webinar Series Announcement & Registration | MARCOM |  | 0 | August 18 34: 18; September 1 36: 5
| Business Outreach Webinar #A Preperation | MARCOM |  | 0 | August 18 34: 18; September 1 36: 5
| Business Outreach Webinar #A Announcement | MARCOM |  | 0 | August 25 35: 25; September 1 36: 5
| Business Outreach Webinar #A Session(s) & Recording | MARCOM |  | 0 | bar: September 8 37
| Business Outreach Webinar #A Upload & Availability | MARCOM |  | 0 | September 8 37: 12
| Business Outreach Webinar #B Preperation | MARCOM |  | 0 | September 15 38: 15; September 29 40: 3
| Business Outreach Webinar #B Announcement | MARCOM |  | 0 | September 22 39: 22; September 29 40: 3
| Business Outreach Webinar #B Session(s) & Recording | MARCOM |  | 0 | bar: October 6 41
| Business Outreach Webinar #B Upload & Availability | MARCOM |  | 0 | October 6 41: 10
| Business Outreach Webinar #C Preperation | MARCOM |  | 0 | October 13 4142: 13; October 27 44: 31
| Business Outreach Webinar #C Announcement | MARCOM |  | 0 | October 20 43: 20; October 27 44: 31
| Business Outreach Webinar #C Session(s) & Recording | MARCOM |  | 0 | bar: November 3 45
| Business Outreach Webinar #C Upload & Availability | MARCOM |  | 0 | November 3 45: 7
| oneM2M Overview Webinar Series Announcement & Registration | MARCOM (TP Involved) |  | 0 | August 4 32: 4; August 18 34: 22
F27 | Webinar #1 (Overview) Preparation | TP (MARCOM Involved) |  | 0 | August 4 32: 4; August 18 34: 22
| Webinar #1 (Overview) Announcement | MARCOM |  | 0 | August 18 34: 22
F28 | Webinar #1 (Overview) Session & Recording | MARCOM |  | 0 | August 25 35: 26?
F29 | Webinar #1 (Overview) Upload & Availability | MARCOM |  | 0 | August 25 35: 29
F30 | Webinar #2 (Security) Preparation | TP (MARCOM Involved) |  | 0 | September 1 36: 1; September 15 38: 19
| Webinar #2 (Security) Announcement | MARCOM |  | 0 | September 8 37: 8; September 15 38: 19
F31 | Webinar #2 (Security) Session & Recording | MARCOM |  | 0 | September 22 39: 23?
F32 | Webinar #2 (Security) Upload & Availability | MARCOM |  | 0 | September 22 39: 26
F33 | Webinar #3 (Architecture) Preparation | TP (MARCOM Involved) |  | 0 | September 29 40: 4; October 13 4142: 22
| Webinar #3 (Architecture) Announcement | MARCOM |  | 0 | October 6 41: 6; October 13 4142: 22
F34 | Webinar #3 (Architecture) Session & Recording | MARCOM |  | 0 | October 20 43: 21?
F35 | Webinar #3 (Architecture) Upload & Availability | MARCOM |  | 0 | October 20 43: 24
| Webinar #4 (Protocols) Preparation | TP (MARCOM Involved) |  | 0 | October 20 43: 4; November 3 45: 22
| Webinar #4 (Protocols) Announcement | MARCOM |  | 0 | October 27 44: 27; November 3 45: 22
| Webinar #4 (Protocols) Session & Recording | MARCOM |  | 0 | November 10 46: 11?
| Webinar #4 (Protocols) Upload & Availability | MARCOM |  | 0 | November 10 46: 14
| Showcase Live Webinar (tbd) | MARCOM (TP Involved) |  | tbd | December 8 50: 9
| Live Webinar Post Production (tbd) | MARCOM (TP Involved) |  | tbd | December 8 50: 12
Z | Other
Z20 | Launch new website | MARCOM | tbc | 20000 | July 14 29: 15
| Decision on PR Firm | MARCOM (with SC/FC) |  | tbd | August 4 32: 4; August 11 33: 15
| Decision on Web Advertizing (e.g. AdWords) | MARCOM (with SC/FC) |  | $100 / mo | August 4 32: 4; August 11 33: 15
| Plan and schedule Video content | MARCOM | (TIA?) | 0
Z36 | oneM2M Video preparation | MARCOM |  | 1000 | September 1 36: ???
Z37 | oneM2M Video filming / post-production | MARCOM |  | 3000 | October 6 41: ???
Z38 | oneM2M Video on-line launch | MARCOM |  | ? | October 27 44: ???
40550
Note on E98: 4mo @ $850/mo https://www.brighttalk.com/marketing-solutions/pricing
Note on E83: $2500/Qtr