## PR Tracker
oneM2M PR Activity Tracker From February 2015
Activity | Details | oneM2M Actions | PPR Actions
MOA | Amendments made 3rd Aug | Sign and send back | Sent to Kazunori MATSUO/Ultan/Richard 4th August with amendments
News releases / Media Invites |  |  |  | URGENT
IoT Evolution 17th - 20th August Las Vegas | Richard is speaking. Press relesase required? RB asked about a joint press release with OMA. HTML sent by oneM2M | RB needs to speak to Carl Ford re content and Session description | Draft Press release once RB has sent us content. Also use contnt from session agenda online. DefIinitely do Media invites and analyst briefing outreach. (just waiting on final press list from event)
Write Down - Lite version | App i.d press release | oneM2M to distribute internally for sign-off | await final copy
McKinsey report | refer to this in press release oneM2M to talk about Interoperability | Press release to comment on the report. Instruct PPR to draft / issue | Await sign off of Ken's article - link to McKinsey article - media invite, link back to website. Convert Ken's article into an Exec brifing doc. Also using Ken's content to update / create new content for website
IoT Security 22nd - 23rd September 2015 Boston, USA | Vinod Choyi speaking - 'oneM2M working group security expert' - Vinod's title |  | Request media list end of Aug / beg of september. Media invites and analyst briefing outreach once we have attendee list Chase HTML
IoT Europe 6th - 7th October 2015 Berlin | Omar speaking. Need to do a press release and media / analyst invites on this | RB agreed definitely need release for this | Request media list. PPR to do stand alone Press Release on oneM2M terms (not joint with Informa) Chase HTML
New Partners signing - ongoing activity | PPR to ask who is due to be signed up / when | Ultan/Richard aware to let PPR know of new members signing up. Please advise if you need us to do a HGI press release re taking on their work / merger (if appropriate) | Press release needed for all new partners - Ultan / Richard agreed its good proactice (HGI winding down and closing 2016)
ITU Geneva - Standardisation Group | RB said there is a possible opportunity for a joint press release with ITU. Ultan to advise PPR. Possibly imminent milestone agreement. Will extend reach to all areas they don’t have partners in. probably a stand alone press release for oneM2M, as ITU will want to do their own (before september) | Need to update PPR asap with content | pressinfo@itu.int email for press room off the ITU website
Features / Pitching In
Possible article written by Gartner - Eric Goodness | on the back of Webinar pitch in - Eric will listen to webinar playback to assist in his article. Have asked for link once written |  | http://www.gartner.com/technology/home.jsp PPR to stay in touch with Eric. He estimates the article will be ready early August
Gartner article on M2M | Eric Goodness would like a quote direct from oneM2M | Omar and oneM2M approved quote | PPR to monitor for link/article
Thought Leadership Piece around IoT World event |  | With Richard and Ultan to check and send edits. RB acknowledges they still need to discuss / circulate
Connect world article (Nov issue) | Connect World Feature: 'Big Data is' November article... Deadline 1st October |  | Obtain article synopsis from Connect World
IEEE article | Article: Introduction to oneM2M. 1000 words use GTB article as base DEADLINE: 31st July - KP to do first draft - Stuart Sharrock Angle for article: UM to check with Omar, to copy in KP. KP in process of drafting. Will be with oneM2M by mid July. Will now use GTB article as base and to cut down approval time Industrial Industry article - RB to send to KP to see what other gorups have done | 6th August to have the editorial board meeting - With Stuart? | PPR to check for coverage / link
Awards
IoT Awards http://www.terrapinn.com/awards/internet-of-things/index.stm | 2 opportunities - We have secured a potential place on the judging panel for a oneM2M representitive There are also 3 potential categories we think would be a good fit to enter (Most Innovitive Connectivity Solution, Most Innovitive Platform Solution, Special Recognition award for Contribution to the IoT Ecosystem) deadline for entries July 31st, shortlist announced September, Ceremony 30th Nov Probably Fran O'Brian to be the Judge |  | Await instructions (Fran's bio is on oneM2M website under Leadership) Fran O'Brian - Cisco - Chair of steering committee to be on the panel? oneM2M have a call with Fran on Thursday. PPR to accept panel offer. Not appropriate to enter categories. PPR to send new oneM2M template contra to Rob Chambers for review/approval
Contras underway
M2M NOW | IoT Partnership opportunity - email from Natasha Blakemore to Ultan proposing contra opportunity/partnership with M2M Now | Ultan to respond and let PPR know if he wants us to take it forward Richard thinks M2M Now might be looking for 'early' content... Would Ken Figueredo's piece fit well here | Await response from Ultan on moving forwards
IoT Evolution 17th - 20th August Las Vegas | Richard going (Eshwar speaking from OMA too) |  | Richard/Ultan knows organiser?! Carl Ford? Contra now with oneM2M to approve. Signed by IoT Evolution Richard is listed as a speaker on behalf of oneM2M on website (the Thursday?) MM went back to Diana on oneM2M contra to include logo swaps etc one press releasest to focus on oneM2M? PPR sent logo/description to oneM2M
M2M Innovation World 15th - 17th September 2015 France | Event wanted to contact oneM2M direct for contra Fran could join programme committee? | Await UM's response to carry on with contra | PPR to carrry on with plain contra - no speaker (If needed, Ultan could go)
IoT Europe 6th - 7th October 2015 Berlin | Speaker slot confirmed. OMAR to speak. Informa are already in talks with Qualcomm for speaker but will come back to PPR if they need help | Ultan needs HTML | Press release for this event? Only go with one speaker for now. PPR asked for HTML 30/07
M2M Summit 2015 (previously CeBit) 8th - 9th Sep Dusseldorf | Event support - contra with speaking opportunity. Use previous ETSI stand - 'ETSI brings oneM2M next year |  | Normal contra for now - see if the event ask for a speaker (oneM2M may not be able to provide one) PPR in talks with Wagma at M2M Summit for plain contra PPR to make contact and get photos for 2016 event for oneM2M so Ultan can prepare for next year - Size, criteria, space etc. They already have a stand measuring 30m2 NO speaker - PPR to try for plain contra PPR chased 04/08
IoT Security 22nd - 23rd September 2015 Boston, USA | PPR have now confirmed speaker (Vinod Choyi) with Dominie from IoT Security. | Ultan needs HTML | Ultan speaking with committee - we will continue to dig. Richard probably wont speak - can look into interdigital for someone to promote oneM2M and step up - Need confirmed speaker by w/c 15th June? Ultan/Richard to look into security list and look into three names; Phil Hawkes, Tim Theory, Paul Russel/Dale Sees?? Dominie all confirmed Vinod is speaking PPR sent logos/description to oneM2M and asked for HTML 30/07/2015
IEEE | Ultan knows programme comittee. oneM2M want contra. Wants technical presence here (OMAR involved). Looking to reference oneM2M,. Leave with OMAR Await update from Ultan to see if he has direct contact. Supporting oneM2M members Omar agrees we need to do something. Deadline 31st July. Sign up for tutorial | Ultan to update PPR on progress... oneM2M dealing with. Ultan organising half day tutorial event? Submit a paper? 3/4 presentations. Industry track. Active people in programme commitee - Ultan needs to prepare submission for involved in this from oneM2m - permission for half day tutorial and industry track - need to invent titles/presentations
European Utility Week 3rd - 5th November Vienna, Austria | In course with the event to discuss topics plain contra | Ultan to leave printed flyers for event in ETSI reception. Send an eblast with event HTML | PPR to wait for signed copy of contra deal from Rogier - chased 30/07 Request marketing material for Ultan
IoT World Forum 2015 18th - 19th November 2015 London | Possible Contra with Speaker opportunity? Now only Contra, no speaker |  | CONTRA NO SPEAKER Agenda looks quite full already - oneM2M Members will need to be briefed to quite high level. May be better off with a contra and brief high level speakers - can we get speaker/panel opportunity? Not many operators/vendors... Approach for April 2016 for a contra deal with speaking opp PPR to chase
API: World Conference and Expo 2015 - Colocated with Integrate 2015 Conference & Expo/ DATA WEEK - co located? 28th - 30th September 2015 Santa Clara |  |  | PPR to speak with event organisers w/c 27th July 2015
IoT Tech Expo 2nd - 3rd December 2015 London | Event contacted oneM2M | Ultan to distribute between MARCOM for approval/signature of signature Event have requested the 12th August for their e-blast. | Event have offered a moderator speaker slot. PPR in discussions with Rachel/Natasha for speaking/moderating slot Ultan interested in moderating slot PPR to speak with Natasha (cc'd on email) about moderating slot - Could we get the advisory board?
Events
Asia Pacific Carriers Coalition/IDA co-hosted event - Singapore August | • Panel Discussion on wider policy issues - Interoperability & Global Standards- OneM2M ? (speaker from OneM2M project (a consortium of different standardization bodies from across the globe who could speak about the work the consortium is doing to create M2M standards. The standards experts could also reinforce the policy arguments made in the preceding session |  | PPR to do plain contra (not enough time for speaker)
M2M Innovation World Congress - France - 15th - 17th Sep | Event support - possible contra? | Ultan speaking on behalf of ETSI? - not sure if this is happening now... Ultan to find out and get back to us
oneM2M Interoperbility event 14th - 16th September 2015 France | Event Support - Increase awareness: social media support with Press Release |  | PPR to send out Media invite PPR to schedule Tweets from PPR Twitter to promote the workshop May just leave oneM2M 'ABOUT US' section not TTA or ETSI Should be ready to send out on Monday 22nd. Press release sent
ETSI M2M Workshop featuring oneM2M 9th - 11th December 2015 France | Event Support - Increase awareness: social media support with Press Release |  | PPR to tweet to promotoe. 3 tweets already scheduled with link - PPR to asses interest and repeat. Possible Press Release ETSI will send out PR soon (regarding call for speakers) Wait until closer to the event - PPR to rewrite ETSI Release - send to onem2m for approval and distrivute maybe PR before and one after Something similar to TIA (in terms of PR's)
Interviews / Briefings
Interview with Greg Whelan - Principle with Greywale | Greg Whelan Principal Greywale Management Boston, MA U.S.A +978 992 2203 www.greywale.com Greg is planning on writing a number of articles and blogs which will feature oneM2M, and Omar has told him to speak with you for content |  | keep following up with Greg
Case Studies
| Awaiting News Gathering from oneM2M | Ultan to inform us
Additional activity
Stock Images to use in Press Releases and articles | Would be useful to have a few approved high res images on file to accompany articles and media outreach. Appreciate its difficult to show the workings behind the device | oneM2M to ask internally / members to see if there are any
Industrial Internet Consortium (Its mission is “to accelerate growth of the Industrial Internet by coordinating ecosystem initiatives to connect and integrate objects with people, processes, and data using common architectures, interoperability, and open standards that lead to transformational business outcomes.”) | Richard sent over the details on the last call
Social Media activity - oneM2M control | Post relevant M2M, IoT and member news articles on PPR Twitter including key media coverage |  | Re-Tweet event mentions / speaker mentions / member mentions Richard to follow members, PPR, journalists/analysts this week. Link to ETSI and oneM2M website to increase visitor traffic.
Vertical sectors | Thought Leadership pieces on vertical sectors |  | Ties in with News gathering from members - need input from oneM2M - Ultan aware Keep Global focus - Speak with RB/UM about more specific TL pieces to submit to vertical sectors e.g Oil + Gas, industrial, home and medical This will come from news gathering and will be able to target vertical sectors - webinars coming up will be on mhealth/personal health Next webinar may be End of June w/c 29th June) oneM2M to target OMA webinar two weeks after this
oneM2M Twitter | PPR has offered assistance with development and running of their new Twitter account |  | PPR to guide oneM2M on Twitter when required
oneM2M LinkedIn | KP to continue to post relevent content from personal LinkedIn account |  | KP has posted the TIA series of videos on oneM2M LinkedIn KP to post oneM2M release
2016 event / contra research | Ongoing research into verticle sectors |  | 20 events found, some events have not uploaded latest info. PPR to continue to monitor. Check links for events for updates on dates
Webinar
OMA and oneM2M webinar | OMA to run webinar - possibily late september. oneM2M / Estelle now in talks with OMA to confirm |  | PPR have confirmed with OMA they are happy to proceed with webinar. Elizabeth and Estelle are in touch. Going for Mid September
HGI Webinar with oneM2M | HGI to run webinar - mid- October |  | PPR to try for a webinar from HGI - oneM2M want them to talk about how HGI will use oneM2M and how they help them - the relationship between the two Duncan has agreed the webinar is still a good idea idea to do - In September. October timeframe- send to Estelle Ultan recommends October onwards for HGI/oneM2M webinar
| Open source project - Cisco...? Lionell Florit? Ask for more details on this | oneM2M to speak with Omar

## Completed items
Activity | Details | Action | Additional Information
News releases
oneM2M Interoperbility event 14th - 16th September 2015 France | PPR drafted press release to aid oneM2M. Sent to oneM2M for approval | With Ultan / Richard to finalise end copy & send to PPR for distribution | Press release sent 2nd July
oneM2M Webinar on July 1st |  | Check attendee numbers for webinar | Media invite sent 26th June
TSDSI and Global Platform | oneM2M Welcomes GlobalPlatform and TSDSI as their Newest Partners | Sent to oneM2M list
TIA | TIA hosts oneM2M Showcase Demonstrating oneM2M Standards in Action | Sent to oneM2M list
Proposed press release on oneM2M elections and Release 2 plans | Announcing spec in Release 2. Look out for approved content. | PPR sent final version for distribution
Recap Technical Plenary | send Targets for Release 2, what will be in release 2, change of chairs (Internal Only) May not merit Press Release but would merit sending to oneM2M list | Ultan has drafted and sent to RB for comments. Please let PPR know when this is approved for slotting into a press release | Next 2 Press relesase in August- Ultan has drafted something and sent over to RB for comments. Announcing spec in Release 2. Look out for approved content. Check website for content
PPR to create current analyst target list | PPR to research top industry analysts | list now refined and contains c450 industry analysts
TIA release | Contacted top 10 media to pitch in | Received confirmation from Connect World they will cover
Media invite for TIA event | Sent to oneM2M and OMA media and analyst lists and TIA registered press (done) | PPR to follow up with top 10
Media invite for RB speaking at IoT World | Sent Media Invite to IoT world press list | Follow up with David. Obtained interview/podcast with David Essex
Analyst/Telephone briefings | Awaiting replies from TIA and webinar outreach | PPR to follow up with contact list | TIA have recorded interviews - Ultan to send over videos (potentially could help KP with TL/Article) Can we look at Youtube and see if UM can make TIA videos visible and link on right hand side?! Can we link Youtube channels?! MM to do second follow up with top 10 media for telephone briefings - on the back of TIA / TSDSI & Global Platform release
Media Invite - webinar | Sent media invite to oneM2M list | Look at figures for attendees at webinar
Possible Article for TIA - Dallas workshop | Ultan advised to wait on Richard's report - could link in with other annoucements |  | Richard to speak with Tally and get us some notes - Await to hear from Richard KP emailed Taly 17/6 - await response RB was having a review call with Taly on fri 19. he will update us on this possible article KP to email Taly again. Done
Outreach for telephone briefings | Post IoT World event and Tokyo event | No takers
Articles
GTB Article | Deadline Thursday 16th July. Brian had a call with Ultan and wrote article. Was sent to both Omar and Ultan 13/7 for approval. Need image and Bio for Omar |  | Submit to GTB editor once approved
Rise of the Machines | The Rise of the Machines – World’s First Global Standards for M2M Deployment | Sent to oneM2M list
Awards
Cloud World Series | Ultan declined - not relevant
Interviews
David Essex | Interview (done) with Richard brennan at IoT event in San Francisco (May 12th-13th) | Follow up with David to retrieve any posts/online content - await link from David
Pitching out | Control Global blog | http://www.controlglobal.com/blogs/in-and-out-of-control/this-internet-of-things-thing-not-as-simple-as-it-looks/
Features
Contras
PPR to write template contra | Contra template sent to oneM2M to sign off | Template agreed and in use
Appnation IoT... RESPONSE? | Plain contra with logo swaps etc | Await on Drew (already chased) to continue with contra - never came back with info on contra deal
SDN & NFV EUROPE 15th - 17th September 2015 Madrid | SERIES SDN & NFV - Possible Contra. Ask for panel / speaking slots |  | not appropriate
SDN & NFV USA 6th - 7th October Dallas | SERIES SDN & NFV - Possible Contra. Ask for panel / speaking slots |  | not appropriate
SDN & NFV Asia 2nd - 3rd December Singapore | SERIES SDN & NFV - Possible Contra. Ask for panel / speaking slots |  | not appropriate
IoT World in San Francisco (12th - 13th May) | Speaking slot and contra deal with IoT World (May 12th-13th) | Follow up with Richard for further action (Done)
Broadband World Forum 20th - 22nd October London, UK | Speak to UM/RB about possible contra/speaking opportunity |  | DROP Event
Location Based Services (2nd - 3rd June) | Contra deal with HTML's and Logo's. | Follow up with Richard for further action (Start post event)
IIR Telecoms | No contra - no appropriate
Case Studies
MWC case studies x 2 | Interdigital and HP | Ultan to put on website
Interviews
GTB oneM2M Interview | GTB 1,500 word article for m2m suppliment to be written by Brian Dolby. Interveiw with Omar (Ultan to be on the call too) | Ultan to have a call with Brian re GTB article 9am CET 10th July. Omar to approve / edit | Brian has set aside Tues 14th to write and send back to Omar to approve. GTB deadline is 17th July
Pitching In Success from Top 10 Publications
Networking Plus | Got Front Cover coverage! | http://www.networkingplus.co.uk/Media/Default/archive/Net1503.pdf
M2M now | Coverage achieved | http://www.m2mnow.biz/2015/05/01/32622-tia-hosts-onem2m-showcase-demonstrating-onem2m-standards-in-action/
Bloomberg Business | Coverage achieved | http://www.m2mnow.biz/2015/05/01/32622-tia-hosts-onem2m-showcase-demonstrating-onem2m-standards-in-action/
Wireless Developer Network | Coverage achieved | http://www.wirelessdevnet.com/news/2015/apr/28/news4.html
Sat News | Coverage achieved | http://www.satnews.com/story.php?number=884649701
Social Media for Webinar | Social media posts from PPR | Social Media posts for webinar from Proactive PR twitter. Also connected with OMA to gain more reach - Qualcomm are a sponsor member of OMA | on 21st May; first tweet gained 4 additional followers and 4 favourites within 4 minutes. Reached 9997 users on Twitter within 4minutes | Linked In Company and Group - Richard and Ultan managers of group
Webinar pitched to M2M now | confirmation they will cover, await link |  | PPR to follow up - Coverage retained
Webinar pitched to Vanilla Plus | confirmation they will cover, await link |  | PPR to followed up - no coverage (M2M Now)
Awards
PPR currenrtly researching possible award entries | PPR to send list to oneM2M | - no -
Smart City Expo | Chased x3 but no response as yet |  | Maybe leave this one - double check emails sent / Find new contact?
Developer Week 2016 |  | PPR to make contact | Ultan explained not relevant for oneM2M
Webinars
Webinar with Qualcomm | PPR pitched out invite and increased registration numbers |  | Qualcomm webinar received 250 + (600 expected in total)
Webinar with Continua July 1st | PPR have sent our pre media and analyst outreach |  | PPR to send post webinar outreach for playback and tweet from PPR account
Webinar with Continua | PPR pitched out invite and increased registration numbers
HGI Closing 2016 | oneM2M interested in taking on HGI's work or possible merger | email address of HGI contact is duncan.bees@homegatewayinitiative.org Ultan / Richard to contact Duncan directly to take on body of work / begin discussions | PPR has already set the scene with Duncan and he is open to discussions.