## PR Tracker
oneM2M PR Activity Tracker November 2015
Activity | Details | oneM2M Actions | PPR Actions
News releases / Media Invites
[Planned] Open Source Press Release Also: Announce Developer 'corner' on oneM2M website | Open Source - need to reference activities without endorsing Saved EE times article - Open Source in folder - Good alignment for proposed PR No comments received from oneM2M internally. TIA hasn’t discussed inernally within group. | Open Source PR circulated to oneM2M for comments. Neeed to finalise end copy & send to PPR for distribution. Open Source web area in-progress. Richard to chase Qualcomm. oneM2M to request comments, then launch approval process. | oneM2M to write, PPR to edit and then go through approvals Draft may need to be sent to oneM2M legal group No movement on this yet for PPR . Nothing to happen before 30th November. Nothing can happen within next 2 weeks within oneM2M.
New Partners signing - ongoing activity | PPR to ask who is due to be signed up / when. Nothing happened yet | Ultan/Richard aware to let PPR know of new members signing up | Press release needed for all new partners - Ultan / Richard agreed its good proactice (HGI winding down and closing 2016) Number of members drop around January but gradually go up moving forwards. PR can't happen until members sign up…
oneM2M TP 21 joint meeting with OMA San Diego (separate meetings and joint with Elizabeth Rose) | Do press release for both bodies joining together for meeting oneM2M won't bring anything to test event (nothing to test) Seminar will be 5pm local time - good for oneM2M - need to organise speakers . oneM2M probably wont be involved in the hackathon. Elizabeth wants sponsorship from oneM2M. | Advise PPR on press release - are we to draft? UM to send out HTML for OMA . | Once seminar is announced - may be able to do PR - oneM2M to speak with OMA. nothing major in next week or so. This is circulating within oneM2M for discussion but they don't want it to interfere with the technical plenary… Could do workshop on the Wednesday evening after 5pm? may be difficult logistically. UM will go back to ER
PR on opening of App-ID service (ATIS) - North America partner | Likely to be early December Expecting an announcemen from ATIS… Re-working press release internally. Need name and date of webinar to announce in press release before the end of december. Goes live on 1st December - | Ultan wants this annoucning on the day its live and announce in press release. | PPR to wait for fina copy from oneM2M .January 2016 for Webinar
Report from Technical Plenary (w/c 9th Nov) ?? | Nothing came out of this. On 21st Dec a conference call, ratification of another release. This will 'rubber stamp' that these specifications and major updates to release 1 will. | UM to speak with contacts to see if any info came from plenary. Please update PPR | PPR not to send anything on this until January 2016 - wait update from oneM2M - Need a name.
Media Invite to promote Ken's Executive Briefing/white paper |  |  | PPR could send out on 3rd December?
Features / Pitching In
Analyst briefing Alert - offering download | Pitching in / Executive Briefing - Jeff Edlund interview M2M Now have taken this and Natasha Blakemore (new IoT Publication alongside M2M Now) 'IoT Global Network' - name of publication? - oneM2M could help 'announce' the launch with HTML's etc? |  | PPR ACTION: Search for links and send to oneM2M once live Positioning in english language in Asian Press (if we get an interview in a korean company - groups with U.S and Asian language publication in Asia) PPR pitched to GTB Interdigital briefing has been sent to Jeremy 3rd is underway, maybe Gemalto.
Global Telecoms Business Copy deadline: 5th January 2016 | MWC Special Edition | oneM2M want this! | PPR pitched to GTB - Await response
The Sunday Telegraph | They would like to know if either oneM2M or ETSI would like to be involved in an expert panel which will be included within the business reporter? | oneM2M Interest?
Connect World article (North America) March 2016 Secured this place January 11th deadline | Theme: The Internet of things [IoT] The Internet of Things (IoT) is the network of physical objects that contain embedded technology to communicate and sense or interact with their internal states or the external environment. What is the future? 1500 words | YES! oneM2M will have article - RB to contact some NA oneM2M members oneM2M have passed info to Ken. oneM2M to look for authors internally
Connect World (India Edition) March 2016 Secured this place January 11th deadline | Editorial | TSDSI to write - re oneM2M? Ultan to contact Asok Chatterjee or members in Bangalore ? Maybe Cisco? | Need to let Anthony know who author is ASAP
Conectronica February 2015 Deadline: 5th February | M2M communications devices and equipment | oneM2M Interest? Translation may be an issue - oneM2M to discuss internally
GSMA - Mobile World Congress 2016 Show Daily | oneM2M have PDF with cost GSMA are enquiring… | oneM2M to look at pricing for MWC show daily and let PPR know what you would like to pursue ASAP | PPR included in separate MWC 2016 document of opps
Conectronica July 2015 Deadline: 12th July | • IoT • M2M communications devices and equipment | oneM2M Interest? Translation may be an issue - oneM2M to discuss internally
RCR Wireless 2016 October 2016 Deadline: 27th September 2016 | Testing the Internet of Things: Making IoT functional and secure | Good fit for interop testing! Refer this to Omar and test Working Group. JaeSeung Song ? | PPR have contacted RCR wireless to get space booked for this - Need to await confirmation. PPR to ask for length of article, guidelines etc. Start this after May 2016 - more to say.
Conectronica October 2015 Deadline: 8th October | • IoT technology | oneM2M Interest?
Contras underway
IoT Slam '15 9th December 2015 IoT Slam is held in the Cloud and delivered via a bespoke, customized and secure virtual environment! | Possible Contra? Could utilise last years workshop notes 'What is oneM2M' etc? RB to reply to Kevin Grant with updated contra oneM2M may submit a paper and oneM2M may be able to 'attend' the virtual conference from ETSI 3 names on panel and UM as moderator. Only 3min panel session. UM suggested webcam/live webinar - means everyone will be in same room. UM wants slides too. | Contra proposal and panel session is okay - UM promised to give him names of panelists of names/bios of people on there by 18th Nov lunch time. 2pm (UK time)call with Kevin on 18th Nov. Did Ultan send out the HTML (20th or 23rd?) | 30 mins for panel session. Ultan and others on panel - well underway
IEEE Globecom 2015 6th - 10th December 2015 San Diego | Contra done No speaker slot available oneM2M have done Mail Shot and its on the oneM2M website. | Check oneM2M twitter Ultan sent HTML for event | Tweets done
IoT Evolution EXPO http://www.iotevolutionexpo.com/east/ 25-28 Jan 2015 Fort lauderdale Florida | http://itexpo.tmcnet.com/east/collocated.aspx | RB participating in IoT Evolution (Spoke with Carl) - Standards panel, chairing?? Speaking candidates? RB wants first thing on frst session - oneM2M panel. | PPR asked Joann if we can join this event contra with IT Expo (below) for exposure. PPR requested event HTML. Has Richard's panel been finalised with event?
IT EXPO JAN 25 – 28 2016 Florida http://itexpo.tmcnet.com/east/conference-program.aspx | RB talking to Carl on this side of conference. May be business/IT focussed. May only need one contra deal for this event and above | RB to speak with TMC Interdigitail - delivering a message about one of their field trials would be a great example to use for this group. | Communications business strategy trends' tracks to consider Commercial side (slightly older show) Enterprise IT buyer focus PPR asked Joann if we can join this event contra with IoT Evolution Expo (above)
IoT USA Nexus 10th - 11th February 2016 San Francisco Submission Deadline - Closed | Possible Contra? Across bay for RB | Event have requested 2 x HTML's - one for promoting a white paper and one for the event and discount - is this do-able? Whitepaper HTML link: C-Level executives from enterprise have their say on the Internet of Things http://1.iot-nexus.com/LP=7070 | PPR have contacted for a contra deal and asked about speaker submission extension
IoT Tech Expo 10th - 11th February 2016 London | Contra complete (Matt Hunt) Moderating the panel titled: 'Creating a standards framework for IoT'on our Developing for the IoT Track @12:20 day two. | oneM2M - could you schedule some tweets for the event? | PPR requested logo's and updated HTML's from event. PPR to send across Tweets.
IoT Data Analytics and Visualisation 10th - 11th February 2016 Palo Alto Deadline for Speaking Submissions: November 30th, 2015 | I’d like to propose the following panel for the data show… Industry Bodies Panel: Setting Standards and Creating Frameworks to protect IoT data and to manage key privacy concerns • Addressing key data privacy and security concerns • Integrating IoT Technologies and Standards whilst keeping data privacy at the forefront • How can we balance personalized experiences with privacy concerns? • What are the challenges in addressing the convergence of security and privacy in IoT? • How can companies be guided to take a comprehensive view of IoT devices and services, including privacy? • What plans are in place for regulating IoT data activity? • Is legislation required to create possibilities and ensure privacy, or can this be accomplished through self-regulation? | Mas - Working group (focussed on this topic) Please discuss internally and advise PPR Need security/mass group speaker | PPR to await decision from oneM2M for panel/speaker RB to circulate info to two working groups PPR to await response from RB (circulating within the group) Deadline: January 11th for speaker name
China Smart Home Summit 2016 7th - 8th March 2015 Shanghai | No link available yet… file:///C:/Users/Michelle%20Mahoney/AppData/Local/Microsoft/Windows/INetCache/Content.Outlook/FU4U7168/China%20Smart%20Home%20Summit%202016%20(002).pdf | oneM2M to send to chinese partners and update PPR | Can PPR do contra on this? PPR to await response from UM.
IoT World 23rd - 24th March 2016 Paris | Try for speaker on this! | Utan to work on Paris side for this. UM to talk to Omar, UM spoke to Nick Damour about this. Um to speak with Alcatel Lucent and see if they have stand there and if they can speak about onem2m | PPR sent updated contra to event for review/signature - Await response
IoT Asia 30th - 31st March 2016 Singapore | Go ahead! We want under 'supporting organisations' for contra/website Speaking Submission Deadline - 2nd November May struggle for speaker. Easter time, but UM may be able to go. | UM got extention on deadline - and submitted something in his name! Please review and sign contra | Speaker slot being considered - outcome should be known by Dec 7. PPR in discussion with regarding contra PPR to wait on counter signed contra
Sido - The Connected Business 6th - 7th April 2016 Lyon - France | Try for speaker on this! | Um spoke to Nicolas and may be able to speak at this - thinks this is good! And make a speaker proposal. oneM2M are VERY interested in speaking here. | PPR approached and asked about possibility of speaker Can PPR ask about this with event?
Optimal R&D and Innovation Strategies, Smart Grid and Improved VAS for Utilities 11th - 13th April 2016 Berlin, Germany Speaker Submission Deadline - Request Info | Marcus Evans events contacted Richard/Ultan/Chango the dates for this event have now been changed and it will take place on the 11th – 13th of April. | oneM2M to speak with german companies Can oneM2M provide a speaker? - Need to submit a proposal to event | PPR in talks with Constandinos to finalise contra deal PPR to hang fire unti we hear back from Ultan. UM to speak with Nicolas Demour - smart girds his company is involved in.
Smart IoT London 12th - 13th April 2016 London | Go ahead! Speaker Submission Deadline - Closed |  | PPR to approach
Internet of Things North America 13th - 14th April 2016 Chicago | Go ahead! Speaker Submission Deadline: 10th December 2015 Event emailed Lauren for high level speakers within ATIS. UM to follow up with Lauren at ATIS and send her the contra - see if we can follow their lead. | Event requested speaker proposal, session title, 200-300 word presentation description and a speaker bio by Dec. 10th. | PPR sent counter signed version to event with oneM2M logo/descriptiono - Awaiting response from UM on speaker/chair/panel Nick Depperschmidt
5G Forum USA 13th - 14th April 2016 Crown Plaza, Palo Alto | RB emailed Sonal and provided contact information for oneM2M at: http://5gforumusa.com/interested-in-speaking Speaking Submission Deadline - Request Info | RB can make this as a speaker | PPR to continue discussions with Sonal for contra deal. Ask what other events the organisers have (Series of events?) RB email on 21st October to Sonal Can we add this to the series contra
M2M World Congress 2016 26th - 27th April 2016 London | Definitely want this for a speaker!! Speaker Submission Deadline - Still 2015 |  | PPR to continue discussions with event
Internet of Things World 10th - 12th May 2016 Santa Clara Speaking Submission Deadline - Request Info | Definitely want this for a speaker!! Location changed from SF Moscone to Santa Clara/Silicon Valley Gavin Whitechurch may be holding a space 'on the floor' for oneM2M Dominie said panel will be similar to the IoT Data Analytics and Visualisation event in Feb for speaker/panel slot | Definitely contra - as much involvement as possible PPR to await decision from oneM2M on panel/speaker name | PPR sent contra deal to Dominie - await response GET SPEAKER! Deadline: 29th January for speaker name Can we do floor space at event? OEA - oneM2M Ecosystem Accelerator (member sponsored/funded marketing effort to support oneM2M) Ken is heading this up!
Smart Home World 21st - 22nd June 2016 London | Possible contra? Speaker Submission Deadline - Request Info | Please discuss internally and advise PPR | PPR approached about this and asked about speaker submission deadline
5G World Summit 28th - 30th June 2016 London | Possible contra? Fran o'Brian came back to RB and cannot attend due to other commitments | Please send your submission with the title of the presentation, brief summary and contact details no later than Friday, November 27th to be considered for the event. | sonal.ghelani@informa.com alejandro.pinero@informa.com Worthwhile to speak at. UM can send info to event organisers - could propose OMAR or Fran? Cisco could support him at it.
IoT Security Summit 21st - 22nd September 2016 Washington, D.C | Possible contra? Speaker Submission Deadline - Request Info |  | Can informa include in series contra? GET SPEAKER SLOT NOT PANEL PPR to sepak with informa about advisory board
Internet of Things World Europe TBC October 2016 Berlin | Possible contra? Speaker Submission Deadline - Request Info |  | Can informa include in series contra? GET SPEAKER SLOT NOT PANEL
Events
ETSI M2M Workshop featuring oneM2M 9th - 11th December 2015 France | Event Support - Increase awareness: social media support with Press Release oneM2M branding at event... Going online in the next week or so… New video content possibly if demos happen during workshop - Need to be different from last year |  | PPR to tweet to promote. 3 tweets already scheduled with link - PPR to asses interest and repeat. Possible Press Release ETSI will send out PR soon (regarding call for speakers) Wait until closer to the event - PPR to rewrite ETSI Release - send to onem2m for approval and distribute maybe PR before and one after Something similar to TIA (in terms of PR's) Taking place at ETSI HQ Nathalie - Nathalie.Guinet@etsi.org - Email regarding EVENT PR PPR in discussion with UM on this
oneM2M/OMA joint meeting in January 2016 | Event, testfest etc | ongoing discussion…
Mobile World Congress 2016 | 18th September last call for speakers Ultan wants panel here to include two operators, two members from oneM2M, Adrian Scracse from 3gpp, analyst (not same one from workshop last year!) maybe Telecom Italia too? Two standards body oneM2M and one other. (Maximum of 5 people on the panel, plus the chair) Maybe TIA (Scott) for standards body. Message - security problems, interoperability problems, m2m/iot problems - 'we are dealing with them' from oneM2M . Ultan received an automated response to his submission for a panel | Ultan to inform us Need to put placeholder for budget - needs internal discussion. | News crews for interview - via press list Interviews with analysts/media If panel gets confirmed - PPR can push for people to attend Show daily? ACTION: PPR emailed GSMA to find out costs for MWC Daily newspaper £3-4,000 per quarter page? No plans for breakout meetings ETSI will do networking cocktail on the Tuesday evening (23rd) 'friends of ETSI' meeting. TIA people will be welcome, media and analysts are welcome but not a place for interviews. Just a place to meet/greet individuals Submission for panel from Victoria Mitchell to MWC16 has gone in
MWC Special Editions | Connect World – MWC special edition in 2015 - Concentrating on Cloud for 2016 Wireless Magazine – Additional Distribution: MWC in 2015 (Jan/Feb issue) RCR Wireless – MWC special edition in 2015 (February and March issues) GTB – pre MWC issue in 2015 (Pre-MWC showcase in January/February 2015 issue) Mobile Europe – Issue available at MWC (December 15/January 16) Teletimes – Event section on MWC Barcelona (February issue in 2015) Developing Telecoms – Mobile World Congress (March 2015 issue) | Would oneM2M like any additional content (paid or non paid) in these publications? | PPR to source deadlines and topics for MWC special editions PPR to chase GTB again for topics on MWC special editions PPR to chase Mobile Europe for topics on MWC special editions
TIA 2016 Partner event in Dallas, Texas June 2016 | potential speaking track for oneM2M Plus potential demos | on hold for now until TIA give more details | Taly Walsh - PPR to email her that it's been announced - how can we work together. Contact Taly Walsh after MARCOM meeting (3rd Nov?) oneM2M may do showcase / speakers?
TP 21 San Diego, CA, USA Jan 18 ~ 22, 2016 (TIA with OMA)
TP 22 Europe (location tbc) Mar 14 ~ 18, 2016 (ETSI)
TP 23 South Korea May 16 ~ 20 (TTA)
TP 24 USA (location tbc) July 18 ~ 22 (ATIS)
TP 25 Europe (location tbc) Oct 17 ~ 21 (ETSI)
Interviews / Briefings
Rick Merritt | Off back of Turin smart city |  | We have been in contact with Rick Merritt. He is happy to set up a meeting to discuss new news. Will just need about a weeks’ notice to fit him into his diary. Just speak about oneM2M -
Ian Scales - Telecom TV - potential telephone Interview with Ultan |  |  | PPR made contact with Ian to follow up on Omar's interview and offered a telephone interview with Ultan 9 Oct
Case Studies
| Awaiting News Gathering from oneM2M | Ultan to inform us
Additional activity
Testimonial from oneM2M |  | If you have time! Please could you write 1 or 2 paragrphs on your working relationship with PPR. We are developing our website so these are really useful to us
Media list for Korea, Asia and Japan | PPR to research English speaking media contacts within these specific areas |  | PPR to perform ongoing research and update
HGI Closing 2016 | oneM2M interested in taking on HGI's work or possible merger |  | PPR has already set the scene with Duncan and he is open to discussions. email address of HGI contact is duncan.bees@homegatewayinitiative.org Ultan / Richard to contact Duncan directly
ETSI Summit on Standardization and Open Source - 19th Nov - ETSI HQ France | Lionell Florit - How to write specifications |  | http://www.etsi.org/news-events/events/979-2015-11-summit-standardization-and-open-source
Social Media activity - oneM2M control | Post relevant M2M, IoT and member news articles on PPR Twitter including key media coverage |  | Re-Tweet event mentions / speaker mentions / member mentions Richard to follow members, PPR, journalists/analysts this week. Link to ETSI and oneM2M website to increase visitor traffic.
Vertical sectors | Thought Leadership pieces on vertical sectors |  | Ties in with News gathering from members - need input from oneM2M - Ultan aware Keep Global focus - Speak with RB/UM about more specific TL pieces to submit to vertical sectors e.g Oil + Gas, industrial, home and medical This will come from news gathering and will be able to target vertical sectors - webinars coming up will be on mhealth/personal health Next webinar may be End of June w/c 29th June) oneM2M to target OMA webinar two weeks after this
oneM2M LinkedIn | KP to continue to post relevent content from personal LinkedIn account - Keep active
oneM2M Slideshare | Content that PPR can refer to analysts It will be 'open' . Presentations with overview information on oneM2M Will be on oneM2M website -in next week or so - Linked up to LinkedIn.You can subscribe to authors
2016 event / contra research | ongoing research into verticle sectors |  | 20 events found, some events have not uploaded latest info. PPR to continue to monitor. Check links for events for updates on dates
2016 Awards research | Judging/panel opportunities and/or entry
oneTransport project using oneM2M, for background info. | http://www.arup.com/Projects/oneTRANSPORT.aspx http://www.arup.com/News/2015_08_August/17_August_Research_pioneers_new_approach_to_open_data.aspx Video: http://www.arup.com/Smart_Mobility?sc_lang=en-GB Data sheet: http://www.interdigital.com/data_sheets/oneTRANSPORT
Webinar
OMA and oneM2M webinar | OMA to run webinar - possibily September? OMAR suggested webinar on data semantics…? Need a presenter and time slot for this oneM2M and OMA to discuss timings oneM2M to find additional webinars | Estselle is contacting Elizabeth again to follow up for October?
HGI Webinar with oneM2M | HGI to run webinar - mid September? | Ultan / Richard to email or call Duncan to firm up date. | PPR to try for a webinar from HGI - oneM2M want them to talk about how HGI will use oneM2M and how they help them - the relationship between the two. Duncan has agreed the webinar is still a good idea idea to do.
3rd Webinar - Interdigital Transportation 'Intelligent transport' Highways agency in the UK etc | With Buckinghamshire Council Interdigital 'ARUP' - organisation in the UK | Please advise PPR asap so we can send Analyst Alert | Await specific dates from RB
2nd December - ETSI Meeting Marcom call 30th November oneM2M to review on 16th November 2016 and circulate internally for comments | India CJK Translations for Chineese, Korean & Japanese -- in country, in language items http://www.thecjkgroup.com/ |  | PPR to do presentation for 2016
Next Webinar to be in January ?
Paused Activity
oneM2M Release update - Press release | Maybe May next year for release 2 | Paused for now! | Potentially delivery date of March next year for release 2 (cannot talk about this yet) oneM2M release 1 has lots of traction, and release 2 is already coming... Adding in lots of info for this one (open source, etc?)
ITU Press release - (senstive policitally ) | Unsure on when/if anything will be released | Paused for now! Ultan knows Press officer - Please update PPR when/if this can go ahead | Wait until end of October/Nov to see if the ITU have spoken about oneM2M specifications or not Agreement circulating within oneM2M
Plenary | Full release on what came out from Plenary | Paused for now! Confirm schedule for press release - Published point documents - please give PPR details for release. RB to speak to someone re this w/c 1st sep | update on release 1 - use docs on website November plenary next one In Beijing week of 13th Nov
Thought Leadership Piece around IoT World event | PPR wrote draft & sent to oneM2M | With Richard and Ultan to check and send edits. RB acknowledges they still need to discuss / circulate | Paused for a while
PPR to check
Possible article written by Gartner - Eric Goodness | on the back of Webinar pitch in - Eric will listen to webinar playback to assist in his article. Have asked for link once written |  | Double checked for coverage on 6th October - Still nothing http://www.gartner.com/technology/home.jsp PPR to continue to check for coverage
The Network (Information for an article) | Get into Asian IoT market via the article | oneM2M interest? See Liz's email on 23/10/2015 Deadline for leads: 13 Nov 2015 16:00 | China operators? Haier (air conditioners/refridgerators) Contact Chinese members - sent to journalist

## Completed items
Activity | Details | Action | Additional Information
News releases
oneM2M Interoperbility event 14th - 16th September 2015 France | PPR drafted press release to aid oneM2M. Sent to oneM2M for approval | With Ultan / Richard to finalise end copy & send to PPR for distribution | Press release sent 2nd July
oneM2M Webinar on July 1st |  | Check attendee numbers for webinar | Media invite sent 26th June
TSDSI and Global Platform | oneM2M Welcomes GlobalPlatform and TSDSI as their Newest Partners | Sent to oneM2M list
ITU Geneva - Standardisation Group | RB said there is a possible opportunity for a joint press release with ITU. Ultan to advise PPR | Ultan to let PPR know if we should make contact with ITU | pressinfo@itu.int email for press room off the ITU website
App ID Press release |  |  | PPR sent PR 8th sep - Currently recording coverage
TIA | TIA hosts oneM2M Showcase Demonstrating oneM2M Standards in Action | Sent to oneM2M list
oneM2M post first interoperability tesing event | 1pm (uk time) Ultan will send clean FINAL version |  | PPR sent 23 sep afternoon - Look for coverage PPR send update w/c 5th
IoT Week in Korea 26th - 30th October 2015 | iotweek.kr | Advise PPR on press release ChangHo to ask for press list for event . Ultan, please add logo to the oneM2M website. ACTION: RB to get event endorsed IOT Week are drafting a press release - oneM2M to recirculate the endorsement | oneM2M need local partner to do something with this event. oneM2M to speak with TTA ChangHo waiting for Press release from government side…? RB to chase ChangHo… May need to publish results post event (oneM2M action)
Media Invite / Analyst outreach
PPR to create current analyst target list | PPR to research top industry analysts | list now refined and contains c450 industry analysts
TIA release | Contacted top 10 media to pitch in | Received confirmation from Connect World they will cover
Media invite for TIA event | Sent to oneM2M and OMA media and analyst lists and TIA registered press (done) | PPR to follow up with top 10
Media invite for RB speaking at IoT World | Sent Media Invite to IoT world press list | Follow up with David. Obtained interview/podcast with David Essex
IoT Evolution 17th - 20th August Las Vegas | Richard is speaking. Press relesase required? OMA speaker is now Seth, not Eshwar | RB - see instructions from Jessica (McCaffrey) Seabrook Marketing Manager (Email 12th August) | PPR to carry on with Media invites and analyst briefing outreach - PPR to send media invite Las Vegas time 7am 17th to prompt for interviews or analyst briefings. Meet in Press room - give out RB Mobile Number. Not Available on Monday at all
IoT Security 22nd - 23rd September 2015 Boston, USA | Vinod Choyi speaking - 'oneM2M working group security expert!' - Vinod's title Vinod's title has been amended with event |  | PPR to sent media invite w/c 14th Sept for Vinod
IoT Europe 6th - 7th October 2015 Berlin | Omar speaking. Need to do media / analyst invites on this. |  | PPR sent media invite for OMAR speaking. Don't push for briefings - telephone briefings post event
Analyst/Telephone briefings | Awaiting replies from TIA and webinar outreach | PPR to follow up with contact list | TIA have recorded interviews - Ultan to send over videos (potentially could help KP with TL/Article) Can we look at Youtube and see if UM can make TIA videos visible and link on right hand side?! Can we link Youtube channels?! MM to do second follow up with top 10 media for telephone briefings - on the back of TIA / TSDSI & Global Platform release
Media Invite - webinar | Sent media invite to oneM2M list | Look at figures for attendees at webinar
Telephone Briefings
Outreach for telephone briefings | Post IoT World event and Tokyo event | No takers
Articles
Rise of the Machines | The Rise of the Machines – World’s First Global Standards for M2M Deployment | Sent to oneM2M list
Awards
IEEE | Article: Introduction to oneM2M | http://campaign.r20.constantcontact.com/render?ca=1f1198c1-114b-4863-96e5-69f977a22caa&c=cb7efff0-0a1f-11e5-93fe-d4ae527599c4&ch=cb94f8f0-0a1f-11e5-940d-d4ae527599c4 | Ultan has sent photo / bio to Stuart - DONE.
Cloud World Series | Ultan declined - not relevant
IoT Awards http://www.terrapinn.com/conference/total-telecom-festival/C56330.stm | oneM2M on judging panel (Fran O'Brian) UM heard nothing since 31st July | oneM2M contacted Fran… | PPR chased Rob on 4th Nov. Await response Potential for 2016 involvement? No contact was made at all from Rob… Put to completed tab and look for 2016
Interviews
David Essex | Interview (done) with Richard brennan at IoT event in San Francisco (May 12th-13th) | Follow up with David to retrieve any posts/online content - await link from David
GTB oneM2M Interview | GTB 1,500 word article for m2m suppliment to be written by Brian Dolby. Interveiw with Omar (Ultan to be on the call too) | URGENT!! Call penciled in for Friday 10 July 8am BST / 9am CET Ultan to confirm date time. Brian has set aside Tues 14th to write and send back to Omar to approve. GTB deadline is 17th July | NOW Published and in the GTB magazine!
Pitching out | Control Global blog | http://www.controlglobal.com/blogs/in-and-out-of-control/this-internet-of-things-thing-not-as-simple-as-it-looks/
Connect world article (Nov issue) Asia - Pacific | Connect World Feature: 'Big Data is' November article... Deadline 1st October | See email from Kirsty. Let PPR know if this is doable - can we interview someone from oneM2M who is knowledgable in this area? Copy deadline - October 5th | Connect World Feature: 'Big Data is' November article... Deadline 1st October Connect World have agreed to receive a free article from a oneM2M rep. PPR need bio+head shot of author (KP has Anthony's attachments)
Features
Possible Article for TIA - Dallas workshop | Ultan advised to wait on Richard's report - could link in with other annoucements | Is this still required? | Richard to speak with Tally and get us some notes - Await to hear from Richard KP emailed Taly 17/6 - await response RB was having a review call with Taly on fri 19. he will update us on this possible article KP to email Taly again. Done
Connect World article (Europe II) April 2016 DEADLINE: 5th February 2016 | Theme: Networks and network infrastructure, the future. Discuss | oneM2M want this one | oneM2M neeed to decide between Europe edition and North America edition for Connect World (Already had invitation for North America)
Vanilla Plus (Paid for content) VanillaPlus Guide to IoT which is included within the Dec / Jan MWC edition Deadline Dec 8th | Topic: Vanilla Plus guide to IoT They have 2 editions going to MWC one is the Dec / Jan which is important as its the pre MWC edition and is good for pre MWC promo and the other the Feb / Mar that will be released for the event. | oneM2M Interest? (Vanilla plus need confirmation by 19th November if oneM2M want this) | PPR sent attachment to oneM2M
CSI Magazine February 2016 Copy deadline: 15th January | 2016 trends & predictions' and LoRa, 802.11ah and 'IoT standards' Key shows: Mobile World Congress, CABSAT 2016, DVB World | oneM2M interest? Internal deadline of November 15th for internal commitment for author for this
OSP March 2016 Deadline: 29th January 2016 | * IoT/M2M/ Connected Devices * IoT/M2M/Interconnected Data Center | oneM2M Interest? To discuss internally
OSP April 2016 Deadline: 29th February 2016 | Understanding the Connected World - Internet of Everything | oneM2M Interest? | Await response from oneM2M
OSP October 2015 Deadline: 30th June 2016 | IoT/M2M/Interconnected Data Center | oneM2M interest? | Await response from oneM2M
Contras
PPR to write template contra | Contra template sent to oneM2M to sign off | Template agreed and in use
M2M Summit 2015 (previously CeBit) 8th - 9th Sep Dusseldorf | Event support - contra with speaking opportunity. |  | Normal contra for now - see if the event ask for a speaker (oneM2M may not be able to provide one) PPR in talks with Dennis at M2M Summit for contra with speaker opp. PPR have been chasing since 16th July - no response. Shall we drop this one? Don’t chase now. no response from event
Appnation IoT... RESPONSE? | Plain contra with logo swaps etc | Await on Drew (already chased) to continue with contra - never came back with info on contra deal
IoT World in San Francisco (12th - 13th May) | Speaking slot and contra deal with IoT World (May 12th-13th) | Follow up with Richard for further action (Done)
Location Based Services (2nd - 3rd June) | Contra deal with HTML's and Logo's. | Follow up with Richard for further action (Start post event)
M2M Innovation World 15th - 17th September 2015 France | Event wanted to contact oneM2M direct for contra Fran could join programme committee? | Await UM's response to carry on with contra
SDN & NFV EUROPE 15th - 17th September 2015 Madrid | SERIES SDN & NFV - Possible Contra. Ask for panel / speaking slots |  | As ETSI are at these events, shall we take off oneM2M tracker? PPR to continue talks with event Already an ETSI endorsement NFV Track - ETSI Group going
Connections Europe 10th - 11th November 2015 Amsterdam | Possible contra? Ultan thinks may not be right…… | Ultan /oneM2M to review event for a contra
SDN & NFV Asia 2nd - 3rd December Singapore | SERIES SDN & NFV - Possible Contra. Ask for panel / speaking slots |  | PPR to continue talks with event
IoT Security 22nd - 23rd September 2015 Boston, USA | PPR have now confirmed speaker (Vinod Choyi) with Dominie from IoT Security. |  | ultan speaking with committee - we will continue to dig. Richard probably wont speak - can look into interdigital for someone to promote oneM2M and step up - Need confirmed speaker by w/c 15th June? Ultan/Richard to look into security list and look into three names; Phil Hawkes, Tim Theory, Paul Russel/Dale Sees?? Dominie all confirmed Vinod is speaking
IoT Evolution 17th - 20th August Las Vegas | Richard going (Eshwar speaking from OMA too) |  | Richard/Ultan knows organiser?! Carl Ford? Contra now with oneM2M to approve. Signed by IoT Evolution Richard is listed as a speaker on behalf of oneM2M on website Maybe do two press releases, one joint with OMA and one just to focus on oneM2M and who is going??
IoT Tech Expo 2nd - 3rd December London, UK | will endores | Please send HTML 16th Sept Please add event listing and logo on oneM2M website | Chase for HTML and asked for a push back on the date for HTML - DONE. EVNET HAS BEEN CANCELLED BY ORGANISORS. 2 SEP 2015
oneM2M Interoperbility event 14th - 16th September 2015 France | Event Support - Increase awareness: social media support with Press Release (DONE) Registration was closed on 31 July. It is a great success so far as we have about 60 registered attendees, actually we are over capacity but the Plugtest team is working on that. Of course the names of the companies need to remain confidential as they have all signed a NDA. They are working together using a private wiki. I suppose you have seen it already but just in case, details on what will be tested is on the event page: http://www.etsi.org/news-events/events/957-onem2m-interop | oneM2M to tweet - PPR to re-tweet | PPR to Re-Tweet posts off the oneM2M Twitter page re this event
M2M Innovation World Congress - France - Sep (Mid June for PR) Same as above event 'Contras Underway' | Event support - possible contra?
IIR Telecoms | No contra - no appropriate
API: World Conference and Expo 2015 - Colocated with Integrate 2015 Conference & Expo/ DATA WEEK - co located? 28th - 30th September 2015 Santa Clara | 45 min drive from RB house! 10 o clock or later on 30th |  | Intergratecon.com/iotsummit world. Sara Jones@devnet.com. RB is available to give a brief overview - Intergrate Summit most relevant. Do contra too. Just 30th Sep PPR continue conversation with Sara - Advise Sara of distribution stats
IoT Europe 6th - 7th October 2015 Berlin | Speaker slot confirmed. OMAR to speak. Informa are already in talks with Qualcomm for speaker but will come back to PPR if they need help |  | CONTRA COMPLETE Go back to Ian at Telecom TV, could organise call between Ian and Ultan to discuss oneM2M and future opportunities
IoT Week in Korea 26th - 30th October 2015 | iotweek.kr |  | ChangHo/PPR to request press list for event oneM2M need local partner to do something with this event. oneM2M to speak with TTA ChangHo waiting for Press release from government side…?
Industrial Internet of Things Summit 12th - 13th November 2015 Berlin | Yes if we can get a speaker (Don't want plain contra, only want if we can get speaker) Don't push for endorsement package PPR to contact organisers for a contra and request press list - could do analyst invite if OMAR speaks? |  | See Richard's email on this - Omar has been invited to speak… PPR to contact John Joseph to continue discussions for contra agreement Yes if we can get a speaker (Don't want plain contra, only want if we can get speaker) Don't push for endorsement package PPR to contact organisers for a contra and request press list - could do analyst invite if OMAR speaks?
Location and Context 3rd - 4th November 2015 Palo Alto | RB would not favor a contra unless a panel slot was made available. There are a few topics that 'could' intersect oneM2M... If panel is not available then 'NO' to a contra RB's email on Mon 21st Sept |  | Updated contra sent across for consideration - awaiting suggested agenda replacement.
European Utility Week 3rd - 5th November Vienna, Austria |  | UM to send out contra Nick Damour participating | How did this event go? oneM2M to update PPR
IoT Planet 4th - 5th November 2015 Grenoble, France http://www.iot-planet.org/ |  | UM spoke with Orange - Jedd edlund - speaking and on panel - He will name drop oneM2M and get coverage there to some extent | No contra - UM has said oneM2M should be covered/named here from Jeff PPR chased for press list
Fokus Fuseco 5th - 6th November 2015 Berlin, Germany https://www.fokus.fraunhofer.de/go/fuseco-forum-2015 | No contra - organised within oneM2M/Omar? | Replacement needed for OMAR Wolfgang Granzow - Qualcomm (Speaking slot)
IoT World Forum 2015 18th - 19th November 2015 London | Possible Contra with Speaker opportunity? Ultan could go as speaker if we can get opportunity |  | Agenda looks quite full already - oneM2M Members will need to be briefed to quite high level. May be better off with a contra and brief high level speakers - can we get speaker/panel opportunity? Not many operators/vendors... PPR chased 2nd Nov - await response
CES 11th - 13th May 2016 Shanghai, China | CES Asia Submissions must be completed by November 20, 2015 | Please discuss internally and advise PPR
DoE SSL Connected Lighting Workshop 16th November 2015 Portland, Oregon ssl.energy.gov | Remy Marcotorchino (Sierra Wireless) to speak on behalf of oneM2M | Upload event description to oneM2M website | Sent signed contra to sign and event description to oneM2M
Internet of Things World Forum 6th - 8th December 2015 Dubai https://www.iotwf.com/ | Possible Contra? Plain Contra deal - NO speaker |  | PPR have contacted for contra and sent plain contra over (no speaker) Drop to complete tab
CES 6th - 9th January 2016 Las Vegas | Discuss… Original email from RB/UM Potentially a oneM2M panel may be taking place? UM | oneM2M to inform PPR on what is happening with this (OIC) | Put on hold OIC contacted oneM2M - May do something joint. PPR to wait feedback from oneM2M before we do anything with this PPR - carry on digging on this (may not have enough time on this one - speakers etc)
IoT Global Directory Natasha Blakemore | Later this year they will launch an Affiliates page on their website. They would like to link this page to both ETSI and One M2M websites. We can include a logo and a short profile of each organisation. It would be great if both sites could link back to ours as well as a reciprocal arrangement. | oneM2M interest? Logo swaps for websites
Developer Week 16 12th - 18th February 2016 San Francisco http://developerweek.com/ | PPR have already reached out them on this event and they would happy to offer something - contra / email blast and possile speaker. RB lives nearby. Open Source for oneM2M, interop Contra is fine to go. Speaker Deadline is November 22, 2015 | Omar may be here (If Omar is speaking and willing to mention oneM2M we may not do contra) RB CAN speak on this. Please advise PPR if you would like a contra | Not sure if event is relevant as oneM2M have no specific easy to use support Group for Developers. oneM2M to question ??? Event involvement. PPR ACTION: Advise event of distribution figures c620 contacts, global, technical / developer community.
MWC case studies x 2 | Interdigital and HP | Ultan to put on website
Pitching In Success from Top 10 Publications
Networking Plus | Got Front Cover coverage! | http://www.networkingplus.co.uk/Media/Default/archive/Net1503.pdf
M2M now | Coverage achieved | http://www.m2mnow.biz/2015/05/01/32622-tia-hosts-onem2m-showcase-demonstrating-onem2m-standards-in-action/
Bloomberg Business | Coverage achieved | http://www.m2mnow.biz/2015/05/01/32622-tia-hosts-onem2m-showcase-demonstrating-onem2m-standards-in-action/
Wireless Developer Network | Coverage achieved | http://www.wirelessdevnet.com/news/2015/apr/28/news4.html
Sat News | Coverage achieved | http://www.satnews.com/story.php?number=884649701
Social Media for Webinar | Social media posts from PPR | Social Media posts for webinar from Proactive PR twitter. Also connected with OMA to gain more reach - Qualcomm are a sponsor member of OMA | on 21st May; first tweet gained 4 additional followers and 4 favourites within 4 minutes. Reached 9997 users on Twitter within 4minutes
Webinar pitched to M2M now | confirmation they will cover, await link |  | PPR to follow up - Coverage retained
Webinar pitched to Vanilla Plus | confirmation they will cover, await link |  | PPR to followed up - no coverage (M2M Now)
Awards
PPR currenrtly researching possible award entries | PPR to send list to oneM2M | - no -
Smart City Expo | Chased x3 but no response as yet |  | Maybe leave this one - double check emails sent / Find new contact?
Developer Week 2016 |  | PPR to make contact | Ultan explained not relevant for oneM2M
Webinars
Webinar with Qualcomm | PPR pitched out invite and increased registration numbers |  | Qualcomm webinar received 250 + (600 expected in total)
Webinar with Continua | PPR pitched out invite and increased registration numbers
Webinar with Continua July 1st | PPR have sent our pre media and analyst outreach |  | PPR to send post webinar outreach for playback and tweet from PPR account
Industrial Internet Consortium ( Its mission is “to accelerate growth of the Industrial Internet by coordinating ecosystem initiatives to connect and integrate objects with people, processes, and data using common architectures, interoperability, and open standards that lead to transformational business outcomes.”) | Richard sent over the details on the last call - organisational relationship | RB to speak / email to them (Richard Foley, Fran and Omar)
EVENTS
IEEE … dates / times / speaker TBC - Milan, December | Ultan knows programme comittee. oneM2M want contra. Wants technical presence here (OMAR involved). Looking to reference oneM2M,. Leave with OMAR | Await update from Ultan to see if he has direct contact. Supporting oneM2M members | Send Ultan email to check status - oneM2M dealing with. Ultan organising half day tutorial event? Submit a paper? 3/4 presentations. Industry track. Active people in programme commitee - ULTan needs to prepare submission for nvolved in this from oneM2m - permission for half day tutorial and industry track - need to invent titles/presentations
GITEX EVENT http://www.gitex.com/ 18 - 22nd October DUBAI | 35th anniversary edition will be the rapidly evolving Internet of Everything and Smart Technology markets and the ripple effect they are having across key industry verticals |  | PPR to contact them for a contra deal - no speaker
Broadband World Forum 20th - 22nd October London, UK | Speak to UM/RB about possible contra/speaking opportunity |  | PPR to speak with Robin about oneM2M being a partner organisation for BBWF - What are his thoughts? oneM2M to speak if opportunity is there. Robin can speak with RB/UM if he needs to BBWF call on 14th Sept PPR - Can we leverage anything for oneM2M being a member of BBF
oneM2M Twitter | PPR has offered assistance with development and running of their new Twitter account |  | Richard confirmed Twitter will be back under oneM2M control
Asia Pacific Carriers Coalition/IDA co-hosted event Singapore The M2M workshop is scheduled for 19th November 2015 | • Panel Discussion on wider policy issues - Interoperability & Global Standards- OneM2M ? (speaker from OneM2M project (a consortium of different standardization bodies from across the globe who could speak about the work the consortium is doing to create M2M standards. The standards experts could also reinforce the policy arguments made in the preceding session Richard updated PPR with date change from Victoria Mitchell (TIA) works with Tally Plan: to have a full session dedicated to M2M regulatory frameworks, Technical and standardization issues. We Plan to have GSMA and OneM2M lead this session.This would be a hour and half session divided into two followed by Q&A First half would be an open session for all the industry stakeholders such as M2M vendors , providers and associations. We would want speaker to talk about technical standards and global initiatives on standardisation. It can be a presentation. I am not sure we will have a panel on standards unless we have a few panelist for that. The session would be attended by regulator in SG and industry. The second half would closed door interaction with APCC members and IDA. Your members who can talk about standards etc can get a chance to speak on this forum and visibility with regulator Could we get a speaker from Korea? Not necessarily a TP or Marcom delegate, but someone from one of the Korean operators backing oneM2M? Or a delegate from China? E.g. someone from Huawei? | Please advise on who will be speaking / attending - crutial event. Details from Priya: 1. The plan is to have GSMA talk about how regulators in other regions are considering IoT and M2M deployments (US, EU perspective ) –as well as a Presentation on Global SIM & M2M Traffic Annex to Roaming agreements 2. Interoperability & Global Standards- OneM2M We plan to have OneM2M talk about international trends on standardization, interoperability on M2M and IoT. | No speaker available RB to speak with Priya Richard gave regrets to the organisers No speaker available. Omar has asked to get in touch with Singapore directly.
Alliance for IoT Innovation Brussels 4th November 2015 | Omar Elloumi speaking No contra Group of research projects coming together - put together by European Commission |  | No action. No press release
IWPC IoT Workshop 12th November 2015 San Jose | Vanja Subotic - Senior Manager, Solutions Management (Interdigital) speaking and presenting on oneM2M The title of the talk is: oneM2M Standard for Multi-Vertical Interoperability
Interviews / Briefings
Ian Scales - Telecom TV - Interview with Omar at IoT Europe Berlin | Film crew with him on Wednesday and would like to interview Omar if poss | Omar to confirm he has avilability to meet with Ian Scales | Omar to speak with Ian on 7th October PPR followed up with Ian to check he has everything he needs from this 9 Oct
Russell Coffin Strategic Architect America Core Network Product Management Huawei Technologies USA Inc. | Is it possible to get a summary of the event and results? | UM responded to Russell and put him in touch with Huawei representative Jiaxin Yin | PPR to leave with Ultan on this Company results are embargoed under a non disclosure UM to pass on to Huawei rep who attended to discuss internally
James Atkinson Editor - Wireless magazine www.wireless-mag.com | Telephone breifing opportunity - Andrew is putting together an article looking at low power wide area networks for IoT. Interested in what work oneM2M is doing on LoPoWANs - but would be interested to get a view from oneM2M on how things are developing | http://www.wireless-mag.com/search/default.aspx | PPR to keep in contact with James for coverage - should be on the website by 9th Oct
Response to Turin Smart City | http://www.rethinkresearch.biz/articles/turins-smart-city-project-adopts-onem2m-and-m-bus-2/ | UM to go back to Enrico - is there anything to announce? | KP reached out to Rick via LinkedIn and Twitter Move to complete list and PPR will independently contact Rick for media contact for oneM2M… don't contact for the Turin Smart City - ignore that item

## Editorial Opportunities
oneM2M PR Activity Tracker From February 2015
Activity | Details | oneM2M Actions | PPR Actions
Editorial Opportunities
Connect World article (North America) March 2016 | Theme: The Internet of things [IoT] The Internet of Things (IoT) is the network of physical objects that contain embedded technology to communicate and sense or interact with their internal states or the external environment. What is the future? | oneM2M will have article - Maybe Ken for this Me Hai from Telit? Names who are committed to oneM2M oneM2M to pass to Ken | January 11th deadline
Connect World (India Edition) March 2016 |  | TSDSI.....
Connect World article (Europe II) April 2016 | Theme: Networks and network infrastructure, the future The communication network and service environment of 2020 will be infinitely richer and more complex than that of today. The expectation is that in 2020 the network infrastructure will be capable of connecting everything according to a multiplicity of application specific requirements: People, things, processes, computing centres, content, knowledge, information, goods, in a flexible, truly mobile, and powerful way. The future will encompass connected sensors, connected vehicles, smart meters and smart home gadgets way beyond our current experience of tablet and smartphone connectivity. Discuss. | Yes!! Want this one | Will North America have larger circulation? We could tweak this article for a Europe focus if that's the case? If they are similar they can do two articles anyway RB said we can do two articles? Maybe one with focus on U.S and one with focus on Europe? With similar structure? Jim Nolan could be focus on oneM2M Ghost written by Fran OBrian Get DEADLINE
RCR Wireless 2016 October 2016 | Testing the Internet of Things: Making IoT functional and secure | oneM2M Interest?
Contra deals
IoT Evolution EXPO http://www.iotevolutionexpo.com/east/ 25-28 Jan 2015 Fort lauderdale Florida | http://itexpo.tmcnet.com/east/collocated.aspx Rb has spoken to Carl | Please let PPR know which co-located events you would like to speak at | PPR to start dealing with TMC Media - broden out to CEO community ACTION: PPR to continue conversations re contra. Ken is speaking here Could get more oneM2M people to speak at this event (as well as Richard being there) Let Richard know who our contact is... Telit, conectiv, interdigital could all potentially speak? Vanya from Marcom from Interdigital. Jim Nolan from Interdigital (very pro oneM2M) Carl Ford. PPR contacted TMC for contra, speaker, panel, chairman opportunities.
IT EXPO JAN 25 – 28 2016 Florida http://itexpo.tmcnet.com/east/conference-program.aspx | Right event. Already had their call for papers - Rb to speak with Carl to see how to structure this moving forward Joint contra for both events (TMC for IT EXPO and IOT Evolution Expo) Rb to work directly with IOT EVOLUTION EXPO. PPR to contact TMC to do joint contra moving forwards to get visibility on both sides. oneM2M message out there - seperate message for IoT Evolution Expo | RB to speak with TMC (Vanja - Marcom)- contra? Interdigital - very good opp for a speaker for this … | PPR to email TMC - standard contra with speaker - look at all co-located events Contact for contra and speaker for this side of the conference 'Communications business strategy trends' tracks to consider
IoT USA Nexus 10th - 11th February 2016 San Francisco | Possible Contra? | Please discuss internally and advise PPR
IoT Tech Expo 10th - 11th February 2016 London | Contra complete Chairing the panel “Creating a standards framework for IoT” on our Developing for the IoT Track @12:20 day two. | Do you have a speaker name? Are you able to schedule an eblast for 12th January? | oneM2M to go back to Matt and say yes! They want the chairing opportunity CS OR? Cambridge and pushing for oneM2M - may be able to speak
IoT Data Analytics and Visualisation 10th - 11th February 2016 Palo Alto |  | Please discuss internally and advise PPR | PPR to await agenda from Dominie to place oneM2M on panel/speaker
Developer Week 16 12th - 18th February 2016 San Francisco http://developerweek.com/ | PPR have already reached out them on this event and they would happy to offer something - contra / email blast and possile speaker. RB lives nearby. Open Source for oneM2M, interop |  | Not sure if event is relevant as oneM2M have no specific easy to use support Group for Developers. oneM2M to question ??? Event involvement. ACTION: Advise event of distribution figures c620 contacts, global, technical / developer community
IoT World 23rd - 24th March 2016 Paris | Possible Contra? | Please discuss internally and advise PPR
IoT Asia 30th - 31st March 2016 Singapore | Possible Contra? | Please discuss internally and advise PPR
Sido - The Connected Business 6th - 7th April 2016 Lyon - France | Possible Contra? | Please discuss internally and advise PPR
Smart IoT London 12th - 13th April 2016 London | Possible Contra? | Please discuss internally and advise PPR
Internet of Things North America 13th - 14th April 2016 Chicago | Possible Contra? | Please discuss internally and advise PPR
M2M World Congress 2016 26th - 27th April 2016 London |  |  | PPR contacted - await response
Internet of Things World 10th - 12th May 2016 Santa Clara | Possible Contra? Gavin Whitechurch may be hoding a space 'on the floor' for oneM2M | Please discuss internally and advise PPR | PPR to await agenda from Dominie to place oneM2M on panel/speaker
CES 11th - 13th May 2015 Shanghai, China | CES Asia | Please discuss internally and advise PPR
Smart Home World 21st - 22nd June 2016 London | Possible Contra? | Please discuss internally and advise PPR