## Sheet3
Section | Title | pp | Editor's Note ID | Editor' Note | Reccommendation | Action |  |  | Complete | Owner/Contributor | CR
[6 empty] | Revise | Delete | Other
1 | Scope | 10 | -
2 | References | 11 | - | - | -
2.1 | Normative references | 11 | 2.1.a | Editor's Note: Need to identify Normative and Informative References. To update the document with correct references thereafter. | Under discussion
2.2 | Informative references | 11 | 2.2.a | oneM2M Drafting Rules {Editor's} NOTE: Available at http://member.onem2m.org/Static_pages/Others/Rules_Pages/oneM2M-Drafting-Rules-V1_0.doc | Not needed for pub?
|  |  | 2.2.b | {Editor's} Note: The above stated references are for section -12 | Check Sect 12 Ref
3 | Definitions, symbols and abbreviations | 13 | - | - | -
3.1 | Definitions | 13 | 3.1.a | Common Services Entity: Editor's Note: This is a provisional definition. | Consensus
|  |  | 3.1.b | Common Services Function: Editor's Note: This definition needs some more work so that it is more clear (about the M2M environment and the relationship between CSE/CSF and level of service functions. | Discuss & Clarify
|  |  | 3.1.c | Local CSE: Editor's Note: Need to provide definition of an End Node. This is FFS. | FFS - Modify Text?
|  |  | 3.1.d | Editor's Note: The concept of a CSE registering at a Local CSE needs to be understood. This is FFS. | FFS - Modify Text?
|  |  | 3.1.e | Editor's Note: Review/clarify "or a CSE" in the definition of Local CSE. Should "or a CSE" be replaced with "or a Node"? This is FFS. | FFS - Modify Text?
|  |  | 3.1.f | Editor's Note: Need definition for "Application Entity". Need to define relationship between an Application Entity and an Application. | Clarify
|  |  | 3.1.g | Resource: Editor's Note: The above stated definition of Resource needs to be revisited. This is FFS. | Clarify
|  |  | 3.1.h | Editor's Note: It is expected that more definitions are needed. This is FFS. | Clarify
3.2 | Symbols | 15 | - | - | -
3.3 | Abbreviations {& Acronyms} | 15 | 3.3.a | Editor’s Note: Missing some Text | Complete
4 | Conventions | 17 | 4.1.a | Editor's Note: The meaning of URI (Uniform Resource Indicator) as used in this stage 2 Arch TS should be stated here since it may be constrained, extended or otherwise diverge from the very well known Generic Syntax of RFC 3986. . For example considering the following: * What is the difference between Request(op="CREATE",to=" HYPERLINK "http://thebaseofmycse/?view=default&update=10s#NEW", http://theBaseOfmyCSE?view=default&update=10s#NEW ", ty="container"…) and Request(op="CREATE", to="//theBaseOfmyCSE", ty="container",…) ? In both cases the 'to' parameter uses an URI. We have some constraints to define here. * What if some resource is hosted by a CSE that is reachable in public internet through 'normal' IP technology (FQDN may be resolved into a public IP address), but another resource may reside on a CSE that has no IP connectivity and in fact needs to be reached through some specific gateway that offers a conversion into anther transport and node addressing scheme (e.g. KNX or just some non-IP transport). In that case we may decide to use the {scheme} part of a URI to indicate that. The first resource may use "to=oneM2MpublicIP://{FQDN of the target CSE}/xxx" and the second one may use "to=oneM2MprivateKNX://{FQDN of KNX Gateway/{KNX-address-of-target-CSE}/xxx" These examples also using URIs but the "scheme" part now refers to how to interpret the segments of the path. One could also think of allowing some hierarchy in the "scheme" field. * Even in IP-only scenarios, one could have a private network A with a number of CSEs and a private network B with a number of CSE. If you need to address a resource of Network B within a request made in Network A, how would that look? Can we do that with a URI? Probably we can, but we would have to define some special interpretation of a URI. Or we would define some extension like a AE in network A makes a request with to=networkB::oneM2MprivateIP://{IP-address-of-target-CSE-in-Network-B}/container. In that case the receiver of the request only needs to know how to reach a gateway to network B (a CSE that is connected to Network A and Network B) | Consesnsus & move to 3.x
5 | Architecture Model | 18 | 5.a | Editor's Note: Definitions are FFS. As definitions get refined and agreed to, the following text to be adjusted to eflect the agreements {Empty Clause} | Consensus & intro clause text
5.1 | General Concepts | 18 | - | - | -
5.2 | Architecture Reference Model | 18 | - | - | -
5.2.1 | Functional Architecture | 18 | 5.2.1.a | Figure 5.2.1-1: oneM2M Functional Architecture: Editor's Note: To update the picture above showning Mch reference point | Align / Update Figure
5.2.2 | Reference Points | 19 | - | - | -
5.2.2.1 | Mca Reference Point | 19 | - | - | -
5.2.2.2 | Mcc Reference Point | 20 | 5.2.2.2.a | Editor's Note: In the event oneM2M develops specifications for more than one CSE implementation, the use of the Mcc reference point between them (for both intra-domain and inter-domain instances) would need elaboration, and is FFS. This requires coordination between the ARC and PRO working groups. | FFS - Modify Text?
5.2.2.3 | Mcn Reference Point | 20 | 5.2.2.3.a | Editor's Note: The following NOTE should be moved into clause 6.x. NOTE: Information exchange between two M2M nodes assumes the usage of the transport and connectivity services of the Underlying Network Services Entity, which are considered to be the basic services. | Move to 6.x ?
|  |  | 5.2.2.3.b | Editor's Note: While allowing for different instantiations of the CS Function into different functional Entities, this specification follows the following guidelines/principles while specifying the interfaces on Mca, Mcc and Mcn reference points: - Specification of the interfaces on reference points Mca and Mcc are independent of the functionality provided by the CSE. - Specification of the interfaces on reference point Mcn may take into account the functionality provided by the CSE. | Move up to 5.2.2 Text for Technical Solution?
5.2.2.4 | Mcc' Reference Point | 20 | - | - | -
5.2.2.5 | Mch Reference Point | 20 | - | - | -
6 | Configurations supported by oneM2M Architecture | 21 | - | - | -
{6.1} | { } |  |  | {added missing section header} | "Application of Nodes in oneM2M Architecture"
|  |  | 6.1.a | Editor's Note: How Node-less AEs are classified is FFS. | FFS - Modify "Node-less AEs" text above?
|  |  | 6.1.b1 | The illustration above does not provide an exhaustive list of possible configurations and is subject to qualifications. Other possible functions/configurations are FFS. | Move immediately below Fig. 6.1 find Technical Solution?
|  |  | 6.1.b2 | Mcc' reference point aims to be as similar as possible to the Mcc reference point. But due to the nature of inter-M2M Service Provider communications, some differences are anticipated. | Move to 5.2.2.4 text for Technical Solution ?
|  |  | 6.1.c | Editor's Note: It is not clear what differentiates an Infrastructure Node from an Application Service Node or from a Middle Node. It could be a minimum feature scope of its CSE that would be bigger, or a particular requirement on its Mcn reference point. It could also be the cardinality of this Node in a deployment. Typically there would be just one Infrastructure Node in a deployment. | Clarify
6.2 | Common Services Functions | 23 | - | - | -
6.2.1 | Application and Service Layer Management | 23 | - | - | -
6.2.1.1 | General Concepts | 23 | - | - | -
6.2.1.2 | Detailed Descriptions | 23 | 6.2.1.2.a | Editor's Note: Specific management capabilities for functions are FFS. | Clarify - WG5?
|  |  | 6.2.1.2.b | Editor's Note: Once more work has been completed on the DMG CSF and this CSF - these CSFs should be reviewed to determine if they should be merged or kept separate | Clarify - WG5?
6.2.1.2.1 | Configuration Function | 24 | 6.2.1.2.1.a | Editor’s Note: Need CSF information | Clarify - Add Text
6.2.1.2.2 | Diagnostic and Monitoring Function | 24 | - | - | -
6.2.1.2.2.1 | CSE Diagnostics |  | 6.2.1.2.2.1.a | Editor’s Note: Need CSF information | Clarify - Add Text
6.2.1.2.2.2 | CSE Monitoring |  | 6.2.1.2.2.2.a | Editor’s Note: Need other CSF information | Clarify - Add Text
6.2.1.2.3 | Software Management Function | 25 | - | - | -
6.2.2 | Communication Management and Delivery Handling | 25 | - | - | -
6.2.2.1 | General Concepts | 25 | - | - | -
6.2.2.2 | Detailed Descriptions | 26 | 6.2.2.2.a | Editor's Note: For Rel-1 it would probably make sense to limit to one Middle Node along the path since we need to define how to handle routing which could become more complex and should be able to be added at a later stage without or with little impact on the message exchanges. | Consensus on Rel 1 scope & text
|  |  | 6.2.2.2.b | Editor's Note: Clarification of complexity impacts due to use of multiple Underlying Networks are FFS | Consensus on Rel 1 scope & text
6.2.3 | Data Management and Repository | 26 | - | - | -
6.2.3.1 | General Concepts | 26 | - | - | -
6.2.3.2 | Detailed Descriptions | 27 | 6.2.3.2.a | Editor's Note: Needs to clarify what is meant by "peer entity" being on-line or not. Is the reference to peer-CSE or something more than that? | Clarify
|  |  | 6.2.3.2.b | Editor's Note: Semantics related capabilities are FFS subject to discussions in MAS (WG5) WG | Clarify - WG5?
6.2.4 | Device Management | 27 | 6.2.4.a | Editor’s Note: Some of the detailed Device Management material might fit in Section 8.3.2.3 | Move or combine with 8.3.2.3
6.2.4.1 | General Concepts | 27 | - | - | -
6.2.4.1.1 | Device Management Architecture | 27 | 6.2.4.1.1.a | Editor's Note: Terms and definitions needed for Management Adapter, Management Server, Management Client,Device Management Server, Device Management Client, Management Proxy, Proxy Management client. | Clarify - WG5?
6.2.4.1.2 | Management Server Interaction | 28 | 6.2.4.1.2.2.a | Editor's Note: The procedure for selecting the Management Server is FFS. | Find Technical Solution? "FFS" or "OOS"
6.2.4.1.3 | Management Client Interaction | 30 | - | - | -
6.2.4.1.4 | Device Management Resource Lifecycle | 31 | - | - | -
6.2.4.2 | Detailed Descriptions | 32 | 6.2.4.2.a | Editor's Note: Need to provide definition of Management Server in order to describe the interaction with the Management Server. | Clarify - WG5?
|  |  | 6.2.4.2.b | Editor's Note: Need to provide definition of Management Server, Management Clients, Role based permissions. | Clarify - WG5?
|  |  | 6.2.4.2.c | Editor's Note: The CSF must document the management functions that cause impacts to the underlying network and document they must utilize access rights that are delegated from the network operator. | Clarify - WG5?
6.2.4.2.1 | Device Configuration Function | 32 | 6.2.4.2.1.a | Editor's Note: Handling of Security configuration parameters and the interaction with SEC CSF is for FFS | FFS - Clarify WG4?
6.2.4.2.2 | Device Diagnostics and Monitoring Function | 33 | - | - | -
6.2.4.2.3 | Device Firmware Management Function | 33 | - | - | -
6.2.4.2.4 | Device Topology Management Function | 33 | - | - | -
6.2.5 | Discovery | 33 | - | - | -
6.2.5.1 | General Concepts | 33 | - | - | -
6.2.5.2 | Detailed Descriptions | 34 | - | - | -
6.2.6 | Group Management | 34 | - | - | -
6.2.6.1 | General Concepts | 34 | 6.2.6.1.a | Editor's Note: provide definition of Group or change it to lowercase | Describe "group" in 6.2.6 or elsewhere?
6.2.6.2 | Detailed Descriptions | 34 | 6.2.6.2.a | Editor's Note: How the Underlying Network supports broadcasting/multicasting is FFS | FFS - Find Technical Solution?
|  |  | 6.2.6.2.b | Editor's Note: Suggest adding description on what is meant by Group member, what entities can be members of a Group? Can a Group consist of heterogeneous members? | Describe in 6.2.6 or elsewhere?
|  |  | 6.2.6.2.c | Editor's Note: The structure of the resource in oneM2M System is FFS. | FFS - Clarify?
|  |  | 6.2.6.2.d | Editor's Note: Methods used for subscribing to and for querying a Group are FFS | FFS - Find Technical Solution?
6.2.7 | Location | 35 | - | - | -
6.2.7.1 | General Concepts | 35 | - | - | -
6.2.7.2 | Detailed Descriptions | 35 | - | - | -
6.2.8 | Network Service Exposure, Service Execution and Triggering | 35 | - | - | -
6.2.8.1 | General Concepts | 35 | - | - | -
6.2.8.2 | Detailed Descriptions | 36 | - | - | -
6.2.9 | Registration | 36 | - | - | -
6.2.9.1 | General Concepts | 36 | - | - | -
6.2.9.2 | Detailed Descriptions | 36 | 6.2.9.2.a | Editor's Note: The need for Device Registration and the relationship with CSE Registration are FFS | FFS - Clarify?
|  |  | 6.2.9.2.b | Editor's Note: The use of External ID in Registration is FFS | FFS - Clarify or Find Technical Solution?
|  |  | 6.2.9.2.c | Editor’s Note: Authorization above might only be needed for AEs, this is FFS in Security WG | FFS - Clarify WG4?
|  |  | 6.2.9.2.d | Editor’s Note: The use of “instance” above might be removed if other definitions are changed. If kept, the description regarding “instances” should be expanded. | Clarify
|  |  | 6.2.9.2.e | Editor's note: Further Registration information is FFS. | FFS - Clarify or Find Technical Solution?
6.2.10 | Security | 38 | 6.2.10.a | Editors Note: Need to add definitions or remove capitalization. | Review and Clarify WG4 ?
6.2.10.1 | General Concepts | 38 | - | - | -
6.2.10.2 | Detailed Descriptions | 38 | 6.2.10.2.a | Editor's Node: The definition of Security Association will be provided by WG4. A definition may be: "Security associations (SAs) are logical relationships between 2 entities that may be associated with a communications link, but SAs are not communications links. Security associations may take a number of forms but in each case they identify the nature of the security service (confidentiality, integrity, authentication or authorisation), the required algorithm and key. Security associations may be established for single transactions (and thus their establishment may form part of the transaction itself) or for session based associations (in such instances the association is generally established independently of the individual transactions that are to be secured)". | Provide definition text WG4?
6.2.11 | Service Charging and Accounting | 39 | - | - | -
6.2.11.1 | General Concepts | 39 | - | - | -
6.2.11.2 | Detailed Descriptions | 40 | 6.2.11.2.a | Editor's Note: Online charging items is FFS. | FFS - Find Technical Solution?
|  |  | 6.2.11.2.b | Editor's Note: The system may record information for other purposes also such as for Event Logging. Some of such information may be applicable for charging purposes. | Find Technical Solution? Clarify wording
6.2.12 | Subscription and Notification | 40 | - | - | -
6.2.12.1 | General Concepts | 40 | 6.2.12.1.a | Editor's Note: Determining subscribe-able resources is FFS. | Clarify
6.2.12.2 | Detailed Descriptions | 40 | - | - | -
6.3 | Functional Entities Comprising Enablers | 41 | 6.3.a | Editor's Note: The above list is preliminary and is for FFS | FFS - Find Technical Solution?
|  |  | 6.3.b | Editor's Note: How the Service Extension Enabler is associated with the APIs is FFS. | FFS - Find Technical Solution?
6.4 | Security Aspects | 42 | 6.4.a | Editor's Note: Clarify the difference between "application nodes and devices" in the para above. | Clarify
|  |  | 6.4.b | Editor's Note: Define Application Providers or use lowercase. | Clarify and/or define in text
6.5 | Other Aspects | 43 | - | - | -
6.5.1 | Inter M2M SP communication for oneM2M compliant nodes | 43 | 6.5.1.a | Editors Note: The CSE registration procedures will be updated to include normative text for the creation of the needed DNS entries | Update text
6.5.1.1 | Public Domain Names and CSEs | 44 | - | - | -
6.5.1.2 | M2M Service Subscription | 44 | 6.5.1.2.a | Editor’s Note: Change Access Right to Access Control Policy if such a recommendation is made by WG4 | Clarify & edit - WG4
6.5.2 | Inter M2M SP Generic Procedures | 45 | - | - | -
6.5.2.1 | Actions in the originating M2M node in Originating Domain | 45 | - | - | -
6.5.2.2 | Actions in the Receiving CSE in originating domain | 45 | - | - | -
6.5.2.3 | Actions in the IN of the target domain | 45 | - | - | -
7 | M2M Identification and Addressing | 46 | - | - | -
7.1 | M2M Identifiers | 46 | 7.1.a | Editor's Note: There is need to clarify the usage of the term CSE-ID/App-ID as opposed to CSE-ID instance/App-ID instance. | Clarify
7.1.1 | M2M Service Provider Identifier (M2M-SP-ID) | 46 | - | - | -
7.1.2 | Application Instance Identifier (App-Inst-ID) | 46 | - | - | -
7.1.3 | Application Identifier (App-ID) | 46 | 7.1.3.a | Editor's Note: Who assigns the App-ID is FFS | FFS - Find Technical Solution?
7.1.4 | CSE Identifier (CSE-ID) | 46 | - | - | -
7.1.5 | M2M Node Identifier (M2M-Node-ID) | 47 | - | - | -
7.1.6 | M2M Service Subscription Identifier (M2M-Sub-ID) | 47 | 7.1.6.a | Editor's Note: The specification needs to include a section on services, service identifiers | Text needed
7.1.7 | M2M Request Identifier (M2M-Request-ID) | 47 | 7.1.7.a | Editor's Note: Bring in a contribution to indicate where this information will carried | Clarify
|  | 47 | 7.1.7.b | Editor's Note: In order to allow interworking, how the platform understands whether the Request Identifier is globally unique or not needs to be specified. | Clarify
7.1.8 | M2M External Identifier (M2M-Ext-ID) | 48 | 7.1.8.a | Editor's Note: The method for dynamic plug-and-play association of M2M-Ext-ID and the 3GPP Underlying Network Identifier is FFS. | FFS - Find Technical Solution?
|  |  | 7.1.8.b | Editor's Note: Define "identity of the Underlying Network". | Clarify
7.1.9 | Underlying Network Identifier (UNetwork-ID) | 48 | - | - | -
7.1.10 | Trigger Recipient Identifier (Trigger-Recipient-ID) | 48 | - | - | -
7.1.11 | M2M Service Identifier (M2M-Serv-ID) | 48 | - | - | -
7.2 | M2M Identifiers lifecycle and characteristics | 49 | - | - | -
7.3 | Addressing an Application Entity | 50 | - | - | -
7.3.1 | Application Entity Addressing | 50 | - | - | -
7.3.2 | Application Entity Reachability | 50 | - | - | -
7.3.2.1 | CSE Point of Access (CSE-PoA) | 50 | - | - | -
7.3.2.2 | Locating Application Entities | 50 | 7.3.2.2.a | Editor's note: Abbreviations required above and below. | Add Abbreviations
7.3.2.3 | Usage of CSE-PoA by the M2M System | 50 | 7.3.2.3.a | Editor's Note: CSE registration refresh procedure is FFS | FFS - Find Technical Solution?
7.3.2.3.1 | CSE-PoA related to CSEs associated with a Fixed Network | 51 | - | - | -
7.3.2.3.2 | CSE-PoA related to CSEs associated with Mobile Networks | 51 | - | - | -
7.3.2.3.3 | CSE-PoA to CSEs associated with multiple Underlying Networks | 51 | 7.3.2.3.3.a | Editor's Note: Multiple sets of reachibility information for M2M Nodes accessible via multiple Underlying Networks needs to be supported. This is FFS. | FFS - Clarify or Tech Solution?
7.3.3 | Notification Re-targeting | 51 | - | - | -
7.3.3.1 | Application Entity Point of Access (AE-PoA) | 51 | - | - | -
8 | Description and Flows of Reference Points | 53 | - | - | -
8.1 | General Communication Flow Scheme on Mca and Mcc Reference Points | 53 | 8.1.a | Editor's Note: It is suggested to delete the above para if such alternative procedures cannot be identified. | Clarify or Delete?
|  | 53 | 8.1.b | Editors Note: Which of the procedures do not adopt the approach described in this clause and how they are performed is FFS. | FFS - Clarify or Find Technical Solution?
8.1.1 | Description | 53 | - | -
8.1.2 | Request | 53 | 8.1.2.a | Editor's Note: This is made under the assumption that the CSE-ID is incorporated in the URI of the target resource or the parent of the target resource. | Verify assumption
|  |  | 8.1.2.b | Editor's Note: Defaults for meta-information are FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 8.1.2.c | Editor's Note: How pre-provisioning and discovery are performed is FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 8.1.2.d | Editor's Note: This is an initial list of the verbs. The need for more verbs is anticipated to cover all use cases, configuration and functions | Check completeness - Delete
|  |  | 8.1.2.e | Editor's Note: Link types A, B, C are examples and are FFS. Or should it be converted to a NOTE. | FFS - Find Technical Solution?
|  |  | 8.1.2.f | Editor's Note: Details on what settings for rc are possible can be added at a later when the specific operations that can be requested are defined (e.g. register an AE, modify content of a container, etc.) | FFS - Find Technical Solution?
|  |  | 8.1.2.g | Editor's Note: Details on how to limit use of ec by AEs and relationship to provisioned policies are FFS | FFS - Find Technical Solution?
8.1.2.1 | Summary of Request Message Parameters | 58 | - | - | -
8.1.3 | Successful Operation | 60 | 8.1.3.a | Editor's Note: Defaults for meta-information are FFS. | FFS - Find Technical Solution?
8.1.4 | Unsuccessful Operation | 61 | 8.1.4.a | Editor's Note: Default for meta-information are FFS | FFS - Find Technical Solution?
8.1.5 | Summary of Response Message Parameters | 61 | - | -
8.2 | Procedures for Accessing Resources | 62 | 8.2.a | Editor's Note: Other procedures related to accessing the resources are FFS. | FFS - Find Technical Solution?
8.2.1 | Generating Responses | 62 | 8.2.1.a | Editor's Note: References to Protocol specifications will be provided when available. | WG3 - PRO Forward Ref?
|  |  | 8.2.1.b | Editor's Note: Details of Acknowledgement Response type is FFS. | FFS - Find Technical Solution?
8.2.2 | Accessing Resources in CSEs - Blocking Requests | 63 | 8.2.2.a | Editor's Note: How the target of a Request (i.e, an Application or local/hosting CSE) is identified and addressed, is FFS. | FFS - Find Technical Solution?
|  |  | 8.2.2.b | Editor's Note: A message (Request, Response) can be forwarded immediately or forwarded at a later time (e.g in the case of congestion).The procedures related to the forwarding of the Request at a later time are FFS. | FFS - Find Technical Solution?
|  |  | 8.2.2.c | {REF} Editor's Note-1 | Delete or REF to final text
|  |  | 8.2.2.d | {REF} Editor's Note-2 | Delete or REF to final text
|  |  | 8.2.2.e | Editor's Note-1: One-Hop case could potentially include the CSE-to-CSE communication also. The need for such procedures is FFS | FFS - Find Technical Solution?
|  |  | 8.2.2.f | Editor's Note-2: The multi-hop procedures address the scenario when the target is on a specific remote CSE. How a flow will work when the target is distributed on multiple remote CSEs is FFS | FFS - Find Technical Solution?
8.2.3 | Accessing Resources in CSEs - Non-Blocking Requests | 68 | - | - | -
8.2.3.1 | Response with Reference to Result of Requested Operation | 68 | - | - | -
8.2.3.2 | Synchronous Case | 68 | - | - | -
8.2.3.3 | Asynchronous Case | 71 | - | - | -
8.3 | Description and Flows on Mcn Reference Point | 71 | - | - | -
8.3.1 | General Description | 71 | 8.3.1.a | Editor's Note: The above is example of services requests from IN-CSE to Underlying Networks. {Need} To provide similar examples of service requests from ASN-CSEs and MN-CSEs to the Underlying Networks. | Clarify add examples
8.3.2 | Service Requests | 72 | - | - | -
8.3.2.1 | Connection Request | 72 | 8.3.2.1.a | Editor’s Note: Connection request is for FFS | FFS - Clarify or Find Technical Solution?
8.3.2.2 | Location Request | 72 | 8.3.2.2.a | Editor’s Note: Location request is for FFS | FFS - Clarify or Find Technical Solution?
8.3.2.3 | Device Management | 72 | 8.3.2.3.a | Editor's Note: The detailed content from section 6.2.4 might fit better in this section than in the high level CSF description. | Add text from 6.2.4?
8.3.2.4 | Device Triggering | 72 | - | - | -
8.4 | Device Triggering | 72 | - | - | -
8.4.1 | Definition and scope | 72 | 8.4.1.a | Editor’s Note: Verify reference and Annexes | Verify
8.4.2 | General Procedure for Device Triggering | 73 | - | - | -
8.4.2.1 | Triggering procedure for targeting ASN/MN-CSE | 73 | 8.4.2.1.a | Editor’s Note: M2M-Ext-ID is set on registration, how the IN-CSE gets it is FFS. | FFS - Clarify or Find Technical Solution?
|  | 73 | 8.4.2.1.b | Editor’s Note: The above list with information to be sent over Device Triggering request on the underlying network is not complete and/or limiting. What is needed is for FFS. | FFS - Clarify or Find Technical Solution?
9 | Resource Management | 76 | - | - | -
9.1 | General Principles | 76 | 9.1.a | Editor's Note: These above stated resource types needs to be validated as for clause 9.6. | verify w/9.6
|  |  | 9.1.b | Editor’s note: This section may need fixing due to inconsistency | Clarify
|  |  | 9.1.c | Editor’s note: local CSE terminology needs discussing | Clarify
|  |  | 9.1.d | Editors note: All the highlighted text (in magenta) shall be removed once some figures are available (as per ARC#2014-101R02) | Update to align with ageed figures
|  |  | 9.1.e | Editor's Note: Contribution #0505R1 already address the fact that URI is not used in a proper manner in the TS. However the term structured and flat URI still use the term URI. Detailed definition on how to do addressing in oneM2M still needs to be drafted. Alignment of the proper terminology in the TS is needed. | Align text
|  |  | 9.1.f | Editor's Note: how the flat URI can be distinguished from the structured URI is for FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 9.1.g | Editor's Note: if there is a need to provide both structured URI or flat URI of a resource if for FFS | FFS - Clarify or Find Technical Solution?
9.1.1 | Resource Announcement | 77 | - | - | -
9.2 | Resource Types | 77 | 9.2.a | [REF} Editor's Note-2 | Delete or REF to Final text
|  |  | 9.2.b | [REF} Editor's Note-3 | Delete or REF to Final text
|  |  | 9.2.c | {REF} Editor's Note-1. <this row needs to be removed> | Delete ?
|  |  | 9.2.d | Editor's Note-1: For the <Entity> resource storing information related to CSEs: Is the reference to local CSEs or to both the local and remote CSEs. Need to be clarified. | Clarify
|  |  | 9.2.e | Editor's Note-2: The type of resources included in this Table is not complete yet. This is FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 9.2.f | Editor's Note-3: As the work progresses, the resource types may change. This is FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 9.2.g | Editor'Note: Resource Type Tag in the Table above (Table 9.2-1) seems to have the same function as the common attribute "resourceType" which is defined in clause 9.6.1. There is inconsistency amongst the two: single character in Table 9.2.1 and two capital-letters in clause 9.6.1 definition of "resourceType" attribute. It is proposed that a single naming convention be used - and all resource types be defined in Table 9.2.1 - possibly using two capital-letters | Clarify
|  |  | 9.2.h | Editor's Note: The use of the notation of pointy brackets <...> is for indicating "resource type". For the case of <CSEBase>, they (pointy brackets) have been used in another way. Instead of being used to indicate a "resource type", they are being used as a placeholder for an address {which could be URI}. Since the URI has nothing to do with the "resource type", it is suggested to call this Base Resource as either the "Base Resource <base>", or the "Base-CSE Resource <baseCSE>". If such change is agreed, it needs to be reflected in the "General Principles" clause 9.1 as well. Need discussions and resolution with the WG. If agreed, it will have impact on figure 9.4.1 as well | Clarify Check consistant use of < >
|  |  | 9.2.i | Editor's Note: Attributes for the Resource Types are FFS. | FFS - Find Technical Solution?
|  |  | 9.2.j | Editor's Note: The term "name" does not seem appropriate in <name> in the Table above. It is probably meant to be the Resource Type. Whenever we have <xxxxx>, the string within < >, should be a resource type identifier. Needs discussions and resolution within the WG. If agreed, the descriptive section in the Table above also needs to be adjusted. | Clarify & Align text
9.2.1 | Types of Virtual Resources | 79 | 9.2.1.a | Editor's Note: The list of virtual resources is FFS. E.g. <Members> is one of the virtual resource type specified in this document. | FFS - Find Technical Solution?
9.3 | Resource Addressing | 79 | - | - | -
9.3.1 | Generic principles | 79 | - | - | -
9.3.1.1 | Support for Multiple CSEs within a single node | 80 | - | - | -
9.3.2 | Resource addressing via a FQDN URI | 80 | 9.3.2.a | Editor's Note: With this change of /baseRoot to /<CSEBase>: we need to examine the whole specification for the appropriate use of the /baseRoot vs. /<CSEBase> terminology. It is suggested to identify a task group to review the document and suggest appropriate changes. | Discuss & Clarify
9.4 | Resource Structure | 81 | - | - | -
9.4.1 | Links between resources | 81 | 9.4.1.a | Editor's Note: The resource structure picture needs to be updated as the resource structure evolves. | Align figure with Final text
|  |  | 9.4.1.b | Editor's Note: Links management (creation, deletion, etc.) is FFS | FFS - Find Technical Solution?
9.4.2 | Link Types | 81 | 9.4.2.a | Editor’s Note: There are more links to define in this Table to reflect the current state of the TS | Align Table with Final text
9.5 | Resource Specification Guidelines | 82 | 9.5.a | Editor's Note: Clarification is needed on how acronyms should be handled. For example we could choose nodeID or nodeId. It is proposed that acronyms/abbreviated-names are always CAPITALIZED. | Clarify Check consistant use of CAPS
|  |  | 9.5.b | Editor’s Note: Actual mapping rules is FFS, and it should be part of Protocol Core TS | Verify w/WG3 PRO Delete or find Technical Solution
9.5.1 | Resource Template | 83 | - | - | -
9.5.1.1 | Resource Type resourceType | 83 | - | - | -
9.5.2 | Examples for Resource Specification | 85 | - | - | -
9.5.2.1 | Example of a Resource with attributes only | 85 | - | - | -
9.5.2.1.1 | Resource Type accessRight | 85 | - | - | -
9.5.2.2 | Example of a Resource with attributes and child resources | 85 | - | - | -
9.5.2.2.1 | Resource Type container | 85 | - | - | -
9.5.3 | Handling of Unsupported and non compliant Resources | 86 | - | - | -
9.6 | Specified Resource Types | 87 | 9.6.a | Editor’s Note: This Table was based upon revision 0.3.2 and may be missing information from subsequent agreed contributions. It is expected to be updated as we further define resources. Cells marked “None Documented” indicate the status of 0.3.2, if no addition is needed to these cells then they should be marked “None” when this Table is finalised. | Align Table with Final text
9.6.1 | Common Attributes | 89 | 9.6.1.a | Editor's Note: The adoption of a URI format is still to be confirmed. | Align URI format with Final text
|  | 89 | 9.6.1.b | Editor's Note: what is the list of permission holders | Clarify
|  | 89 | 9.6.1.c | Editor's Note: The usage of creator (cr) attribute is FFS. | FFS - Clarify or Find Technical Solution?
|  | 89 | 9.6.1.d | Editor's Note: The following attributes are FFS depending on resource structure discussions: • child: resources with child relation with the considered resource • parent: resources with parent relation with the considered resource | FFS - Clarify or Find Technical Solution?
9.6.2 | Resource Type accessControlPolicy | 90 | 9.6.2.a | Editor's Note: There is a need for a global replacement of accessRight with accessControlPolicy, accessRightsID with accessControlPolicyID, permission with privilege. | Clarify and Align text
|  |  | 9.6.2.b | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute | Align figure with Final text
|  |  | 9.6.2.c | Editor's Note: Contribution ARC-2014-0089R03 does not provide the table for the <subscription> child-resource. The contributor to verify the accuracy of the proposal. | Verify text and Add child-resource Table
|  |  | 9.6.2.d | Editor's Note: Mechanisms for announcing are FFS | FFS - Find Technical Solution?
9.6.2.1 | originatorPrivileges | 93 | - | - | -
9.6.2.2 | contexts | 93 | - | - | -
9.6.2.3 | operationFlags | 93 | 9.6.2.3.a | Editor’s Note: A non-verbose privilege flag description could be the following: <pf>RcUeDN</pf> that means: RETRIEVE allowed, CREATE not allowed, UPDATE allowed, DELETE not allowed, DISCOVER allowed, NOTIFY allowed. | Discuss & Clarify
9.6.3 | Resource Type CSEBase | 94 | 9.6.3.a | Editor’s Note: this list should be updated. Which resource types are added is FFS. | Update List FFS - Find Technical Solution?
|  | 94 | 9.6.3.b | Editor’s Note: how to extend functionality is FFS | FFS - Find Technical Solution?
9.6.4 | Resource Type remoteCSE | 95 | 9.6.4.a | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute | Align figure with Final text
|  |  | 9.6.4.b | Editor's Note on CSE-ID: an alignment between CSE-ID and CSEBase is needed. | Align Text
|  |  | 9.6.4.c | Editor's Note on CSEBase: the alignment with naming convention proposed for inter-M2M service provider is needed. | Align Text
|  |  | 9.6.4.d | Editor's Note on child resources: child resources of <remoteCse> resource can accommodate listed resources and their announced versions. | Clarify or Find Technical Solution?
9.6.5 | Resource Type application | 98 | 9.6.5.a | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute | Align figure with Final text
|  |  | 9.6.5.b | Editor’s Note: Needs to be defined. | Clarify / Definition
|  |  | 9.6.5.c | Editor's Note: Cardinality of pointOfAccess attribute (0..n) needs to be investigated for all its occurrences. | Discuss & Clarify
9.6.6 | Resource Type container | 101 | 9.6.6.a | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute. | Align figure with Final text
|  |  | 9.6.6.b | Editor's Note: Susbscription relation with this resource is for FFS | FFS - Clarify or Find Technical Solution?
|  |  | 9.6.6.c | Editor's Note: location resource relation with containers is for FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 9.6.6.d | Editor's Note: Mechanisms for announcing are FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 9.6.6.e | Editor's Note: The container type is FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 9.6.6.f | Editor's Note: The following attributes are FFS depending on resource structure discussions: • child: resources with child relation with the considered resource • parent: resources with paren relation with the considered resource | Discuss and Align FFS - Find Technical Solution?
9.6.7 | Resource Type instance | 105 | 9.6.7.a | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute. | Align figure with Final text
|  |  | 9.6.7.b | Editor’s Note: Clairify forward reference to Stage 3 | Clarify
9.6.8 | Resource Type subscription | 106 | 9.6.8.a | Editor’s Note: No such resource has been described - propose to remove it | Delete resource, or add Description
|  |  | 9.6.8.b | Editor's Note: It is not yet clear how or where to best to explain the applicability of the resource <subscription>. Subscribable resources can be added to the list above, Non-subscribable resources can also be added to the list above, and/or we could ensure that the applicability of the resource <subscription> is clearly described with each resource, removing or keeping the list here | Discuss and Clarify
|  |  | 9.6.8.c | Editor's Note: criteria is shown as an attribute, However, whether we need a separate attribute or child resource for notification policy is FFS | FFS - Clarify or Find Technical Solution?
|  |  | 9.6.8.d | Editor's Note: In the case when there are Intermediate Nodes between the Originator and a Receiver, the Intermediate Nodes may not act in accordance with the subscription notification policy. Examples include: a policy of batching subscribed events for up to 30 seconds then deliver immediately, but an intermediate node may decide to delay or further aggregate the subscription notifications. The solution to this problem is FFS, but may include sending a representation of policy with the subscription notifications, which is to be considered by Intermediate Nodes (e.g. Request Expiration Time). | Discuss and Clarify FFS - Find Technical Solution?
9.6.9 | Resource Type schedule | 110 | 9.6.9.a | Editor's Note: It is expected that the reachability period will be extended by the duration of a transaction which is currently occurring, but the details need further study | FFS - Clarify or Find Technical Solution?
|  |  | 9.6.9.b | Editor's Note: This list will be revised as resources are further progressed | Align list with Final resource text
|  |  | 9.6.9.c | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute. | Align figure with Final text
|  |  | 9.6.9.d | Editor's Note: The multiplicity of attribute must be aligned to the new understanding | Discuss and Align
9.6.10 | Resource Type locationPolicy | 111 | 9.6.10.a | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute | Align figure with Final text
9.6.11 | Resource Type delivery | 113 | 9.6.11.a | Editor's Note: Further details on mechanisms how to do delivery handling are FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 9.6.11.b | Editor's Note: The particular position in the addressable space of resources id FFS | FFS - Clarify or Find Technical Solution?
9.6.12 | Resource Type request | 115 | 9.6.12.a | Editor's Note: The exact way how to define that setting (e.g. via DM) is FFS | Discuss w/WG5 MAS FFS - Find Technical Solution?
9.6.13 | Resource Type group | 117 | 9.6.13.a | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute | Align figure with Final text
9.6.14 | Resource Type Members | 119 | - | - | -
9.6.15 | Resource Type mgmtObj | 120 | 9.6.15.a | Editor's note - add references? | Add References
|  |  | 9.6.15.b | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute | Align figure with Final text
9.6.16 | Resource Type parameters | 122 | - | - | -
9.6.17 | Resource Type mgmtCmd | 123 | 9.6.17.a | Editor's Note: The types of management operations (e.g. cmdType) to be used by mgmtCmd are FFS. | FFS - Clarify or Find Technical Solution?
9.6.18 | Resource Type execInstance | 124 | 9.6.18.a | Editor's note: the relationships between execMode, execFrequncy and execNumber are FFS | FFS - Clarify or Find Technical Solution?
9.6.19 | Resource Type node | 126 | 9.6.19.a | Editor's Note: ADN case needs to be defined | Add case aligned with Final ADN text
|  |  | 9.6.19.b | Editor's Note: More specific information regarding a node can be added. | Align with Final node definition
|  |  | 9.6.19.c | Editor's Note: To update the picture to include "link", "announceTo" and "announcedAttribute" attribute. | Align figure with Final text
9.6.20 | Resource Type m2mServiceSubscription | 128 | 9.6.20.a | Editor's Note: The link between the M2M Service Subscription resource and RBAC will be added once RBAC is included in the specification. | Align with Final RBAC text
|  |  | 9.6.20.b | Editor's Note: the M2M-Sub-ID storage is FFS | FFS - Clarify or Find Technical Solution?
9.6.21 | Resource Type nodeInfo | 129
9.6.22 | Resource Type pollingChannel | 130
9.6.23 | Resource Type cmdhPolicy | 131 | 9.6.23.a | Editor’s Note: The parent resource for this <cmdhPolicy> resource type is TBD. The <cmdhPolicy> resource type will be defined as a management Object. | Clarify / Discuss w/WG5 MAS ?
|  |  | 9.6.23.b | Editor’s Note: When the <CSEBase> resource is accepted, an attribute or link in the <CSEBase> resource could be used to point to the active <cmdhPolicy> resource. | Align with <CSEBase> resource text
9.6.24 | Resource Type cmdhDefaults | 133 | - | - | -
9.6.25 | Resource Type cmdhDefEcValue | 134 | - | - | -
9.6.26 | Resource Type cmdhEcDefParamValues | 137 | - | - | -
9.6.27 | Resource Type cmdhLimits | 139 | - | - | -
9.6.28 | Resource Type cmdhNetworkAccessRules | 141 | - | - | -
9.6.29 | Resource Type cmdhNwAccessRule | 143 | - | - | -
9.6.30 | Resource Type cmdhBuffer | 146 | - | - | -
9.6.31 | Resource Type statsConfig | 148 | - | - | -
9.6.32 | Resource Type eventConfig | 149 | - | - | -
9.6.33 | Resource Type statsCollect | 150 | - | - | -
9.6.34 | Resource Announcement | 151 | 9.6.34.a | Editor's Note: For the announced resource type, some postfix shall be used for the resource type. The naming convention is FFS. | FFS - Clarify post-fix or find Technical Solution?
10 | Information Flows | 152 | 10.a | Editor's Note: It is FFS about the suitable section for the proposed generic call flows and potential re-org of the sections due to the correlation of current clauses 8 and 10 | Discuss and Clarify relationship between Sect 8 and Sect 10
10.1 | Basic Procedures | 152 | 10.1.a | Editor's Note: The procedures in the following sub-clauses assume blocking requests as described in clause 8.2.2 | Find Technical Solution?
10.1.1 | CREATE (C) | 152 | - | - | -
10.1.1.1 | Non-registration related CREATE procedure | 152 | 10.1.1.1.a | Editor’s Note: Add SEC reference | Align with WG4 SEC
|  |  | 10.1.1.1.b | Editor's Note: AE or CSE may not have the ID upon its registration request. Alternative information for fr is FFS. | Discuss w/WG4 SEC and Clarify. FFS - Find Technical Solution?
|  |  | 10.1.1.1.c | Editor’s Note: which parameters are deducted to be mandatory/optional in the request is for FFS. Section 8.1 should provide a generic mechanism to identify mandatory params for a request by looking at how the resource is defined. E.g. If the attribute in the resource definition is identified as mandatory and it is of type RW, then it is also intended as mandatory in the request | Discuss w/WG4 SEC and Clarify. FFS - Find Technical Solution?
|  |  | 10.1.1.1.d | Editor's Note: references to elements defined in sect 8 have been added here. They may be removed if we decide to move sect 8.1.2-4 to stage 3 doc. In this case, these references will be removed and sect 1 of this document would replace sect 8.1.2-4 in the TS-0001. | Discuss Sect 8 structure and Clarify.
|  |  | 10.1.1.1.e | Editor’s Note: how far should the Receiver go back to a parent to look for an accessControlPolicyID is FFS | FFS - Clarify or Find Technical Solution?
|  |  | 10.1.1.1.f | Editor’s Note: which parameter is allowed to be provided by the Receiver CSE is for FFS. There are few cases: RO in most of the cases, and in some cases the Receiver may also changes the RW attributes, e.g. the expirationTime or the max number of instances which could be related to subscription agreements or policies. | FFS - Clarify or Find Technical Solution?
10.1.1.2 | Registration related CREATE procedure | 154 | - | - | -
10.1.1.2.1 | CSE Registration procedure | 154 | 10.1.1.2.1.a | Editor’s Note: The section that should refer to section 6.5 somewhere where the public domains of CSEs are defined | Clarify relationship to Sect. 6.5
10.1.1.2.2 | Application Registration procedure | 156 | 10.1.1.2.2.a | Editor’s Note: which accessControlPolicy needs to be used is FFS | FFS - Clarify or Technical Solution?
|  |  | 10.1.1.2.2.b | Editor’s Note: more investigation is needed in WG4 for clarify what will be the value of fr and in which section it will be described. | Discuss w/WG4 SEC and Clarify.
10.1.2 | RETRIEVE (R) | 156 | 10.1.2.a | Editor's Note: The statement in the para above is not clear. Is this operation targeted for retrieving ALL attributes for a resource together (as a Group) or for specific attributes only? Depending on the answer, the text above needs to be updated. The text in the para that follows assumes that this operation is for retrieving all attributes for a resource. If the Request is for retrieving only a specific attribute, then the identity of such attribute is included in the Request message. | Discuss and Clarify
10.1.3 | UPDATE (U) | 158 | - | - | -
10.1.4 | DELETE (D) | 159 | - | - | -
10.1.5 | NOTIFY (N) | 159 | 10.1.5.a | Editor’s Note: not sure how to align this procedure with the other one. The Receiver should also have a local processing, but if the addressed of the resource in the to is not one of the defined resource types what the receiver does is out of scope. However if the NOTIFY will correspond to a create instance then the procedures describe in the create should apply. This operation needs more refining. | Discuss and Clarify
|  |  | 10.1.5.b | Editor's note: General exceptions are FFS in particular for notification failures. | FFS - Clarify or Find Technical Solution?
10.2 | Resource Type-Specific Procedures | 160 | - | - | -
10.2.1 | <application> Resource | 160 | - | - | -
10.2.1.1 | Create <application>, aka Application Registration | 160 | 10.2.1.1.a | Editor’s Note: Currently there is no section with specific text on the authentication/access control from SEC. | Discuss with WG4 SEC and Clarify
|  |  | 10.2.1.1.b | Editor’s note: It is not clear if the case of non-authenticated AE can register to a local CSE, but with a very limited access. This case is FFS | FFS - Clarify or Find Technical Solution?
|  |  | 10.2.1.1.c | Editor’s note: the relation with the accessControlPolicy is for FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 10.2.1.1.d | Editor’s Note: More investigation is needed in WG4 to clarify what will be the value of fr and in which section it will be described | Discuss with WG4 SEC and Clarify
|  |  | 10.2.1.1.e | Editor’s Note: fix Table 7 for optional App-Inst-ID | Align Table to App-Inst-ID text
10.2.1.2 | Retrieve <application> | 161 | - | - | -
10.2.1.3 | Update <application> | 162 | - | - | -
10.2.1.4 | Delete <application>, aka De-Register | 162 | 10.2.1.4.a | Editor’s note: if and how credentials are cleaned is FFS, in scope of WG4 | Discuss w/WG4 SEC and Clarify. FFS - Find Technical Solution?
10.2.2 | <RemoteCSE> Resource | 163 | - | - | -
10.2.2.1 | Create <RemoteCSE>, aka CSE Registration | 163 | - | - | -
10.2.2.2 | Retrieve <remoteCSE> | 164 | - | - | -
10.2.2.3 | Update <remoteCSE>, aka Re-registration | 164 | - | - | -
10.2.2.4 | Delete <remoteCSE>, aka CSE De-Registration | 164 | 10.2.2.4.a | Editor’s note: if and how credentials are cleaned is FFS, in scope of WG4 | Discuss w/WG4 SEC and Clarify. FFS - Find Technical Solution?
10.2.3 | <container> Resource | 165 | - | - | -
10.2.3.1 | Create <container> | 165 | 10.2.3.1.a | Editor's Note: Section x.y.z referes to the table which describes the attribtues of <container> resource | Verify table reference
|  |  | 10.2.3.1.b | Editor's Note: The type of the resource to be created (ty) needs to be specified by the contributor as part of "Information on Request message". | Clarify
10.2.3.2 | Retrieve <container> | 166 | 10.2.3.2.a | Editor's Note: Section 9.6.6 referes to the table which describes the attributes of <container>. | Add reference to Sect 9.6.6
10.2.3.3 | Update <container> | 167 | - | - | -
10.2.3.4 | Delete <container> | 167 | - | - | -
10.2.4 | Access to Remotely Hosted Resources via CMDH CSF | 168 | - | - | -
10.2.4.1 | Introduction to use of <delivery> related flows | 168 | 10.2.4.1.a | Editor's note: The section below is not written in normative language, and terminology is not consistent with other sections: | Clarify and align text
10.2.4.2 | Create <delivery> | 171 | 10.2.4.2.a | Editor's Note: This call flow template will be evolving as we handle more examples. | Verify & Delete
10.2.4.3 | Retrieve <delivery> | 173 | 10.2.4.3.a | Editor's Note: This call flow template will be evolving as we handle more examples. | Verify & Delete
10.2.4.4 | Update <delivery> | 173 | 10.2.4.4.a | Editor's Note: This call flow template will be evolving as we handle more examples. | Verify & Delete
10.2.4.5 | Delete <delivery> | 174 | 10.2.4.5.a | Editor's Note: This call flow template will be evolving as we handle more examples. | Verify & Delete
10.2.5 | Resource Discovery Procedure | 175 | - | - | -
10.2.5.1 | Introduction | 175 | 10.2.5.1.a | Editor's Note: It is FFS how this temporary resource is operated such as the access right of this temporary resource, expiration time, the condition for creation | FFS - Clarify or Find Technical Solution?
10.2.5.2 | Discovery procedure via Retrieve Operation | 175 | 10.2.5.2.a | Editor's Note: It is FFS about discovery propagation mechanism, i.e. multi-hop discovery propagation and its policies. | FFS - Clarify or Find Technical Solution?
10.2.6 | Group Management Procedures | 176 | - | - | -
10.2.6.1 | Introduction | 176 | - | - | -
10.2.6.2 | Create <group> | 176 | - | - | -
10.2.6.3 | Retrieve <group> | 177 | 10.2.6.3.a | Editor’s Note: Add Clause Reference | Add Clause Ref
10.2.6.4 | Update <group> | 177 | - | - | -
10.2.6.5 | Delete <group> | 178 | 10.2.6.5.a | Editor's Note: The original contributor has been reqeusted to provide update/fixes for clauses 10.2.4.6 to 10.2.4.9 that are in line with the ARC TS notation rules. The contributor is requested to verify the cross references provided by the Rapporteur and help provide missing cross-references as well. | Clarify and Align text
10.2.6.6 | Create <Members> | 179 | 10.2.6.6.a | Editor's Note: How to aggregate synchronous and asynchronous responses is to be considered in stage 3. | Coordinate with WG3 PRO. Find Technical Solution?
|  |  | 10.2.6.6.b | Editor's Note: How to generate and maintain the gid is to be FFS is stage 3. | Coordinate with WG3 PRO. FFS - Clarify or Find Technical Solution?
10.2.6.7 | Retrieve <Members> | 181 | 10.2.6.7.a | Editor’s Note: Add Clause reference | Add Clause Ref
10.2.6.8 | Update <Members> | 182 | 10.2.6.8.a | Editor’s Note: Add Clause reference | Add Clause Ref
10.2.6.9 | Delete <Members> | 183 | 10.2.6.9.a | Editor’s Note: Add Clause reference | Add Clause Ref
10.2.6.10 | Subscribe and Un-Subscribe <Members> of a group | 184 | - | - | -
10.2.6.11 | Aggregate the notifications by group | 185 | 10.2.6.11.a | Editor’s Note: The policy defined in <subscription> resource may not be still valid after the aggregation by group. How to guarantee the validity of the policies is FFS together with the way to guarantee the validity of the policies in store and forward occasions | FFS - Clarify or Find Technical Solution?
10.2.7 | mgmtObj Management Procedures | 186 | - | - | -
10.2.7.1 | Introduction | 186 | - | - | -
10.2.7.2 | Create <mgmtObj> | 186 | - | - | -
10.2.7.3 | Retrieve <mgmtObj> | 187 | 10.2.7.3.a | Editor’s Note: Add external references | Add references
10.2.7.4 | Update <mgmtObj> | 188 | 10.2.7.4.a | Editor’s Note: Add external references | Add references
10.2.7.5 | Delete <mgmtObj> | 189 | 10.2.7.5.a | Editor’s Note: Add external references | Add references
10.2.7.6 | Execute <mgmtObj> | 190 | 10.2.7.6.a | Editor’s Note: Add external references | Add references
|  |  | 10.2.7.6.b | Editor's note: The definition of Execute is to be for FFS in clause 10.1. | Define / Align with Sect 10.1
10.2.8 | External Management Operations through <mgmtCmd> | 191 | 10.2.8.a | Editor’s Note: Add external references (BBF etc.) in Section | Add references
10.2.8.1 | Introduction | 191 | - | - | -
10.2.8.2 | Create <mgmtCmd> | 191 | - | - | -
10.2.8.3 | Retrieve <mgmtCmd> | 192 | 10.2.8.3.a | Editor's Note: We need to agree on a terminology on how to refer to a specific instance of a resource type. | Clarify notation
10.2.8.4 | Update <mgmtCmd> | 193 | - | - | -
10.2.8.5 | Delete <mgmtCmd> | 194 | - | - | -
10.2.8.6 | Execute <mgmtCmd> | 195 | 10.2.8.6.a | Editor's note: The definition of Execute is to be for FFS in clause 10.1. | Define / Align with Sect 10.1
|  |  | 10.2.8.6.b | Editor’s Note: Reference to Steps 004 & 005 needed | Clarify / reference
10.2.8.7 | Cancel <execInstance> | 196 | 10.2.8.7.a | Editor's Note: The Cancel flow shall be updated based on the definition of EXEC procedure | Clarify and Align with EXEC text
10.2.8.8 | Retrieve <execInstance> | 197 | - | - | -
10.2.8.9 | Delete <execInstance> | 198 | - | - | -
10.2.9 | Supported Attribute Discovery Procedure | 199 | - | - | -
10.2.9.1 | Introduction | 199 | - | - | -
10.2.9.2 | Supported Attributes Discovery procedure via Retrieve Operation | 199 | 10.2.9.2.a | Editor's Note: How to maintain/expose supported resource types of CSEs is FFS. | FFS - Clarify or Find Technical Solution?
10.2.10 | Location Management Procedures | 200 | - | - | -
10.2.10.1 | Procedure related to <locationPolicy> resource | 200 | - | - | -
10.2.10.1.1 | Create <locationPolicy> | 200 | 10.2.10.1.1.a | Editor's Note: Handling of various levels of the <locationPolicy> resources needs to be defined. | Discuss and Clarify
|  |  | 10.2.10.1.1.b | Editor’s Note: Align and/or provide references | Align / Add references
10.2.10.1.2 | Retrieve <locationPolicy> | 201 | - | - | -
10.2.10.1.3 | Update <locationPolicy> | 202 | - | - | -
10.2.10.1.4 | Delete <locationPolicy> | 202 | 10.2.10.1.4.a | Editor's Note: If deleted by CSE is the AE that created it notified. | Clarify or Find Technical Solution?
10.2.10.2 | Procedure when the <container> and <instance> resource contain location information | 203 | - | - | -
10.2.10.2.1 | Procedure for <container> resource that stores the location information | 203 | - | - | -
10.2.10.2.2 | Procedure for <instance> resource that stores the location information | 203 | - | - | -
10.2.11 | <subscription> Resource Procedures | 203 | - | - | -
10.2.11.1 | Introduction | 203 | - | - | -
10.2.11.2 | Create <subscription> | 203 | 10.2.11.2.a | Editor's Note: Access right to send notification to an entity can be represented as NOTIFY permission. | Clarify or Find Technical Solution?
|  |  | 10.2.11.2.b | Editor's Note: The validation process described in the last two bullet points above needs to be investigated further, This is FFS | FFS - Clarify or Find Technical Solution?
|  |  | 10.2.11.2.c | Editor’s Note: Clarify use of “??” in Table | Clarify
10.2.11.3 | Retrieve <subscription> | 204 | 10.2.11.3.a | Editor’s Note: Clarify use of “??” in Table | Clarify
10.2.11.4 | Update <subscription> | 205 | - | - | -
10.2.11.5 | Delete <subscription> | 205 | - | - | -
10.2.12 | Notification Procedures for Resource Subscription | 206 | 10.2.12.a | Editor’s Note: The notification policy enforcement between subscription resource hosting CSE and the notification target CSE need to be FFS. | FFS - Clarify or Find Technical Solution?
|  |  | 10.2.12.b | Editor’s Note: How the latestNotify is carried in the notification is FFS | FFS - Clarify or Find Technical Solution?
|  |  | 10.2.12.c | Editor’s Note: The specific threshold mentioned above needs to be added as an attribute in the <CSEBase> resource type. | Clarify threshold
10.2.13 | Polling Channel Management Procedures | 208 | - | - | -
10.2.13.1 | Introduction | 208 | - | - | -
10.2.13.2 | Create <pollingChannel> | 209 | - | - | -
10.2.13.3 | Retrieve <pollingChannel> | 209 | - | - | -
10.2.13.4 | Update <pollingChannel> | 210 | - | - | -
10.2.13.5 | Delete <pollingChannel> | 210 | - | - | -
10.2.13.6 | Re-targeting Requests to Polling Channel | 210 | - | - | -
10.2.13.7 | Long Polling on Polling Channel | 211 | - | - | -
10.2.14 | <node> Resource Procedure | 211 | - | - | -
10.2.14.1 | Create <node> | 211 | - | - | -
10.2.14.2 | Retrieve <node> | 212 | - | - | -
10.2.14.3 | Update <node> | 213 | - | - | -
10.2.14.4 | Delete <node> | 213 | 10.2.14.4.a | Editor’s Note: if and how credentials are cleaned is FFS, in scope of WG4 | Discuss w/WG4 SEC and Clarify. FFS - Find Technical Solution?
10.2.15 | Service Charging and Accounting Procedures | 214 | - | - | -
10.2.15.1 | Introduction | 214 | - | - | -
10.2.15.1.1 | Service Event-based Statistics Collection for Applications | 214 | - | - | -
10.2.15.2 | CREATE <statsConfig> | 215 | 10.2.15.2.a | Editor’s Note: The texts below provide examples on how to populate the sub-resources and attributes. Many of the attributes are enumeration type and the exact values will be defined in Stage 3. | Coordinate with WG3 PRO. Find Technical Solution?
10.2.15.3 | RETRIEVE <statsConfig> | 216 | - | - | -
10.2.15.4 | UPDATE <statsConfig> | 217 | - | - | -
10.2.15.5 | DELETE <statsConfig> | 217 | - | - | -
10.2.15.6 | CREATE <statsCollect> | 218 | - | - | -
10.2.15.7 | RETRIEVE <statsCollect> | 219 | - | - | -
10.2.15.8 | UPDATE <statsCollect> | 219 | - | - | -
10.2.15.9 | DELETE <statsCollect> | 220 | - | - | -
10.2.15.10 | Service Statistics Collection Record | 220 | 10.2.15.10.a | Editor’s Note: More contents can be added when more chargeable events are specified | FFS - Clarify or Find Technical Solution?
10.2.16 | <m2mServiceSubscription> Resource | 221 | - | - | -
10.2.16.1 | Create <m2mServiceSubscription> | 221 | - | - | -
10.2.16.2 | Retrieve <m2mServiceSubscription> | 222 | - | - | -
10.2.16.3 | Update <m2mServiceSubscription> | 222 | - | - | -
10.2.16.4 | Delete <m2mServiceSubscription> | 223 | - | - | -
10.2.17 | <nodeInfo> Resource | 223 | - | - | -
10.2.17.1 | Create <nodeInfo> | 223 | - | - | -
10.2.17.2 | Retrieve <nodeInfo> | 224 | - | - | -
10.2.17.3 | Update <nodeInfo> | 224 | - | - | -
10.2.17.4 | Delete <nodeInfo> | 225 | - | - | -
10.2.18 | Resource Announcement Procedure | 225 | - | - | -
10.2.18.1 | Procedure for AE and CSE to initiate the creation or deletion of the Announced Resource | 225 | - | - | -
10.2.18.2 | Procedure for original resource hosting CSE to Announce Resource | 226 | - | - | -
10.2.18.3 | Procedure for original resource hosting CSE to delete the Announced Resource | 227 | - | - | -
10.2.18.4 | Procedure for AE and CSE to initiate the creation or deletion of the Announced Attribute | 228 | - | - | -
10.2.18.5 | Procedure for original resource hosting CSE to Announce Attribute | 229 | - | - | -
10.2.18.6 | Procedure for original resource hosting CSE to delete the Announced Attribute | 230 | - | - | -
11 | Trust Enabling Architecture | 231 | - | - | -
11.1 | Enroling M2M Nodes and M2M applications for oneM2M Services | 231 | - | - | -
11.2 | M2M Initial Provisioning Procedures | 231 | - | - | -
11.2.1 | M2M Node Enrolment and Service Provisioning | 231 | - | - | -
11.2.1 | M2M Application Enrolment | 232 | - | - | -
11.3 | M2M Operational Security Procedures | 232 | - | - | -
11.3.1 | Identification of CSE and AE | 233 | - | - | -
11.3.2 | Authentication of CSE and AE | 233 | - | - | -
11.3.3 | M2M Security Association Establishment | 233 | - | - | -
11.3.4 | M2M Authorization Procedure | 234 | - | - | -
12 | Information Recording | 235 | - | - | -
12.1 | M2M Infrastructure Node (IN) Information Recording | 235 | - | - | -
12.1.1 | Information Recording Triggers | 235 | - | - | -
12.1.2 | M2M Recorded Information Elements | 235 | - | - | -
12.1.2.1 | Unit of Recording | 235 | - | - | -
12.1.2.2 | Information Elements within an M2M Event Record | 235 | - | - | -
12.1.3 | Identities Associations in support of Recorded Information | 238 | - | - | -
12.2 | Offline Charging | 238 | - | - | -
12.2.1 | Architecture | 238 | 12.2.1.a | Editors Note: Update Figure 5.2.1-1 to include this new interface. | Align Architecture Figures
|  |  | 12.2.1.b | Editor's Note: Once this picture is moved to section 5.5; need to remove the picture from here | Align with Sect 5.2.2.5
12.2.2 | Filtering of Recorded Information for Offline Charging | 239 | - | - | -
12.2.3 | Examples of Charging Scenarios | 239 | - | - | -
12.2.3.1 | Example CharginScenario 1 – Data Storage Resource Consumption | 239 | - | - | -
12.2.3.2 | Example Charging Scenario 2 – Data transfer | 239 | - | - | -
12.2.3.3 | Example Charging Scenario 3 – Connectivity | 239 | - | - | -
12.2.4 | Correlation between charging information of M2M IN and charging in the access network | 239 | 12.2.4.a | Editor's Note: <<FFS>> | FFS - provide text for Technical Solution?
12.2.5 | Definition of Charging Information | 239 | - | - | -
12.2.5.1 | Triggers for Charging Information | 239 | - | - | -
12.2.5.2 | Charging Messages over the Mch Reference point | 240 | 12.2.5.2.a | Editor's Note: Provide references Y and Z. | Add references
12.2.5.3 | Structure of the Accounting Message Formats | 240 | - | - | -
12.2.5.3.1 | Accounting-Request Message | 240 | 12.2.5.3.1.a | Editor's Note: Provide references Y, Z and other references | Add references
|  |  | 12.2.5.3.1.b | Editors Note: The inclusion of additional information is FFS | FFS - provide text for Technical Solution?
12.2.5.3.2 | Accounting-Answer Message | 241 | - | - | -
Annex A | (Informative): Mapping of Requirements with CSFs | 243 | - | - | -
Annex B | (Informative): oneM2M System and 3GPP MTC Release-11 Underlying Network Interworking | 247 | B.a | Editor’s Note: Many terms and abbreviations are missing from clause 3. | Review and Clarify text
B.1 | 3GPP MTC Release-11 Underlying Network Introduction | 247
B.2 | 3GPP Release-11 MTC functionality | 247 | B.2.a | Editor’s Note Add to references Section 2 | Move to References
|  |  | B.2.b | Editor's Note: Further release upgrade of 3GPP MTC functionality will be incorporated into this Annex, depending on the progress. | Coordinate with 3GPP SA and update
|  |  | B.2.c | Editor’s Note: Many acronyms and abbreviations in the diagram need to be added to clause 3. | Review and add Acronyms & Abbreviations
|  |  | B.2.d | Editor's Note: The mapping of identifiers between the oneM2M System and the 3GPP MTC network are FFS. | Coordinate with 3GPP SA and align FFS - Find Technical Solution?
B.3 | ASN-CSE initiated connectivity establishment | 249 | - | - | -
B.3.1 | Use of DHCP and DNS | 249 | B.3.1.a | Editor's Note: How a non-CSE resident device node (i.e. Application Dedicated Node) interworks with this system is FFS | FFS - Clarify or Find Technical Solution?
B.3.2 | Pre-configuration | 249 | B.3.2.a | {B.3.2.a} Editor's Note: There might be other ASN-CSE initiated IN-CSE discovery schemes and this section does not intend to exclude them. Further description of these schemes is FFS. | FFS - Clarify or Find Technical Solution?
B.4 | Serving IN-CSE initiated connectivity establishment | 250 | B.4.a | Editor's Note: How a non-CSE resident ADN interworks with this system is FFS. | FFS - Clarify or Find Technical Solution?
B.5 | Idle mode Management | 250 | B.5.a | Editor's Note: This section should describe oneM2M System dormant device management capability in conjunction with 3GPP related Idle Mode management. | Coordinate with 3GPP SA and align text
B.6 | Procedure | 250 | - | - | -
B.6.1 | General | 250 | B.6.1.a | Editor's Note: The procedure indicated below is one of the realization examples. This does not exclude any other realizations | Find Technical Solution?
B.6.1.1 | ASN/MN-CSE initiated connectivity establishment procedure | 251 | B.6.1.1.a | Editor's Note: It is FFS how oneM2M and 3GPP IDs map to each other for a particular device node to be able to deliver information to a particular serving IN-CSE. | FFS - Clarify or Find Technical Solution?
B.6.1.2 | IN-CSE initiated connectivity establishment procedure over Tsp | 252 | B.6.1.2.a | Editor’s Note: How the M2M-Ext-ID is obtained is FFS. The ID should at least be available somewhere in the ASN/MN-CSE resource or the IN-CSE should keep a map between M2M-Ext-ID and CSE-ID, so that the IN-CSE can access the information when needed. | FFS - Clarify or Find Technical Solution?
|  |  | B.6.1.2.b | Editor’s Note: In case of any request as described in section 8.1 for resource manipulation over Mca reference point, the request indicates by the address of the target resource URI. In order to reach the specified resource a Device Triggering may be required. | Clarify or Find Technical Solution?
|  |  | B.6.1.2.c | Editor's Note: Mechanisms other than DNS query could be used for determining the IP address(es)/port(s) of the MTC-IWF. These are FFS. | FFS - Clarify or Find Technical Solution?
|  |  | B.6.1.2.d | Editor’s Note: What information could be transported in the payload is FFS | FFS - Clarify or Find Technical Solution?
Annex C | (Informative): Interworking between oneM2M System and 3GPP2 Underlying Networks | 255 | - | - | -
C.1 | General Concepts | 255 | - | - | -
C.2 | M2M Communication Models | 255 | - | - | -
C.3 | 3GPP2 Architectural Reference Model for M2M | 257 | - | - | -
C.4 | Communication between oneM2M Service Layer and the 3GPP2 Underlying Network | 258 | - | - | -
C.5 | Information Flows | 258 | - | - | -
C.5.1 | Discovery of M2M Devices | 258 | C.5.1.a | Editor’s Note: <tbd> | FFS - Text Needed
C.5.2 | Tsp Interface Call Flow | 258 | - | - | -
C.5.2 | Point to point device triggering | 260 | - | - | -
C.5.3 | Broadcast device triggering | 260 | - | - | -
Annex D | (Normative) <mgmtObj> Resource Instances Description | 261 | - | - | -
D.1 | oneM2M Management Functions | 261 | D.1.a | Editor’s Note: The notation for addressing the resources in this section still need to be further studied. | Coordinate with WG5 MAS. Clarify text
D.2 | Resource firmware | 261 | - | - | -
D.3 | Resource software | 262 | D.3.a | Editor’s Note: The state machine diagram is to be added according to section 6.2.1.2.3. The names of the attributes also need to be aligned with the wording in the same section. | Add diagram and align text
D.4 | Resource memory | 264 | - | - | -
D.5 | Resource areaNwkInfo | 265 | - | - | -
D.6 | Resource areaNwkDeviceInfo | 266 | - | - | -
D.7 | Resource Type battery | 268 | D.7.a | Editor's Note: Using [battery] notation needs more discussion with WG2 | Discuss & Clarify
|  |  | D.7.b | Editor's Note: The notation used for describing [battery] needs to be discussed and to be added to the Guidelines section 9.1 | Review Guidelines
D.8 | Resource Type deviceInfo | 270 | D.8.a | Editor's Note: The notation used for describing [deviceInfo] needs to be discussed and to be added to the Guidelines section 9.1 | Review Guidelines
D.9 | Resource Type deviceCapability | 272 | D.9.a | Editor's Note: The notation used for describing [deviceapability] needs to be discussed | Discuss & Clarify
D.10 | Resource Type capabilityInstance | 274 | D.10.a | Editor's Note: The notation used for describing [capabilityInstance] needs to be discussed | Discuss & Clarify
D.11 | Resource Type reboot | 276 | D.11.a | Editor's Note: The notation used for describing [deviceapability] needs to be discussed | Discuss & Clarify
D.12 | Resource Type eventLog | 278 | D.12.a | Editor's Note: The notation used for describing [deviceapability] needs to be discussed | Discuss & Clarify
Annex E | (Informative) CSE Minimum Provisioning | 281 | - | - | -
Annex F | (Informative) Interworking / Integration of non-oneM2M solutions and protocols | 282 | - | - | -
F.1 | Introduction | 282 | - | - | -
F.2 | Interworking with non-oneM2M solutions through specialized interworking applications | 282 | F.2.a | Editor’s note: Figure title needed | Add Figure Title
|  |  | F.2.b | Editors’Note: Retargeting mechanisms may also be mentioned, if and when defined. | Clarify or Find Technical Solution?
F.3 | Interworking versus integration of non-oneM2M solutions | 285 | - | - | -
F.4 | Entity-relation representation of an non-IP based M2M Area network | 285 | - | - | -
F.4.1 | Responsibilities of the Interworking Proxy Application Entity (IPE) | 286 | F.4.1.a | Editor’s Note: Mapping principles of the non-oneM2M information model into oneM2M resources is FFS | FFS - Clarify or Find Technical Solution?
Annex G | (Informative) List of M2M Services | 287 | G.a | Editor’s Note: Each role must be mapped to a set of resource types and related primitives | Clarify or Find Technical Solution?
Annex H | (Informative) Object Identifier Based M2M Device Identifier | 288 | - | - | -
H.1. | Overview of Object Identifier | 288 | - | - | -
H.2. | OID Based M2M Device Identifier | 288 | - | - | -
H.2.1 | M2M Device Indication ID – (higher arc) | 289 | - | - | -
H.2.2. | Manufacturer ID – (x) | 289 | - | - | -
H.2.3. | Model ID – (y) | 289 | - | - | -
H.2.4. | Serial Number ID – (z) | 289 | - | - | -
H.2.5. | Expanded ID – (a) | 289 | - | - | -
H.3. | Example of M2M device ID based on OID | 289 | - | - | -
Annex I | (Informative) Functionalities for the Subsequent Architecture TS Release | 291 | - | - | -
I.1 | Service Session Management Text for Removal | 291 | - | - | -
I.1.1 6.2.12 | Service Session Management | 291 | - | - | -
I.1.1.1 6.2.12.1 | General Concepts | 291 | I.1.1.1.a | Editor's Note: Provide information as to when an M2M service session is needed | Discuss and Clarify FFS
I.1.1.2 6.2.12.2 | Detailed Descriptions | 291 | I.1.1.2.a | Editor' Note: Security related descriptions for this CSF need to be updated | Coordinate with WG4 SEC - FFS
|  |  | I.1.1.2.b | Editor' Note: The session involves Mcn reference point or does it involve Mca and Mcc reference points as well. This is FFS. | Discuss and Clarify FFS
|  |  | I.1.1.2.c | Editor’s Note: This Annex shall be removed at the time of approval of TS-0001 Release-1. | Delete Annex I
|  |  | I.1.1.2.d | Editor’s Note: need Title and eventual disposition of Figure | Clarify
Annex Z | (Informative) Bibiliography | 293 | Z.1 | Editor’s Note: Need Decision on Annex Z Bibiliography | Decision and Input
Note on C1: Approximate Page
Note on A32: added section header:
Note on A173: re-number
Note on A527: corrected Annex sub-clause numbering

## Sheet4
1 | Scope | 10
2 | References | 11
2.1 | Normative references | 11
2.2 | Informative references | 11
3 | Definitions, symbols and abbreviations | 13
3.1 | Definitions | 13
3.2 | Symbols | 15
3.3 | Abbreviations | 15
4 | Conventions | 17
5 | Architecture Model | 18
5.1 | General Concepts | 18
5.2 | Architecture Reference Model | 18
5.2.1 | Functional Architecture | 18
5.2.2 | Reference Points | 19
5.2.2.1 | Mca Reference Point | 19
5.2.2.2 | Mcc Reference Point | 20
5.2.2.3 | Mcn Reference Point | 20
5.2.2.4 | Mcc' Reference Point | 20
5.2.2.5 | Mch Reference Point | 20
6 | Configurations supported by oneM2M Architecture | 21
6.2 | Common Services Functions | 23
6.2.1 | Application and Service Layer Management | 23
6.2.1.1 | General Concepts | 23
6.2.1.2 | Detailed Descriptions | 23
6.2.1.2.1 | Configuration Function | 24
6.2.1.2.2 | Diagnostic and Monitoring Function | 24
6.2.1.2.3 | Software Management Function | 25
6.2.2 | Communication Management and Delivery Handling | 25
6.2.2.1 | General Concepts | 25
6.2.2.2 | Detailed Descriptions | 26
6.2.3 | Data Management and Repository | 26
6.2.3.1 | General Concepts | 26
6.2.3.2 | Detailed Descriptions | 27
6.2.4 | Device Management | 27
6.2.4.1 | General Concepts | 27
6.2.4.1.1 | Device Management Architecture | 27
6.2.4.1.2 | Management Server Interaction | 28
6.2.4.1.3 | Management Client Interaction | 30
6.2.4.1.4 | Device Management Resource Lifecycle | 31
6.2.4.2 | Detailed Descriptions | 32
6.2.4.2.1 | Device Configuration Function | 32
6.2.4.2.2 | Device Diagnostics and Monitoring Function | 33
6.2.4.2.3 | Device Firmware Management Function | 33
6.2.4.2.4 | Device Topology Management Function | 33
6.2.5 | Discovery | 33
6.2.5.1 | General Concepts | 33
6.2.5.2 | Detailed Descriptions | 34
6.2.6 | Group Management | 34
6.2.6.1 | General Concepts | 34
6.2.6.2 | Detailed Descriptions | 34
6.2.7 | Location | 35
6.2.7.1 | General Concepts | 35
6.2.7.2 | Detailed Descriptions | 35
6.2.8 | Network Service Exposure, Service Execution and Triggering | 35
6.2.8.1 | General Concepts | 35
6.2.8.2 | Detailed Descriptions | 36
6.2.9 | Registration | 36
6.2.9.1 | General Concepts | 36
6.2.9.2 | Detailed Descriptions | 36
6.2.10 | Security | 38
6.2.10.1 | General Concepts | 38
6.2.10.2 | Detailed Descriptions | 38
6.2.11 | Service Charging and Accounting | 39
6.2.11.1 | General Concepts | 39
6.2.11.2 | Detailed Descriptions | 40
6.2.12 | Subscription and Notification | 40
6.2.12.1 | General Concepts | 40
6.2.12.2 | Detailed Descriptions | 40
6.3 | Functional Entities Comprising Enablers | 41
6.4 | Security Aspects | 42
6.5 | Other Aspects | 43
6.5.1 | Inter M2M SP communication for oneM2M compliant nodes | 43
6.5.1.1 | Public Domain Names and CSEs | 44
6.5.1.2 | M2M Service Subscription | 44
6.5.2 | Inter M2M SP Generic Procedures | 45
6.5.2.1 | Actions in the originating M2M node in Originating Domain | 45
6.5.2.2 | Actions in the Receiving CSE in originating domain | 45
6.5.2.3 | Actions in the IN of the target domain | 45
7 | M2M Identification and Addressing | 46
7.1 | M2M Identifiers | 46
7.1.1 | M2M Service Provider Identifier (M2M-SP-ID) | 46
7.1.2 | Application Instance Identifier (App-Inst-ID) | 46
7.1.3 | Application Identifier (App-ID) | 46
7.1.4 | CSE Identifier (CSE-ID) | 46
7.1.5 | M2M Node Identifier (M2M-Node-ID) | 47
7.1.6 | M2M Service Subscription Identifier (M2M-Sub-ID) | 47
7.1.7 | M2M Request Identifier (M2M-Request-ID) | 47
7.1.8 | M2M External Identifier (M2M-Ext-ID) | 48
7.1.9 | Underlying Network Identifier (UNetwork-ID) | 48
7.1.10 | Trigger Recipient Identifier (Trigger-Recipient-ID) | 48
7.1.11 | M2M Service Identifier (M2M-Serv-ID) | 48
7.2 | M2M Identifiers lifecycle and characteristics | 49
7.3 | Addressing an Application Entity | 50
7.3.1 | Application Entity Addressing | 50
7.3.2 | Application Entity Reachability | 50
7.3.2.1 | CSE Point of Access (CSE-PoA) | 50
7.3.2.2 | Locating Application Entities | 50
7.3.2.3 | Usage of CSE-PoA by the M2M System | 50
7.3.2.3.1 | CSE-PoA related to CSEs associated with a Fixed Network | 51
7.3.2.3.2 | CSE-PoA related to CSEs associated with Mobile Networks | 51
7.3.2.3.3 | CSE-PoA to CSEs associated with multiple Underlying Networks | 51
7.3.3 | Notification Re-targeting | 51
7.3.3.1 | Application Entity Point of Access (AE-PoA) | 51
8 | Description and Flows of Reference Points | 53
8.1 | General Communication Flow Scheme on Mca and Mcc Reference Points | 53
8.1.1 | Description | 53
8.1.2 | Request | 53
8.1.2.1 | Summary of Request Message Parameters | 58
8.1.3 | Successful Operation | 60
8.1.4 | Unsuccessful Operation | 61
8.1.5 | Summary of Response Message Parameters | 61
8.2 | Procedures for Accessing Resources | 62
8.2.1 | Generating Responses | 62
8.2.2 | Accessing Resources in CSEs - Blocking Requests | 63
8.2.3 | Accessing Resources in CSEs - Non-Blocking Requests | 68
8.2.3.1 | Response with Reference to Result of Requested Operation | 68
8.2.3.2 | Synchronous Case | 68
8.2.3.3 | Asynchronous Case | 71
8.3 | Description and Flows on Mcn Reference Point | 71
8.3.1 | General Description | 71
8.3.2 | Service Requests | 72
8.3.2.1 | Connection Request | 72
8.3.2.2 | Location Request | 72
8.3.2.3 | Device Management | 72
8.3.2.3 | Device Triggering | 72
8.4 | Device Triggering | 72
8.4.1 | Definition and scope | 72
8.4.2 | General Procedure for Device Triggering | 73
8.4.2.1 | Triggering procedure for targeting ASN/MN-CSE | 73
9 | Resource Management | 76
9.1 | General Principles | 76
9.1.1 | Resource Announcement | 77
9.2 | Resource Types | 77
9.2.1 | Types of Virtual Resources | 79
9.3 | Resource Addressing | 79
9.3.1 | Generic principles | 79
9.3.1.1 | Support for Multiple CSEs within a single node | 80
9.3.2 | Resource addressing via a FQDN URI | 80
9.4 | Resource Structure | 81
9.4.1 | Links between resources | 81
9.4.2 | Link Types | 81
9.5 | Resource Specification Guidelines | 82
9.5.1 | Resource Template | 83
9.5.1.1 | Resource Type resourceType | 83
9.5.2 | Examples for Resource Specification | 85
9.5.2.1 | Example of a Resource with attributes only | 85
9.5.2.1.1 | Resource Type accessRight | 85
9.5.2.2 | Example of a Resource with attributes and child resources | 85
9.5.2.2.1 | Resource Type container | 85
9.5.3 | Handling of Unsupported and non compliant Resources | 86
9.6 | Specified Resource Types | 87
9.6.1 | Common Attributes | 89
9.6.2 | Resource Type accessControlPolicy | 90
9.6.2.1 | originatorPrivileges | 93
9.6.2.2 | contexts | 93
9.6.2.3 | operationFlags | 93
9.6.3 | Resource Type CSEBase | 94
9.6.4 | Resource Type remoteCSE | 95
9.6.5 | Resource Type application | 98
9.6.6 | Resource Type container | 101
9.6.7 | Resource Type instance | 105
9.6.8 | Resource Type subscription | 106
9.6.9 | Resource Type schedule | 110
9.6.10 | Resource Type locationPolicy | 111
9.6.11 | Resource Type delivery | 113
9.6.12 | Resource Type request | 115
9.6.13 | Resource Type group | 117
9.6.14 | Resource Type Members | 119
9.6.15 | Resource Type mgmtObj | 120
9.6.16 | Resource Type parameters | 122
9.6.17 | Resource Type mgmtCmd | 123
9.6.18 | Resource Type execInstance | 124
9.6.19 | Resource Type node | 126
9.6.20 | Resource Type m2mServiceSubscription | 128
9.6.21 | Resource Type nodeInfo | 129
9.6.22 | Resource Type pollingChannel | 130
9.6.23 | Resource Type cmdhPolicy | 131
9.6.24 | Resource Type cmdhDefaults | 133
9.6.25 | Resource Type cmdhDefEcValue | 134
9.6.26 | Resource Type cmdhEcDefParamValues | 137
9.6.27 | Resource Type cmdhLimits | 139
9.6.28 | Resource Type cmdhNetworkAccessRules | 141
9.6.29 | Resource Type cmdhNwAccessRule | 143
9.6.30 | Resource Type cmdhBuffer | 146
9.6.31 | Resource Type statsConfig | 148
9.6.32 | Resource Type eventConfig | 149
9.6.33 | Resource Type statsCollect | 150
9.6.34 | Resource Announcement | 151
10 | Information Flows | 152
10.1 | Basic Procedures | 152
10.1.1 | CREATE (C) | 152
10.1.1.1 | Non-registration related CREATE procedure | 152
10.1.1.2 | Registration related CREATE procedure | 154
10.1.1.2.1 | CSE Registration procedure | 154
10.1.1.2.2 | Application Registration procedure | 156
10.1.2 | RETRIEVE (R) | 156
10.1.3 | UPDATE (U) | 158
10.1.4 | DELETE (D) | 159
10.1.5 | NOTIFY (N) | 159
10.2 | Resource Type-Specific Procedures | 160
10.2.1 | <application> Resource | 160
10.2.1.1 | Create <application>, aka Application Registration | 160
10.2.1.2 | Retrieve <application> | 161
10.2.1.3 | Update <application> | 162
10.2.1.4 | Delete <application>, aka De-Register | 162
10.2.2 | <RemoteCSE> Resource | 163
10.2.2.1 | Create <RemoteCSE>, aka CSE Registration | 163
10.2.2.2 | Retrieve <remoteCSE> | 164
10.2.2.3 | Update <remoteCSE>, aka Re-registration | 164
10.2.2.4 | Delete <remoteCSE>, aka CSE De-Registration | 164
10.2.3 | <container> Resource | 165
10.2.3.1 | Create <container> | 165
10.2.3.2 | Retrieve <container> | 166
10.2.3.3 | Update <container> | 167
10.2.3.4 | Delete <container> | 167
10.2.4 | Access to Remotely Hosted Resources via CMDH CSF | 168
10.2.4.1 | Introduction to use of <delivery> related flows | 168
10.2.4.2 | Create <delivery> | 171
10.2.4.3 | Retrieve <delivery> | 173
10.2.4.4 | Update <delivery> | 173
10.2.4.5 | Delete <delivery> | 174
10.2.5 | Resource Discovery Procedure | 175
10.2.5.1 | Introduction | 175
10.2.5.2 | Discovery procedure via Retrieve Operation | 175
10.2.6 | Group Management Procedures | 176
10.2.6.1 | Introduction | 176
10.2.6.2 | Create <group> | 176
10.2.6.3 | Retrieve <group> | 177
10.2.6.4 | Update <group> | 177
10.2.6.5 | Delete <group> | 178
10.2.6.6 | Create <Members> | 179
10.2.6.7 | Retrieve <Members> | 181
10.2.6.8 | Update <Members> | 182
10.2.6.9 | Delete <Members> | 183
10.2.6.10 | Subscribe and Un-Subscribe <Members> of a group | 184
10.2.6.11 | Aggregate the notifications by group | 185
10.2.7 | mgmtObj Management Procedures | 186
10.2.7.1 | Introduction | 186
10.2.7.2 | Create <mgmtObj> | 186
10.2.7.3 | Retrieve <mgmtObj> | 187
10.2.7.4 | Update <mgmtObj> | 188
10.2.7.5 | Delete <mgmtObj> | 189
10.2.7.6 | Execute <mgmtObj> | 190
10.2.8 | External Management Operations through <mgmtCmd> | 191
10.2.8.1 | Introduction | 191
10.2.8.2 | Create <mgmtCmd> | 191
10.2.8.3 | Retrieve <mgmtCmd> | 192
10.2.8.4 | Update <mgmtCmd> | 193
10.2.8.5 | Delete <mgmtCmd> | 194
10.2.8.6 | Execute <mgmtCmd> | 195
10.2.8.7 | Cancel <execInstance> | 196
10.2.8.8 | Retrieve <execInstance> | 197
10.2.8.9 | Delete <execInstance> | 198
10.2.9 | Supported Attribute Discovery Procedure | 199
10.2.9.1 | Introduction | 199
10.2.9.2 | Supported Attributes Discovery procedure via Retrieve Operation | 199
10.2.10 | Location Management Procedures | 200
10.2.10.1 | Procedure related to <locationPolicy> resource | 200
10.2.10.1.1 | Create <locationPolicy> | 200
10.2.10.1.2 | Retrieve <locationPolicy> | 201
10.2.10.1.3 | Update <locationPolicy> | 202
10.2.10.1.4 | Delete <locationPolicy> | 202
10.2.10.2 | Procedure when the <container> and <instance> resource contain location information | 203
10.2.10.2.1 | Procedure for <container> resource that stores the location information | 203
10.2.10.2.2 | Procedure for <instance> resource that stores the location information | 203
10.2.11 | <subscription> Resource Procedures | 203
10.2.11.1 | Introduction | 203
10.2.11.2 | Create <subscription> | 203
10.2.11.3 | Retrieve <subscription> | 204
10.2.11.4 | Update <subscription> | 205
10.2.11.5 | Delete <subscription> | 205
10.2.12 | Notification Procedures for Resource Subscription | 206
10.2.13 | Polling Channel Management Procedures | 208
10.2.13.1 | Introduction | 208
10.2.13.2 | Create <pollingChannel> | 209
10.2.13.3 | Retrieve <pollingChannel> | 209
10.2.13.4 | Update <pollingChannel> | 210
10.2.13.5 | Delete <pollingChannel> | 210
10.2.13.6 | Re-targeting Requests to Polling Channel | 210
10.2.13.7 | Long Polling on Polling Channel | 211
10.2.14 | <node> Resource Procedure | 211
10.2.14.1 | Create <node> | 211
10.2.14.2 | Retrieve <node> | 212
10.2.14.3 | Update <node> | 213
10.2.14.4 | Delete <node> | 213
10.2.15 | Service Charging and Accounting Procedures | 214
10.2.15.1 | Introduction | 214
10.2.15.1.1 | Service Event-based Statistics Collection for Applications | 214
10.2.15.2 | CREATE <statsConfig> | 215
10.2.15.3 | RETRIEVE <statsConfig> | 216
10.2.15.4 | UPDATE <statsConfig> | 217
10.2.15.5 | DELETE <statsConfig> | 217
10.2.15.6 | CREATE <statsCollect> | 218
10.2.15.7 | RETRIEVE <statsCollect> | 219
10.2.15.8 | UPDATE <statsCollect> | 219
10.2.15.9 | DELETE <statsCollect> | 220
10.2.15.10 | Service Statistics Collection Record | 220
10.2.16 | <m2mServiceSubscription> Resource | 221
10.2.16.1 | Create <m2mServiceSubscription> | 221
10.2.16.2 | Retrieve <m2mServiceSubscription> | 222
10.2.16.3 | Update <m2mServiceSubscription> | 222
10.2.16.4 | Delete <m2mServiceSubscription> | 223
10.2.17 | <nodeInfo> Resource | 223
10.2.17.1 | Create <nodeInfo> | 223
10.2.17.2 | Retrieve <nodeInfo> | 224
10.2.17.3 | Update <nodeInfo> | 224
10.2.17.4 | Delete <nodeInfo> | 225
10.2.18 | Resource Announcement Procedure | 225
10.2.18.1 | Procedure for AE and CSE to initiate the creation or deletion of the Announced Resource | 225
10.2.18.2 | Procedure for original resource hosting CSE to Announce Resource | 226
10.2.18.3 | Procedure for original resource hosting CSE to delete the Announced Resource | 227
10.2.18.4 | Procedure for AE and CSE to initiate the creation or deletion of the Announced Attribute | 228
10.2.18.5 | Procedure for original resource hosting CSE to Announce Attribute | 229
10.2.18.6 | Procedure for original resource hosting CSE to delete the Announced Attribute | 230
11 | Trust Enabling Architecture | 231
11.1 | Enroling M2M Nodes and M2M applications for oneM2M Services | 231
11.2 | M2M Initial Provisioning Procedures | 231
11.2.1 | M2M Node Enrolment and Service Provisioning | 231
11.2.1 | M2M Application Enrolment | 232
11.3 | M2M Operational Security Procedures | 232
11.3.1 | Identification of CSE and AE | 233
11.3.2 | Authentication of CSE and AE | 233
11.3.3 | M2M Security Association Establishment | 233
11.3.4 | M2M Authorization Procedure | 234
12 | Information Recording | 235
12.1 | M2M Infrastructure Node (IN) Information Recording | 235
12.1.1 | Information Recording Triggers | 235
12.1.2 | M2M Recorded Information Elements | 235
12.1.2.1 | Unit of Recording | 235
12.1.2.2 | Information Elements within an M2M Event Record | 235
12.1.3 | Identities Associations in support of Recorded Information | 238
12.2 | Offline Charging | 238
12.2.1 | Architecture | 238
12.2.2 | Filtering of Recorded Information for Offline Charging | 239
12.2.3 | Examples of Charging Scenarios | 239
12.2.3.1 | Example CharginScenario 1 – Data Storage Resource Consumption | 239
12.2.3.2 | Example Charging Scenario 2 – Data transfer | 239
12.2.3.3 | Example Charging Scenario 3 – Connectivity | 239
12.2.4 | Correlation between charging information of M2M IN and charging in the access network | 239
12.2.5 | Definition of Charging Information | 239
12.2.5.1 | Triggers for Charging Information | 239
12.2.5.2 | Charging Messages over the Mch Reference point | 240
12.2.5.3 | Structure of the Accounting Message Formats | 240
12.2.5.3.1 | Accounting-Request Message | 240
12.2.5.3.2 | Accounting-Answer Message | 241
Annex A | (Informative): Mapping of Requirements with CSFs | 243
Annex B | (Informative): oneM2M System and 3GPP MTC Release-11 Underlying Network Interworking | 247
B.1 | 3GPP MTC Release-11 Underlying Network Introduction | 247
B.2 | 3GPP Release-11 MTC functionality | 247
B.3 | ASN-CSE initiated connectivity establishment | 249
B.3.1 | Use of DHCP and DNS | 249
B.3.2 | Pre-configuration | 249
B.4 | Serving IN-CSE initiated connectivity establishment | 250
B.5 | Idle mode Management | 250
B.6 | Procedure | 250
B.6.1 | General | 250
B.6.1.1 | ASN/MN-CSE initiated connectivity establishment procedure | 251
B.6.1.2 | IN-CSE initiated connectivity establishment procedure over Tsp | 252
Annex C | (Informative): Interworking between oneM2M System and 3GPP2 Underlying Networks | 255
C.1 | General Concepts | 255
C.2 | M2M Communication Models | 255
C.3 | 3GPP2 Architectural Reference Model for M2M | 257
C.4 | Communication between oneM2M Service Layer and the 3GPP2 Underlying Network | 258
C.5 | Information Flows | 258
C.5.1 | Discovery of M2M Devices | 258
C.5.2 | Tsp Interface Call Flow | 258
C.5.2 | Point to point device triggering | 260
C.5.3 | Broadcast device triggering | 260
Annex D | (Normative) <mgmtObj> Resource Instances Description | 261
D.1 | oneM2M Management Functions | 261
D.2 | Resource firmware | 261
D.3 | Resource software | 262
D.4 | Resource memory | 264
D.5 | Resource areaNwkInfo | 265
D.6 | Resource areaNwkDeviceInfo | 266
D.7 | Resource Type battery | 268
D.8 | Resource Type deviceInfo | 270
D.9 | Resource Type deviceCapability | 272
D.10 | Resource Type capabilityInstance | 274
D.11 | Resource Type reboot | 276
D.12 | Resource Type eventLog | 278
Annex E | (Informative) CSE Minimum Provisioning | 281
Annex F | (Informative) Interworking / Integration of non-oneM2M solutions and protocols | 282
F.1 | Introduction | 282
F.2 | Interworking with non-oneM2M solutions through specialized interworking applications | 282
F.3 | Interworking versus integration of non-oneM2M solutions | 285
F.4 | Entity-relation representation of an non-IP based M2M Area network | 285
F.4.1 | Responsibilities of the Interworking Proxy Application Entity (IPE) | 286
Annex G | (Informative) List of M2M Services | 287
Annex H | (Informative) Object Identifier Based M2M Device Identifier | 288
H.1. | Overview of Object Identifier | 288
H.2. | OID Based M2M Device Identifier | 288
H.2.1 | M2M Device Indication ID – (higher arc) | 289
H.2.2. | Manufacturer ID – (x) | 289
H.2.3. | Model ID – (y) | 289
H.2.4. | Serial Number ID – (z) | 289
H.2.5. | Expanded ID – (a) | 289
H.3. | Example of M2M device ID based on OID | 289
Annex I | (Informative) Functionalities for the Subsequent Architecture TS Release | 291
I.1 | Service Session Management Text for Removal | 291
6.2.12 | Service Session Management | 291
6.2.12.1 | General Concepts | 291
6.2.12.2 | Detailed Descriptions | 291
Annex Z | (Informative) Bibiliography | 293