## Slide 1: Participation Ad-Hoc Legal Ad-Hoc Joint status

## Slide 2: General
General good progresses made on the document’s structure
The two ad-hocs are meeting jointly
One more joint ad-hoc (21 March 2011,13:00-15 GMT) is planned before the Tokyo physical meeting
A document package update will be released for plenary consideration after that meeting

## Slide 3: Main documents under development and status
Partnership Agreement:
  The draft is stable in its main content but still incomplete in some part, mainly description of plenary and steering group, some voting aspects and IPR refinements
  Additionally there are a set of issue that has been identified but not yet agreed, including
      How to bind associations (Partner type 2 and members) to a compatible IPR policy
      One company one vote (TIA) vs One vote per company per SDO (ARIB, ATIS, ETSI and TTC) (CCSA and TTA did not express a preference yet)
      Exact duty of partner type one (publishing, listing members)
  An addendum clarifying the IPR obligations has been proposed ATIS and is under off-line review (potential annex to the Partnership agreement

## Slide 4: Main documents under development and status
Secretariat Functions:
  The draft is stable and only one contentious issue is present, dealing with the Hosting support, where TIA and ETSI have a different view. The ppt presentation has been transposed in a word document
Cost evaluation:
  The excel model is stable and it has been refined further according to the discussions held during the previous calls
Working procedures:
  A draft version based on 3GPP and 3GPP2 WP is available and under off-line review, but it has not been discussed by the ad-hocs yet