## Slide 1: Vertical Outreach Program
Create story (presentation)
  Identify the needs/challenges (beyond telecom-centric viewpoint)
  What we are trying to do
  Benefits to verticals
  Why now
  Expectations from verticals
  How to solve the problem
    scope, timeline
    Need to develop input on: structure, funding, participation, IPR, etc. (still need consensus)
M2MCons028

## Slide 2: Milestones
Need to develop input/principles on: structure, funding, participation, IPR, etc. (still need consensus)
  15 September 2011 – input on above topics to AHG at a higher/marketing level
Outreach to verticals
  30 September 2011 – AHG deliver draft material
  15 October 2011 – material ready/finalized
  30 October 2011 – provide material to verticals
  15 December 2011 – provide initial feedback to SDOs
Launch consolidation group
  No later than 1Q2012

## Slide 3: Input to AHG
Teleconferences targeted at each specific topic
  Call for contributions
    Structure [draft doc #30]
    Participation
    Funding
    IPR
Completion of input by 15 September
  Progress via telecon and virtual
  One call per week between 18 Aug and 15 Sept
    24 August (Wednesday): 1400 GMT
    31 August (Wed): Time TBD
    7 September (Wed): Time TBD
    14 September (Wed): Time TBD

## Slide 4: 3rd “M2M Meeting”
15-16 December 2011
  Berlin (hosted by ETSI)
  Draft agenda requested
    This will be a topic for the first two conference calls (per previous slide)
      24 August
      31 August