## Doucment Allocation
Part B: List of all contributions to the WG meeting | [11 empty] | DEADLINE: | 2014-04-01 09:00
WG5 OPENing (Mon, 14:00 – 15:15, Breakout)
Doc-Number | Title | Source | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Upload Time | Type (Draft, Change Request, other) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
<opening>
MAS-2014-0362R01 | Agenda MAS 10.0 | Chair | Noted |  | Agenda
MAS-2014-0362R02 | Agenda MAS 10.0 | Chair | Agreed |  | Agenda
MAS-2014-0364R01 | MAS#10 contribution list | Chair | Noted |  | Other
MAS-2014-0364R04 | MAS#10 contribution list | Chair | Agreed |  | Other
MAS-2014-0369 | HGI Device Templates | HGI | Noted | 2014-04-07 | INC | [5 empty] | PT2 input for information and discussions on smart home related data models - proposed to be considered at the opening session so as to be able to have this PT2 work in mind during the week Action Item agreed (Action Point for NEC, & Orange) to ensure oneM2M requirements are correctly shared with HGI / BBF Smart Home team on this Device Template activity.
ARC-2014-1277 | mgmtCmd CR | InterDigital Communications | Noted | 2014-03-30 21:39 | INC | TS-0001 |  |  |  | WI-0002 | 1277R01 endorsed by WG5; will be presented to WG2. Further discussions identified for possibly future release to maybe consider a generalized scheduling resource (together with CMDH) ?
ARC-2014-1277R01 | mgmtCmd CR | InterDigital Communications | Agreed | 2014-03-30 21:39 | INC | TS-0001 |  |  |  | WI-0002
MAS-2014-0352R01 | DataType Identification Mapping for OMA DM | LG Electronics | Noted | 2014-03-31 01:50 | CR | TS-0005 |  |  |  | WI-0010 | Revision expected
MAS-2014-0351R01 | Resource Mapping for OMA DM | LG Electronics |  | 2014-03-31 01:53 | CR | TS-0005 |  |  |  | WI-0010 | NOT TREATED
WG3-WG5 joint (Mon,17:15 – 18:30, Breakout)
Doc-Number | Title | Source | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Upload Time | Type (Draft, Change Request, other) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
PRO-2014-0155 | execInstance | InterDigital Communications | Noted | 2014-03-30 21:40 | INC | TS-0004 |  |  |  | WI-0009 | Revision Expected. ACTION: Possible to treat at MAS session on new revised document and agreed to joint conference call for further discussion if it needed.
PRO-2014-0154 | mgmtCmd | InterDigital Communications | Noted | 2014-03-30 21:40 | INC | TS-0004 |  |  |  | WI-0009 | Revision Expected. ACTION: Possible to treat at MAS session on new revised document and agreed to joint conference call for further discussion if it needed.
WG5 (Tue, 14:00 – 15:15, 15:45 – 17:00, Breakout)
Doc-Number | Title | Source | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Upload Time | Type (Draft, Change Request, other) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
ARC-2014-1233R03 | Correction of node resource | LG Electronics, Huawei Technologies | Noted | 2014-03-31 04:07 | CR | TS-0001 |  |  |  | WI-0002
ARC-2014-1233R04 | Correction of node resource | LG Electronics, Huawei Technologies | Agreed | 2014-03-31 04:07 | CR | TS-0001 |  |  |  | WI-0002
ARC-2014-1268 | managements_to_nodes | Huawei Technologies Co.,Ltd. | Noted | 2014-03-29 08:32 | INC | TS-0001 |  |  |  | WI-0002 | 1.<node> resource can be located in the field nodes with CSE (i.e. MN, ASN). 2. Creator of <node> resource needs offline discussion. 3. Some refinement may be needed for the 1st bullet of <node> creation. Revision expected.
ARC-2014-1266 | remove-parameters-resource | Huawei Technologies Co.,Ltd. | Agreed | 2014-03-29 08:30 | INC | TS-0001 |  |  |  | WI-0002
ARC-2014-1265 | modify-deviceCapability | Huawei Technologies Co.,Ltd. | Noted | 2014-03-29 08:28 | INC | TS-0001 |  |  |  | WI-0002
ARC-2014-1265R01 | modify-deviceCapability | Huawei Technologies Co.,Ltd. | Agreed | 2014-03-29 08:28 | INC | TS-0001 |  |  |  | WI-0002
MAS-2014-0358 | CMDH_Policy_Management | Qualcomm Inc. (TIA) | Noted | 2014-03-31 01:18 | INC | TS-0001 |  |  |  | WI-0002 | Agree on option-3
ARC-2014-1278 | Conversion_of_CMDH_Policies_to_mgmtObj | Qualcomm Inc. (TIA) | Noted | 2014-03-31 19:31 | CR | TS-0001 |  |  |  | WI-0002 | Nicolas takes an Action Item to put in the ARC issue list for further refinement of the terminology of 'instance' of <mgmtObj> resource (as actually the sub-class of <mgmtOjb> resource,e.g. [CMDHPolicies]). Nevertheless, 'instance'is acceptable in the contribution for the time being. "Management Annotation" may be used for introducing <schedule> resource into the management plane. Changes may be added as a sub-section of 9.1.1, 9.6.1. To be seen in revision.
ARC-2014-1264 | modification_to_mgmtObj_procedure | Huawei Technologies Co.,Ltd. | Noted | 2014-03-29 08:27 | INC | TS-0001 |  |  |  | WI-0002 | Remove the proposed change to the reference seciton, which is handled by 1192R03
ARC-2014-1264R01 | modification_to_mgmtObj_procedure | Huawei Technologies Co.,Ltd. | Agreed | 2014-03-29 08:27 | INC | TS-0001 |  |  |  | WI-0002
ARC-2014-1192R02 | Cleanup of editors notes and highlights in ASM and DMG CSFs | Tim Carey, ALU, timothy.carey@alcatel-lucent.com | Noted | 2014-03-28 14:11 | CR | TS-0001 |  |  |  | WI-0002 | modify the refence to the full release package of OMA DM 1.3 and OMA LWM2M.
ARC-2014-1192R03 | Cleanup of editors notes and highlights in ASM and DMG CSFs | Tim Carey, ALU, timothy.carey@alcatel-lucent.com | Agreed | 2014-03-28 14:11 | CR | TS-0001 |  |  |  | WI-0002
WG5 (Wed, 10:45 – 12:00, Breakout)
Doc-Number | Title | Source | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Upload Time | Type (Draft, Change Request, other) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
<Revisions & Leftovers from Day 2>
ARC-2014-1268R01 | managements_to_nodes | Huawei Technologies Co.,Ltd. |  | 2014-03-29 08:32 | CR | TS-0001 |  |  |  | WI-0002
ARC-2014-1280 | Creation of node resource | LG Electronics | Draft | 2014-03-31 03:56 | CR | TS-0001 |  |  |  | WI-0002
ARC-2014-1286 | define mgmt objects for SCA resource | InterDigital |  | 2014-03-31 04:31 | CR | TS-0001 |  |  |  | WI-0002
ARC-2014-1269 | state-machine-for-sw-mgmt | Huawei Technologies Co.,Ltd. |  | 2014-03-29 08:32 | CR | TS-0001 |  |  |  | WI-0002
MAS-2014-0355 | resource-mapping-for-management | Huawei Technologies Co.,Ltd. |  | 2014-03-29 08:20 | CR | TS-0005 |  |  |  | WI-0010
MAS-2014-0352R02 | DataType Identification Mapping for OMA DM | LG Electronics |  | 2014-03-31 01:50 | CR | TS-0005 |  |  |  | WI-0010
MAS-2014-0351R01 | Resource Mapping for OMA DM | LG Electronics |  | 2014-03-31 01:53 | CR | TS-0005 |  |  |  | WI-0010
MAS-2014-0367R01 | Resource Mapping for OMA LWM2M | Gemalto N.V |  | 2014-04-07 16:52 | CR | TS-0005 |  |  |  | WI-0010
MAS-2014-0366R02 | DataType_Identification_Mapping_for_OMA_LWM2M | Gemalto N.V |  | 2014-04-07 16:51 | CR | TS-0005 |  |  |  | WI-0010
MAS-2014-0365 | App-ID Additional Clarification Text | Ericsson |  | 2014-04-01 21:42 | CR | TS-0001 |  |  |  | WI-0002
MAS-2014-0368 | Editorial updates to correct grammar and proper wording | Ericsson |  | 2014-04-03 | CR | TS-0001 |  |  |  | WI-0002
WG5 (Wed,14:00 – 15:15, Breakout)
Doc-Number | Title | Source | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Upload Time | Type (Draft, Change Request, other) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
MAS-2014-0354R01 | Device+DeviceTemplate-Modelling | NEC |  | 2014-03-28 16:43 | INC
MAS-2014-0349 | Architectural Considerations for Semantic Support | NEC |  | 2014-03-24 09:06 | INC | TR-0007 |  |  |  | WI-0005
MAS-2014-0353 | Architectural Considerations for Semantic Support | NEC |  | 2014-03-27 16:29 | INC | TR-0007 |  |  |  | WI-0005
MAS-2014-0356 | proper_usage_terminologies_ABS_TR | Modacom Co., Ltd (TTA) |  | 2014-03-30 21:20 | INC | TR-0007 |  |  |  | WI-0005
MAS-2014-0357 | Discussion_abstraction_semantics | Modacom Co., Ltd (TTA) |  | 2014-03-30 21:30 | INC | TR-0007 |  |  |  | WI-0005
MAS-2014-0359 | Key Issues on Semantics and Ontologies | KETI |  | 2014-03-31 07:22 | INC | TR-0007 |  |  |  | WI-0005
MAS-2014-0360 | semantic home automation | Haier |  | 2014-03-31 08:41 | INC | TR-0007 |  |  |  | WI-0005
MAS-2014-0361R02 | Semantic web best practices | Eurecom, Amelie Gyrard, gyrard@eurecom.fr, Christian Bonnet, bonnet@eurecom.fr | Draft | 2014-04-01 16:01 | INC | TR-0007 |  |  |  | WI-0005
MAS-2014-0361 | Semantic web best practices | Eurecom, Amelie Gyrard, gyrard@eurecom.fr |  | 2014-03-31 10:35 | INC | TR-0007 |  |  |  | WI-0005
WG5 (Thu,8:00 - 8:45, 09:00 – 10:15, 10:45 – 12:00, Breakout)
Doc-Number | Title | Source | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Upload Time | Type (Draft, Change Request, other) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
<Revisions & Leftovers>
PRO-2014-0155R01 | execInstance | InterDigital Communications |  | 2014-03-30 21:40 | INC | TS-0004 |  |  |  | WI-0009
PRO-2014-0154R01 | mgmtCmd | InterDigital Communications |  | 2014-03-30 21:40 | INC | TS-0004 |  |  |  | WI-0009
WG5 CLOSing (Fri, 08:00 – 08:45, 09:00 – 10:15, Breakout)
Doc-Number | Title | Source | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Upload Time | Type (Draft, Change Request, other) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
<wrap up & draft report>

## Summary (hidden)
Report at oneM2M TP#10 & Interim report from WG5
Part A: Executive Summary for Plenary
<Text>
<Text>
<Text>
A1. Documents NOT AGREED in WG (to be presented to Plenary for discussion).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | LATE FLAG | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A2. Documents NOT AGREED in WG (noted / postponed / not treated etc).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | LATE FLAG | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A3. Documents AGREED in WG
Doc-Number | Title | Source | Type (Draft, Change Request, other) | LATE FLAG | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes

## ARC (hidden)
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | UPLOADED | DOC TYPE | VERS
ARC-2014-1300R01 | Subscription CSF Updates | LG Electronics | Draft | 2014-04-01 02:39 | CR
ARC-2014-1300 | Subscription CSF Updates | LG Electronics | Draft | 2014-04-01 01:14 | CR
ARC-2014-1299 | CR on Registration CSF | Huawei Technologies, Co. Ltd. | Draft | 2014-03-31 23:21 | CR
ARC-2014-1298R01 | CR for Discovery CSF | Huawei Technologies, Co. Ltd. | Draft | 2014-04-01 01:00 | CR
ARC-2014-1298 | CR for Discovery CSF | Huawei Technologies, Co. Ltd. | Draft | 2014-03-31 23:17 | CR
ARC-2014-1297R01 | Addition of missing abbreviations | Philip Jacobs, Cisco Systems, phjacobs@cisco.com | Draft | 2014-03-31 21:29 | CR
ARC-2014-1297 | Addition of missing abbreviations | Philip Jacobs, Cisco Systems, phjacobs@cisco.com | Draft |  | INC
ARC-2014-1296 | Guidelines for Resource Addressing | Ericsson | Draft | 2014-03-31 20:29 | CR
ARC-2014-1295 | DNS-Provisioning for Inter M2M SP Communication | Ericsson | Draft | 2014-03-31 20:26 | CR
ARC-2014-1294 | Restructuring for Section 6.5 | Ericsson | Draft | 2014-03-31 20:24 | CR
ARC-2014-1293 | Routing Clarifications | Ericsson | Draft | 2014-03-31 20:23 | CR
ARC-2014-1292 | Request Parameter Review | Ericsson | Draft | 2014-03-31 20:21 | CR
ARC-2014-1291 | Application Instance ID Clarification | Ericsson | Draft | 2014-03-31 20:19 | CR
ARC-2014-1290 | Group-Management-Refinement | LG Electronics | Draft | 2014-03-31 12:05 | CR
ARC-2014-1289 | Flat URI terminology update | KETI | Draft | 2014-03-31 08:09 | CR
ARC-2014-1288 | Flat URI terminology update | KETI | Draft |  | CR
ARC-2014-1287 | Device Triggering within field domain | Haier | Draft | 2014-03-31 04:54 | CR
ARC-2014-1286 | define mgmt objects for SCA resource | InterDigital | Draft | 2014-03-31 04:31 | INC
ARC-2014-1285 | Information flows for instance resource | Huawei Technologies | Draft | 2014-03-31 04:29 | CR
ARC-2014-1284 | update CSEbase with SCA resources | InterDigital | Draft | 2014-03-31 04:26 | INC
ARC-2014-1283 | SCA Call Flow Clean Up | InterDigital | Draft | 2014-03-31 04:21 | INC
ARC-2014-1282 | SCA resource description clean up | InterDigital | Draft | 2014-03-31 04:17 | INC
ARC-2014-1281 | SCA CSF description clean up | InterDigital | Draft | 2014-03-31 04:14 | INC
ARC-2014-1280 | Creation of node resource | LG Electronics | Draft | 2014-03-31 03:56 | CR
ARC-2014-1279 | Correction of LocationPolicy Attribute | LG Electronics | Draft | 2014-03-31 03:43 | CR
ARC-2014-1278 | Conversion_of_CMDH_Policies_to_mgmtObj | Qualcomm Inc. (TIA) | Draft | 2014-03-31 19:31 | CR
ARC-2014-1277 | mgmtCmd CR | InterDigital Communications | Draft | 2014-03-30 21:39 | INC
ARC-2014-1276 | Resource Announcement Cleanup Part 4 | Rajesh Bhalla, ZTE | Draft | 2014-03-30 21:37 | CR
ARC-2014-1275 | Resource Announcement Cleanup Part 3 | Rajesh Bhalla, ZTE | Draft | 2014-03-30 21:38 | CR
ARC-2014-1274 | Resource Announcement Cleanup Part 2 | Rajesh Bhalla, ZTE | Draft | 2014-03-30 21:32 | CR
ARC-2014-1273 | Identifiers cleanup | NEC | Draft | 2014-03-30 17:12 | CR
ARC-2014-1272 | Resource Announcement Cleanup Part 1 | Rajesh Bhalla, ZTE | Draft | 2014-03-30 21:31 | CR
ARC-2014-1271R01 | Notification Policy in Request | LG Electronics | Draft | 2014-04-01 01:16 | CR
ARC-2014-1271 | Notification Policy in Request | LG Electronics | Draft | 2014-03-29 23:43 | CR
ARC-2014-1270 | notificationCongestionPolicy | Philip Jacobs, Cisco Systems Inc., phjacobs@cisco.com | Draft | 2014-03-30 13:55 | CR
ARC-2014-1269 | state-machine-for-sw-mgmt | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:32 | INC
ARC-2014-1268 | managements_to_nodes | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:32 | INC
ARC-2014-1267 | solve-editor-note-for-subscription | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:31 | INC
ARC-2014-1266 | remove-parameters-resource | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:30 | INC
ARC-2014-1265 | modify-deviceCapability | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:28 | INC
ARC-2014-1264 | modification_to_mgmtObj_procedure | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:27 | INC
ARC-2014-1263 | cn-optional | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:23 | INC
ARC-2014-1262 | VersionTag cleanup | NEC | Draft | 2014-03-28 21:43 | CR
ARC-2014-1261 | TS-0007-Mca_Sub-Pub-Notify | Tim Carey, ALU, timothy.carey@alcatel-lucent.com | Draft | 2014-03-28 14:22 | INC
ARC-2014-1260 | TS-0007-Mca_Request_Services | Tim Carey, ALU, timothy.carey@alcatel-lucent.com | Draft | 2014-03-28 14:20 | INC
ARC-2014-1259 | TS-0007-Reference_Update | timothy.carey@alcatel-lucent.com | Draft | 2014-03-28 14:18 | INC
ARC-2014-1258 | M2M Data Exchange Services | Tim Carey, ALU, timothy.carey@alcatel-lucent.com | Draft | 2014-03-28 14:16 | INC
ARC-2014-1257 | M2M Services Uses Case Scenarios | Timothy Carey, ALU, Timothy.carey@alcatel-lucent.com | Draft | 2014-03-28 14:15 | INC
ARC-2014-1256 | Clarify Optional Resources | ALU, Ericsson | Draft | 2014-03-28 14:09 | CR
ARC-2014-1255 | Announcement Issues | NEC | Draft | 2014-03-28 11:27 | INC
ARC-2014-1254 | requestReachability in CSEBase | LG Electronics | Draft | 2014-03-28 07:22 | INC
ARC-2014-1253 | virtual attribute description | LG Electronics | Draft | 2014-03-28 05:47 | INC
ARC-2014-1252 | Correction of <node> description | LG Electronics | Draft | 2014-03-28 01:24 | CR
ARC-2014-1251 | Device Node | NEC | Draft | 2014-03-27 15:08 | CR
ARC-2014-1250 | Hosting CSE definition modification | LG Electronics | Draft | 2014-03-28 05:14 | CR
ARC-2014-1249 | Local CSE cleanup | LG Electronics | Draft | 2014-03-29 04:43 | CR
ARC-2014-1248 | subscription attributes clarification | LG Electronics | Draft | 2014-03-28 03:17 | CR
ARC-2014-1247 | Resource Refinements for Subscription | LG Electronics | Draft | 2014-03-27 05:38 | CR
ARC-2014-1245 | Resource Specification Refinements | LG Electronics | Draft | 2014-03-27 03:24 | CR
ARC-2014-1244 | Resource Template Refinements | LG Electronics | Draft | 2014-03-27 03:19 | CR
ARC-2014-1242 | Location Filter Criteria | Hongbeom Ahn, LG Electronics, Hongbeom.ahn@lge.com, Philip Jacobs, Cisco Systems, phjacobs@cisco.com | Draft | 2014-03-28 15:32 | CR
ARC-2014-1241 | Summary of CMDH Policy | LG Electronics | Draft | 2014-03-26 02:07 | CR
ARC-2014-1240R01 | Cleanup of Notification Procedure | LG Electronics | Draft | 2014-04-01 01:18 | CR
ARC-2014-1240 | Cleanup of Notification Procedure | LG Electronics | Draft | 2014-03-26 00:51 | CR
ARC-2014-1239 | Cleanup of Subscription Procedure | LG Electronics | Draft | 2014-03-26 00:48 | CR
ARC-2014-1238 | Attribute Creation and Deletion | LG Electronics | Draft | 2014-03-26 00:18 | CR
ARC-2014-1237 | Connection_Request | NTT DOCOMO, LG Electronics | Draft | 2014-03-26 | CR
ARC-2014-1236 | DMR_CSF_revised | NTT DOCOMO, NEC | Draft | 2014-03-25 22:54 | INC
ARC-2014-1235R01 | Rename the attribute of PoA | Huawei Technologies | Draft | 2014-03-31 04:27 | CR
ARC-2014-1234R01 | Clarification on M2M Identifiers used for device triggering | Haier | Draft | 2014-03-28 06:30 | CR
ARC-2014-1233R03 | Correction of node resource | Huawei Technologies, LG Electronics | Draft | 2014-03-31 04:07 | CR
ARC-2014-1233R02 | Correction of node resource | Huawei Technologies, LG Electronics | Draft | 2014-03-31 04:03 | CR
ARC-2014-1233R01 | Correction of node resource | Huawei Technologies, LG Electronics | Draft | 2014-03-27 06:10 | CR
ARC-2014-1233 | Correction of node resource | Huawei Technologies | Draft | 2014-03-25 04:07 | CR
ARC-2014-1232 | Cleanup-clause-9 | NEC | Draft | 2014-03-24 18:34 | CR
ARC-2014-1231R02 | Location Request | LG Electronics, NTT docomo, AT&T | Draft | 2014-04-01 02:48 | CR
ARC-2014-1231R01 | Location Request | LG Electronics, NTT docomo | Draft | 2014-03-31 03:41 | CR
ARC-2014-1231 | Location Request | LG Electronics, NTT docomo | Draft | 2014-03-21 07:49 | CR
ARC-2014-1230 | app-inst-id cleanup | LG Electronics | Draft | 2014-03-21 07:34 | CR
ARC-2014-1229R01 | instance notion cleanup | LG Electronics | Draft | 2014-03-24 00:45 | CR
ARC-2014-1229 | instance notion cleanup | LG Electronics | Draft | 2014-03-21 07:34 | CR
ARC-2014-1228 | AE CSE definition | LG Electronics | Draft | 2014-03-21 07:33 | CR
ARC-2014-1227 | application resource type rename cleanup | LG Electronics | Draft | 2014-03-21 07:33 | CR
ARC-2014-1226 | m2m application service cleanup | LG Electronics | Draft | 2014-03-21 07:33 | CR
ARC-2014-1225 | application terminology cleanup | LG Electronics | Draft | 2014-03-21 07:33 | CR
ARC-2014-1224R01 | Correction of Post Condition | LG Electronics | Draft | 2014-03-28 01:26 | CR
ARC-2014-1222 | MN-MN-registration | NEC | Draft | 2014-03-20 12:55 | CR
ARC-2014-1221 | expirationTime alignment | NEC | Draft | 2014-03-20 12:44 | CR
ARC-2014-1218 | Cleanup_of_CSFs | Syed Husain, NTT DOCOMO | Draft | 2014-03-20 03:12 | INC
ARC-2014-1217 | filter criteria clarification | LG Electronics | Draft | 2014-03-19 06:49 | CR
ARC-2014-1214R01 | Attribute Announcement Procedure Option 2 | Rajesh Bhalla, Hao Wo, ZTE | Draft | 2014-03-19 16:32 | CR
ARC-2014-1213R01 | Attribute Announcement Procedure Option 1 | Rajesh Bhalla, Hao Wo, ZTE | Draft | 2014-03-19 16:31 | CR
ARC-2014-1212R01 | Attribute Announcement Issues | Rajesh Bhalla, Hao Wo, ZTE | Draft | 2014-03-19 16:30 | CR
ARC-2014-1211R02 | Cleanup of section 10.1 | Rajesh Bhalla, ZTE | Draft | 2014-03-18 13:57 | CR
ARC-2014-1209R02 | Announceable Resource Clean up | LG Electronics | Draft | 2014-04-01 03:48 | CR
ARC-2014-1209R01 | Announceable Resource Clean up | LG Electronics | Draft | 2014-03-20 09:55 | CR
ARC-2014-1202 | Removal section 9.5.2 | NEC | Draft | 2014-03-10 12:08 | CR
ARC-2014-1198R02 | Update table 9.6-1 | Philip Jacobs, Cisco Systems Inc, Barbara Pareglio, NEC Labs | Draft | 2014-03-29 12:10 | CR
ARC-2014-1198R01 | Update table 9.6-1 | Philip Jacobs, Cisco Systems Inc, Barbara Pareglio, NEC Labs | Draft | 2014-03-23 17:07 | CR
ARC-2014-1196R01 | Inconsistency list | NEC | Draft | 2014-03-20 10:04 | INC
ARC-2014-1192R02 | Cleanup of editors notes and highlights in ASM and DMG CSFs | Tim Carey, ALU, timothy.carey@alcatel-lucent.com | Draft | 2014-03-28 14:11 | CR
ARC-2014-0178R03 | Attribute consistency | NEC | Draft | 2014-03-28 11:18 | CR
ARC-2014-0155R03 | Request-Resource-Refinement | LG Electronics | Draft | 2014-03-31 12:01 | CR
ARC-2014-0030 | Section 5.2-cleanup | NEC | Draft | 2014-01-13 16:58 | INC
ARC-2014-0029 | NSE-consistency-usage | NEC | Draft | 2014-01-13 16:56 | INC
ARC-2014-0028R06 | NodeLess-AE renamed | NEC | Draft | 2014-03-27 22:25 | CR
ARC-2014-0027R01 | Definition cleanup | NEC | Draft | 2014-03-31 15:23 | CR

## PRO (hidden)
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | UPLOADED | DOC TYPE | VERS
SC-2014-0359 | TS-00004 outline | LM Ericsson | Draft | 2014-03-27 17:23 | INC
PRO-2014-0162 | Applicability of Primitives | Philip Jacobs, Cisco, phjacobs@cisco.com | Draft | 2014-03-31 19:41 | INC
PRO-2014-0161 | CRUD mapping on HTTP | FUJITSU | Draft | 2014-03-31 09:27 | INC
PRO-2014-0160 | WebSocket based Notification | FUJITSU | Draft | 2014-03-31 10:47 | INC
PRO-2014-0159 | HTTP Authentication | FUJITSU | Draft | 2014-03-31 08:50 | INC
PRO-2014-0158 | Basic Data and Enumeration Type | LG Electronics | Draft | 2014-03-31 06:42 | INC
PRO-2014-0157 | Proposal for design principles and requirements on energy efficient protocols | KETI, KT, Institut Mines-Telecom | Draft | 2014-03-30 23:01 | INC
PRO-2014-0156 | Discussion on energy efficient protocols | Institut Mines-Telecom, KETI, KT | Draft | 2014-03-30 22:57 | INC
PRO-2014-0155 | execInstance | InterDigital Communications | Draft | 2014-03-30 21:40 | INC
PRO-2014-0154 | mgmtCmd | InterDigital Communications | Draft | 2014-03-30 21:40 | INC
PRO-2014-0153 | Identifiers | NEC | Draft | 2014-03-30 18:07 | INC
PRO-2014-0152 | group-management-procedures | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:24 | INC
PRO-2014-0151 | common-operations | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:19 | INC
PRO-2014-0150 | primitives | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:17 | INC
PRO-2014-0149 | HTTP_binding_TS_clause6_clause7 | LG Electronics | Draft | 2014-03-29 07:47 | INC
PRO-2014-0148 | HTTP_binding_TS_clause5 | LG Electronics | Draft | 2014-03-29 07:46 | INC
PRO-2014-0147 | HTTP_binding_TS_clause2_clause3 | LG Electronics | Draft | 2014-03-29 07:46 | INC
PRO-2014-0146 | Support for Bluetooth | LM Ericsson | Draft | 2014-03-28 17:10 | INC
PRO-2014-0145 | Core Protocol TS Restructuring | FUJITSU | Draft | 2014-03-28 12:34 | INC
PRO-2014-0144 | Device triggering for 3GPP | NEC, NTT Docomo | Draft | 2014-03-28 10:33 | INC
PRO-2014-0143 | Draft Core Protocol TS v0.3.2 | Core Protocol TS Rapportuer | Draft | 2014-03-28 08:52 | INC
PRO-2014-0142 | XML Schema Change Request | IBM | Draft | 2014-03-27 19:32 | CR
PRO-2014-0141R01 | TS-00004 Outline | LM Ericsson | Draft | 2014-03-28 12:05 | INC
PRO-2014-0141 | TS-00004 Outline | LM Ericsson | Draft | 2014-03-27 17:28 | INC
PRO-2014-0140 | WG3 PRO Agenda | WG3 Chairman | Draft | 2014-03-31 16:35 | AG
PRO-2014-0139 | Device triggering for 3GPP presentation | NEC, NTT Docomo | Draft | 2014-03-27 08:42 | INC
PRO-2014-0138 | CoAP | Mukesh Taneja, Cisco | Draft | 2014-03-27 08:12 | AG
PRO-2014-0137 | XMPP | Mukesh Taneja, Cisco | Draft | 2014-03-27 05:52 | INC
PRO-2014-0136 | Modbus | Mukesh Taneja, Cisco | Draft | 2014-03-27 04:23 | INC
PRO-2014-0135 | DNP3 and oneM2M Requirements | Mukesh Taneja, Cisco | Draft | 2014-03-26 16:41 | INC
PRO-2014-0132R01 | WirelessHART Analysis | Mukesh Taneja, Cisco | Draft | 2014-03-26 11:25 | INC
PRO-2014-0131R01 | HTTP-REST Overview | FUJITSU | Draft | 2014-03-25 14:48 | INC
PRO-2014-0128R03 | ISA100.11a Analysis | Mukesh Taneja, Cisco | Draft | 2014-03-26 13:32 | INC
PRO-2014-0128R02 | ISA100.11a Analysis | Mukesh Taneja, Cisco | Draft | 2014-03-26 11:27 | INC

## MAS (hidden)
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | UPLOADED | DOC TYPE | VERS
MAS-2014-0352R02 | DataType Identification Mapping for OMA DM | LG Electronics | Draft | 2014-04-08 04:31 | CR
| Resource Mapping for OMA LWM2M | Gemalto N.V | Draft | 2014-04-07 16:52 | CR
MAS-2014-0366R01 | DataType_Identification_Mapping_for_OMA_LWM2M | Gemalto N.V | Draft | 2014-04-07 16:51 | CR
MAS-2014-0364R03 | MAS 10.0 contribution list | Yongjing Zhang (Chair) | Draft | 2014-04-04 02:13 | AG
MAS-2014-0368 | Editorial updates to correct grammar and proper wording | Ericsson | Draft | 2014-04-03 20:46 | CR
MAS-2014-0367 | Resource Mapping for OMA LWM2M | Gemalto N.V | Draft | 2014-04-04 13:43 | CR
MAS-2014-0366 | DataType_Identification_Mapping_for_OMA_LWM2M | Gemalto N.V | Draft | 2014-04-04 13:43 | CR
MAS-2014-0361R03 | Semantic web best practices | Eurecom, Amelie Gyrard, gyrard@eurecom.fr, Christian Bonnet, bonnet@eurecom.fr | Draft | 2014-04-03 15:17 | INC
MAS-2014-0364R02 | MAS 10.0 contribution list | Yongjing Zhang (Chair) | Draft | 2014-04-03 04:01 | AG
MAS-2014-0364R01 | MAS 10.0 contribution list | Yongjing Zhang (Chair) | Draft | 2014-04-03 03:52 | AG
MAS-2014-0362R01 | Agenda MAS 10.0 | Yongjing Zhang (Chair) | Draft | 2014-04-03 03:52 | AG
MAS-2014-0365 | App-ID Additional Clarification Text | Ericsson | Draft | 2014-04-01 21:42 | CR
MAS-2014-0361R02 | Semantic web best practices | Eurecom, Amelie Gyrard, gyrard@eurecom.fr, Christian Bonnet, bonnet@eurecom.fr | Draft | 2014-04-01 16:01 | INC
MAS-2014-0361R01 | Semantic web best practices | Eurecom, Amelie Gyrard, gyrard@eurecom.fr | Draft | 2014-04-01 10:23 | INC
MAS-2014-0364 | MAS 10.0 contribution list | Yongjing Zhang (Chair) | Draft | 2014-04-02 16:50 | AG
MAS-2014-0363 | Minutes-MAS TP #10 | Secretary | Draft |  | MIN
MAS-2014-0362 | Agenda MAS 10.0 | Yongjing Zhang (Chair) | Draft | 2014-04-02 16:50 | AG
MAS-2014-0361 | Semantic web best practices | Eurecom, Amelie Gyrard, gyrard@eurecom.fr | Draft | 2014-03-31 10:35 | INC
MAS-2014-0360 | semantic home automation | Haier | Draft | 2014-03-31 08:41 | INC
MAS-2014-0359 | Key Issues on Semantics and Ontologies | KETI | Draft | 2014-03-31 07:22 | INC
MAS-2014-0351R01 | Resource Mapping for OMA DM | LG Electronics | Draft | 2014-03-31 01:53 | CR
MAS-2014-0352R01 | DataType Identification Mapping for OMA DM | LG Electronics | Draft | 2014-03-31 01:50 | CR
MAS-2014-0358 | CMDH_Policy_Management | Qualcomm Inc. (TIA) | Draft | 2014-03-31 01:18 | INC
MAS-2014-0357 | Discussion_abstraction_semantics | Modacom Co., Ltd (TTA) | Draft | 2014-03-30 21:30 | INC
MAS-2014-0356 | proper_usage_terminologies_ABS_TR | Modacom Co., Ltd (TTA) | Draft | 2014-03-30 21:20 | INC
MAS-2014-0355 | resource-mapping-for-management | Huawei Technologies Co.,Ltd. | Draft | 2014-03-29 08:20 | INC
MAS-2014-0354R01 | Device෫骙媵Modelling | NEC | Draft | 2014-03-28 16:43 | INC
MAS-2014-0354 | Device෫骙媵Modelling | NEC | Draft | 2014-03-28 16:40 | AG
MAS-2014-0353 | Architectural Considerations for Semantic Support | NEC | Draft | 2014-03-27 16:29 | INC
MAS-2014-0352 | DataType Identification Mapping for OMA DM | LG Electronics | Draft | 2014-03-27 03:01 | CR
MAS-2014-0351 | Resource Mapping for OMA DM | LG Electronics | Draft | 2014-03-27 02:49 | CR
MAS-2014-0349 | Architectural Considerations for Semantic Support | NEC | Draft | 2014-03-24 09:06 | INC