## Tabelle1
Report at oneM2M TP#11 & Interim report from WG-3
Part A: Executive Summary for Plenary
Progress on 4 of 5 Work-Items WI-0008 TR-00009, WI-0009 TS-0004, WI-0012 TS-0008 & WI-0014 TS-0010
WI-0008 TR-0009 reasonable progress 95% complete ready for TP apprval & WI-0009 TS-0004 35%
Bindngs WI-0012 TS-0008 CoAP 20% complete; WI-0013 TS-0009 HTTP 25% complete; MQTT WI-0014 TS-0010 35%
In the main for June TP.11 for shared room with WG-2 to avoid overlap, if the Stage 3 is to be complete in August 2014 attention has shifted to WG3 at TP.10.
Planning for next Meeting(s)
Conference Calls
Conference Calls
o PRO11.2 Tuesday – 12:00 noon UTC, June 24
o PRO11.3 Tuesday – 12:00 noon UTC, July 01
o PRO11.4 Tuesday – 12:00 noon UTC, July 08 (chaired by a Vice Chairman)
o PRO11.5 Tuesday – 12:00 noon UTC, July 15
Face to Face
o PRO11.0 Week 09-13 June 2014, Xi’an China
o PRO11.1 interim Ad’hoc Monday 16 Wednesday – 18 June Beijing China.
o PRO11.6 interim Wednesday 23 - Friday 25 July ETSI (Sophia-Antipolis).
o PRO12.0 Week 28 July – 02 August 2014, ETSI Sophia Antipolis, France.
A1. Documents NOT AGREED in WG (to be presented to Plenary for discussion).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A2. Documents NOT AGREED in WG (noted / postponed / not treated etc).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A3. Documents AGREED in WG
A3. Documents AGREED in WG
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A4. WG Actions:
REFERENCE | WHAT | WHO | STATUS
A-PRO-2014-0005 | PRO-2014-0113R10 Call for volunteers/Issues list on TS-0004 • When each area will be contributed (month)? • Is there a volunteer for all the unassigned topics? • One addition uploaded to PRO11.0 | WG Chairman & Vice Chairman | ongoing
A-PRO-2014-0007 | Template for oneM2M Resource Type Definition PRO-2014-0205 contained in PRO-2014-0215 | S.FUJIMOTO on behalf of WG3 Drafting Team | ongoing
A-PRO-2014-0008 | PRO-2014-0212R01 - Proposed Conference calls btween TP.11&TP.12 | WG Chairman & Vice Chairman | To Be Discussed
A5. WG Decisions: See agreed Documents
REFERENCE | WHAT
D-WG<no.>
D-WG<no.>
A6. WG Information to Plenary (AoB):
<Text>
<Text>
Part B: List of all contributions to the WG meeting
Working area to be used during the WG meeting
WG3 PRO#3 meeting contributions
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
PRO-2014-0245 | WG3 Agenda | WG3 Chairman |  | Agreed |  |  |  |  | n/a
PRO-2014-0213R01 | Minutes-2014-05-27&28 | Secretary |  | Agreed |  |  |  |  | n/a
PRO-2014-0243 | Minutes-2014-06-03 | Secretary |  | Agreed |  |  |  |  | n/a
PRO-2014-0232 | Candidate for approval | TR Rapporteur | 2014-06-02 | Noted | TR-0009 | V0.6.2 |  |  | WI-0008
· Version 0.6.3
· Noted TR-50 clause re-instantiated
PRO-2014-0234R01 | TR-50 Protocol Description | Mihai Voicu | 2014-06-03 | Agreed | TR-0009 | V0.6.2 |  |  | WI-0008
· Approval by correspondence until 11 June
· After AbC if agreed then version 0.7.0 will be reviewed on Fri 13 June at WG3
PRO-2014-0215 | Draft Core Protocol TS v0.4.2 | FUJITSU | 2014-05-30 | Agreed | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0195R03 | Child Resource Conversion Rules | FUJITSU | 2014-05-27 | Agreed | TS-0004 | V0.4.2 |  |  | WI-0009
· 195R03 to be approved by correspondence until 3 June
PRO-2014-0194R02 | CSEBase Resource Type Definition | FUJITSU | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0206R01 | Connection Settings | FUJITSU | 2014-05-28 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0152R01 | group-management-procedures | Huawei Technologies Co. | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0217 | Attribute Creation and Deletion | LG Electronics | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0218 | Announcement Procedures | LG Electronics | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0219 | Resource Discovery Procedure | LG Electronics | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0220 | management-common-operations | Huawei Technologies Co. | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0221 | mgmtObj-management-procedures | Huawei Technologies Co. | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0222 | Primitive_templates_and_procedure outlines_modification | Huawei Technologies Co. | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0223 | node-resource-type-procedures | Huawei Technologies Co. | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0224 | design_principles_scalability | KETI | 2014-05-31 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0225 | Common Operations Updates | FUJITSU | 2014-06-01 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0226 | Send Request in HTTP | FUJITSU | 2014-06-01 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0227 | cmdh_policies_TS0004 | Qualcomm Inc. (TIA) | 2014-06-01 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0228 | LocationPolicy Resource Primitive | LG Electronics | 2014-06-01 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0229 | Location Request on Mcn Reference Point | LG Electronics | 2014-06-01 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0230 | mgmtCmd input TS0004 | InterDigital | 2014-06-01 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0231R01 | Request resource type definition | QUALCOMM | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0233R01 | Resource Announcement Operations | ZTE; Hao Wu | 2014-06-02 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0235 | pollingChannel procedures | LG Electronics | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0236 | Stage 3 text for Resource Type <statsConfig> | InterDigital | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0237 | Stage 3 text for Resource Type <eventConfig> | InterDigital | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0238 | Stage 3 text for Resource Type <statsCollect> | InterDigital | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0239 | Resource Type XSD example | FUJITSU | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0241 | mapping types | LG Electronics | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0242 | Correction to Table 7.2.1.1-2 in TS-0004 | QUALCOMM | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0216R01 | Response Status Clause | Philip Jacobs, Cisco Systems, phjacobs@cisco.com | 2014-06-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009 | Revised & 2014-06-03
PRO-2014-0242 | Correction to Table 7.2.1.1-2 in TS-0004 | QUALCOMM | 2014-06-04 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0244 | Draft CoreProtocol TS v0.4.3 with name of leaders | Core Protocol TS Rapportuer | 2014-06-04 |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0197R01 | Access Control Consideration | FUJITSU |  |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0196r01 | pollingChannel resource type definition | LG Electronics |  |  | TS-0004 | V0.4.2 |  |  | WI-0009
PRO-2014-0167R02 | Generic primitives and procedures | QUALCOMM Incorporated | 2014-04-03 |  | TS-0004 | V0.4.2 |  |  | WI-0009
[5 empty] | TS-0008 | V0.2.0 |  |  | WI-0012
[5 empty] | TS-0008 | V0.2.0 |  |  | WI-0012
PRO-2014-0214 | Draft TS-0009 v0.3.0 | TS-0009 Rapporteur | 2014-05-30 |  | TS-0009 | V0.3.0 |  |  | WI-0013
PRO-2014-0240 | TS-0009 cleanup | LG Electronics | 2014-06-03 |  | TS-0009 | V0.3.0 |  |  | WI-0013
PRO-2014-0241 | mapping types | LG Electronics | 2014-06-04 |  | TS-0009 | V0.3.0 |  |  | WI-0013
[5 empty] | TS-0010 | V0.1.2 |  |  | WI-0014
[5 empty] | TS-0010 | V0.1.2 |  |  | WI-0014

## Tabelle2
oneM2M IPR STATEMENT
Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by all provisions of IPR policy of the admitting Partner Type 1 and permission that all communications and statements, oral or written, or other information disclosed or presented, and any translation or derivative thereof, may without compensation, and to the extent such participant or attendee may legally and freely grant such copyright rights, be distributed, published, and posted on oneM2M’s web site, in whole or in part, on a non-exclusive basis by oneM2M or oneM2M Partners Type 1 or their licensees or assignees, or as oneM2M SC directs.