## Slide 1: TST #35 WG Status Report
Group Name: TP
Source: TST WG Chair, JaeSeung Song (KETI, jssong@sejong.ac.kr )
TST WG Vice-Chair, Mahdi Ben Alaya (Sensinov, benalaya@sensinov.com)
Meeting Date: 2018-05-22 to 2018-05-25
TP-2018-0166R03-TST#35_report

## Slide 2: Summary
WG6 Objectives for TST 35
  Working on the development of new Test Purposes (TPs) for Rel-2 and Rel-3
  Publish oneM2M Rel-1 Conformance Testing Specs
  Joint workshop with GCF for oneM2M Certification
Status
  Developer guides:
    TR-0038, Security DG  100%
    TR-0047, 3GPP Interworking DG  80%
    TR-0051, Developers API  50%
  Conformance testing specs Rel-1 Done
  Rel-2 Conformance testing WID  40%
  On track developing Rel-2 and Rel-3 TPs

## Slide 3: Item for DECISION
TSes for approval
  TS-0017  TP-2018-0168-TS-0017_Rel-1
  TS-0018  TP-2018-0169-TS-0018_Rel-1
  TS-0019  TP-2018-0170-TS-0019_Rel-1
  TR-0038, Security Developer Guide  TP-2018-0174-TR-0038-DG-security-V0_5_0
CR packs for approval
  None

## Slide 4: Action Items
Develop new Interop. Test cases:
  (AP1) Location policy : C-Dot
  (AP2) Announcement : ETSI
  (AP3) Non-Blocking : Convida Wireless
  (AP4) Polling channel : KETI
  (AP5) Time series : KETI
  (AP6) CSE-CSE registration : ETSI
  (AP7) Security e.g., certificate-based test case : Convida Wireless
  (AP8) A scenario-based test case : TTA

## Slide 5: Items for Information (Workshop with GCF)
Summary:
  An half-day (09:00~12:00) and additional work on afternoon
  Around 25~30 participants (three delegates from GCF)
  Resolved most key items (e.g., database design, migration schedule, reviewed GCF oneM2M certification Work Item Descriptions)
  Plan for next steps
  A big handshake
  Migration is on track
GCF is currently finalising the oneM2M Certification Program, targeting a launch date in early Q1/2019
Joint communication (PR) with oneM2M, GCF and TTA (Q3/2018)
Invitation to GCF Steering Meeting on June (TTA, Convida?, KETI?, and ETSI? )
Rapporteurship of GCF oneM2M certification (TBD, TTA??)
Formal relationship between GCF and oneM2M: ILC will help on this

## Slide 6: Items for Information
Interop 6
  Date: July (09. July ~ 13. July) , the week before TP#36
  Venue: Washington D. C., USA, Sofitel Washington DC Lafayette Square
  Host: ETSI & TTA
  Registration : http://www.etsi.org/news-events/events/1298-onem2m-interop-6
  Free of charge and open to all with oneM2M Implementation
  Interop. Testing Coverage:
    Announcement, Non-blocking, Polling channel, Time series, Security
    A scenarios based Interop. testing
  Conformance Testing Coverage:
    Announcements, Polling channels, Time series, non-Blocking cases
Interop 7 (TBD)
  Option 1: Europe
  Option 2: Japan in conjunction with TP
  Option 3: In conjunction with IEEE ICNC ’19 (USA)
  Survey after Interop6

## Slide 7: Items for Information
LS from GCF
  TP-2018-0139-Reply_LS_on_Cooperation_between_GCF_and_oneM2M
  Reviewed at a TST session
  TST will generate a response LS as GCF requests participants to their steering meeting on June
  oneM2M TST accepts their invitation
  Also oneM2M TST will invite GCF to upcoming Interop6 as observers
  Bob is now drafting an LS out to GCF (email approval is required to handle this)

## Slide 8: Next Meetings / Calls
Conference Calls
  TST#35.1: 12. June. 2018, UTC 13:00-14:30
  TST#35.2: 28. June. 2018, UTC 13:00-14:30
Face-to-Face
  Interop 6: July, 09-13, Washington D. C., USA
  TST#36: July, 16-18, Washington D. C., USA
  TST#37: September, 17-21, TTA, Bundang, Republic of Korea

## Slide 9: Thank you!