## Cover
Website Build Timeline
Author: Lizzie Hawker
Date: 23rd July 2019
Le Petrel
21 Princess Caroline
Monaco 98000
www.relevanceweb.com

## Timeline
Assigned | Item | October | [30 empty] | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1
Research & Planning | bar: October 5; October 12; October 19; October 26; November 2; November 9; November 16; November 23; November 30; December 7; December 14; December 21; December 28; January 4; January 11; January 18; January 25; February 1; February 9; February 16
TBC | Brainstorm workshop | October 7: FALSE
TBC | Competitor & market analysis | October 10: FALSE
TBC | Website functionality checklist | October 10: FALSE
SEO & Content
TBC | Keyword research | October 15: FALSE
TBC | SEO sitemap | October 15: FALSE
TBC | Assignment of Keywords to Sitemap | October 18: FALSE
TBC | SEO META data | October 25: FALSE
TBC | SEO content optimisation | January 10: TRUE
Prototyping & Design
NW | Website wireframes | October 11: FALSE
TBC | Revision and feedback session | October 14: FALSE
NW | Second round of wireframes | October 16: FALSE
NW | Homepage design | October 18: FALSE
NW | Homepage amends | October 18: FALSE
NW | Template designs | October 29: FALSE
NW | Mobile designs | November 1: FALSE
NW | Interactive map 1 & 2 | November 1: FALSE
Build
TB | Website build, including setup, template coding, mobile responsive CSS and backend work | January 17: FALSE
TB | bar: January 6 to January 9; January 13 to January 16
Go Live & Measure
Rel, TB | Website testing & amends | February 8: TRUE
TBC | Analytics & reporting setup | February 8: FALSE
TBC | Website migration | February 15: FALSE
Website Go Live |  | March 1: FALSE

## Revised_Timeline
Assigned | Item | March | [10 empty] | April | [29 empty] | May | [30 empty] | June | [29 empty] | July | [30 empty] | August
|  | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
Research & Planning | bar: March 21; March 28; April 4; April 11; April 18; April 25; May 2; May 9; May 16; May 23; June 6; June 13; June 20; June 27; July 4; July 11; July 18; August 1; August 8; August 15; August 22
TBC | Brainstorm workshop | March 23: TRUE
TBC | Competitor & market analysis | March 26: TRUE
TBC | Website functionality checklist | March 26: TRUE
SEO & Content
TBC | Keyword research | March 31: TRUE
TBC | SEO sitemap | March 31: FALSE
TBC | Assignment of Keywords to Sitemap | April 3: FALSE
TBC | SEO META data | April 10: FALSE
TBC | SEO content optimisation | June 26: FALSE
Prototyping & Design
NW | Website wireframes | March 27: FALSE
TBC | Revision and feedback session | March 30: FALSE
NW | Second round of wireframes | April 1: FALSE
NW | Homepage design | April 3: TRUE
NW | Homepage amends | April 3: TRUE
NW | Template designs | April 14: FALSE
NW | Mobile designs | April 16: FALSE
NW | Interactive map 1 & 2 | April 16: FALSE
Build
TB | Website build, including setup, template coding, mobile responsive CSS and backend work | July 3: FALSE
TB | bar: June 22 to June 25; June 29 to July 2
Go Live & Measure
Rel, TB | Website testing & amends | July 24: FALSE
TBC | Analytics & reporting setup | July 24: FALSE
TBC | Website migration | July 31: FALSE
Website Go Live |  | August 18: FALSE

## Revised_Timeline_2
Assigned | Item | May |  | June | [31 empty] | July | [28 empty] | August | [30 empty] | September | [29 empty] | October | [30 empty] | November
|  | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
Research & Planning | bar: May 30; June 6; June 13; June 20; June 27; July 4; July 11; July 18; July 25; August 1; August 15; August 22; August 29; September 5; September 12; September 19; September 26; October 10; October 17; October 24; October 31
TBC | Brainstorm workshop | June 1: TRUE
TBC | Competitor & market analysis | June 4: TRUE
TBC | Website functionality checklist | June 4: TRUE
SEO & Content
TBC | Keyword research | June 9: TRUE
TBC | SEO sitemap | June 9: TRUE
TBC | Assignment of Keywords to Sitemap | June 12: TRUE
TBC | SEO META data | July 3: FALSE
TBC | SEO content optimisation | August 14: FALSE
Prototyping & Design
NW | Website wireframes | June 5: TRUE
TBC | Revision and feedback session | June 8: TRUE
NW | Second round of wireframes | June 10: TRUE
NW | Homepage design | June 12: TRUE
NW | Homepage amends | June 12: TRUE
NW | Template designs | June 16: TRUE
NW | Mobile designs | June 18: TRUE
NW | Interactive map 1 & 2 | June 11: TRUE
Build
TB | Website build, including setup, template coding, mobile responsive CSS and backend work | September 11: FALSE
TB | bar: August 31 to September 3; September 7 to September 10
Go Live & Measure
Rel, TB | Website testing & amends | October 2: FALSE
TBC | Analytics & reporting setup | October 2: FALSE
TBC | Website migration | October 9: FALSE
Website Go Live |  | October 27: FALSE