## Slide 1: oneM2M website project - Status
Estelle Mancini - MARCOM Secretary
MARCOM91- 23 Sept 2020

## Slide 2: Completion of the build phase
The overall development is being finalized
Development of a database containing the deployment page information for the interactive map
Access to the oneM2M website database and website backup has been provided
Migration is going to start progressively with as content becomes available for testing.

## Slide 3: Go-live phase
12-30 October - Testing and amend phase
2-6 November - Migration of the website
9 November - Start of the go-live phase
24 November - The new website is publicly available
NB – The delay is due to the content optimisation started later that planned.
These new dates are provisional.
We will still aim to go live at the end of October/early November.