| Input Contribution |  |
| --- | --- |
| Meeting ID* | Marcom 106 |
| Title:* | oneM2M 10 Years anniversary plan |
| Source:* | Bindoo Srivastava, TSDSI, Chair – oneM2M Marcom , bindoo@tsdsi.in |
| Date:* | 2022-05-26 |
| Input related to* | Draft plan for 10 years anniversary of oneM2M |
| Intended purpose of document:* | Decision Discussion Information Other <specify> |
| Impacted other TS/TR(s) |  |
| Decision requested or recommendation:* |  |
| Template Version: January 2020 (do not modify) |  |

oneM2M Notice

The document to which this cover statement is attached is submitted to oneM2M.  Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by terms of the Working Procedures and the Partnership Agreement, including the Intellectual Property Rights (IPR) Principles Governing oneM2M Work found in Annex 1 of the Partnership Agreement.

# Plan

Launch the 10th Anniv celeb with SC62 (27th Jul) and culminate in a hybrid conference in Dec ’22

| oneM2M Launch date 24-26 Jul’ 2012 in a SC1 hosted by ATIS-TIA | Launch the Celebrations: Commemorate the event in SC62 meeting on 27th July: Flashback collage of photos from meetings held over the years; Photo collages from Industry Days Special session to felicitate the founder partner members from SC1? And who joined later (like TSDSI). Do we call PT2 and MROs also? Read out messages from the founder member reps and post on website Felicitate past SC Chairs/Vice Chairs and seek their messages 10 years of oneM2M Campaign: Post on website and LinkedIN and Twitter: - Banner - Interesting metrics (oneM2M timeline and numbers - any figures/stats) - Video (or written) Interviews/messages from partners - Message from the Steering Committee members (Chair or Vice Chair) - Video (or written) messages from past SC Chairs/Vice Chairs - Ken’s article on oneM2M history? – launch the paper - oneM2M Video shoot from TP54 of folks saying happy 10th anniversary oneM2M 😊 - ecosystem engagement – liaisons/interop capabilities - showcase demos/pilots/implementations? Launch the oneM2M short tutorials (Ken/Andreas Kraft) |
| --- | --- |
| oneM2M TP1 held in ETSI HQ in Sep 2012 | Coming back to ETSI HQ for TP#56 from 26-30 Sep’22 Celebrate- long serving experts- JaeSeung Song, Roland Hechwartner Felicitate and seek Messages from past TP Chairs /Vice Chairs Sponsored social celebration event? And/or A LIVE oneM2M Webinar – a video interaction with oneM2M Experts past and present – as part of the Social Event ? and later we can derive excerpt articles from here. Photo collages from TPs , Interops, developer Events/Hackathons/tutorials |
| Launch oneM2M Annual Flagship Conference. To be rotated across regions and organized by partners- budget to be worked out (prefer the host partner SDO to manage – hybrid event – like an ANNUAL INDUSTRY DAY in a new AVATAR) | Hybrid conference spread over 2 days in Seoul collocated with the TP 57 between 28 Nov-9 Dec’22 + offsite Visit to a oneM2M implemented smart city campus nearby + sponsored social event? Launch the oneM2M Handbook English version from TTA? Announce Any resolve from the introspection on oneM2M status – discussions for which have been kicked off in the TP 54? Example: oneM2M for IoT2.0 |
|  | Digital PR campaign – something around the growth/development of IoT devices and their role in society/across industries |

| Item/Activity | Volunteer SPOC |
| --- | --- |
| Collate Photographs from past events/activities and develop collage/sets |  |
| Secure Messages from Partners/Stakeholders Written with their photos Videos |  |
| Multi location – Video shoot – of oneM2M stakeholders and stitch together |  |
| Reach out to - invite named experts to the relevant Celebratory events – coordinate their participation |  |
| Orchestrate the celebratory events Online 24-26 Jul In SC62 27 Jul In TP 56 Social Event? |  |
| Social Event @TP56 Need Sponsor |  |
| Social Event in Dec’22 Need Sponsor |  |
| Felicitations - how ? nice notes OR mementos? Mementos? NEED SPONSORS |  |
| oneM2M Conference – Program Committee and Org. Committee |  |
| Articles oneM2M @10 etc. |  |
| oneM2M Short Tutorial Videos Launch |  |
| oneM2M Handbook - translate |  |
| Website- SM content creation and upload Partner websites SM Engagement |  |