## ADM-0001 V 17.1.0
Administrative Document
ADM-0001-V-17.1.0
Title: oneM2M Work Programme
2015-07-15
Copyright Notification
No part may be reproduced except as authorized by written permission.
The copyright and the foregoing restriction extend to reproduction in all media.
This document is intended for distribution only to oneM2M Participants.
© oneM2M Partners Type 1 (ARIB, ATIS, CCSA, ETSI, TIA, TTA, TTC)
Contents
1 Scope ……………………………………………………………….…………………Page 3
2 References …………………………………………………………..…………...…...Page 3
2.1 Normative References ……………………………...……………………………….………………..… Page 3
2.2 Informative References ………………………………………………………...…………...……...…… Page 3
3 Definitions, symbols, abbreviations and acronyms ………………………….….....……Page 3
3.1 Definitions …………………………….……………………………………………………………........ Page 3
3.2 Symbols …………………………….………………………………………………………………...…. Page 3
3.3 Abbreviations, acronyms……………………………………………………………….…………...… Page 3
4 Conventions …………………………………………………………………..……… Page 3
5 oneM2M Work Programme ……………………..…………………………..……… Page 3
Annex A: Work Programme Overview …….…………………………….……………..Register WIs
Annex B: List of Technical Specifications ……………………………………...……….Register TSs
Annex C: List of Technical Reports …….………………………………...…………….Register TRs
Annex D: List ADM ………………...………………….…………………….…...........Register ADMs
History of Change …………………………………………………….……….……… Register History
1 Scope
The present document is the “oneM2M Work Programme” referred to in Articles 31 in the Working Procedures Document [1], and addresses the Work Item reporting process within the Technical Plenary, its subordinate groups and the Secretariat to accomplish the tasks extracted from Article 12. In addition, the present document addresses processes to accomplish tasks not specifically identified in the Working Procedures Document but considered essential to the efficient operation of the Technical Plenary.
2 References
References are either specific (identified by date of publication and/or edition number or version number) or non specific. For specific references,only the cited version applies. For non-specific references, the latest version of the referenced document (including any amendments) applies.
2.1 Normative References
The following referenced documents are necessary for the application of the present document. [1] ADM-0002 oneM2M Partnership Agreement [2] ADM-0005 oneM2M Working Procedures Document [3] ADM-0004 Method of work
2.2 Informative References
The following referenced documents are not necessary for the application of the present document but they assist the user with regard to a particular subject area.
[i.1] ADM-0003 oneM2M Drafting Rules (http://member.onem2m.org/Static_pages/Others/Rules_Pages/oneM2M-Drafting-Rules-V1_0.doc)
3 Definitions and Abbreviations
For the present document the following apply:
3.1 Definitions
Approval: the decision of the Technical Plenary that a deliverable is ready for getting ratified in order to publish it (see process description in [2]).
Change Control: the decision of a Working Group that the content of a draft deliverable is sufficiently advanced that it will utilize the Change Control process (see process description in [2]).
Drafting:the editorial phase of a deliverable until it is placed under Change Control (see process description in [2]).
Forecast: the date estimation (best guess) for the required milestones of a deliverable based on the current state of it taking into account the level of completeness, risks and uncertainties
Freeze: the decision of a Working Group that the technical content of a draft deliverable is complete (given consideration of the Work Item scope and workplan), and it is frozen for further technical input (see process description in [2])
Level of Completeness:the estimation of how much of a deliverable has been already drafted in relation to the expected total amount being necessary for the approval
Milestone dates: dates for the main process corner stones of a deliverable specified in the respective Work Item documents (see process description in [2])
Start: means the beginning of drafting a deliverable
Target: a requested date for a deliverable which is specified in the respective Work Item document for all its main milestones
TP#n-1 means the last Technical Plenary meeting before the current one. The current one is the basis for an update of the Work Programme.
3.2 Abbreviations
ARC Architecture
Doc_ID Document Identifier
MAS Management, Abstraction and Semantics
REQ Requirements
SEC Security
TP Technical Plenary
TS Technical Specification
TST Testing
WI Work Item
WG Working Group
4 Conventions
Work Programme updates
Form for updating planning (Register WIs) - serves for updating forecasts of milestone dates and level of completeness by the respective rapporteurs of the deliverables. The dates in the target columns are taken from the actual revisions of the approved respective Work Item documents.
Scaling of level of completeness
• Value range from 0% - 100%, no special scaling requested. Highest level achievable in a WG is 95%
• Measurement will be against milestone “Approval” listed in the agreed respective Work Item (meaning that 100% completeness must be achieved for reaching this milestone)
• Expected levels of completeness at milestones:
Start - 0%
First draft / skeleton - 10%
Freeze - 90%
WG decision: “ready for approval” - 95%
(shall be achieved for the deliverable being presented to Technical Plenary for approval, rest of 5 % is considered as remaining editorial effort for producing the final revision, which is candidate for TP ratification, candidate for getting published by the Partners Type 1)
Approval (by TP) - 100%
5 oneM2M Work Programme
Please see also the WPM portal for the latest work program status.

## WIs
WI number | Titel | Ver | Status | Deliverables | Titel | Start | Freeze | Change Control | Approval | primary responsible | % completion* | Comment
WI-0001 | Requirements | v1.4 | Draft | TS-0002 | Requirements |  |  |  |  | WG1 | n.a. | Rapporteur: Yu Qi, Huawei; WI to be closed;
|  |  |  | TR-0001 | Use Cases Collection |  |  |  |  | WG1 | n.a. | Rapporteur: Catalina Mladin, InterDigital
WI-0002 | Architecture | v1.4 | obsolete | TS-0001 | Functional Architecture |  |  |  |  | WG2 | n.a. | Rapporteur: Rajesh Bhalla, ZTE & Yingjie Hong, ZTE (CCSA)
|  |  |  | TR-0002 | Architecture Analysis Part1 |  |  |  |  | WG2 | n.a. | Rapporteur: Richard Brennan, Telxxis
|  |  |  | TR-0003 | Architecture Analysis Part2 |  |  |  |  | WG2 | n.a. | Rapporteur: Phillip Brown, InterDigital
WI-0003 | VocabPrinciples | v1.4 | Draft | TS-0011 | Common Terminology | TP#2 | TP#3 | TP#11 | TP#12 | WG1 | n.a. | Rapporteur: Roland Hechwartner, Deutsche Telekom
|  |  |  | TR-0005 | Roles and Focus Areas | TP#2 | TP#3 | TP#11 | TP#12 | WG1 | n.a. | Rapporteur: Josef Blanz, Qualcomm; TR-0005 - expected to be progressed; Then close of WI.
WI-0004 | Management_Capability_Enablement_Technologies | v1.1 | Approved | TR-0006 | Study of Capability Enablement Technologies for Consideration by oneM2M | TP#3 | TP#7 | TP#7 | TP#8 | WG5 | 100% | Rapporteur: Jiaxin Yin, Huawei
WI-0005 | Abstraction & Semantics Capability Enablement | v1.3 | Approved | TR-0007 | Study of Abstraction and Semantics Enablements | TP#16 | N/A | TP#19 | TP#20 | WG5 | 15% | Rapporteur: Joerg Swetina, NEC
|  |  |  | TS-0012 | Base Ontology | TP#16 | TP#18 | TP#19 | TP#20 | WG5 |  | TS-0012 is developed under WI-0025 (Generic Interworking with Area Networks)
|  |  |  | TS-0002 | Requirements | TP#16 | N/A | TP#18 | TP#19 | WG1 |  | Rapporteur: Yu Qi, Huawei
|  |  |  | TS-0001 | Functional Architecture | TP#18 | N/A | TP#20 | TP#21 | WG2
|  |  |  | TS-0003 | oneM2M Security Solutions | TP#18 | N/A | TP#20 | TP#21 | WG4
|  |  |  | TS-0004 | Service Layer Core Protocol | TP#20 | N/A | TP#22 | TP#23 | WG3 |  | and related protocol bindings
WI-0006 | Device_Gateway_Class | v1.3 | obsolete | TR-0010 | [6 empty] | n.a. | Rapporteur: Hongbeom Ahn, LGE
WI-0007 | Security | v1.4 | obsolete | TR-0008 | Analysis of security solutions | TP#5 | TP#9 | TP#9 | TP#10 | WG4 | n.a. | Rapporteur: Claus Dietze (G&D)
|  |  |  | TS-0003 | Security Solutions | TP#6 | TP#10 | TP#10 | TP#11 | WG4 | n.a. | Rapporteurs: Claus Dietze (G&D)
WI-0008 | Protocol-TR | v1.2 | Approved | TR-0009 v0.7.0 | Protocol Analysis | TP5 | TP9 | TP9 | TP10 | WG3 | 100% | Rapporteur: Richard Brennan, Telxxis
WI-0009 | Protocol-Development | v1.4 | obsolete | TS-0004 v0.7.1 | Service Layer Protocol Core Specification | TP#5 | TP#11 | TP#11 | TP#12 | WG3 | n.a.
WI-0010 | Management Enablement | v1.1 | Draft | TS-0005 v0.4.0 | Management enablement (OMA) | TP#8 | TP#11 | TP#11 | TP#12 | WG5 | n.a. | Rapporteur: SeungKyu Park, LG Electronics, Jiaxin Yin, Huawei; The work in the WI is based on the work in WG2 and has different focus compared to WG3
|  |  |  | TS-0006 v0.5.2 | Management enablement (BBF) | TP#8 | TP#11 | TP#11 | TP#12 | WG5 | n.a. | Rapporteur: Tim Carey, Alcatel-Lucent; The work in the WI is based on the work in WG2 and has different focus compared to WG3
WI-0011 | Service_Component_Architecture | v2.1 | Draft | TS-0007 v0.5.1 | Service Components | TP#9 | TP#15 | TP#15 | TP#17 | WG2 | 100% | Rapporteur: Tim Carey, Alcatel-Lucent
WI-0012 | ProCoapBinding | v1.1 | obsolete | TS-0008 v1.1 | CoAP Protocol Binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: SeongYoon Kim, LGE
WI-0013 | ProHttpBinding | v1.1 | obsolete | TS-0009 v0.6.0 | HTTP Protocol Binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: SeungMyeong Jeong, LGE
WI-0014 | ProMQTTBinding | v1.1 | obsolete | TS-0010 v0.3.0 | MQTT protocol binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: Peter Niblett, IBM
|  |  |  | TR-0011 | MQTT Protocol Interworking Study | TP#9 | TP#11 | TP#11 | TP#12 | WG2 | n.a. | Rapporteur: Peter Niblett, IBM
WI-0015 | Use Cases Collection | v1.2 | Draft | TR-0001 | Use Cases Collection | TP8 | TP8 | TPz | TPv | WG1 | n.a. | Rapporteur: Catalina Mladin, InterDigital; The “Freeze” and “Approval” dates in the above schedule will be determined when the Requirements TS “Freeze” and “Approval” dates are established.
WI-0016 | End-to-End Security and Group Authentication | v2.1 | Approved | TR-0012 v0.2.0 | End-to-End Security and Group Authentication | TP 12 | TP 19 | TP 20 | TP 21 | WG4 | 40% | Rapporteur: Ziyao Cheng, China Mobile
|  |  |  | CRs to TS 0002 | End-to-End Security and Group Authentication requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs to TS 0001 | oneM2M Function Architecture changes related to End-to-End Security and Group Authentication | n.a. | n.a. | n.a. | TP 20 | WG2
|  |  |  | CRs to TS-0003 | End-to-End Security and Group Authentication security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | CRs to TS-0004 | oneM2M Core Protocol changes related to End-to-End Security and Group Authentication | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0017 | Home Domain Enablement | v2.0.0 | Draft | TR-0013 | Home Domain Enablement | TP13 | -- | TP17 | TP18 | WG1 | 50% | Rapporteur: Sungchan Choi, KETI & Heedong Choi, LGE; Secondary responsibility by WG2, WG3, WG4, WG5.
|  |  |  | TR-0017 | Home Domain Abstract Information Model | TP16 | -- | TP20 | TP21 | WG5 |  | to be checked with portal
WI-0018 | oneM2M and AllJoyn Interworking | v1.1 | Approved | TR-0014 | oneM2M and AllJoyn Interworking | TP14 | - | TP18 | TP19 | WG2 | 70% | Rapporteur: Hongbeom Ahn, LGE & Yali Guo, Haier
WI-0019 | Dynamic Authorization for IoT | v1.1 | Approved | TR-0019 | Dynamic Authorization for IoT | TP 12 | TP 19 | TP 20 | TP 21 | WG4 | 5% | Rapporteur: Phil Hawkes, Qualcomm;
|  |  |  | CRs to TS 0002 | Dynamic Authorization requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs toTS 0001 | oneM2M Function Architecture changes related to Dynamic Authorization | n.a. | n.a. | n.a. | TP 20 | WG2
|  |  |  | CRs toTS-0003 | Dynamic Authorization security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | CRs toTS-0004 | oneM2M Core Protocol changes related to Dynamic Authorization | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0020 | Service_Layer_API | v1.0.0 | Draft | TR-0015 | Service Layer API Core Principles | TP#15 | - | TP#18 | TP#19 | WG3 | 5% | Rapporteur: X. He / to be checked with portal
[5 empty] | Service Layer API C Language Binding | TP#15 | - | TP#18 | TP#19 | WG3 |  | Rapporteur: X. He
WI-0021 | Secure Environment Abstraction | v1.1 | Draft | TS-0016 | Secure Environment Abstraction | TP 15 | TP 19 | TP 20 | TP 21 | WG4 | 10% | Rapporteur: Claus Dietze, Giesecke & Devrient
|  |  |  | CRs toTS 0002 | Secure Environment Abstraction requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs toTS 0001 | oneM2M Function Architecture changes related to Secure Environment Abstraction | n.a. | n.a. | n.a. | TP 20 | WG2
|  |  |  | CRs toTS-0003 | Secure Environment Abstraction security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | CRs toTS-0004 | oneM2M Core Protocol changes related to Secure Environment Abstraction | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0022 | Interoperability Testing | v1.1.0 | Draft | TS-0013 |  | n.a. | n.a. | n.a. |  |  | 80% | Rapporteur: Laurent Velez, ETSI
WI-0023 | Authorization Architecture & Access Control Policy | v1.2.0 | Approved | TR-0016 | Authorization Architecture and Policies | TP 15 | TP 19 | TP 20 | TP 21 | WG4 | 35% | to be checked with portal
|  |  |  | CRs to TS 0002 | Authorization Architecture and Policies requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs to TS 0001 | oneM2M Function Architecture changes related to End-to- Authorization Architecture and Policies | n.a. | n.a. | n.a. | TP 20 | WG2
|  |  |  | CRs to TS-0003 | Authorization Architecture and Policies security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | Crs to TS-0004 | oneM2M Core Protocol changes related to Authorization Architecture and Policies | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0024 | LWM2M Interworking | v0.1.1 | Draft | TS-0014 | LWM2M Interworking | TP#16 | TP#21 | TP#21 | TP#23 | WG2 | 40% | Rapporteur: Timothy Carey, Alcatel-Lucent ; TS is expected to incorporate Architecture Work.
|  |  |  | CRs to TS-0002 | oneM2M Requirements | TP#16 | N/A | TP#19 | N/A | WG1 |  | Change Requests to Requirements TS-0002 For LWM2M Interworking Requirements
WI-0025 | Generic Interworking | v2.1 | Approved | CRs to TR-0007 | CRs to include elaboration / enhancements for interworking (IPEs) | TP#15 | n/a | TP#17 | TP#18 | WG5 | 20%
|  |  |  | CRs toTS-0002 | CRs to include additional interworking reqs. | TP#15 | n/a | TP#17 | TP#17 | WG1
|  |  |  | CRs toTS-0012 | oneM2M_Base_Ontology | TP#15 | TP#18 | TP#19 | TP#20 | WG5
|  |  |  | CRs toTS-0001 | CRs to include functionality of IPEs | TP#17 | n/a | TP#19 | TP#20 | WG2
|  |  |  | CRs toTS-0003 | CRs to include security enhancements for support of IPEs | TP#17 | n/a | TP#19 | TP#20 | WG4
|  |  |  | CRs toTS-0004 | CRs to include protocol enhancements for support of IPEs | TP#19 | n/a | TP#20 | TP#21 | WG3
WI-0026 | Efficient Communications | v1.0.0 | Approved | CRs to TR-0001 | Use Cases Collection | TP#15 | n/a | TP#17 | TP#18 | WG1 | 5%
|  |  |  | CRs to TS-0002 | Requirements | TP#15 | n/a | TP#17 | TP#18 | WG1
|  |  |  | CRs to TS-0001 | Functional Architecture | TP#16 | n/a | TP#18 | TP#19 | WG2
|  |  |  | CRs to TS-0004 | Protocols TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0008 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0009 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0010 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0005 | Management TSs | TP#16 | n/a | TP#20 | TP#21 | WG5
|  |  |  | CRs to TS-0006 | Management TSs | TP#16 | n/a | TP#20 | TP#21 | WG5
WI-0027 | Testing Framework | v1.0.0 | Approved | TS-00xx | Test framework defining methodology for testing oneM2M specifications | TP#16 | TP#18 | TP#21 | TP#22 | WG6 | 30% | Rapporteur: Jiaxin Yin , Huawei Technologies
WI-0028 | Industrial Domain Enablement | v1.2.0 | Approved | TR-0018 | Industrial Domain Enablement | TP#16 | TP#20 | TP#20 | TP#21 | WG1 | 45% | Rapporteur: Toshiko Matsumoto, Hitachi Ltd
WI-0029 | App-ID Clarification | v1.0.0 | Approved | CRs to TS-0001 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG2 | 25% | Rapporteur: Darold Hemphill, iconectiv
|  |  |  | CRs to TS-0002 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG1
|  |  |  | CRs to TS-0003 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG4
|  |  |  | CRs to TS-0004 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG3
|  |  |  | CRs to TS-0011 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG1
WI-0030 | M2M Application & Field Domain Component Configuration | v1.0.0 | Approved | CRs to TS-0002 | Requirements regarding Device/Component Configuration | n.a. | n.a. | n.a. | TP 18 | REQ/ARC/SEC/MAS | 5% | Rapporteur: Shingo Fujimoto, FUJITSU
WI-0031 | Optimized Group-based Operation | v1.0.0 | Approved | CRs to TS-0002 | Group enhancement requirements | n.a. | n.a. | n.a. | TP#19 | WG1 | 10% | Rapporteur: Jiaxin Yin, Huawei Technologies Co., Ltd.
|  |  |  | CRs to TS-0001 | Enhancement in architecture | n.a. | n.a. | n.a. | TP#20 | WG2
|  |  |  | CRs to TS-0004 | Enhancement in protocol | n.a. | n.a. | n.a. | TP#21 | WG3
|  |  |  | CRs to TR-0001 | Group related use cases | n.a. | n.a. | n.a. | TP#19 | WG1
|  |  |  | CRs to TR-00012 | Potential CR related to group authentication | n.a. | n.a. | n.a. | TP#19 | WG4
WI-0032 | Conformance Test | v0.0.1 | Approved | TS-0017 | Implementation Conformance Statements | TP17 | TP21 | TP22 | TP26 | WG6 | 5% | Rapporteur: Sung-Chan Choi
|  |  |  | TS-0018 | Test Suite Structure and Test Purposes | TP17 | TP21 | TP24 | TP26 | WG6 |  | Rapporteur: Sung-Chan Choi
|  |  |  | TS-0019 | Abstract Test Suite and Implementation eXtra Information for Test | TP19 | TP23 | TP24 | TP26 | WG6 |  | Rapporteur: Laurent Velez
WI-0033 | Supporting Time Series Data | v0.0.1 | Approved | TS-0001 | Architecture to support the integrity of data collection monitoring in oneM2M | n.a. | n.a. | n.a. | TP#22 | WG2 | 0%
|  |  |  | TS-0004 | Procedure and data type to support the integrity of data collection monitoring in oneM2M | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0034 | Study of re-usable service layer context &Transaction enablement | v0.0.3 | Approved | TR-00xy | Study of service transactions and re-usable service layer context | TP#17 | TP 20 | TP 21 | TP 22 | WG2 | 0%
|  |  |  | CRs to TS-0001 | Architecture to support transaction in oneM2M | n.a. | n.a. | n.a. | TP#22 | WG2
|  |  |  | CRs to TS-0004 | Procedure and data type to support transaction in oneM2M | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0035 | Action Triggering | v0.0.1 | Approved | TR-00xx | Study of the action triggering in M2M | TP 18 | TP 21 | TP 22 | TP 23 | WG2 | 0%
|  |  |  | CRs to TS0001 | New resources definition to support action triggering | n.a. | n.a. | n.a. | TP22 | WG2
|  |  |  | CRs to TS0004 | Procedure and data type definition to support action triggering | n.a. | n.a. | n.a. | TP23 | WG3
WI-0036 | Update Security Analysis TR for Release 2 | v0.0.1 | Approved | TR-0008 | Outcome of the Release 2 specific threat analysis | n.a. | n.a. | n.a. | TP 19 | WG4 SEC | 0%
|  |  |  | TS-0003 | Impact of Release 2 Threat Analysis | n.a. | n.a. | n.a. | TP 20 | WG4
|  |  |  | TS-0001 | Architecture impact (if any) | n.a. | n.a. | n.a. | TP 20 | WG2
|  |  |  | TS-0004 | Protocol impact (if any) | n.a. | n.a. | n.a. | TP 21 | WG3
WI-0037 | 3GPP_Rel13_IWK | v0.0.1 | Approved | TR-00yx | 3GPP Rel-13 Interworking | TP#17 | n/a | TP#21 | TP#22 | WG2 | 0%
|  |  |  | CRs to TS-0001 |  | n.a. | n.a. | n.a. | TP#23 | WG2 |  | Depending on the conclusion of TR-00yx
WI-0038 | REL1_MNT | v0.0.1 | Approved | CRs to Rel1 TSs | Maintenance of oneM2M Release 1 Specifications (REL1_MNT) | n.a. | n.a. | n.a. |  | TP | n.a. | Maintenance of oneM2M Release 1 Specifications (REL1_MNT)
WI-0039 | REL2_STE | v0.0.1 | Approved | CRs to Rel2 TSs | Small Technical Enhancements of oneM2M Release 2 Specifications (REL2_STE) | n.a. | n.a. | n.a. |  | TP | n.a. | Small Technical Enhancements of oneM2M Release 2 Specifications (REL2_STE)
WI-0040 | Web-Socket-Binding | v0.0.1 | Approved | TS-00yy | WebSocket protocol binding | TP 18 | TP 20 | TP 22 | TP 23 | WG3 | 0%
WI-0041 | Subscription Notification | v0.0.1 | Draft | CRs to TS-0001 | subscription/notification mechanism non-blocking communication mechanism | n.a. | n.a. | n.a. | TP#20 | WG2 | 0%
|  |  |  | CRs to TS-0004 | subscription/notification mechanism non-blocking communication mechanism | n.a. | n.a. | n.a. | TP#21 | WG3
* status TP17 closure

## TSs
Nr | Title | appr. Rel 1 | latest Rel1 | Version Rel 2 | completion
TS-0001 | Functional Architecture | v1.6.0 | v1.9.0 | v2.1.0
TS-0002 | Requirements | v1.0.1 | v1.0.1 | v2.0.0
TS-0003 | Security Solutions | v1.0.1 | v1.1.0
TS-0004 | Service Layer Core Protocol | v1.0.1 | v1.1.0
TS-0005 | Management Enablement (OMA) | v1.0.1 | v1.0.1
TS-0006 | Management enablement (BBF) | v1.0.1 | v1.0.1
TS-0007 | Service Components | n.a. | n.a. | v0.8.1 | 100%
TS-0008 | CoAP Protocol Binding | v1.0.1 | v1.0.1
TS-0009 | HTTP Protocol Binding | v1.0.1 | v1.1.0
TS-0010 | MQTT protocol binding | v1.0.1 | v1.1.0
TS-0011 | Common Terminology | v1.2.1 | v1.3.0 | v2.1.1
TS-0012 | Base Ontology | n.a. | n.a. | v0.1.0
TS-0013 | Interoperability Testing | n.a. | v0.0.4
TS-0014 | LWM2M Interworking | n.a. | v0.2.0
TS-0015 | Testing Framework | n.a. | v0.2.0
TS-0016 | Secure Environment Abstraction | n.a. | v0.0.1
TS-0017 | Implementation Conformance Statements | n.a. | v0.0.1
TS-0018 | Test Suite Structure and Test Purposes | n.a. | v0.0.1
TS-0019 | Abstract Test Suite & implementation eXtra Information for Test | n.a. | v0.0.1

## TRs
Nr | Title | latest version | status | comment
TR-0001 | Use Cases Collection | v1.5.0 | Draft
TR-0002 | Architecture Analysis Part1 | v0.2.0 | Approved
TR-0003 | Architecture Analysis Part 2 | v0.5.0 | Approved
TR-0004 | Definitions and Acronyms | v0.4.0 | Stable Draft | obsolete; content moved to TS-0011 Common Terminology
TR-0005 | Roles and Focus Areas | v0.0.4 | Draft
TR-0006 | Study of Management Capability Enablement | v0.5.1 | Approved
TR-0007 | Study on Abstraction and Semantics Enablement | v1.1.0 | Draft
TR-0007 | Study on Abstraction and Semantics Enablement | v2.4.0 | Draft
TR-0008 | Security | v1.0.0 | Approved
TR-0009 | Protocol Analysis | v0.7.0 | Approved
TR-0010 | Device_Gateway_Classification | v0.0.0 | Draft | WI-0006 obsolete. TR not started
TR-0011 | MQTT Protocol Interworking Study | v0.1.0 | Draft
TR-0012 | End-to-End-Security and Group Authentication | v0.3.0 | Draft
TR-0013 | Home Domain Enablement | v0.2.1 | Draft
TR-0014 | oneM2M AllJoyn Interworking | v0.1.0 | Draft
TR-0015 | Service Layer API Core Principles | v0.1.0 | Draft
TR-0016 | Authorization Architecture and Access Control Policy | v0.1.1 | Draft
TR-0017 | Home Domain Abstract Information Model | v0.2.0 | Draft
TR-0018 | Industrial Domain Enablement | v0.1.1 | Draft
TR-0019 | Dynamic_Authorization | v0.0.1 | Draft

## ADM
Nr | Title | latest version | status | comment
ADM-0001 | oneM2M Work Programme | v12.0.0 | Draft | version number reflects corresponding # of TP meeting
ADM-0002 | oneM2M_Partnership_Agreement-V2_0 | v2 | Approved
ADM-0003 | oneM2M-Drafting-Rules | v1 | Approved
ADM-0004 | Method_of_work | v1.2.0 | Draft
ADM-0005 | oneM2M_Working_Procedures | v6.0 | Draft
ADM-0006 | Business Card Policy | v1.0.3 | Draft
ADM-0007 | Release Control Document-Aubergine | v1.0.0 | Draft
ADM-0008 | Release 1 Control Document | v1.0.0 | Draft
ADM-0009 | Test Event Working Procedure | v0.1 | Draft

## Timeline R2
Target Timeline for Release 2
2
TP15
Jan 2015
TP17
May 2015
TP18
July 2015
TP20
Nov 2015
TP23
May 2016
R1 Publication and ratification
TP15.1
R2 feature WIs
R2 work program
Marcom provides market view
Initial version of Release description - check list for release finalization
Target date for Stage 1 freeze R2
Essential Corrections - MNT
Small Technical Enhancements - STE (R2)
Target date for Stage 2 freeze R2
Target date for Stage 3 freeze R2
Source: TP-2015-0578R03-Release_2_planning_considerations

## History
History of Change
V0.0.0 | 2013-08-05 | First draft of new Work Programme Report
V0.1.0 | 2013-08-08 | Incorporation of Raporteur updates
V7.0.0 | 2013-10-18 | First draft of administrative perm document "oneM2M-ADM-0001-oneM2M_Work_Programme-V7_00_00"
V8.0.0 | 2013-12-12 | Input to TP#8 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - register ADM Text Part adapted to official ADM template (oneM2M-Template-ADM-20131008.doc)
V9.0.0 | 2014-02-21 | Input to TP#9 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0005R01 into register ADM Text Part
V10.0.0 | 2014-04-11 | Input to TP#10 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - conversion TR-0004 into TS-0011 according to CR TP-2014-0028 - update target dates for TS-0003 according to CR TP-2014-0029R1 - update target dates for TS-0007 according to CR TP-2014-0408 - update target dates for TR-0009 according to CR TP-2014-0417
V11.0.0 |  | Input to TP#11 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0008R01 into register ADM Text Part- update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E
V12.0.0 | 2014-08-01 | Input to TP#12 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - approved deliverables deleted from tracking registers B, C, D, E - new WI16 (TR 0012) incorporated
V17.0.0 | 2015-06-04 | Input post TP#17 : - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V17.1.0 | 2015-07-15 | Input prior TP18: - new register: R2 timeline - register WIs: added column level of completeness as of TP17