## ADM-0001 V 21.0.0
Administrative Document
ADM-0001-V-21.0.0
Title: oneM2M Work Programme
2016-01-22
Copyright Notification
No part may be reproduced except as authorized by written permission.
The copyright and the foregoing restriction extend to reproduction in all media.
This document is intended for distribution only to oneM2M Participants.
© oneM2M Partners Type 1 (ARIB, ATIS, CCSA, ETSI, TIA, TSDSI, TTA, TTC)
Contents
1 Scope ……………………………………………………………….…………………Page 3
2 References …………………………………………………………..…………...…...Page 3
2.1 Normative References ……………………………...……………………………….………………..… Page 3
2.2 Informative References ………………………………………………………...…………...……...…… Page 3
3 Definitions, symbols, abbreviations and acronyms ………………………….….....……Page 3
3.1 Definitions …………………………….……………………………………………………………........ Page 3
3.2 Symbols …………………………….………………………………………………………………...…. Page 3
3.3 Abbreviations, acronyms……………………………………………………………….…………...… Page 3
4 Conventions …………………………………………………………………..……… Page 3
5 oneM2M Work Programme ……………………..…………………………..……… Page 3
Annex A: Work Programme Overview …….………………………….………Register Wis
Annex B: List of Technical Specifications …………………………...…...…Register TSs
Annex C: List of Technical Reports …….……………………………..………Register TRs
Annex D: List ADM ………………...………………….……………...….…..Register ADMs
Annex E: Timeline Release 2...…………………………………………...……Register Timeline R2
Annex F: Work Item Progress…………………………………………...…….Register Progress R2
Annex G: Testing Work Item Progress………………………...………………Register Progress Testing
History of Change …………………………………………………….……….……… Register History
1 Scope
The present document is the “oneM2M Work Programme” referred to in Articles 31 in the Working Procedures Document [1], and addresses the Work Item reporting process within the Technical Plenary, its subordinate groups and the Secretariat to accomplish the tasks extracted from Article 12. In addition, the present document addresses processes to accomplish tasks not specifically identified in the Working Procedures Document but considered essential to the efficient operation of the Technical Plenary.
2 References
References are either specific (identified by date of publication and/or edition number or version number) or non specific. For specific references,only the cited version applies. For non-specific references, the latest version of the referenced document (including any amendments) applies.
2.1 Normative References
The following referenced documents are necessary for the application of the present document. [1] ADM-0002 oneM2M Partnership Agreement [2] ADM-0005 oneM2M Working Procedures Document [3] ADM-0004 Method of work
2.2 Informative References
The following referenced documents are not necessary for the application of the present document but they assist the user with regard to a particular subject area.
[i.1] ADM-0003 oneM2M Drafting Rules (http://member.onem2m.org/Static_pages/Others/Rules_Pages/oneM2M-Drafting-Rules-V1_0.doc)
3 Definitions and Abbreviations
For the present document the following apply:
3.1 Definitions
Approval: the decision of the Technical Plenary that a deliverable is ready for getting ratified in order to publish it (see process description in [2]).
Change Control: the decision of a Working Group that the content of a draft deliverable is sufficiently advanced that it will utilize the Change Control process (see process description in [2]).
Drafting:the editorial phase of a deliverable until it is placed under Change Control (see process description in [2]).
Forecast: the date estimation (best guess) for the required milestones of a deliverable based on the current state of it taking into account the level of completeness, risks and uncertainties
Freeze: the decision of a Working Group that the technical content of a draft deliverable is complete (given consideration of the Work Item scope and workplan), and it is frozen for further technical input (see process description in [2])
Level of Completeness:the estimation of how much of a deliverable has been already drafted in relation to the expected total amount being necessary for the approval
Milestone dates: dates for the main process corner stones of a deliverable specified in the respective Work Item documents (see process description in [2])
Start: means the beginning of drafting a deliverable
Target: a requested date for a deliverable which is specified in the respective Work Item document for all its main milestones
TP#n-1 means the last Technical Plenary meeting before the current one. The current one is the basis for an update of the Work Programme.
3.2 Abbreviations
ARC Architecture
Doc_ID Document Identifier
MAS Management, Abstraction and Semantics
REQ Requirements
SEC Security
TP Technical Plenary
TS Technical Specification
TST Testing
WI Work Item
WG Working Group
4 Conventions
Work Programme updates
Form for updating planning (Register WIs) - serves for updating forecasts of milestone dates and level of completeness by the respective rapporteurs of the deliverables. The dates in the target columns are taken from the actual revisions of the approved respective Work Item documents.
Scaling of level of completeness
• Value range from 0% - 100%, no special scaling requested. Highest level achievable in a WG is 95%
• Measurement will be against milestone “Approval” listed in the agreed respective Work Item (meaning that 100% completeness must be achieved for reaching this milestone)
• Expected levels of completeness at milestones:
Start - 0%
First draft / skeleton - 10%
Freeze - 90%
WG decision: “ready for approval” - 95%
(shall be achieved for the deliverable being presented to Technical Plenary for approval, rest of 5 % is considered as remaining editorial effort for producing the final revision, which is candidate for TP ratification, candidate for getting published by the Partners Type 1)
Approval (by TP) - 100%
5 oneM2M Work Programme
Please see also the WPM portal for the latest work program status.

## WIs
WI number | Title | Ver | Status | Deliverables | Title | Start | Change Control | Freeze | Approval | primary responsible | % completion TP21 closing | Comment | Supporting Companies
WI-0001 | Requirements | v1.4 | Approved | TS-0002 | Requirements |  |  |  |  | WG1 | n.a. | Rapporteur: Yu Qi, Huawei; WI to be closed;
|  |  |  | TR-0001 | Use Cases Collection |  |  |  |  | WG1 | n.a. | Rapporteur: Catalina Mladin, InterDigital
WI-0002 | Architecture | v1.4 | obsolete | TS-0001 | Functional Architecture |  |  |  |  | WG2 | n.a. | Rapporteur: Rajesh Bhalla, ZTE & Yingjie Hong, ZTE (CCSA)
|  |  |  | TR-0002 | Architecture Analysis Part1 |  |  |  |  | WG2 | n.a. | Rapporteur: Richard Brennan, Telxxis
|  |  |  | TR-0003 | Architecture Analysis Part2 |  |  |  |  | WG2 | n.a. | Rapporteur: Phillip Brown, InterDigital
WI-0003 | VocabPrinciples | v1.4 | Approved | TS-0011 | Common Terminology | TP#2 | TP#3 | TP#11 | TP#12 | WG1 | n.a. | Rapporteur: Roland Hechwartner, Deutsche Telekom | AT&T (ATIS), Deutsche Telekom (ETSI), Qualcomm Inc. (TIA), InterDigital Communications (TIA), Telecom Italia (ETSI), Vodafone (ETSI), Huawei Device Company (TIA), Intel (TIA), Sprint (TIA) , NEC Corporation (TTC), NEC Europe (ETSI)
|  |  |  | TR-0005 | Roles and Focus Areas | TP#2 | TP#3 | TP#11 | TP#12 | WG1 | n.a. | Rapporteur: Josef Blanz, Qualcomm; TR-0005 - expected to be progressed; Then close of WI.
WI-0004 | Management_Capability_Enablement_Technologies | v1.1 | Approved | TR-0006 | Study of Capability Enablement Technologies for Consideration by oneM2M | TP#3 | TP#7 | TP#7 | TP#8 | WG5 | 100% | Rapporteur: Jiaxin Yin, Huawei | Huawei (CCSA), NEC (ETSI), NEC (TTC), Alcatel-Lucent (ATIS), InterDigital (ETSI), Eurecom
WI-0005 | Abstraction & Semantics Capability Enablement | v1.3 | Approved | TR-0007 | Study of Abstraction and Semantics Enablements | TP#16 | N/A | TP#19 | TP#20 | WG5 | 90% | Rapporteur: Joerg Swetina, NEC
|  |  |  | TS-0012 | Base Ontology | TP#16 | TP#18 | TP#19 | TP#20 | WG5 |  | TS-0012 is developed under WI-0025 (Generic Interworking with Area Networks)
|  |  |  | TS-0002 | Requirements | TP#16 | N/A | TP#18 | TP#19 | WG1 |  | Rapporteur: Yu Qi, Huawei
|  |  |  | TS-0001 | Functional Architecture | TP#18 | N/A | TP#20 | TP#21 | WG2
|  |  |  | TS-0003 | oneM2M Security Solutions | TP#18 | N/A | TP#20 | TP#21 | WG4
|  |  |  | TS-0004 | Service Layer Core Protocol | TP#20 | N/A | TP#22 | TP#23 | WG3 |  | and related protocol bindings
WI-0006 | Device_Gateway_Class | v1.3 | obsolete | TR-0010 | [6 empty] | n.a. | Rapporteur: Hongbeom Ahn, LGE
WI-0007 | Security | v1.4 | obsolete | TR-0008 | Analysis of security solutions | TP#5 | TP#9 | TP#9 | TP#10 | WG4 | n.a. | Rapporteur: Claus Dietze (G&D)
|  |  |  | TS-0003 | Security Solutions | TP#6 | TP#10 | TP#10 | TP#11 | WG4 | n.a. | Rapporteurs: Claus Dietze (G&D)
WI-0008 | Protocol-TR | v1.2 | Approved | TR-0009 | Protocol Analysis | TP5 | TP9 | TP9 | TP10 | WG3 | 100% | Rapporteur: Richard Brennan, Telxxis
WI-0009 | Protocol-Development | v1.4 | obsolete | TS-0004 | Service Layer Protocol Core Specification | TP#5 | TP#11 | TP#11 | TP#12 | WG3 | n.a.
WI-0010 | Management Enablement | v1.1 | Approved | TS-0005 | Management enablement (OMA) | TP#8 | TP#11 | TP#11 | TP#12 | WG5 | n.a. | Rapporteur: SeungKyu Park, LG Electronics, Jiaxin Yin, Huawei; The work in the WI is based on the work in WG2 and has different focus compared to WG3 | Alcatel-Lucent (ETSI), Huawei Technologies Co., Ltd. (CCSA, ETSI), InterDigital Communications (ATIS), LG Electronics (TTA), NEC Europe (ETSI), Samsung Electornics (ETSI)
|  |  |  | TS-0006 | Management enablement (BBF) | TP#8 | TP#11 | TP#11 | TP#12 | WG5 | n.a. | Rapporteur: Tim Carey, Alcatel-Lucent; The work in the WI is based on the work in WG2 and has different focus compared to WG3
WI-0011 | Service_Component_Architecture | v2.1 | Approved | TS-0007 | Service Components | TP#9 | TP#15 | TP#15 | TP#17 | WG2 | 100% | Rapporteur: Tim Carey, Alcatel-Lucent | Alcatel-Lucent; AT&T; Verizon; Ericsson; ZTE; Orange; LG Electronics
WI-0012 | ProCoapBinding | v1.1 | obsolete | TS-0008 | CoAP Protocol Binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: SeongYoon Kim, LGE
WI-0013 | ProHttpBinding | v1.1 | obsolete | TS-0009 | HTTP Protocol Binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: SeungMyeong Jeong, LGE
WI-0014 | ProMQTTBinding | v1.1 | obsolete | TS-0010 | MQTT protocol binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: Peter Niblett, IBM | CISCO (ATIS/ETSI), Telefon AB LM Ericsson (ETSI), IBM (ETSI), Qualcomm (ARIB/ETSI), Sierra Wireless SA (ETSI), Telecom Italia SpA (ETSI)
|  |  |  | TR-0011 | MQTT Protocol Interworking Study | TP#9 | TP#11 | TP#11 | TP#12 | WG2 | n.a. | Rapporteur: Peter Niblett, IBM
WI-0015 | Use Cases Collection | v1.2 | Approved | TR-0001 | Use Cases Collection | TP8 | TP8 | n.a. | n.a. | WG1 | n.a. | Rapporteur: Catalina Mladin, InterDigital; The “Freeze” and “Approval” dates in the above schedule will be determined when the Requirements TS “Freeze” and “Approval” dates are established. | Sprint; Huawei; NEC; Telecom Italia; ZTE
WI-0016 | End-to-End Security and Group Authentication | v2.4.0 | Approved | TR-0012 | End-to-End Security and Group Authentication | TP 12 | TP 21 | TP 21 | TP 22 | WG4 | 85% | Rapporteur: ZUO Min (China Mobile) and QI Minpeng (China Mobile) for “End-to-End Security and Group Authentication” | British Telecom, China Mobile, CATT, Hitachi, Huawei, LG Electronics, Qualcomm
|  |  |  | CRs to TS 0002 | End-to-End Security and Group Authentication requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs to TS 0001 | oneM2M Function Architecture changes related to End-to-End Security and Group Authentication | n.a. | n.a. | n.a. | TP 21 | WG2
|  |  |  | CRs to TS-0003 | End-to-End Security and Group Authentication security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | CRs to TS-0004 | oneM2M Core Protocol changes related to End-to-End Security and Group Authentication | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0017 | Home Domain Enablement | v2.1.0 | Approved | TR-0013 | Home Domain Enablement | TP13 | -- | TP17 | TP18 | WG1 | 80% | Rapporteur: Sungchan Choi, KETI & Dongjoo KIM, LGE; Secondary responsibility by WG2, WG3, WG4, WG5. | KETI, LGE, ETRI, SK Telecom, LG uplus, nTels, KCA, Kaonmedia, Haier, InterDigital,NTT, KDDI, Fujitsu, Hitachi, NEC, Orange, Samsung Electronics
|  |  |  | TR-0017 | Home Domain Abstract Information Model | TP16 |  | TP20 | TP21 | WG5 |  | Satus as of TP21 cölosing:TR-0013: 80% (expected to be finalized by TP22) TR-0017: 99% (expected to be approved at TP21) TS-0023: 60% (expected to be finalized by TP23)
|  |  |  | TS-0023 | Home Appliances Information Model and Mapping | TP19 | -- | TP21 | TP22 | WG5
|  |  |  | TS-0002 | Normative CRs to Requirements | n.a. | n.a. | n.a. | TP18 | WG1
|  |  |  | TS-0001 | Normative CRs to Functional Architecture | n.a. | n.a. | n.a. | TP21 | WG2
|  |  |  | TS-0004 | Normative CRs to Core Protocol | n.a. | n.a. | n.a. | TP21 | WG3
WI-0018 | oneM2M and AllJoyn Interworking | v1.3.0 | Approved | TR-0014 | oneM2M and AllJoyn Interworking | TP14 | - | TP18 | TP19 | WG2 | 90% | WI Rapporteur: SeungMyeong JEONG, LG Electronics | LG Electronics, Qualcomm, LG U+, Haier, AT&T, Huawei, ALU
|  |  |  | TS-0021 | oneM2M and AllJoyn Interworking | TP19 |  | TP22 | TP23 | WG2
|  |  |  | CRs to TS-0001 | Normative texts to include the solutions studied in the TR-0014 | n.a. | n.a. | n.a. |  | WG2
|  |  |  | CRs to TS-0004 | Normative texts to include the solutions studied in the TR-0014 | n.a. | n.a. | n.a. |  | WG3
WI-0019 | Dynamic Authorization for IoT | v1.3.0 | Approved | TR-0019 | Dynamic Authorization for IoT | TP 12 | TP 21 | TP 21 | TP 22 | WG4 | 75% | Rapporteur: Phil Hawkes, Qualcomm; | Gemalto NV, LG Electronics, CATT, Interdigital, Qualcomm, Oberthur Technologies, Giesecke & Devrient
|  |  |  | CRs to TS 0002 | Dynamic Authorization requirements | n.a. | n.a. | n.a. | TP 18 | WG1 |  | WI-0019: Dynamic Authorization for IoT: 75% • 55% completion of TR-0019 “Dynamic Authorization for IoT”. No change: It is at 55% complete, • 90% completion of changes TS-0001 Functional Architecture. Previously at 0%. • 90% completion of stage 2 changes to TS-0003 Security. Previously at 0%. • The remaining 25% is for work on TR-0019 and stage 3 work in TS-0003 and TS-0004.
|  |  |  | CRs toTS 0001 | oneM2M Function Architecture changes related to Dynamic Authorization | n.a. | n.a. | n.a. | TP 21 | WG2
|  |  |  | CRs toTS-0003 | Dynamic Authorization security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4 |  | If needed, this deadline can slip to TP 23
|  |  |  | CRs toTS-0004 | oneM2M Core Protocol changes related to Dynamic Authorization | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0020 | Service_Layer_API | v1.0.0 | Approved | TR-0015 | Service Layer API Core Principles | TP#15 | - | TP#18 | TP#19 | WG3 | 5% | Rapporteur: vacant; @TP22assessment whether to close WI | Sierra Wireless, Ericsson, LG Electronics, ZTE, Interdigital, AT&T, NEC, Hitachi
|  |  |  | TR-00xx | Service Layer API C Language Binding | TP#15 | - | TP#18 | TP#19 | WG3 |  | Rapporteur: vacant
WI-0021 | Secure Environment Abstraction | v1.2.0 | Approved | TS-0016 | Secure Environment Abstraction | TP 15 | TP 21 | TP 22 | TP 23 | WG4 | 30% | Rapporteur: Claus Dietze, Giesecke & Devrient | Giesecke & Devrient, Gemalto NV, Oberthur Technologies, Interdigital, CATT, LG Electronics
|  |  |  | CRs toTS 0002 | Secure Environment Abstraction requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs toTS 0001 | oneM2M Function Architecture changes related to Secure Environment Abstraction | n.a. | n.a. | n.a. | TP 21 | WG2
|  |  |  | CRs toTS-0003 | Secure Environment Abstraction security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | CRs toTS-0004 | oneM2M Core Protocol changes related to Secure Environment Abstraction | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0022 | Interoperability Testing | v1.1.0 | Approved | TS-0013 | Interoperability Testing | n.a. | n.a. | n.a. | TP25 | WG6 | 100% | Rapporteur: Laurent Velez, ETSI | KETI, KCA, NEC, InterDigital
WI-0023 | Authorization Architecture & Access Control Policy | v1.4.0 | Approved | TR-0016 | Authorization Architecture and Policies | TP 15 | TP 21 | TP 21 | TP 22 | WG4 | 80% | Wei Zhou, Datang (CCSA); Secondary responsibility WG3, WG2 | Datang, China Unicom, CATR, ZTE , Huawei, Haier, Gemalto NV
|  |  |  | CRs to TS 0002 | Authorization Architecture and Policies requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs to TS 0001 | oneM2M Function Architecture changes related to End-to- Authorization Architecture and Policies | n.a. | n.a. | n.a. | TP 21 | WG2
|  |  |  | CRs to TS-0003 | Authorization Architecture and Policies security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | Crs to TS-0004 | oneM2M Core Protocol changes related to Authorization Architecture and Policies | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0024 | LWM2M Interworking | v0.1.1 | Approved | TS-0014 | LWM2M Interworking | TP#16 | TP#21 | TP#21 | TP#23 | WG2 | 85% | Rapporteur: Timothy Carey, Alcatel-Lucent ; TS is expected to incorporate Architecture Work. | Alcatel-Lucent (TIA, ATIS), Gemalto (ETSI), Eurecom (ETSI) Huawei (CCSA), LG Electronics (TTA), InterDigital (ATIS), Sierra Wireless (ETSI), Ericsson (ETSI), KDDI (TTC)
|  |  |  | CRs to TS-0002 | oneM2M Requirements | TP#16 | N/A | TP#19 | N/A | WG1 |  | Change Requests to Requirements TS-0002 For LWM2M Interworking Requirements
|  |  |  | CRs to TS-0001 | Modifications to the oneM2M Architecture is not expected. |  |  |  |  | WG2
|  |  |  | CRs to TS-0004 | Modifications to the oneM2M Protocols is not epected |  |  |  |  | WG3
|  |  |  | CRs to TR-0001 | Modifications to Use cases is not expected |  |  |  |  | WG1
WI-0025 | Generic Interworking | v2.1 | Approved | CRs to TR-0007 | CRs to include elaboration / enhancements for interworking (IPEs) | TP#15 | n/a | TP#17 | TP#18 | WG5 | 85% | Rapporteur: Joerg Swetina, NEC | NEC, China Unicom, Modacom, KETI, EURECOM, InterDigital, Alcatel-Lucent
|  |  |  | CRs toTS-0002 | CRs to include additional interworking reqs. | TP#15 | n/a | TP#17 | TP#17 | WG1
|  |  |  | CRs toTS-0012 | oneM2M_Base_Ontology | TP#15 | TP#18 | TP#19 | TP#20 | WG5
|  |  |  | CRs toTS-0001 | CRs to include functionality of IPEs | TP#17 | n/a | TP#19 | TP#20 | WG2 |  | … exception needed for ARC part
|  |  |  | CRs toTS-0003 | CRs to include security enhancements for support of IPEs | TP#17 | n/a | TP#19 | TP#20 | WG4
|  |  |  | CRs toTS-0004 | CRs to include protocol enhancements for support of IPEs | TP#19 | n/a | TP#20 | TP#21 | WG3
WI-0026 | Efficient Communications | v1.0.0 | Approved | CRs to TR-0001 | Use Cases Collection | TP#15 | n/a | TP#17 | TP#18 | WG1 | 60% | Rapporteur: Josef Blanz, Qualcomm | Qualcomm, Sierra Wireless, Gemalto, Telia Sonera, Deutsche Telekom, Orange, KDDI, Interdigital
|  |  |  | CRs to TS-0002 | Requirements | TP#15 | n/a | TP#17 | TP#18 | WG1
|  |  |  | CRs to TS-0001 | Functional Architecture | TP#16 | n/a | TP#18 | TP#19 | WG2
|  |  |  | CRs to TS-0004 | Protocols TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0008 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0009 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0010 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0005 | Management TSs | TP#16 | n/a | TP#20 | TP#21 | WG5
|  |  |  | CRs to TS-0006 | Management TSs | TP#16 | n/a | TP#20 | TP#21 | WG5
WI-0027 | Testing Framework | v1.0.0 | Approved | TS-0015 | Test framework defining methodology for testing oneM2M specifications | TP#16 | TP#18 | TP#21 | TP#22 | WG6 | 70% | Rapporteur: Jiaxin Yin , Huawei Technologies | KETI, Dt&C, Huawei Technologies, LG Electronics, iconectiv, Sierra Wireless
WI-0028 | Industrial Domain Enablement | v1.4.1 | Approved | TR-0018 | Industrial Domain Enablement | TP#16 | TP#20 | TP#20 | TP#21 | WG1 | 95% | Rapporteur: Miao Jiang, Hitachi (China) Research &Development Corporation (CCSA), Toshiko Matsumoto, Hitachi (TTC), and Yanping Jiang, Huawei (CCSA) | Hitachi, Huawei, KDDI, Telecom Itallia SpA, NTT, NEC, InterDigital, KETI, Federal Network Agency (BNetzA)
|  |  |  | CRs to TS-0002 |  |  | n.a. | n.a. | TP#18 | WG1
|  |  |  | CRs toTS-0001 | Architecture impact from industrial domain enablement | n.a. | n.a. | n.a. |  | WG2
|  |  |  | CRs toTS-0004 | Protocol impact from industrial domaine enablement | n.a. | n.a. | n.a. |  | WG3
WI-0029 | App-ID Clarification | v1.1.0 | Approved | CRs to TS-0001 | App-Id clarification | n.a. | n.a. | n.a. | TP#20 | WG2 | 90% | Rapporteur: Darold Hemphill, iconectiv | Fujitsu Ltd. (TTC), iconectiv (ATIS), Gemalto (ETSI),Sierra Wireless (ETSI)
|  |  |  | CRs to TS-0002 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG1
|  |  |  | CRs to TS-0003 | App-Id clarification | n.a. | n.a. | n.a. | TP#23 | WG4
|  |  |  | CRs to TS-0004 | App-Id clarification | n.a. | n.a. | n.a. | TP#23 | WG3
|  |  |  | CRs to TS-0011 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG1
WI-0030 | M2M Application & Field Domain Component Configuration | v1.1.1 | Approved | CRs to TS-0002 | Requirements regarding Device/Component Configuration | n.a. | n.a. | n.a. | TP 18 | REQ/ARC/SEC/MAS | 50% | Rapporteur: Shingo Fujimoto, FUJITSU | FUJITSU(TTC), Deutsche Telekom AG (ETSI), Telecom Italia SpA (ETSI), InterDigital Communications (TIA), Alcatel-Lucent (TIA)
|  |  |  | TS-0022 | Field Device Configuration | TP19 | TP22 | TP22 | TP24 | WG5 |  | Impacted WGs: ARC, PRO, SEC, TST
WI-0031 | Optimized Group-based Operation | v1.0.0 | Approved | CRs to TS-0002 | Group enhancement requirements | n.a. | n.a. | n.a. | TP#19 | WG1 | 50% | Rapporteur: Jiaxin Yin, Huawei Technologies Co., Ltd. | Huawei Technologies Co., Ltd.; InterDigital; KETI; China Unicom
|  |  |  | CRs to TS-0001 | Enhancement in architecture | n.a. | n.a. | n.a. | TP#20 | WG2
|  |  |  | CRs to TS-0004 | Enhancement in protocol | n.a. | n.a. | n.a. | TP#21 | WG3
|  |  |  | CRs to TR-0001 | Group related use cases | n.a. | n.a. | n.a. | TP#19 | WG1
|  |  |  | CRs to TR-00012 | Potential CR related to group authentication | n.a. | n.a. | n.a. | TP#19 | WG4
WI-0032 | Conformance Test | v0.0.1 | Approved | TS-0017 | Implementation Conformance Statements | TP17 | TP21 | TP22 | TP26 | WG6 | 39% | Rapporteur: Sung-Chan Choi, KETI | Huawei Technologies Co., Ltd., KETI, TTA, Telecom Italia, China Unicom, Dt&C, NTT
|  |  |  | TS-0018 | Test Suite Structure and Test Purposes | TP17 | TP21 | TP24 | TP26 | WG6 |  | Rapporteur: Sung-Chan Choi, KETI
|  |  |  | TS-0019 | Abstract Test Suite and Implementation eXtra Information for Test | TP19 | TP23 | TP24 | TP26 | WG6 |  | Rapporteur: Laurent Velez, ETSI
WI-0033 | Supporting Time Series Data | v0.0.1 | Approved | TS-0001 | Architecture to support the integrity of data collection monitoring in oneM2M | n.a. | n.a. | n.a. | TP#22 | WG2 | 60% | Rapporteur: Qi Yu, Huawei Technologies Co., Ltd | Huawei Technologies, Hitachi , Haier, China Unicom, China academy of information and communications technology
|  |  |  | TS-0004 | Procedure and data type to support the integrity of data collection monitoring in oneM2M | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0034 | Study of re-usable service layer context &Transaction enablement | v0.0.3 | Approved | TR-0020 | Study of service transactions and re-usable service layer context | TP#17 | TP 20 | TP 21 | TP 22 | WG2 | 20% | Rapporteurs: Qiuting Li, ZTE & Jiaxin Yin, Huawei | LGE, ZTE, InterDigital, Spirent, Huawei, IBM, ALU
|  |  |  | CRs to TS-0001 | Architecture to support transaction in oneM2M | n.a. | n.a. | n.a. | TP#22 | WG2
|  |  |  | CRs to TS-0004 | Procedure and data type to support transaction in oneM2M | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0035 | Action Triggering | v0.0.1 | Approved | TR-0021 | Study of the action triggering in M2M | TP 18 | TP 21 | TP 22 | TP 23 | WG2 | 40% | Rapporteur: Jiaxin Yin, Huawei | Huawei Technologies Co., Ltd.; Fujitsu; LGE; Qualcomm
|  |  |  | CRs to TS0001 | New resources definition to support action triggering | n.a. | n.a. | n.a. | TP22 | WG2
|  |  |  | CRs to TS0004 | Procedure and data type definition to support action triggering | n.a. | n.a. | n.a. | TP23 | WG3
WI-0036 | Update Security Analysis TR for Release 2 | v0.0.1 | Approved | TR-0008 | Outcome of the Release 2 specific threat analysis | n.a. | n.a. | n.a. | TP 19 | WG4 SEC | n.a. | Rapporteur: Dragan Vujcic, Oberthur Technologies | Giesecke & Devrient, Gemalto, BT Group, Oberthur Technologies, Datang
|  |  |  | TS-0003 | Impact of Release 2 Threat Analysis | n.a. | n.a. | n.a. | TP 20 | WG4
|  |  |  | TS-0001 | Architecture impact (if any) | n.a. | n.a. | n.a. | TP 20 | WG2
|  |  |  | TS-0004 | Protocol impact (if any) | n.a. | n.a. | n.a. | TP 21 | WG3
WI-0037 | 3GPP_Rel13_IWK | v1.0.1 | Approved | TR-0024 | 3GPP Rel-13 Interworking | TP#17 | n/a | TP#21 | TP#22 | WG2 | 40% | Rapporteur: Shao Weixiang (ZTE), | Intel, AT&T, ZTE, Telecom Italia, Sierra Wireless, NEC, Huawei, LG Electronics, China Unicom, Qualcomm, KDDI, Orange
|  |  |  | CRs to TS-0001 |  | n.a. | n.a. | n.a. | TP#23 | WG2 |  | Depending on the conclusion of TR-0024
WI-0038 | Maintanance of oneM2M release 1 (REL1_MNT) | v0.0.1 | Approved | CRs to Rel1 TSs | Maintenance of oneM2M Release 1 Specifications (REL1_MNT) | n.a. | n.a. | n.a. |  | TP | n.a. | Maintenance of oneM2M Release 1 Specifications (REL1_MNT)
WI-0039 | Small Technical Enhancements of oneM2M release 2 Specifications (REL2_STE) | v0.0.1 | Approved | CRs to Rel2 TSs | Small Technical Enhancements of oneM2M Release 2 Specifications (REL2_STE) | n.a. | n.a. | n.a. |  | TP | n.a. | Small Technical Enhancements of oneM2M Release 2 Specifications (REL2_STE)
WI-0040 | Web-Socket-Binding | v0.0.1 | Approved | TS-0020 | WebSocket protocol binding | TP 18 | TP 20 | TP 22 | TP 23 | WG3 | 50% | Rapporteur: Shingo Fujimoto, Fujitsu | FUJITSU(TTC), Qualcomm Inc.(TIA), Huawei(CCSA/ETSI), SIERRA WIRELESS(ETSI), Telecom Italia(ETSI), InterDigital (ATIS)
WI-0041 | Subscription Notification | v0.0.1 | Approved | CRs to TS-0001 | subscription/notification mechanism non-blocking communication mechanism | n.a. | n.a. | n.a. | TP#20 | WG2 | 90% | Rapporteur: SeungMyeong Jeong, LGE | LG Electronics, Huawei Technologies, Qualcomm, Ericsson
|  |  |  | CRs to TS-0004 | subscription/notification mechanism non-blocking communication mechanism | n.a. | n.a. | n.a. | TP#21 | WG3
WI-0042 | Application developer guide | v1.0.0 | Approved | TR-0025 | Application developer guide | TP 19 | TP 22 | TP 23 | TP 25 | WG6 | 100% | Rapporteur: Laurent Velez (ETSI) | KETI, LAAS-CNRS, Huawei Technologies Co. Ltd, iconectiv, Fujitsu Ltd., LG Electronics, KDDI Corporation
WI-0043 | Continuation & integration of HGI Smart Home activities | v1.0.1 | Approved | TR-0022 | Continuation & integration of HGI Smart Home activities | TP19 | - | TP21 | TP22 | WG5 | 55% | Rapporteur: Patricia Martigne (Orange); Some HGI SH items are expected to be forwarded to different oneM2M WGs, but WG5 has the responsibility to keep track of the whole transfer. | Orange, Huawei, DT, NEC, Telecom Italia, Modacom, AT&T
|  |  |  | CRs to TR-0007 | CR to Abstraction & Semantic TR to take into account HGI SH architecture deliverable |  | n.a. | n.a. | TP#20 | WG5
|  |  |  | CRs to TR-0017 | CR to Home Information Model TR based on HGI SDT evolution |  | n.a. | n.a. | TP#20 | WG5
|  |  |  | CRs to TS-0001 | CR to oneM2M architecture based on analysis detailed in TR-0022 |  | n.a. | n.a. | TP#20 | WG2
|  |  |  | CRs to TS-0023 | CR to Home Abstract Information model to take into account HGI SDT |  | n.a. | n.a. | TP#21 | WG5
|  |  |  | CRs to TS-0012 | CR to oneM2M base ontology |  | n.a. | n.a. | TP#21 | WG5
WI-0044 | oneM2M OIC Interworking | v1.1.0 | Approved | CRs to TS-0002 | Requirements for information model | n.a. | n.a. | n.a. | TP18 | WG1 | 90% | Rapporteur: Kiran Vedula, Samsung Electronics | Samsung Electronics, Intel, Fujitsu, MODACOM, DT&C, KDDI, TeliaSonera, IFAST, Orange, KETI, MediaTek, HITACHI, Cisco
|  |  |  | TR-0023 | oneM2M and OIC Interworking | TP#18 | - | TP#20 | TP#21 | WG2
|  |  |  | TS-0024 | oneM2M and OIC Interworking | TP#20 | n.a. | TP#21 | TP#22 | WG2
|  |  |  | CRs to TS-0001 | oneM2M functional architecture | n.a. | n.a. | n.a. | TP#21 | WG2
|  |  |  | CRs to TS-0004 | Service layer core specification | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0045 | Addition of Interoperable Privacy Profiles to oneM2M Security Solutions TS 0003 | v1.0.0 | Approved | CRs to TS-0003 | 1. To store and process privacy preferences in an interoperable manner. 2. To support privacy profiles at various levels to care for conditions of legal requirements, manufacturers, and data subjects. 3. To prioritise privacy profiles where there is a conflict between profiles | TP#19 | n.a. | n.a. | TP#23 | WG4 | 5% | Rapporteur: Colin Blanchard, BT Group | BT Group Plc.; Cadzow Communications Consulting Ltd.; Datang Telecom Technology@Industry Holdings Co., LTD; KDDI Corporation
WI-0046 | Vehicular domain enablement | v1.0.0 | Approved | TR-0026 | Vehicular Domain Enablement | TP#20 | n.a. | TP 27 | TP 28 | WG1,WG2 | 20% | Rapporteurs: Hiroyuki Kubo (Hitachi Ltd.), Jiaxin Yin (Huawei Technologies, Co. Ltd), DongJoo Kim (LG Electronics) | Hitachi, KDDI, Toyota ITC, Huawei Technologies, Co. Ltd., LG Electronics, NEC, China Unicom, Samsung

## TSs
Nr | Title | appr. Rel 1 | latest Rel1 | Version Rel 2 | Rapporteur | Comment
TS-0001 | Functional Architecture | v1.6.0 | v1.12.1 | v2.5.0 | Rajesh Bhalla, ZTE & Yingjie Hong, ZTE
TS-0002 | Requirements | v1.0.1 | v1.0.1 | v2.4.0 | Yu Qi, Huawei
TS-0003 | Security Solutions | v1.0.1 | v1.4.0 |  | Claus Dietze, Giesecke & Devrient
TS-0004 | Service Layer Core Protocol | v1.0.1 | v1.3.0 | v2.1.0 | Shingo Fujimoto, Fujitsu
TS-0005 | Management Enablement (OMA) | v1.0.1 | v1.3.0 |  | SeungKyu Park, LG Electronics & Jiaxin Yin, Huawei
TS-0006 | Management enablement (BBF) | v1.0.1 | v1.1.3 |  | Tim Carey, Alcatel-Lucent
TS-0007 | Service Components | n.a. | n.a. | v0.8.1 | Tim Carey, Alcatel-Lucent
TS-0008 | CoAP Protocol Binding | v1.0.1 | v1.2.0 |  | SeongYoon Kim, LGE
TS-0009 | HTTP Protocol Binding | v1.0.1 | v1.3.0 | v2.1.0 | SeungMyeong Jeong, LGE
TS-0010 | MQTT protocol binding | v1.0.1 | v1.3.0 |  | Peter Niblett, IBM
TS-0011 | Common Terminology | v1.2.1 | v1.3.0 | v2.3.0 | Roland Hechwartner, Deutsche Telekom
TS-0012 | Base Ontology | n.a. | n.a. | v0.6.0 | Joerg Swetina, NEC
TS-0013 | Interoperability Testing | n.a. | v0.4.2 |  | Laurent Velez, ETSI
TS-0014 | LWM2M Interworking | n.a. | v0.8.0 |  | Timothy Carey, Alcatel-Lucent
TS-0015 | Testing Framework | n.a. | v0.3.0 |  | Jiaxin Yin , Huawei Technologies
TS-0016 | Secure Environment Abstraction | n.a. | v0.3.0 |  | Claus Dietze, Giesecke & Devrient
TS-0017 | Implementation Conformance Statements | n.a. | v0.0.4 |  | Sungchan Choi, KETI
TS-0018 | Test Suite Structure and Test Purposes | n.a. | v0.0.6 |  | Sungchan Choi, KETI
TS-0019 | Abstract Test Suite & implementation eXtra Information for Test | n.a. | v0.0.1 |  | Laurent Velez, ETSI
TS-0020 | WebSocket Protocol Binding | n.a. | v0.2.0 |  | Shingo Fujimoto, Fujitsu
TS-0021 | oneM2M and AllJoyn Interworking | n.a. | n.a. | v0.0.1 | SeungMyeong Jeong, LGE
TS-0022 | Field Device Configuration | n.a. | n.a. | v0.2.0 | Shingo Fujimoto, Fujitsu
TS-0023 | Home Appliances Information Model and Mapping | n.a. | n.a. | v0.2.0 | Dongjoo KIM, LGE
TS-0024 | oneM2M and OIC Interworking | n.a. | n.a. | v0.0.1 | Kiran Vedula, Samsung

## TRs
Nr | Title | latest version | status | Rapporteur | comment
TR-0001 | Use Cases Collection | v1.8.0 | Draft | Catalina Mladin, InterDigital
TR-0002 | Architecture Analysis Part1 | v0.2.0 | Approved | Richard Brennan, Telxxis
TR-0003 | Architecture Analysis Part 2 | v0.5.0 | Approved | Phillip Brown, InterDigital
TR-0004 | Definitions and Acronyms | v0.4.0 | Stable Draft | n.a. | obsolete; content moved to TS-0011 Common Terminology
TR-0005 | Roles and Focus Areas | v0.0.4 | Draft | Josef Blanz, Qualcomm
TR-0006 | Study of Management Capability Enablement | v0.5.1 | Approved | Jiaxin Yin, Huawei
TR-0007 | Study on Abstraction and Semantics Enablement | v2.8.0 | Draft | Joerg Swetina, NEC
TR-0008 | Security | v1.0.0 | Approved | Dragan Vujcic, Oberthur
TR-0009 | Protocol Analysis | v0.7.0 | Approved | Richard Brennan, Telxxis
TR-0010 | Device_Gateway_Classification | v0.0.0 | Draft | Hongbeom Ahn, LGE | WI-0006 obsolete. TR not started
TR-0011 | MQTT Protocol Interworking Study | v0.1.0 | Draft | Peter Niblett, IBM
TR-0012 | End-to-End-Security and Group Authentication | v0.8.0 | Draft | Ziyao Cheng, China Mobile
TR-0013 | Home Domain Enablement | v0.4.0 | Draft | Sungchan Choi, KETI & Dongjoo KIM, LGE
TR-0014 | oneM2M AllJoyn Interworking | v0.4.0 | Draft | SeungMyeong JEONG, LG Electronics
TR-0015 | Service Layer API Core Principles | v0.1.0 | Draft | Xuan He, Hitachi
TR-0016 | Authorization Architecture and Access Control Policy | v0.5.0 | Draft | Wei Zhou, Datang
TR-0017 | Home Domain Abstract Information Model | v0.8.0 | Draft | Sungchan Choi, KETI & Dongjoo KIM, LGE
TR-0018 | Industrial Domain Enablement | v0.4.0 | Draft | Toshiko Matsumoto, Hitachi Ltd
TR-0019 | Dynamic_Authorization | v0.0.1 | Draft | Phil Hawkes, Qualcomm
TR-0020 | Study of service transactions and re-usable service layer context | v0.2.0 | Draft | Qiuting Li, ZTE
TR-0021 | Study of the action triggering in M2M | v0.2.0 | Draft | Jiaxin Yin, Huawei Technologies Co.,Ltd
TR-0022 | Continuation and Integration of HGI Smart Home activities | v0.3.0 | Draft | Patricia Martigne, ORANGE
TR-0023 | oneM2M and OIC Interworking | v0.1.0 | Draft | Kiran Vedula, Samsung Electronics
TR-0024 | 3GPP_Rel13_IWK | v0.1.0 | Draft | Shao Weixiang, ZTE
TR-0025 | Application Developer Guide | v0.1.3 | Draft | Laurent Velez, ETSI
TR-0026 | Vehicular Domain Enablement | v0.1.0 | Draft | Hiroyuki Kubo (Hitachi Ltd.), Jiaxin Yin (Huawei Technologies, Co. Ltd), DongJoo Kim (LG Electronics)

## ADM
Nr | Title | latest version | status | comment
ADM-0001 | oneM2M Work Programme | v21.0.0 | Draft | version number reflects corresponding # of TP meeting
ADM-0002 | oneM2M Partnership Agreement-V2_0 | v2 | Approved
ADM-0003 | oneM2M-Drafting-Rules | v1 | Approved
ADM-0004 | Method of Work | v1.4.0 | Approved
ADM-0005 | oneM2M Working Procedures | v7.0 | Draft
ADM-0006 | Business Card Policy | v1.0.3 | Draft
ADM-0007 | Release Control Document-Aubergine | v1.0.0 | Draft
ADM-0008 | Release 1 Control Document | v1.0.0 | Draft
ADM-0009 | Test Event Working Procedure | v0.1 | Draft
ADM-0010 | Release 2 Description Document | v0.4.0 | Draft
ADM-0011 | Method of Work-v1.3.2 | v1.3.2 | Draft | latest version

## Progress R2
oneM2M Release 2 schedule
Freeze Dates: Stage 1 TP#18 - Stage 2 TP#21* - Stage 3 TP#23
Work Item Progress
WI number | Title | % completion TP17 | % completionTP18 | % completion TP19 | % completion TP20 | % completion TP21
WI-0005 | Abstraction & Semantics Capability Enablement | 15% | 20% | 30% | 50% | 90%
WI-0016 | End-to-End Security and Group Authentication | 40% | 60% | 70% | 85% | 85%
WI-0017 | Home Domain Enablement | 50% | 50% | 60% | 70% | 80%
WI-0018 | oneM2M and AllJoyn Interworking | 70% | 70% | 70% | 75% | 90%
WI-0019 | Dynamic Authorization for IoT | 5% | 20% | 35% | 55% | 75%
WI-0020 | Service Layer API | 5% | 5% | 5% | 5% | 5%
WI-0021 | Secure Environment Abstraction | 10% | 20% | 25% | 30% | 30%
WI-0023 | Authorization Architecture & Access Control Policy | 35% | 40% | 60% | 80% | 80%
WI-0024 | LWM2M Interworking | 40% | 40% | 50% | 75% | 85%
WI-0025 | Generic Interworking | 20% | 30% | 40% | 75% | 85%
WI-0026 | Efficient Communications | 5% | 5% |  | 60% | 60%
WI-0028 | Industrial Domain Enablement | 45% | 65% | 80% | 90% | 95%
WI-0029 | App-ID Clarification | 25% | 30% | 70% | 75% | 90%
WI-0030 | M2M Application & Field Domain Component Configuration | 5% | 30% | 35% | 45% | 50%
WI-0031 | Optimized Group-based Operation | 10% | 20% | 30% | 30% | 50%
WI-0033 | Supporting Time Series Data | 0% | 40% | 30% | 60% | 60%
WI-0034 | Study of re-usable service layer context &Transaction enablement | 0% | 10% | 15% | 20% | 20%
WI-0035 | Action Triggering | 0% | 10% | 20% | 30% | 40%
WI-0037 | 3GPP Rel13 Interworking | 0% | 0% | 5% | 20% | 40%
WI-0040 | Web-Socket-Binding | 0% | 20% | 20% | 40% | 50%
WI-0041 | Enhancements to Subscription/Notification Framework | 0% | 0% |  | 80% | 90%
WI-0042 | Application developer guide |  | 0% | 20% | 90% | 100%
WI-0043 | Continuation & integration of HGI Smart Home activities |  | 0% | 10% | 40% | 55%
WI-0044 | oneM2M OIC Interworking |  |  | 30% | 60% | 90%
WI-0045 | Addition of Interoperable Privacy Profiles to oneM2M Security Solutions TS 0003 |  |  |  | 5% | 5%
WI-0046 | Vehicular domain enablement |  |  |  | 5% | 20%
* The request for exceptions to the freeze date was agreed for the following issues: – Work on Security for WI-0016 (E2E security) and WI-0019 (dyn. authoriz.) – Work on Interworking: WI-24 (LWM2M), WI-18 (AllJoyn), WI-44 (OIC) – Work on WI-00025 Generic InterworkingSemantics

## Progress Testing
Testing
Work Item Completion
WI number | Title | % completion TP17 | % completionTP18 | % completion TP19 | % completion TP20 | % completion TP21
WI-0022 | Interoperability Testing | 80% | 85% | 90% | 95% | 100%
WI-0027 | Testing Framework | 30% | 70% | 70% | 70% | 70%
WI-0032 | Conformance Test | 5% | 10% | 15% | 35% | 39%
WI-0042 | Application developer guide |  | 0% | 20% | 90% | 100%

## History
History of Change
V0.0.0 | 2013-08-05 | First draft of new Work Programme Report
V0.1.0 | 2013-08-08 | Incorporation of Raporteur updates
V7.0.0 | 2013-10-18 | First draft of administrative perm document "oneM2M-ADM-0001-oneM2M_Work_Programme-V7_00_00"
V8.0.0 | 2013-12-12 | Input to TP#8 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - register ADM Text Part adapted to official ADM template (oneM2M-Template-ADM-20131008.doc)
V9.0.0 | 2014-02-21 | Input to TP#9 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0005R01 into register ADM Text Part
V10.0.0 | 2014-04-11 | Input to TP#10 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - conversion TR-0004 into TS-0011 according to CR TP-2014-0028 - update target dates for TS-0003 according to CR TP-2014-0029R1 - update target dates for TS-0007 according to CR TP-2014-0408 - update target dates for TR-0009 according to CR TP-2014-0417
V11.0.0 |  | Input to TP#11 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0008R01 into register ADM Text Part- update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E
V12.0.0 | 2014-08-01 | Input to TP#12 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - approved deliverables deleted from tracking registers B, C, D, E - new WI16 (TR 0012) incorporated
V17.0.0 | 2015-06-04 | Input post TP#17 : - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V17.1.0 | 2015-07-15 | Input prior TP18: - new register: R2 timeline - register WIs: added column level of completeness as of TP17
V18.0.0 | 2015-07-24 | Input TP#18 : - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated - added Annex F WI Progress and new Register Progress
V18.1.0 | 2015-08-20 | progress update for WI-0033 and update of TR and TS list
V19.0.0 | 2015-09-11 | Input TP#19 : - update with latest WI status including added column supporting companies - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated - added Annex G: Progress Testing
V19.1.0 | 2015-10-14 | update of WIs with recently uploaded TRs and TSs
V19.2.0 | 2015-10-22 | update of WIs and TRs/TSs list with recently uploaded TRs and TSs
V19.3.0 | 2015-11-02 | update of TR and TS list
V20.0.0 | 2015-11-13 | Input TP#20: - updated with latest WI status including progress and timeline
V20.1.0 | 2015-12-14 | update of TR and TS list with latest versions, as well as WI-0046 with TR number
V21.0.0 | 2016-01-22 | Input TP#21: - updated with latest WI status including progress