## ADM-0001 V 34.0.0
Administrative Document
ADM-0001-V-34.0.0
oneM2M Work Programme
2018-03-23
Copyright Notification
No part may be reproduced except as authorized by written permission.
The copyright and the foregoing restriction extend to reproduction in all media.
This document is intended for distribution only to oneM2M Participants.
© oneM2M Partners Type 1 (ARIB, ATIS, CCSA, ETSI, TIA, TSDSI, TTA, TTC)
Contents
1 Scope ……………………………………………………………….…………………Page 3
2 References …………………………………………………………..…………...…...Page 3
2.1 Normative References ……………………………...……………………………….………………..… Page 3
2.2 Informative References ………………………………………………………...…………...……...…… Page 3
3 Definitions, symbols, abbreviations and acronyms ………………………….….....……Page 3
3.1 Definitions …………………………….……………………………………………………………........ Page 3
3.2 Symbols …………………………….………………………………………………………………...…. Page 3
3.3 Abbreviations, acronyms……………………………………………………………….…………...… Page 3
4 Conventions …………………………………………………………………..……… Page 3
5 oneM2M Work Programme ……………………..…………………………..……… Page 3
Annex A: Work Programme Overview …….………………………….… Register Active Wis
Annex B: Work Programme Overview …….………………………….… Register Closed WIs
Annex C: List of Technical Specifications …………………………...….Register TSs
Annex D: List of Technical Reports …….…………………………. ..… Register TRs
Annex E: List ADM ………………...………………….……………...….Register ADMs
Annex F: Release 2A ...…………………………………………… Register Release 2A
Annex G: Timeline Release 2...………………………………………….. Register Timeline R2&R3
Annex H: Work Item Progress……………………………………… ..… Register Progress
Annex I: Testing Work Item Progress………………………...……..…… Register Progress Testing
Annex J: Association of Work Tracks with Work Items ………………… Register Association WT WI
History of Change …………………………………………………….……….……… Register History
1 Scope
The present document is the “oneM2M Work Programme” referred to in Articles 31 in the Working Procedures Document [1], and addresses the Work Item reporting process within the Technical Plenary, its subordinate groups and the Secretariat to accomplish the tasks extracted from Article 12. In addition, the present document addresses processes to accomplish tasks not specifically identified in the Working Procedures Document but considered essential to the efficient operation of the Technical Plenary.
2 References
References are either specific (identified by date of publication and/or edition number or version number) or non specific. For specific references,only the cited version applies. For non-specific references, the latest version of the referenced document (including any amendments) applies.
2.1 Normative References
The following referenced documents are necessary for the application of the present document. [1] ADM-0002 oneM2M Partnership Agreement [2] ADM-0005 oneM2M Working Procedures Document [3] ADM-0004 Method of work
2.2 Informative References
The following referenced documents are not necessary for the application of the present document but they assist the user with regard to a particular subject area.
[i.1] ADM-0003 oneM2M Drafting Rules (http://member.onem2m.org/Static_pages/Others/Rules_Pages/oneM2M-Drafting-Rules-V1_0.doc)
3 Definitions and Abbreviations
For the present document the following apply:
3.1 Definitions
Approval: the decision of the Technical Plenary that a deliverable is ready for getting ratified in order to publish it (see process description in [2]).
Change Control: the decision of a Working Group that the content of a draft deliverable is sufficiently advanced that it will utilize the Change Control process (see process description in [2]).
Drafting:the editorial phase of a deliverable until it is placed under Change Control (see process description in [2]).
Forecast: the date estimation (best guess) for the required milestones of a deliverable based on the current state of it taking into account the level of completeness, risks and uncertainties
Freeze: the decision of a Working Group that the technical content of a draft deliverable is complete (given consideration of the Work Item scope and workplan), and it is frozen for further technical input (see process description in [2])
Level of Completeness:the estimation of how much of a deliverable has been already drafted in relation to the expected total amount being necessary for the approval
Milestone dates: dates for the main process corner stones of a deliverable specified in the respective Work Item documents (see process description in [2])
Start: means the beginning of drafting a deliverable
Target: a requested date for a deliverable which is specified in the respective Work Item document for all its main milestones
TP#n-1 means the last Technical Plenary meeting before the current one. The current one is the basis for an update of the Work Programme.
3.2 Abbreviations
ARC Architecture
Doc_ID Document Identifier
MAS Management, Abstraction and Semantics
REQ Requirements
SEC Security
TP Technical Plenary
TR Technical Report
TS Technical Specification
TST Testing
WI Work Item
WG Working Group
4 Conventions
Work Programme updates
Form for updating planning (Register WIs) - serves for updating forecasts of milestone dates and level of completeness by the respective rapporteurs of the deliverables. The dates in the target columns are taken from the actual revisions of the approved respective Work Item documents.
Scaling of level of completeness
• Value range from 0% - 100%, no special scaling requested. Highest level achievable in a WG is 95%
• Measurement will be against milestone “Approval” listed in the agreed respective Work Item (meaning that 100% completeness must be achieved for reaching this milestone)
• Expected levels of completeness at milestones:
Start - 0%
First draft / skeleton - 10%
Freeze - 90%
WG decision: “ready for approval” - 95%
(shall be achieved for the deliverable being presented to Technical Plenary for approval, rest of 5 % is considered as remaining editorial effort for producing the final revision, which is candidate for TP ratification, candidate for getting published by the Partners Type 1)
Approval (by TP) - 100%
5 oneM2M Work Programme
Please see also the WPM portal for the latest work program status.

## Active WIs
WI number | Title | Ver | Status | Deliverables | Title | Start | Change Control | Freeze | Approval | primary responsible | % completion TP32 closing | Comment | Supporting Companies
WI-0015 | Use Cases Collection | v1.2 | Approved | TR-0001 | Use Cases Collection | TP8 | TP8 | n.a. | n.a. | WG1 | n.a. | Rapporteur: Catalina Mladin, InterDigital; The “Freeze” and “Approval” dates in the above schedule will be determined when the Requirements TS “Freeze” and “Approval” dates are established. | Sprint; Huawei; NEC; Telecom Italia; ZTE
WI-0021 | Secure Environment Abstraction | v1.5.0 | Approved | TS-0016 | Secure Environment Abstraction | TP 15 | TP 26 | TP 31 | TP 32 | WG4 | 90% | Rapporteur: François Ennesser, Gemalto (ETSI); updated at TP29 | Giesecke & Devrient, Gemalto NV, Oberthur Technologies, Interdigital, CATT, LG Electronics
|  |  |  | CRs toTS 0002 | Secure Environment Abstraction requirements | n.a. | n.a. | n.a. | TP 24 | WG1
|  |  |  | CRs toTS 0001 | oneM2M Function Architecture changes related to Secure Environment Abstraction | n.a. | n.a. | n.a. | TP 28 | WG2
|  |  |  | CRs toTS-0003 | Secure Environment Abstraction security spcifications | n.a. | n.a. | n.a. | TP 31 | WG4
|  |  |  | CRs toTS-0004 | oneM2M Core Protocol changes related to Secure Environment Abstraction | n.a. | n.a. | n.a. | TP 32 | WG3
WI-0030 | M2M Application & Field Domain Component Configuration | v1.1.1 | Approved | CRs to TS-0002 | Requirements regarding Device/Component Configuration | n.a. | n.a. | n.a. | TP 18 | REQ/ARC/SEC/MAS | 100% | Rapporteur: Shingo Fujimoto, FUJITSU | FUJITSU(TTC), Deutsche Telekom AG (ETSI), Telecom Italia SpA (ETSI), InterDigital Communications (TIA), Alcatel-Lucent (TIA)
|  |  |  | TS-0022 | Field Device Configuration | TP19 | TP22 | TP22 | TP24 | WG5 |  | Impacted WGs: ARC, PRO, SEC, TST; additional rapporteur for TS-0004: Nobuyuki Uchida, Qualcomm
WI-0031 | Optimized Group-based Operation | v2.0.0 | Approved | CRs to TS-0002 | Group enhancement requirements | n.a. | n.a. | n.a. | TP#19 | WG1 | 95% | Rapporteur: Jiaxin Yin, Huawei Technologies Co., Ltd. | Huawei Technologies Co., Ltd.; InterDigital; KETI; China Unicom
|  |  |  | CRs to TS-0001 | Enhancement in architecture | n.a. | n.a. | n.a. | TP#28 | WG2 |  | approval milestone updated TP26
|  |  |  | CRs to TS-0004 | Enhancement in protocol | n.a. | n.a. | n.a. | TP#31 | WG3 |  | approval milestone updated TP26
|  |  |  | CRs to TR-0001 | Group related use cases | n.a. | n.a. | n.a. | TP#19 | WG1
|  |  |  | CRs to TR-00012 | Potential CR related to group authentication | n.a. | n.a. | n.a. | TP#19 | WG4
WI-0032 | Conformance Test | v2.0.0 | Approved | TS-0017 | Implementation Conformance Statements | TP17 | TP21 | TP22 | TP29 | WG6 | 100% | Rapporteur: Martin MIAO, KETI; rapporteur and approval date updated TP26 | Huawei Technologies Co., Ltd., KETI, TTA, Telecom Italia, China Unicom, Dt&C, NTT
|  |  |  | TS-0018 | Test Suite Structure and Test Purposes | TP17 | TP21 | TP24 | TP29 | WG6 |  | Rapporteur: Martin MIAO, KETI
|  |  |  | TS-0019 | Abstract Test Suite and Implementation eXtra Information for Test | TP19 | TP23 | TP24 | TP29 | WG6 |  | Rapporteur: Laurent Velez, ETSI
WI-0034 | Study of re-usable service layer context &Transaction enablement | v2.0.1 | Approved | TR-0020 | Study of service transactions and re-usable service layer context | TP#17 | TP 20 | TP 29 | TP 30 | WG2 | 95% | Rapporteurs: Qiuting Li, ZTE & Jiaxin Yin, Huawei Freeze and approval milestone updated TP27 | LGE, ZTE, InterDigital, Spirent, Huawei, IBM, ALU, KETI, nTels
|  |  |  | CRs to TS-0001 | Architecture to support transaction in oneM2M | n.a. | n.a. | n.a. | TP#28 | WG2 |  | approval milestone updated TP26
|  |  |  | CRs to TS-0004 | Procedure and data type to support transaction in oneM2M | n.a. | n.a. | n.a. | TP#31 | WG3 |  | approval milestone updated TP26
|  |  |  | CRs to TS-0001 | Architecture to support multimedia streaming session in oneM2M | n.a. | n.a. | n.a. | TP#31 | WG2 |  | approval milestone updated TP27
|  |  |  | CRs to TS-0004 | Procedure and data type to support multimedia streaming session in oneM2M | n.a. | n.a. | n.a. | TP#32 | WG3 |  | approval milestone updated TP27
WI-0035 | Action Triggering | v2.1.0 | Approved | TR-0021 | Study of the action triggering in M2M | TP 18 | TP25 | TP26 | TP33 | WG2 | 95% | Rapporteur: Jiaxin Yin, Huawei; update Approval date @TP32 | Huawei Technologies Co., Ltd.; Fujitsu; LGE; Qualcomm
|  |  |  | CRs to TS0001 | New resources definition to support action triggering | n.a. | n.a. | n.a. | TP28 | WG2 |  | approval date updated TP26
|  |  |  | CRs to TS0004 | Procedure and data type definition to support action triggering | n.a. | n.a. | n.a. | TP31 | WG3 |  | approval date updated TP26
WI-0046 | Vehicular domain enablement | v2.0.2 | Approved | TR-0026 | Vehicular Domain Enablement | TP#20 | n.a. | TP 30 | TP 31 | WG1,WG2 (WG4) | 65% | Rapporteurs: Jairo Lopez (Hitachi Ltd.), Victor Kueh (Huawei Technologies, Co. Ltd), DongJoo Kim (LG Electronics); Kenichi Yamamoto(KDDI), Catalina Mladin(Convida) changed Rapporteur TP30. * Completion level at TP30 closing 95%. For TP31 opening 50%-due to enhancement of scope at TP30. | Hitachi, KDDI, Toyota ITC, Huawei Technologies, Co. Ltd., LG Electronics, NEC, China Unicom, Samsung, AT&T, Convida (added TP30)
|  |  |  | TS-00xy | Advanced Vehicular Domain Enablement | TP31 | n.a. | TP38 | TP40 | WG1,WG2 (WG4)
WI-0047 | DDS usage in oneM2M system | V0.1.0 | Approved | TR-0027 | DDS usage in oneM2M system | TP 23 | TP 27 | TP 29 | TP 30 | WG2 (WG3) | 50% | Rapporteurs: SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr Xu Bei (Echo), Huawei, echo.xubei@huawei.com | KETI, Huawei, Hitachi, China Unicom, BOE
|  |  |  | CRs to TS-0001 | Functional Architecture changes for DDS | t.b.d. | t.b.d. | t.b.d. | t.b.d. | WG2
|  |  |  | CRs to TS-0004 | Service Layer Core Protocol changes for DDS | t.b.d. | t.b.d. | t.b.d. | t.b.d. | WG3
|  |  |  | CRs to TS-0002 | Requirements | t.b.d. | t.b.d. | t.b.d. | t.b.d. | WG1
|  |  |  | CRs to TS-0003 | Security Solutions changes for DDS | t.b.d. | t.b.d. | t.b.d. | t.b.d. | WG4
WI-0048 | OSGi Interworking | v0.1.0 | Approved | TR-0028 | Analysis on the interworking between oneM2M and OSGi Alliance | TP24 | TP27 | TP29 | TP30 | WG2 (WG3, WG5) | 95% | Rapporteur: Jiaxin Yin (Huawei Technologies Co.,Ltd.); updated at TP29 | Huawei Technologies Co., Ltd., Orange, DT, NTT, NEC, AT&T, China Unicom, CATR
|  |  |  | TS-0035 | OSGi Interworking | TP29 | TP30 | TP30 | TP31 | WG2 (WG5)
|  |  |  | CRs to TS-0001 | Potential change to oneM2M resources for the mapping of attributes and metadata as well as to oneM2M procedures for lifecycle management of services related to mapping if needed | n.a. | n.a. | n.a. | TP30 | WG2 (WG3)
|  |  |  | CRs to TS-0004 | Potential change to data types and formats for mapping if needed | n.a. | n.a. | n.a. | TP31 | WG3
WI-0049 | Rel-1 & 2 Maintenance | v0.0.1 | Approved | CRs R1&R2 TSs | Maintenance CRs to oneM2M Release 1 and 2 Specifications (REL1&2_MNT) | TP24 | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | Deutsche Telekom, KDDI, LGE, Sierra Wireless, AT&T, KETI, Huawei, ZTE
WI-0050 | Rel-3 Small Technical Enhancements | v0.0.1 | Approved | CRs to R3 TSs | Small Technical Enhancements CRs to oneM2M Rel 3 Specifications (REL3_STE) | TP25 | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | Deutsche Telekom, KDDI, LGE, Sierra Wireless, AT&T, KETI, Huawei, ZTE
WI-0051 | Security Functions Conformance Testing | v0.0.1 | Approved | TS-0027 | Security Implementation Conformance Statements | TP25 | TP28 | TP29 | TP30 | WG 6 | 100% | Rapporteur: Franck Le Gall (Easy Global Market) | Easy Global Market, Gemalto, Giesecke & Devrient, Cadzow Communications Consulting
|  |  |  | TS-0028 | Security Test Suite Structure and Test Purposes | TP25 | TP28 | TP29 | TP30 | WG 6 |  | Rapporteur: Franck Le Gall
|  |  |  | TS-0029 | Security Abstract Test Suite and Implementation eXtra Information for Test | TP25 | TP28 | TP29 | TP30 | WG 6 |  | Rapporteur: Miguel Reina Ortega
WI-0052 | LWM2M DM & Interworking Enhancements | v1.1.0 | Approved | TR-0031 | LWM2M DM and Interworking Enhancements | TP25 | TP 26 | TP28 | TP29 | WG 5 | 100% | Rapporteur: Dale Seed, InterDigital (Dale.Seed@InterDigital.com) | InterDigital, Huawei, Gemalto, Siera Wireless, NEC
|  |  |  | CRs to TS-0014 | LWM2M Interworking Enhancements | TP25 | n.a. | n.a. | TP31 | WG2, WG5
|  |  |  | CRs to TS-0005 | Completes and extensible LWM2M Object support | TP25 | n.a. | n.a. | TP31 | WG5
WI-0053 | Rel-3 Enhancements on Semantic Support | v1.0.0 | Approved | TS-0034 | Semantics Support in oneM2M | TP 25 | TP 28 | TP 40 | TP 41 | WG5 (WG2, WG3) | 5% | WI Rapporteur: Martin Bauer, NEC (martin . bauer @ neclab . eu); Editor: Chonggang Wang (Convida). At TP33 update for R4: Changed name and extended scope of WI to R4. R3 enhancements finalized. Decided to start reporting R4 progress at 0%. | NEC, Orange, AT&T, Deutsche Telekom, Hitachi, Pineone, China Unicom, Convida Wireless, Huawei, Eurecom, Modacom, KETI, Nokia
|  |  |  | TR-0033 | Study on Enhanced Semantic Enablement | TP 25 | TP 28 | TP 40 | TP 41 | WG5
WI-0054 | Developers’ guide series | v2.1.0 | Approved | TR-0025 | Application developer guide: Light control example using HTTP binding | TP 25 | TP 26 | TP 27 | TP 29 | WG 6 | 95% | WI Rapporteur: Laurent Velez (ETSI, laurent.velez@etsi.org); Editor: Laurent Valez | Sensinov, Gemalto, KETI, Easy Global Market, InterDigital, Cadzow Communications, BT, Huawei, Eurecom, SyncTechno Inc, AT&T, Deutsche Telekom AG, Nokia, Orange, KDDI Corporation, NEC
|  |  |  | TR-0034 | Application developer guide: Temperature monitoring example using CoAP binding | TP 25 | TP 28 | TP 30 | TP 32 | WG 6 |  | Rapporteur: Shane He
|  |  |  | TR-0038 | Developer guide: Implementing security example | TP 25 | TP 28 | TP 30 | TP 32 | WG 6 (WG4) |  | Rapporteur: Francois Ennesser, & Laurent Velez
|  |  |  | TR-0045 | Developer guide: Implementing Semantics | TP 25 | TP 28 | TP 30 | TP 32 | WG 6 (WG5) |  | Rapporteur: Martin Bauer (NEC Europe Ltd. (ETSI))
|  |  |  | TR-00xx | Application developer guide: Interworking Proxy Entity example use case | TP 25 | TP 28 | TP 30 | TP 32 | WG 6 (WG2) |  | Rapporteur: Mahdi Ben Alaya & Laurent Velez
|  |  |  | TR-0035 | Developer guide: Device Management use case | TP 25 | TP 28 | TP 30 | TP 32 | WG 6 (WG5) |  | Rapporteur: Jiaxin Yin
|  |  |  | TR-0037 | Developer guide: smart farm example using MQTT binding | TP 25 | TP 28 | TP 30 | TP 32 | WG 6 |  | Rapporteur: Ting Martin Miao
|  |  |  | TR-0047 | Developer guide: 3GPP interworking example | TP 25 | TP 28 | TP 30 | TP 32 | WG 6 (WG2) |  | Rapporteur: Lijing & Patricia Martigne & James Hu
|  |  |  | TR-0039 | Developer guide: SDT-based implementation | TP 27 | TP29 | TP30 | TP32 | WG6 (WG5) |  | Rapporteur: Maciej Goluch (maciej.goluch@orange.com) & Laurent Velez; Change of Rapporteur TP30
WI-0055 | Product Profiles & oneM2M Features | v1.0.0 | Approved | TR-0029 | Methodology of product profiles definition | TP25 | TP30 | TP31 | TP31 | WG6 | 100% | WI Rapporteur: Jiaxin Yin, Huawei Technologies Co., Ltd., yinjiaxin@huawei.com; SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr. Updated name change and Milestones at TP26 | Huawei Technologies Co.,Ltd., KETI, DT, InterDigital, Qualcomm, Spirent, AT4Wireless, UL, R&S, Anritsu, AT&T, NEC, LG U+
|  |  |  | TS-0025 | Definition of Product Profiles in oneM2M | TP25 | TP30 | TP33 | TP34 | WG6 (WG2, WG3, WG4, WG5) |  | Jiaxin Yin, Huawei Technologies Co., Ltd.,; Renamed to "Product Profiles" at TP 33; adjusted freeeze and approval milestone
|  |  |  | TS-0031 | oneM2M fFeatures Catalogue | TP25 | TP30 | TP33 | TP34 | WG2 (WG3, WG6) |  | SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr; Renamed to Feature Catalogue at TP33; adjusted freeeze and approval milestone
WI-0056 | Evolution of Proximal IoT Interworking | v1.1.0 | Approved | TS-0033 | Proximal IoT Interworking Framework | TP25 | TP28 | TP31 | TP33 | WG2 | 95% | Rapporteur: Josef Blanz, Qualcomm Inc. (TIA); Updated schedule at TP30; Change of name of TS-0033 at TP31; as well as update of apporoval dates. | Qualcomm, Huawei, KETI, LGE, Deutsche Telekom, Orange, Sierra Wireless, AT&T, Gemalto, Interdigital, Nokia
|  |  |  | CRs to TS-0001 |  | TP25 | n.a. | n.a. | TP30 | WG2
|  |  |  | CRs to TS-0004 |  | TP25 | n.a. | n.a. | TP32 | WG3
|  |  |  | CRs to TS-0014 |  | TP25 | n.a. | n.a. | TP33 | WG2
|  |  |  | CRs to TS-0021 |  | TP25 | n.a. | n.a. | TP31 | WG2
|  |  |  | CRs to TS-0024 |  | TP25 | n.a. | n.a. | TP32 | WG2
|  |  |  | CRs to TS-0023 |  | TP25 | n.a. | n.a. | TP32 | WG5
WI-0057 | TEF Interface | v0.0.3 | Approved | TS-0032 | MAF and MEF Interface Specification | TP25 | TP 29 | TP29 | TP30 | WG4 | 100% | Rapporteur: Wolfgang Granzow, Qualcomm, wgranzow@qti.qualcomm.com ; Phil Hawkes, Qualcomm, phawkes@qti.qualcomm.com; TEF… Trust Enabling Function; schedule update TP29 | Qualcomm Inc., InterDigital, Datang, Gemalto, BT Group
|  |  |  | CRs to TS-0003 | Mapping of MEF and MAF procedures to TEF interface | TP25 | n.a. | n.a. | TP 26 | WG4
|  |  |  | CRs to TS-0004 | (possibly impacted) new data types in the m2m: namespace | TP25 | n.a. | n.a. | TP 25 | WG3(WG4)
|  |  |  | CRs to TS-0001 | Introduction of Mtef reference point | TP25 | n.a. | n.a. | TP 25 | WG2 (WG4,WG3)
|  |  |  | CRs to TS-0022 | Configuration parameters provisioned to Enrollees | TP25 | n.a. | n.a. | TP 25 | WG5 (WG4)
WI-0058 | Interworking with 3GPP networks | v0.5.0 | Approved | TS-0026 | 3GPP Interworking | TP25 | n/a | TP#42 | TP43 | WG2 (WG3) | 95% | co-rapporteurs: Xubei "Echo" (Huawei), Patricia Martigne (Orange), James Hu (AT&T); and Shao Weixiang (ZTE Corporation) as a rapporteur of TR-0024 (WI-0037). WI updated: to include 3GPP as well as Cellular IoT Interworking at TP 25. Renamed WI at TP27. Updated schedule at TP29; last update TP34 (i.e. timeline adjusted to 3GPP Rel15 => new milestones freeze and approval; Justification and scope update) | Orange, AT&T, Deutsche Telekom, Huawei, KDDI, Sierra Wireless, Sensinov, Oberthur Technologies, Gemalto, ZTE Corporation, Nokia, NEC, KT
|  |  |  | CRs to TS-0001 | TBD | TP25 | n/a | n/a | TP42 | WG2
|  |  |  | CRs to TS-0004 | TBD | TP25 | n/a | n/a | TP42 | WG3
|  |  |  | CRs to TS-0003 | TBD | TP25 | n/a | n/a | TP42 | WG4
|  |  |  | CRs to TR-0047 | CR to the developer’s guideline related to 3GPP interworking | TP25 | n/a | n/a | TP42 | WG6
|  |  |  | CRs to TR-0024 | CR to the 3GPP interworking | TP25 | n/a | n/a | TP42 | WG2 |  | Link to WI-0037
WI-0059 | OPC-UA Interworking | v0.0.1 | Approved | CRs to TR-0018 | Add additional section describing existing OPC-UA information model and the interworking methods. | TP25 | n/a | n/a | TP29 | WG2 | 100% | Rapporteur: Miao Jiang, Hitachi (China) Research &Development Corporation (CCSA), miaojiang@hitachi.cn. Chengsui Lu, Hitachi (China) Research&Development Corporation (CCSA), cslu@hitachi.cnn. (changed at TP28) | Federal Network Agency (BNetzA), Deutsche Telekom (DT), KDDI, Fujitsu, Anritsu Corporation, KETI, Huawei, InterDigital, Hitachi
|  |  |  | CRs to TS-0012 | Base ontology extension from existing industrial domain information model or ontologies | TP25 | n/a | n/a | TP29 | WG5
|  |  |  | CRs to TR-0007 | Enhancements on semantic modeling and ontologies or semantic annotation | TP25 | n/a | n/a | TP26 | WG5
|  |  |  | CRs to TS-0030 | Enhancements on generic interworking | TP25 | n/a | n/a | TP27 | WG5
|  |  |  | CRs to TS-0001 | Enhancements on architecture based on mapping OPC-UA data to oneM2M resources | TP25 | n/a | n/a | TP28 | WG5
WI-0060 | Interoperability testing Release 2 | V0.0.1 | Approved | TS-0013 | Interoperability Testing | TP24 | TP 28 | TP 29 | TP 30 | WG6 | 92% | Rapporteur: Laurent Velez | KETI, InterDigital, Sensinov, Huawei, Qualcomm inc
WI-0061 | Distributed Authorization | v0.0.1 | Approved | CRs to TS 0001 | Architecture, resources, procedures and policies related to authorization | TP25 | n/a | n/a | TP 28 | WG2/WG4 | 100% | Rapporteur: Wei Zhou, Datang (CCSA). | Datang, CMCC, InterDigital, Huawei, KDDI, Qualcomm Inc., BT, Gemalto NV, ZTE, CATR
|  |  |  | CRs to TS-0003 | Architecture, resources, procedures and policies related to authorization | TP26 | n/a | n/a | TP 29 | WG4
|  |  |  | CRs to TS-0004 | Resources, procedures and data types related to authorization | TP27 | n/a | n/a | TP 29 | WG3/WG4
WI-0062 | Service Layer Forwarding | v0.0.1 | Approved | TR-0030 | Service Layer Forwarding | TP 25 | TP 26 | TP 27 | TP 28 | WG2 (WG3) | 100% | Rapporteur: Dale Seed, InterDgital (Dale.Seed@InterDigital.com) | InterDigital, Huawei, Sensinov, KETI, Siera Wireless
|  |  |  | CRs to TS0001 | Changes/additions to existing resource types and/or parameters to support service layer forwarding | TP 25 | n/a | n/a | TP30 | WG2
|  |  |  | CRs to TS0004 | Procedure and data type definition to support service layer forwarding | TP 25 | n/a | n/a | TP30 | WG3
WI-0063 | Release 3 Enhancements on Base Ontology and Ontology based Interworking | v3.0.0 | Approved | TS-0030 | Ontology based Interworking | TP 25 | TP 28 | TP 31 | TP 32 | WG5 | 99% | WI Rapporteur: Change of WI Rapportuer at TP31: Joerg Swetina, NEC, (joerg.swetina@neclab.eu); Editor (TS Ontology based Interworking): Jaeho Lee (Pineone). Change of both WI name and TS-0030 approved at TP31 (see TP-2017-0276). | NEC, Orange, AT&T, Deutsche Telekom, Hitachi, Pineone, KETI
|  |  |  | CRs to TS-0012 | Extracting Ontology based Interworking from the Base Ontology specification into a new TS | TP24 | n/a | n/a | TP25 | WG5
|  |  |  | CRs to TS-0012 | Additions / changes to the Base Ontology | TP24 | n/a | n/a | TP31 | WG5
WI-0064 | Adaptation of oneM2M for Smart City | v0.1.0 | Approved | TR-0036 | Adaptation of oneM2M for Smart City | TP25 | TP28 | TP31 | TP32 | WG2 | 20% | WI Rapporteur: Jae Young Ahn, ETRI (ahnjy@etri.re.kr ) and SeungMyeong JEONG, KETI (sm.jeong@keti.re.kr); update at TP29 | ETRI, NEC, iconectiv, Modacom, KT, HERIT, ORANGE, TIM
|  |  |  | CRs to | TS-0002 | TP25 |  |  |  | WG1
|  |  |  | CRs to | TS-0001 | TP25 |  |  |  | WG2
|  |  |  | CRs to | TS-0003 | TP25 |  |  | TP32 | WG4
WI-0065 | Trust Management in oneM2M | v1.0.0 | Approved | TR-0040 | Trust management in oneM2M | TP 25 | TP 37 | TP 38 | TP 39 | WG4 | 20% | WI Rapporteur: Jae Young Ahn, ETRI (ahnjy@etri.re.kr ); At TP33 updated schedule: change, freeze and approval date | ETRI, KT, HERIT, Cadzow Communications Consulting Ltd., iconectiv, Nokia, TIM, Huawei
WI-0066 | Decentralized Authentication | v1.0.0 | Approved | TR-0041 | Decentralized Authentication | TP26 | TP34 | TP34 | TP35 | WG4 | 75% | WI Rapporteurs: Guilin Wang, Huawei, wang.guilin@huawei.com (WG4) Jie Shi, Huawei, shi.jie1@huawei.com (WG4). Changed Change Control, Freeze and Approval Milestones at TP30. R4 timing. | Huawei, Datang, Cadzow Communications Consulting Ltd, iconectiv, ETRI
|  |  |  | CRs to | TS-0003 | TP26 | n/a | n/a | TP34 | WG4
|  |  |  | CRs to | TS-0002 | TP26 | n/a | n/a | TP34 | WG4
WI-0068 | GlobalPlatform Interworking (GPI) | v1.0.0 | Approved | TS-00yx | GlobalPlatform Interworking | TP 26 | TP37 | TP37 | TP38 | WG4 (WG5; WG2) | 0% | WI Rapporteur: François Ennesser, Gemalto (ETSI); changed milestone dates at TP29. at TP33: revised schedule, clarification of scope and addition of supporting companies. | GlobalPlatform, Gemalto, Qualcomm Inc., Huawei, Orange, Giesecke + Devrient Mobile Security; (added TP33)
|  |  |  | CRS to TS-0003 | GlobalPlatform Interworking enhancements | TP 26 | n/a | n/a | TP35 | WG4
|  |  |  | CRS to TS-0001 | GlobalPlatform Interworking integration | TP 26 | n/a | n/a | TP35 | WG2
|  |  |  | CRS to TS-0005 | GlobalPlatform Interworking impact | TP 26 | n/a | n/a | TP36 | WG5
|  |  |  | CRS to TS-0006 | GlobalPlatform Interworking impact | TP 26 | n/a | n/a | TP36 | WG5
|  |  |  | CRS to TS-0014 | GlobalPlatform Interworking impact | TP 26 | n/a | n/a | TP36 | WG5
|  |  |  | CRS to TS-0022 | GlobalPlatform Interworking impact | TP 26 | n/a | n/a | TP36 | WG5
WI-0069 | Heterogeneous identification service in oneM2M system | v1.0.0 | Approved | TR-0044 | Heterogeneous identification service in oneM2M | TP 27 | TP 35 | TP 35 | TP 36 | ARC (WG3, WG5, WG4) | 90% | WI Rapporteur: Bo Yuan, Computer network information center, Chinese academy of sciences, yuanbo@cnic.cn (WG1) Yuan Tao, Computer network information center, Chinese academy of sciences Guangzhou sub-center, taoyuan@cnicg.cn (WG2, WG3, WG4, WG5). At TP33 Changed milestones for TR: change , freez and approval date. | Computer Network Information Center, Chinese Academy of Sciences (CNIC); Computer Network Information Center, Chinese Academy of Sciences Guangzhou sub-center (CNICG); China Academy of Telecommunication Research of MIIT; Hitachi; Datang
|  |  |  | CRS to TR-0001 | Use Case Intelligence agricultural product traceability | TP 27 | n/a | n/a |  | WG1
|  |  |  | CRS to TS-0001 | Architecture to support the heterogeneous identification service in oneM2M | TP 27 | n/a | n/a |  | WG2
|  |  |  | CRS to TS-0004 | Procedure and data type to support the heterogeneous identification service in oneM2M | TP 27 | n/a | n/a |  | WG3
|  |  |  | CRS to TS-0003 | Security impact of heterogeneous identification | TP 27 | n/a | n/a |  | WG4
WI-0070 | Disaster Alert Service Enabler (DASE) | v0.0.1 | Approved | TR-0046 | Study on Disaster Alert Service Enabler | TP 28 | n/a | TP 31 | TP 32 | WG5 | 10% | WI Rapporteur: SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr, TaeHyun KIM, SyncTechno, thyun.kim@synctechno.com | KETI, SyncTechno, NTT, Huawei, ZTE, Qualcomm, KDDI
|  |  |  | CR to TR-0001 | Use case addition or updates | TP 28 | n/a | n/a |  | WG1
|  |  |  | CR to TS-0002 | New requirements | TP 28 | n/a | n/a |  | WG1
|  |  |  | CR to TS-0001 | Functional architecture enhancements | TP 28 | n/a | n/a |  | WG2
|  |  |  | CR to TS-0004 | Core protocol enhancements | TP 28 | n/a | n/a |  | WG3
|  |  |  | CR to TS-0003 | Security solutions enhancements | TP 28 | n/a | n/a |  | WG4
WI-0071 | oneM2M and W3C Web of Things Interworking (WOTIWK) | v0.0.1 | Approved | TR-0042 | WoT Interworking | TP#28 | TP#31 | TP#31 | TP#32 | WG5 (WG2, WG3, WG4) | 25% | WI Rapporteur: Yongjing Zhang, zhangyongjing@huawei.com | Huawei Technologies Co., Ltd. (CCSA), NEC (ETSI), Convida Wireless (ETSI), China Unicom (CCSA), China Telecom (CCSA), Hitachi (TTC), Deutsche Telekom AG (ETSI), LGE (TTA)
WI-0072 | Modbus interworking | v1.0.0 | Approved | TR-0043 | Modbus interworking | TP 28 | TP 30 | TP 31 | TP 32 | WG2 | 60% | WI Rapporteur: Qiuting Li, li.qiuting@zte.com.cn | ZTE, Datang, BOE, Hitachi, Computer Network Information Center, Chinese Academy of Sciences (CNIC);
|  |  |  | CR to TS-0001 | Functional Architecture changes for supporting Modbus interworking |  | n/a | n/a |  | WG2
|  |  |  | CR to TS-0002 | Requirements |  | n/a | n/a |  | WG1
|  |  |  | CR to TS-0004 | Service Layer Core Protocol changes for supporting Modbus interworking |  | n/a | n/a |  | WG3
|  |  |  | CR to TS-0033 | Proximal IoT Interworking for supporting Modbus interworking |  | n/a | n/a |  | WG2
WI-0073 | App-ID Registry Function | v1.0.0 | Approved | TR-0048 | oneM2M App-ID Registry Function | TP 30 |  | TP 33 | TP 34 | WG1,WG2 (WG3,4,5) | 100% | WI Rapporteur: Shelby Kiewel (iconectiv) | iconectiv , Convida, BT Group, Qualcomm, Gemalto, Huawei, Sensinov
|  |  |  | CR to TS-0001 | Architecture | TP 30 | n/a | n/a | TP 34 | WG2
|  |  |  | CR to TS-0002 | Requiremnts | TP 30 | n/a | n/a | TP 34 | WG1
|  |  |  | CR to TS-0003 | Security Solutions | TP 30 | n/a | n/a | TP 34 | WG4
|  |  |  | CR to TS-0032 | MAF and MEF Interface Specification | TP 30 | n/a | n/a | TP 34 | WG4
|  |  |  | CR to TS-0022 | Field Device Configuration | TP 30 | n/a | n/a | TP 34 | WG5
WI-0074 | Conformance Test Specifications Release 2 | v1.0.0 | Approved | CRs to TS-0017 | Implementation Conformance Statements | TP31 | TP35 | TP36 | TP40 | WG6 | 0% | WI Rapporteur: Laurent Velez; Rapporteur TS: KETI & Laurent Velez | Huawei Technologies Co., Ltd., KETI, TTA, Convida Wireless, Sensinov, Spirent, NTT, Rohde-Schwarz
|  |  |  | CRs to TS-0018 | Test Suite Structure and Test Purposes | TP31 | TP35 | TP36 | TP40 | WG6 |  | Rapporteur: KETI & Laurent Velez
|  |  |  | CRs to TS-0019 | Abstract Test Suite and Implementation eXtra Information for Test | TP31 | TP35 | TP36 | TP40 | WG6 |  | Rapporteur: Miguel Angel Reina Ortega
WI-0075 | Industrial Domain Information Model Mapping and Semantics Support | v0.0.2 | Approved | TR-0049 | Industrial Domain Information Model Mapping and Semantics Support | TP32 | n/a | TP36 | TP37 | WG5 (WG2) | 10% | WI Rapporteurs: Miao Jiang, Hitachi (China) Research &Development Corporation (CCSA), miaojiang@hitachi.cn, Chengsui Lu, Hitachi (China) Research &Development Corporation (CCSA), cslu@hitachi.cn. WI approved at TP31 | Hitachi, KDDI, NTT, Deutsche Telekom, Convida Wireless, NEC, Huawei, ZTE, CNICG, added at TP32
|  |  |  | CRs to TS-0001 | Normative CRs to the Functional Architecture | TP 32 | n/a | n/a | TP 37 | WG2
|  |  |  | CRs toTS-0004 | Normative CRs to the Core Protocol | TP 32 | n/a | n/a | TP 37 | WG3
|  |  |  | CRs toTR-0018 | Informative CRs to the general description on industrial data models | TP 32 | n/a | n/a | TP 37 | WG5
|  |  |  | CRs toTR-0033 | Informative CRs to the enhancement on semantic support | TP 32 | n/a | n/a | TP 37 | WG5
|  |  |  | CRs toTS-0034 | Normative CRs to the enhancement on semantic support | TP 32 | n/a | n/a | TP 37 | WG5
WI-0076 | Lightweight oneM2M Services | V0.0.1 | Approved | TR-00yx | Lightweight Services | TP 32 | n/a | TP 37 | TP 38 | WG2,WG3 (WG1, WG4, WG5) | 5% | WI Rapportuer: Dale Seed (Convida). WI approved at TP31 | Convida, Qualcomm Inc, NEC, Sensinov, iconectiv, Huawei, Nokia, KETI
|  |  |  | TS-0001 | Enhancements to TS-0001 | TP 32 | n/a | n/a | TP 38 | WG2
|  |  |  | TS-0003 | Enhancements to TS-0003 | TP 32 | n/a | n/a | TP 38 | WG4
|  |  |  | TS-0004 | Enhancements to TS-0004 | TP 32 | n/a | n/a | TP 38 | WG3
WI-0077 | Attribute Based Access Control Policy | V0.0.1 | Approved | TR-0050 | Attribute Based Access Control Policy | TP 32 | TP 36 | TP 37 | TP 38 | WG4 (WG2, WG3) | 15% | WI Rapportuer: Wei Zhou, Datang (CCSA). WI approved at TP31 | Datang, CATR, ZTE, CNIC, Huawei, Gemalto, BT, KDDI, ORANGE
|  |  |  | TS-0001 | Architecture, resources and procedures related to access control policy and access control policy management. | TP 32 | n/a | n/a | TP 38 | WG2/WG4
|  |  |  | TS-0003 | Architecture, resources and procedures related to access control policy and access control policy management. | TP 32 | n/a | n/a | TP 38 | WG4
|  |  |  | TS-0004 | Resources, procedures and data types related to access control policy and access control policy management. | TP 32 | n/a | n/a | TP 38 | WG3/WG4
WI-0078 | oneM2M API guide | V0.0.1 | Approved | TR-0051 | oneM2M API guide | TP 32 | TP 36 | TP 38 | TP 40 | WG6 | 0% | WI Rapporteur: Laurent Velez | KETI, ATT, Sensinov, Convida Wireless, NTT, Deutsche Telekom
WI-0079 | Rel-4 Small Technical Enhancements | V0.0.1 | Approved | CRs to R4 TSs | Small Technical Enhancements CRs to oneM2M Rel 4 Specifications (REL4_STE) | TP 32 | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | AT&T, Convida, Deutsche Telekom, NEC, Nokia
WI-0080 | Edge and Fog Computing | V1.0.0 | Approved | TR-0052 | Study on Edge and Fog Computing in oneM2M systems | TP 33 |  | TP 39 | TP 40 | WG2 (WG1) | 5% | WI Rapporteur: Kenichi Yamamoto (KDDI), Catalina Mladin (Convida) | KDDI, Huawei, Hitachi, TNO, Convida, NEC, NEC Europe, NTT, BOE, Gemalto, Qualcomm, AT&T, KETI, TIM, Cisco, Nokia
|  |  |  | TS-0001 | Enhancements to TS-0001 |  |  |  | TP 40 | WG2
|  |  |  | TS-0002 | Enhancements to TS-0002 |  |  |  | TP 40 | WG1
|  |  |  | TS-0003 | Enhancements to TS-0003 |  |  |  | TP 40 | WG4
|  |  |  | TR-0001 | Enhancements to TR-0001 |  |  |  | TP 40 | WG1
|  |  |  | TR-0018 | Enhancements to TR-0018 |  |  |  | TP 40 | WG1
WI-0081 | Smart Device Template 4.0 | V1.0.0 | Approved | CRs to TS-0023 | CR on HAIM updates or enhancements | TP 33 | n.a. | n.a. | TP 38 | WG5 | 0% | WI Rapporteur: Andreas Kraft (Deutsche Telekom, a.kraft@telekom.de) | Deutsche Telekom, Huawei, Orange, NEC
WI-0082 | 3GPP V2X Interworking | V1.0.0 | Approved | TR-00xx | 3GPP V2X Interworking | TP 33 | n.a. | TP 38 | TP 39 | WG2 (WG5) | 5% | WI Rapporteur: Bei (Echo) Xu (Huawei) | Huawei Technologies, Co. Ltd., Hitachi, China Unicom, AT&T, Convida, Deutsche Telekom, KDDI, Orange
WI-0083 | oneM2M Service Subscribers and Users | V1.0.0 | Approved | TR-00xx | t.b.d. | TP 33 | n.a. | TP 39 | TP 40 | WG2 (WG4, WG3, WG1) | 5% | WI Rapporteur: Dale Seed (Convida) | Convida Wireless, NEC, Gemalto, KDDI, KETI
|  |  |  | CRs to TS-0001 | Enhancements to TS-0001 | TP 33 |  |  | TP 40 | WG 2
|  |  |  | CRs to TS-0003 | Enhancements to TS-0003 | TP 33 |  |  | TP 40 | WG 4
|  |  |  | CRs to TS-0004 | Enhancements to TS-0004 | TP 33 |  |  | TP 40 | WG 3
|  |  |  | CRs to TR-0001 | Additional usecases to TR-0001 | TP 33 |  |  | TP 40 | WG 1
WI-0084 | SDT based Information Model and Mapping for Vertical Industries | V0.0.1 | Approved | CRs to TS-0023 | CRs on HAIM updates or enhancements | TP 35 | n.a. | n.a. | TP 42 | WG 5 | 0% | WI Rapporteur: Maciej Goluch (Orange, maciej.goluch@orange.com), Andreas Kraft (Deutsche Telekom, a.kraft@telekom.de) | Orange, Deutsche Telekom, Huawei, Telecom Italia, NTT
|  |  |  | CRs to TS-0023 | CRs on ModuleClasses and Device descriptions for other service domains | TP 35 | n.a. | n.a. | TP 42 | WG 5

## Closed WIs
WI number | Title | Ver | Status | Deliverables | Title | Start | Change Control | Freeze | Approval | primary responsible | % completion TP24 closing | Comment | Supporting Companies
WI-0001 | Requirements | v1.4 | obsolete | TS-0002 | Requirements |  |  |  |  | WG1 | n.a. | Rapporteur TS-0002: Yu Qi, Huawei;Lijing, Huawei; WI closed at TP#23;
|  |  |  | TR-0001 | Use Cases Collection |  |  |  |  | WG1 | n.a. | Rapporteur: Catalina Mladin, InterDigital
WI-0002 | Architecture | v1.4 | obsolete | TS-0001 | Functional Architecture |  |  |  |  | WG2 | n.a. | Rapporteur: Rajesh Bhalla, ZTE & Yingjie Hong, ZTE (CCSA)
|  |  |  | TR-0002 | Architecture Analysis Part1 |  |  |  |  | WG2 | n.a. | Rapporteur: Richard Brennan, Telxxis
|  |  |  | TR-0003 | Architecture Analysis Part2 |  |  |  |  | WG2 | n.a. | Rapporteur: Phillip Brown, InterDigital
WI-0003 | VocabPrinciples | v1.4 | obsolete | TS-0011 | Common Terminology | TP#2 | TP#3 | TP#11 | TP#12 | WG1 | n.a. | Rapporteur: Roland Hechwartner, Deutsche Telekom | AT&T (ATIS), Deutsche Telekom (ETSI), Qualcomm Inc. (TIA), InterDigital Communications (TIA), Telecom Italia (ETSI), Vodafone (ETSI), Huawei Device Company (TIA), Intel (TIA), Sprint (TIA) , NEC Corporation (TTC), NEC Europe (ETSI)
|  |  |  | TR-0005 | Roles and Focus Areas | TP#2 | TP#3 | TP#11 | TP#12 | WG1 | n.a. | Rapporteur: Josef Blanz, Qualcomm; TR-0005 - expected to be progressed; Then close of WI. WI closed at TP#25
WI-0004 | Management_Capability_Enablement_Technologies | v1.1 | obsolete | TR-0006 | Study of Capability Enablement Technologies for Consideration by oneM2M | TP#3 | TP#7 | TP#7 | TP#8 | WG5 | 100% | Rapporteur: Jiaxin Yin, Huawei. WI closed at TP#25 | Huawei (CCSA), NEC (ETSI), NEC (TTC), Alcatel-Lucent (ATIS), InterDigital (ETSI), Eurecom
WI-0005 | Abstraction & Semantics Capability Enablement | v1.3 | obsolete | TR-0007 | Study of Abstraction and Semantics Enablements | TP#16 | N/A | TP#19 | TP#20 | WG5 | 100% | Rapporteur: Joerg Swetina, NEC. WI closed at TP#25
|  |  |  | TS-0012 | Base Ontology | TP#16 | TP#18 | TP#19 | TP#20 | WG5 |  | TS-0012 is developed under WI-0025 (Generic Interworking with Area Networks)
|  |  |  | TS-0002 | Requirements | TP#16 | N/A | TP#18 | TP#19 | WG1 |  | Rapporteur: Yu Qi, Huawei
|  |  |  | TS-0001 | Functional Architecture | TP#18 | N/A | TP#20 | TP#21 | WG2
|  |  |  | TS-0003 | oneM2M Security Solutions | TP#18 | N/A | TP#20 | TP#21 | WG4
|  |  |  | TS-0004 | Service Layer Core Protocol | TP#20 | N/A | TP#22 | TP#23 | WG3 |  | and related protocol bindings
WI-0006 | Device_Gateway_Class | v1.3 | obsolete | TR-0010 | [6 empty] | n.a. | Rapporteur: Hongbeom Ahn, LGE
WI-0007 | Security | v1.4 | obsolete | TR-0008 | Analysis of security solutions | TP#5 | TP#9 | TP#9 | TP#10 | WG4 | n.a. | Rapporteur: Claus Dietze (G&D)
|  |  |  | TS-0003 | Security Solutions | TP#6 | TP#10 | TP#10 | TP#11 | WG4 | n.a. | Rapporteurs: Claus Dietze (G&D)
WI-0008 | Protocol-TR | v1.2 | obsolete | TR-0009 | Protocol Analysis | TP5 | TP9 | TP9 | TP10 | WG3 | 100% | Rapporteur: Richard Brennan, Telxxis. WI closed at TP25
WI-0009 | Protocol-Development | v1.4 | obsolete | TS-0004 | Service Layer Protocol Core Specification | TP#5 | TP#11 | TP#11 | TP#12 | WG3 | n.a.
WI-0010 | Management Enablement | v1.1 | obolete | TS-0005 | Management enablement (OMA) | TP#8 | TP#11 | TP#11 | TP#12 | WG5 | n.a. | Rapporteur: SeungKyu Park, LG Electronics, Jiaxin Yin, Huawei; The work in the WI is based on the work in WG2 and has different focus compared to WG3. WI closed at TP25 | Alcatel-Lucent (ETSI), Huawei Technologies Co., Ltd. (CCSA, ETSI), InterDigital Communications (ATIS), LG Electronics (TTA), NEC Europe (ETSI), Samsung Electornics (ETSI)
|  |  |  | TS-0006 | Management enablement (BBF) | TP#8 | TP#11 | TP#11 | TP#12 | WG5 | n.a. | Rapporteur: Tim Carey, Alcatel-Lucent; The work in the WI is based on the work in WG2 and has different focus compared to WG3
WI-0011 | Service_Component_Architecture | v2.1 | obsolete | TS-0007 | Service Components | TP#9 | TP#15 | TP#15 | TP#17 | WG2 | 100% | Rapporteur: Tim Carey, Alcatel-Lucent. WI closed at TP25 | Alcatel-Lucent; AT&T; Verizon; Ericsson; ZTE; Orange; LG Electronics
WI-0012 | ProCoapBinding | v1.1 | obsolete | TS-0008 | CoAP Protocol Binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: SeongYoon Kim, LGE
WI-0013 | ProHttpBinding | v1.1 | obsolete | TS-0009 | HTTP Protocol Binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: SeungMyeong Jeong, LGE
WI-0014 | ProMQTTBinding | v1.1 | obsolete | TS-0010 | MQTT protocol binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | n.a. | Rapporteur: Peter Niblett, IBM | CISCO (ATIS/ETSI), Telefon AB LM Ericsson (ETSI), IBM (ETSI), Qualcomm (ARIB/ETSI), Sierra Wireless SA (ETSI), Telecom Italia SpA (ETSI)
|  |  |  | TR-0011 | MQTT Protocol Interworking Study | TP#9 | TP#11 | TP#11 | TP#12 | WG2 | n.a. | Rapporteur: Peter Niblett, IBM
WI-0016 | End-to-End Security and Group Authentication | v2.5.0 | obsolete | TR-0012 | End-to-End Security and Group Authentication | TP 12 | TP 22 | TP 23 | TP 24 | WG4 | 100% | Rapporteur: ZUO Min (China Mobile) and QI Minpeng (China Mobile) for “End-to-End Security and Group Authentication”. Closed at TP25 | British Telecom, China Mobile, CATT, Hitachi, Huawei, LG Electronics, Qualcomm
|  |  |  | CRs to TS 0002 | End-to-End Security and Group Authentication requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs to TS 0001 | oneM2M Function Architecture changes related to End-to-End Security and Group Authentication | n.a. | n.a. | n.a. | TP 21 | WG2
|  |  |  | CRs to TS-0003 | End-to-End Security and Group Authentication security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | CRs to TS-0004 | oneM2M Core Protocol changes related to End-to-End Security and Group Authentication | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0017 | Home Domain Enablement | v2.4.0 | obsolete | TR-0013 | Home Domain Enablement | TP13 | -- | TP17 | TP22 | WG1 | 100% | Rapporteur: Sungchan Choi, KETI & Dongjoo KIM, LGE; Secondary responsibility by WG2, WG3, WG4, WG5. WI closed at TP 25 | KETI, LGE, ETRI, SK Telecom, LG uplus, nTels, KCA, Kaonmedia, Haier, InterDigital,NTT, KDDI, Fujitsu, Hitachi, NEC, Orange, Samsung Electronics
|  |  |  | TR-0017 | Home Domain Abstract Information Model | TP16 |  | TP20 | TP21 | WG5
|  |  |  | TS-0023 | Home Appliances Information Model and Mapping | TP19 | -- | TP22 | TP23 | WG5/WG3
|  |  |  | TS-0002 | Normative CRs to Requirements | n.a. | n.a. | n.a. | TP18 | WG1
|  |  |  | TS-0001 | Normative CRs to Functional Architecture | n.a. | n.a. | n.a. | TP21 | WG2
|  |  |  | TS-0004 | Normative CRs to Core Protocol | n.a. | n.a. | n.a. | TP21 | WG3
WI-0018 | oneM2M and AllJoyn Interworking | v1.3.0 | obolete | TR-0014 | oneM2M and AllJoyn Interworking | TP14 | - | TP18 | TP19 | WG2 | 100% | WI Rapporteur: SeungMyeong JEONG, LG Electronics | LG Electronics, Qualcomm, LG U+, Haier, AT&T, Huawei, ALU
|  |  |  | TS-0021 | oneM2M and AllJoyn Interworking | TP19 |  | TP22 | TP23 | WG2 |  | WI closed at TP#25
|  |  |  | CRs to TS-0001 | Normative texts to include the solutions studied in the TR-0014 | n.a. | n.a. | n.a. |  | WG2
|  |  |  | CRs to TS-0004 | Normative texts to include the solutions studied in the TR-0014 | n.a. | n.a. | n.a. |  | WG3
WI-0020 | Service_Layer_API | v1.0.0 | obolete | TR-0015 | Service Layer API Core Principles | TP#15 | - | TP#18 | TP#19 | WG3 | 5% | Rapporteur: vacant; @TP22assessment: potential candidate WI for OSGi collaboration. WI closed at TP#25 | Sierra Wireless, Ericsson, LG Electronics, ZTE, Interdigital, AT&T, NEC, Hitachi
|  |  |  | TR-00xx | Service Layer API C Language Binding | TP#15 | - | TP#18 | TP#19 | WG3 |  | Rapporteur: vacant
WI-0022 | Interoperability Testing | v1.1.0 | obsolete | TS-0013 | Interoperability Testing | n.a. | n.a. | n.a. | TP25 | WG6 | 100% | Rapporteur: Laurent Velez, ETSI. WI closed at TP#25 | KETI, KCA, NEC, InterDigital
WI-0023 | Authorization Architecture & Access Control Policy | v1.5.0 | obsolete | TR-0016 | Authorization Architecture and Policies | TP 15 | TP 21 | TP 22 | TP 23 | WG4 | 100% | Wei Zhou, Datang (CCSA); Secondary responsibility WG3, WG2. WI closed at TP#25 | Datang, China Unicom, CATR, ZTE , Huawei, Haier, Gemalto NV
|  |  |  | CRs to TS 0002 | Authorization Architecture and Policies requirements | n.a. | n.a. | n.a. | TP 18 | WG1
|  |  |  | CRs to TS 0001 | oneM2M Function Architecture changes related to End-to- Authorization Architecture and Policies | n.a. | n.a. | n.a. | TP 21 | WG2
|  |  |  | CRs to TS-0003 | Authorization Architecture and Policies security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4
|  |  |  | Crs to TS-0004 | oneM2M Core Protocol changes related to Authorization Architecture and Policies | n.a. | n.a. | n.a. | TP 23 | WG3
WI-0024 | LWM2M Interworking | v0.1.1 | obsolete | TS-0014 | LWM2M Interworking | TP#16 | TP#21 | TP#21 | TP#23 | WG2 | 100% | Rapporteur: Timothy Carey, Alcatel-Lucent ; TS is expected to incorporate Architecture Work. | Alcatel-Lucent (TIA, ATIS), Gemalto (ETSI), Eurecom (ETSI) Huawei (CCSA), LG Electronics (TTA), InterDigital (ATIS), Sierra Wireless (ETSI), Ericsson (ETSI), KDDI (TTC)
|  |  |  | CRs to TS-0002 | oneM2M Requirements | TP#16 | N/A | TP#19 | N/A | WG1 |  | Change Requests to Requirements TS-0002 For LWM2M Interworking Requirements
|  |  |  | CRs to TS-0001 | Modifications to the oneM2M Architecture is not expected. |  |  |  |  | WG2 |  | WI closed at TP#25
|  |  |  | CRs to TS-0004 | Modifications to the oneM2M Protocols is not epected |  |  |  |  | WG3
|  |  |  | CRs to TR-0001 | Modifications to Use cases is not expected |  |  |  |  | WG1
WI-0025 | Generic Interworking | v2.1 | obsolete | CRs to TR-0007 | CRs to include elaboration / enhancements for interworking (IPEs) | TP#15 | n/a | TP#17 | TP#18 | WG5 | 100% | Rapporteur: Joerg Swetina, NEC | NEC, China Unicom, Modacom, KETI, EURECOM, InterDigital, Alcatel-Lucent
|  |  |  | CRs toTS-0002 | CRs to include additional interworking reqs. | TP#15 | n/a | TP#17 | TP#17 | WG1 |  | WI closed at TP#25
|  |  |  | CRs toTS-0012 | oneM2M_Base_Ontology | TP#15 | TP#18 | TP#19 | TP#20 | WG5
|  |  |  | CRs toTS-0001 | CRs to include functionality of IPEs | TP#17 | n/a | TP#19 | TP#20 | WG2 |  | … exception needed for ARC part
|  |  |  | CRs toTS-0003 | CRs to include security enhancements for support of IPEs | TP#17 | n/a | TP#19 | TP#20 | WG4
|  |  |  | CRs toTS-0004 | CRs to include protocol enhancements for support of IPEs | TP#19 | n/a | TP#20 | TP#21 | WG3
WI-0026 | Efficient Communications | v1.0.0 | obsolete | CRs to TR-0001 | Use Cases Collection | TP#15 | n/a | TP#17 | TP#18 | WG1 | 100% | Rapporteur: Josef Blanz, Qualcomm | Qualcomm, Sierra Wireless, Gemalto, Telia Sonera, Deutsche Telekom, Orange, KDDI, Interdigital
|  |  |  | CRs to TS-0002 | Requirements | TP#15 | n/a | TP#17 | TP#18 | WG1 |  | WI closed at TP#25
|  |  |  | CRs to TS-0001 | Functional Architecture | TP#16 | n/a | TP#18 | TP#19 | WG2
|  |  |  | CRs to TS-0004 | Protocols TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0008 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0009 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0010 | Protocol Binding TSs | TP#16 | n/a | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0005 | Management TSs | TP#16 | n/a | TP#20 | TP#21 | WG5
|  |  |  | CRs to TS-0006 | Management TSs | TP#16 | n/a | TP#20 | TP#21 | WG5
WI-0027 | Testing Framework | v1.1.0 | obsolete | TS-0015 | Test framework defining methodology for testing oneM2M specifications | TP#16 | TP#18 | TP#23 | TP#23 | WG6 | 100% | Rapporteur: Jiaxin Yin , Huawei Technologies. WI closed at TP#25 | KETI, Dt&C, Huawei Technologies, LG Electronics, iconectiv, Sierra Wireless
WI-0028 | Industrial Domain Enablement | v1.4.1 | obsolete | TR-0018 | Industrial Domain Enablement | TP#16 | TP#20 | TP#20 | TP#21 | WG1 | 100% | Rapporteur: Miao Jiang, Hitachi (China) Research &Development Corporation (CCSA), Toshiko Matsumoto, Hitachi (TTC), and Yanping Jiang, Huawei (CCSA). WI closed at TP#25 | Hitachi, Huawei, KDDI, Telecom Itallia SpA, NTT, NEC, InterDigital, KETI, Federal Network Agency (BNetzA)
|  |  |  | CRs to TS-0002 |  |  | n.a. | n.a. | TP#18 | WG1
|  |  |  | CRs toTS-0001 | Architecture impact from industrial domain enablement | n.a. | n.a. | n.a. |  | WG2
|  |  |  | CRs toTS-0004 | Protocol impact from industrial domaine enablement | n.a. | n.a. | n.a. |  | WG3
WI-0029 | App-ID Clarification | v1.1.0 | obsolete | CRs to TS-0001 | App-Id clarification | n.a. | n.a. | n.a. | TP#20 | WG2 | 100% | Rapporteur: Darold Hemphill, iconectiv | Fujitsu Ltd. (TTC), iconectiv (ATIS), Gemalto (ETSI),Sierra Wireless (ETSI)
|  |  |  | CRs to TS-0002 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG1 |  | WI closed at TP#25
|  |  |  | CRs to TS-0003 | App-Id clarification | n.a. | n.a. | n.a. | TP#23 | WG4
|  |  |  | CRs to TS-0004 | App-Id clarification | n.a. | n.a. | n.a. | TP#23 | WG3
|  |  |  | CRs to TS-0011 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG1
WI-0033 | Supporting Time Series Data | v0.0.1 | obsolete | TS-0001 | Architecture to support the integrity of data collection monitoring in oneM2M | n.a. | n.a. | n.a. | TP#22 | WG2 | 100% | Rapporteur: Qi Yu, Huawei Technologies Co., Ltd | Huawei Technologies, Hitachi , Haier, China Unicom, China academy of information and communications technology
|  |  |  | TS-0004 | Procedure and data type to support the integrity of data collection monitoring in oneM2M | n.a. | n.a. | n.a. | TP#23 | WG3 |  | WI closed at TP#25
WI-0036 | Update Security Analysis TR for Release 2 | v0.0.1 | obsolete | TR-0008 | Outcome of the Release 2 specific threat analysis | n.a. | n.a. | n.a. | TP 19 | WG4 SEC | n.a. | Rapporteur: Dragan Vujcic, Oberthur Technologies | Giesecke & Devrient, Gemalto, BT Group, Oberthur Technologies, Datang
|  |  |  | TS-0003 | Impact of Release 2 Threat Analysis | n.a. | n.a. | n.a. | TP 20 | WG4 |  | WI closed at TP#25
|  |  |  | TS-0001 | Architecture impact (if any) | n.a. | n.a. | n.a. | TP 20 | WG2
|  |  |  | TS-0004 | Protocol impact (if any) | n.a. | n.a. | n.a. | TP 21 | WG3
WI-0037 | 3GPP_Rel13_IWK | v1.1.0 | obsolete | TR-0024 | 3GPP Rel-13 Interworking | TP#17 | n/a | TP#21 | TP#23 | WG2 | 100% | Rapporteur: Shao Weixiang (ZTE), WI closed at TP#25 | Intel, AT&T, ZTE, Telecom Italia, Sierra Wireless, NEC, Huawei, LG Electronics, China Unicom, Qualcomm, KDDI, Orange
|  |  |  | CRs to TS-0001 |  | n.a. | n.a. | n.a. | TP#23 | WG2 |  | Depending on the conclusion of TR-0024
WI-0038 | Maintenance of oneM2M release 1 (REL1_MNT) | v0.0.1 | obsolete | CRs to Rel1 TSs | Maintenance of oneM2M Release 1 Specifications (REL1_MNT) | n.a. | n.a. | n.a. |  | TP | n.a. | Maintenance of oneM2M Release 1 Specifications (REL1_MNT) | WI closed at TP#25
WI-0039 | Small Technical Enhancements of oneM2M release 2 Specifications (REL2_STE) | v0.0.1 | obsolete | CRs to Rel2 TSs | Small Technical Enhancements of oneM2M Release 2 Specifications (REL2_STE) | n.a. | n.a. | n.a. |  | TP | n.a. | Small Technical Enhancements of oneM2M Release 2 Specifications (REL2_STE) | WI closed at TP#25
WI-0040 | Web-Socket-Binding | v0.0.1 | obsolete | TS-0020 | WebSocket protocol binding | TP 18 | TP 20 | TP 22 | TP 23 | WG3 | 100% | Rapporteur: Shingo Fujimoto, Fujitsu. WI closed at TP#25 | FUJITSU(TTC), Qualcomm Inc.(TIA), Huawei(CCSA/ETSI), SIERRA WIRELESS(ETSI), Telecom Italia(ETSI), InterDigital (ATIS)
WI-0041 | Subscription Notification | v0.0.1 | obsolete | CRs to TS-0001 | subscription/notification mechanism non-blocking communication mechanism | n.a. | n.a. | n.a. | TP#20 | WG2 | 100% | Rapporteur: SeungMyeong Jeong, LGE | LG Electronics, Huawei Technologies, Qualcomm, Ericsson
|  |  |  | CRs to TS-0004 | subscription/notification mechanism non-blocking communication mechanism | n.a. | n.a. | n.a. | TP#21 | WG3 |  | WI closed at TP#25
WI-0042 | Application developer guide | v1.0.0 | obsolete | TR-0025 | Application developer guide | TP 19 | TP 22 | TP 23 | TP 25 | WG6 | 100% | Rapporteur: Laurent Velez (ETSI). WI closed at TP#25 | KETI, LAAS-CNRS, Huawei Technologies Co. Ltd, iconectiv, Fujitsu Ltd., LG Electronics, KDDI Corporation
WI-0043 | Continuation & integration of HGI Smart Home activities | v1.3.0 | obsolete | TR-0022 | Continuation & integration of HGI Smart Home activities | TP19 | - | TP21 | TP24 | WG5 | 100% | Rapporteur: Patricia Martigne (Orange); Some HGI SH items are expected to be forwarded to different oneM2M WGs, but WG5 has the responsibility to keep track of the whole transfer. Version v1.3.0 comes from the need to : - take into account the newly created WI on “oneM2M and OSGi Alliance interworking” approved at TP#23 interim Plenary and the late CRs to TR-0022 that were approved at TP#23, thus moving the Approval date of the final version of TR-0022 to TP#24; - create a new TR for HGI requirements gap analysis towards oneM2M specifications. Completion % for WI-0043 upgraded to 85% which reflected the TR-0022 status at TP#23 closing. With the introduction of a new TR in WI-0043 update at TP#23, the % of completion will be reset back to 10% at the TP#24 opening meeting (TR-0022 would probably be 100% while the new TR will be just a skeleton). WI closed at TP#25 | Orange, Huawei, DT, NEC, Telecom Italia, Modacom, AT&T
|  |  |  | TR-00xy | HGI requirements gap analysis | TP24 | - | TP26 | TP27 | WG5
|  |  |  | CRs to TR-0007 | CR to Abstraction & Semantic TR to take into account HGI SH architecture deliverable |  | n.a. | n.a. | TP#20 | WG5
|  |  |  | CRs to TR-0017 | CR to Home Information Model TR based on HGI SDT evolution |  | n.a. | n.a. | TP#20 | WG5
|  |  |  | CRs to TS-0001 | CR to oneM2M architecture based on analysis detailed in TR-0022 |  | n.a. | n.a. | TP#26 | WG2
|  |  |  | CRs to TS-0023 | CR to Home Abstract Information model to take into account HGI SDT |  | n.a. | n.a. | TP#21 | WG5
|  |  |  | CRs to TS-0012 | CR to oneM2M base ontology |  | n.a. | n.a. | TP#21 | WG5
|  |  |  | CRs to TS-0002 | additional requirements from HGI requirements analysis |  |  |  | TP#26 | WG1
|  |  |  | CRs to TS-0022 | additional requirements from HGI requirements analysis |  |  |  | TP#26 | WG5
|  |  |  | CRs to TS-0005 | additional requirements from HGI requirements analysis |  |  |  | TP#26 | WG5
|  |  |  | CRs to TS-0006 | additional requirements from HGI requirements analysis |  |  |  | TP#26 | WG5
WI-0044 | oneM2M OIC Interworking | v1.1.0 | obsolete | CRs to TS-0002 | Requirements for information model | n.a. | n.a. | n.a. | TP18 | WG1 | 100% | Rapporteur: Kiran Vedula, Samsung Electronics. WI closed at TP#25 | Samsung Electronics, Intel, Fujitsu, MODACOM, DT&C, KDDI, TeliaSonera, IFAST, Orange, KETI, MediaTek, HITACHI, Cisco
|  |  |  | TR-0023 | oneM2M and OIC Interworking | TP#18 | - | TP#20 | TP#21 | WG2
|  |  |  | TS-0024 | oneM2M and OIC Interworking | TP#20 | n.a. | TP#21 | TP#22 | WG2
|  |  |  | CRs to TS-0001 | oneM2M functional architecture | n.a. | n.a. | n.a. | TP#21 | WG2
|  |  |  | CRs to TS-0004 | Service layer core specification | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0045 | Addition of Interoperable Privacy Profiles to oneM2M Security Solutions TS 0003 | v1.0.0 | obsolete | CRs to TS-0003 | 1. To store and process privacy preferences in an interoperable manner. 2. To support privacy profiles at various levels to care for conditions of legal requirements, manufacturers, and data subjects. 3. To prioritise privacy profiles where there is a conflict between profiles | TP#19 | n.a. | n.a. | TP#23 | WG4 | 100% | Rapporteur: Colin Blanchard, BT Group . WI closed at TP#25 | BT Group Plc.; Cadzow Communications Consulting Ltd.; Datang Telecom Technology@Industry Holdings Co., LTD; KDDI Corporation
WI-0019 | Dynamic Authorization for IoT | v1.4.0 | obsolete | TR-0019 | Dynamic Authorization for IoT | TP 12 | TP 22 | TP 23 | TP 24 | WG4 | 100% | Rapporteur: Phil Hawkes, Qualcomm; | Gemalto NV, LG Electronics, CATT, Interdigital, Qualcomm, Oberthur Technologies, Giesecke & Devrient
|  |  |  | CRs to TS 0002 | Dynamic Authorization requirements | n.a. | n.a. | n.a. | TP 18 | WG1 |  | WI-0019: Dynamic Authorization for IoT: 75% • 55% completion of TR-0019 “Dynamic Authorization for IoT”. No change: It is at 55% complete, • 90% completion of changes TS-0001 Functional Architecture. Previously at 0%. • 90% completion of stage 2 changes to TS-0003 Security. Previously at 0%. • The remaining 25% is for work on TR-0019 and stage 3 work in TS-0003 and TS-0004.
|  |  |  | CRs toTS 0001 | oneM2M Function Architecture changes related to Dynamic Authorization | n.a. | n.a. | n.a. | TP 21 | WG2
|  |  |  | CRs toTS-0003 | Dynamic Authorization security spcifications | n.a. | n.a. | n.a. | TP 22 | WG4 |  | If needed, this deadline can slip to TP 23
|  |  |  | CRs toTS-0004 | oneM2M Core Protocol changes related to Dynamic Authorization | n.a. | n.a. | n.a. | TP 23 | WG3 |  | WI closed at TP#27
WI-0067 | UICC Framework Public Key Enhancements (UPK) | v0.0.3 | Approved | CRs to TS-0003 | Public Key Framework for UICC | TP26 | n/a | n/a | TP30 | WG4 | 100% | WI Rapporteur: François Ennesser, Gemalto (ETSI); Approval date change approved TP28. WI closed at TP#32 | Gemalto, Oberthur Technologies, Qualcomm Inc., Huawei, Datang

## TSs
Nr | Title | 1st appr. Rel 1 | latest ratified Rel1 version | latest Rel1 | Version Rel 2 | latest Version Rel 2 | Release 2A ratified TP34 | Version Rel 3 | Version Rel 4 | Rapporteur | Comment
TS-0001 | Functional Architecture | v1.6.0 | v1.13.1 | v1.17.0 | v2.10.0 | v2.18.0 | v2.18.1 | v3.10.0 |  | Weixiang Shao, ZTE | Change of Rapporteur TP33
TS-0002 | Requirements | v1.0.1 |  | v1.0.1 | v2.7.1 | v2.10.2 | v2.10.2 | v3.1.0 | v4.0.0 | Xubei (Echo), Huawei | Change of Rapporteur at TP#25
TS-0003 | Security Solutions | v1.0.1 | v1.4.2 | v1.7.0 | v2.4.1 | v2.12.0 | v2.12.1 | v3.7.0 |  | Wolfgang Granzow, Qualcomm, Qualcomm | Change of Rapporteur post TP30
TS-0004 | Service Layer Core Protocol | v1.0.1 | v1.6.0 | v1.12.0 | v2.7.1 | v2.16.0 | v2.16.1 | v3.6.0 |  | Nobuyuki Uchida, Qualcomm | change of Rapporteur after TP27
TS-0005 | Management Enablement (OMA) | v1.0.1 | v1.4.1 | v1.4.1 | v2.0.0 | v2.0.1 | v2.0.2 | v3.3.0 |  | SeungKyu Park, LG Electronics & Jiaxin Yin, Huawei
TS-0006 | Management enablement (BBF) | v1.0.1 | v1.1.4 | v1.1.4 | v2.0.1 | v2.2.0 | v2.2.1 | v3.6.0 |  | Tim Carey, Nokia
TS-0007 | Service Components | n.a. |  | n.a. | v2.0.0 | v2.0.2 | v2.0.2 |  |  | Tim Carey, Nokia
TS-0008 | CoAP Protocol Binding | v1.0.1 | v1.3.2 | v1.6.0 | v2.0.0 | v2.6.0 | v2.6.1 | v3.0.0 |  | Jiaxin Yin , Huawei Technologies
TS-0009 | HTTP Protocol Binding | v1.0.1 | v1.5.1 | v1.10.0 | v2.6.1 | v2.13.0 | v2.13.1 | v3.0.0 |  | SeungMyeong Jeong, LGE
TS-0010 | MQTT protocol binding | v1.0.1 | v1.5.1 | v1.6.0 | v2.4.1 | v2.7.0 | v2.7.1 |  |  | Peter Niblett, IBM
TS-0011 | Common Terminology | v1.2.1 |  | v1.4.0 | v2.4.1 | v2.8.0 | v2.8.1 | v3.0.0 | v4.0.0 | Roland Hechwartner, Deutsche Telekom
TS-0012 | Base Ontology |  | n.a. | n.a. | v2.0.0 | v2.2.1 | v2.2.2 | v3.7.1 |  | Joerg Swetina, NEC
TS-0013 | Interoperability Testing |  | v1.0.0 | v1.4.0 | v2.0.0 | v2.3.1 | v2.3.2 |  |  | Laurent Velez, ETSI
TS-0014 | LWM2M Interworking |  |  | v0.14.0 | v2.0.0 | v2.2.0 | v2.0.1 | v3.1.0 |  | Timothy Carey, Nokia
TS-0015 | Testing Framework |  |  | v0.5.1 | v2.0.0 | v2.0.0 | v2.0.1 |  |  | Jiaxin Yin , Huawei Technologies
TS-0016 | Secure Environment Abstraction | [6 empty] | v0.8.0 |  | François Ennesser, Gemalto (ETSI)
TS-0017 | Implementation Conformance Statements |  |  |  |  | v2.0.0 |  | v0.2.0 |  | Insong Lee, KETI | change of Rapporteur
TS-0018 | Test Suite Structure and Test Purposes |  |  | v1.1.0 | v2.0.0 | v2.0.0 |  |  |  | Insong Lee, KETI | change of Rapporteur
TS-0019 | Abstract Test Suite & implementation eXtra Information for Test |  |  |  |  | v2.0.0 |  | v0.6.0 |  | Miguel Angel Reina Ortega, ETSI
TS-0020 | WebSocket Protocol Binding |  |  |  | v2.0.0 | v2.0.2 | v2.0.2 |  |  | Wolfgang Granzow, Qualcomm | new rapporteur at TP30
TS-0021 | oneM2M and AllJoyn Interworking |  |  |  | v2.0.0 | v2.0.0 | v2.0.1 |  |  | SeungMyeong Jeong, LGE
TS-0022 | Field Device Configuration |  |  |  |  | v2.3.0 | v2.3.1 |  |  | Wolfgang Granzow, Qualcomm | change of rapporteur
TS-0023 | Home Appliances Information Model and Mapping |  |  |  | v2.0.0 | v2.0.1 | v2.0.2 | v3.7.0 |  | Andreas Kraft (Deutsche Telekom) | new Rapporteur TP33
TS-0024 | OIC Interworking |  |  |  | v2.0.0 | v2.0.1 | v2.0.2 | v3.0.0 |  | Kiran Vedula, Samsung
TS-0025 | Product Profiles | [5 empty] | v2.0.0 | v2.0.0 |  | Jiaxin Yin, Huawei Technologies Co., Ltd., | renamed at TP33; TS-0025 to be added to R2A -if applicable.
TS-0026 | 3GPP Interworking* | [6 empty] | v0.7.0 |  | Xubei (Echo), Huawei; Patricia Martigne, Orange; James Hu, AT&T | *at TP25: According to WI-0058 update name changed to 3GPP Interworking; changed Rapporteur Jessie to Xubei
TS-0027 | Security Implementation Conformance Statements |  |  |  |  | v0.0.1 |  |  |  | Rapporteur: Franck Le Gall (Easy Global Market)
TS-0028 | Security Test Suite Structure and Test Purposes |  |  |  |  | v0.0.1 |  |  |  | Rapporteur: Franck Le Gall (Easy Global Market)
TS-0029 | Security Abstract Test Suite and Implementation eXtra Information for Test |  |  |  |  | v0.0.1 |  |  |  | Rapporteur: Miguel Reina Ortega
TS-0030 | Ontology based Interworking | [6 empty] | v3.0.0 |  | Rapporteur: Joerg Swetina, NEC
TS-0031 | Feature Catalogue |  |  |  |  | v0.2.0 | v0.3.1 |  |  | SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr | renamed at TP33; At TP34:TS-0031 was approved atTP34. After successful editHelp check it will be ratified as TS-0031 V2.0.0 (either via email approval or at TP35 opening) and added to Release 2A. Revised version of Release 2A Control Document will be approved.
TS-0032 | MAF and MEF Interface Specification | [5 empty] | v2.1.0 | v0.1.0 |  | Rapporteur: Wolfgang Granzow, Qualcomm, wgranzow@qti.qualcomm.com
TS-0033 | Proximal IoT Interworking | [6 empty] | v0.1.1 |  | Jiaxin Yin (Huawei Technologies UK (ETSI))
TS-0034 | Semantics Support | [6 empty] | v0.6.0 |  | Editor: Chonggang Wang (Convida)
TS-0035 | OSGi Interworking | [6 empty] | v0.2.0 |  | Editor: Jiaxin Yin (Huawei Technologies Co.,Ltd.)
TS-0036 | Advanced Vehicular Domain Enablement | [6 empty] | v0.0.1 |  | Editor: Kenichi YAMAMOTO (KDDI Corporation)
Approved and Ratified
*Release 2A ratified at TP34. See ADM-0012-Release 2A Control document V2.0.0

## TRs
Nr | Title | latest version | Release 2A | status | Rapporteur | comment
TR-0001 | Use Cases Collection | v4.0.0 | V2.4.2 | Approved | Catalina Mladin, InterDigital
TR-0002 | Architecture Analysis Part1 | v0.2.0 |  | Approved | Richard Brennan, Telxxis
TR-0003 | Architecture Analysis Part 2 | v0.5.0 |  | Approved | Phillip Brown, InterDigital
TR-0004 | Definitions and Acronyms | v0.4.0 |  | Stable Draft | n.a. | obsolete; content moved to TS-0011 Common Terminology
TR-0005 | Roles and Focus Areas | v0.0.4 |  | Draft | Josef Blanz, Qualcomm
TR-0006 | Study of Management Capability Enablement | v0.5.1 |  | Approved | Jiaxin Yin, Huawei
TR-0007 | Study on Abstraction and Semantics Enablement | v2.11.1 |  | Approved | Joerg Swetina, NEC
TR-0008 | Security | v2.0.0 | V2.0.1 | Approved | François Ennesser, Gemalto
TR-0009 | Protocol Analysis | v0.7.0 |  | Approved | Richard Brennan, Telxxis
TR-0010 | Device_Gateway_Classification | v0.0.0 |  | Draft | Hongbeom Ahn, LGE | WI-0006 obsolete. TR not started
TR-0011 | MQTT Protocol Interworking Study | v0.1.0 |  | Draft | Peter Niblett, IBM
TR-0012 | End-to-End-Security and Group Authentication | v2.0.0 |  | Approved | Ziyao Cheng, China Mobile
TR-0013 | Home Domain Enablement | v1.0.0 |  | Approved | Sungchan Choi, KETI & Dongjoo KIM, LGE
TR-0014 | oneM2M AllJoyn Interworking | v0.4.0 |  | Draft | SeungMyeong JEONG, LG Electronics | To be adjusted to naming convention: AllJoyn Interworking
TR-0015 | Service Layer API Core Principles | v0.1.0 |  | Draft | Xuan He, Hitachi
TR-0016 | Authorization Architecture and Access Control Policy | v2.0.0 |  | Approved | Wei Zhou, Datang
TR-0017 | Home Domain Abstract Information Model | v2.0.0 |  | Approved | Sungchan Choi, KETI & Dongjoo KIM, LGE
TR-0018 | Industrial Domain Enablement | v2.5.1 | V2.5.2 | Approved | Miao Jiang, Hitachi (China) Research &Development Corporation (CCSA), miaojiang@hitachi.cn. Chengsui Lu, Hitachi (China) Research &Development Corporation (CCSA), cslu@hitachi.cn | new rapporteur at TP28
TR-0019 | Dynamic_Authorization | v2.0.0 |  | Approved | Phil Hawkes, Qualcomm | Ratified at TP#27
TR-0020 | Study of service transactions and re-usable service layer context | v0.8.0 |  | Draft | Qiuting Li, ZTE
TR-0021 | Study of the action triggering in M2M | v0.5.0 |  | Draft | Jiaxin Yin, Huawei Technologies Co.,Ltd
TR-0022 | Continuation and Integration of HGI Smart Home activities | v2.0.0 |  | Approved | Patricia Martigne, ORANGE
TR-0023 | oneM2M and OIC Interworking | v0.2.0 |  | Draft | Kiran Vedula, Samsung Electronics | To be adjusted to naming convention: OIC Interworking
TR-0024 | 3GPP Interworking | v2.2.0 |  | Approved | Shao Weixiang, ZTE
TR-0025 | Application Developer Guide | v2.0.1 | V2.0.2 | Approved | Laurent Velez, ETSI
TR-0026 | Vehicular Domain Enablement | v0.11.0 |  | Approved | Jairo Lopez, Hitachi, Jiaxin Yin, Huawei Technologies, DongJoo Kim, LGE, Kenichi Yamamoto, KDDI | Approved at TP31
TR-0027 | DDS usage in oneM2M | v0.2.0 |  | Draft | Bei Xu (Echo), Huawei
TR-0028 | Analysis on the interworking between oneM2M and OSGi Alliance | v0.1.0 |  | Draft | Jiaxin Yin (Huawei Technologies Co.,Ltd.)
TR-0029 | Methodology of product profiles definition | v0.0.1 |  | Draft | Jiaxin Yin, Huawei Technologies Co., Ltd.,
TR-0030 | Service Layer Forwarding | v0.3.0 |  | Draft | Rapporteur: Dale Seed, InterDgital (Dale.Seed@InterDigital.com)
TR-0031 | LWM2M DM & Interworking Enhancements | v0.5.0 |  | Draft | Rapporteur: Dale Seed, InterDgital (Dale.Seed@InterDigital.com)
TR-0032 | Platform features catalogue | v0.0.1 |  | Draft | Editor: SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr | obsolete
TR-0033 | Study on Enhanced Semantic Enablement | v0.8.1 |  | Draft | Editor: Martin Bauer
TR-0034 | Temperature monitoring example using CoAP binding | v0.2.2 | V2.0.0 | Approved | Rapporteur: Shane He
TR-0035 | Developer guide of device management | v0.2.1 | V2.0.0 | Approved | Rapporteur: Jiaxin Yin
TR-0036 | Smart City | v0.0.1 |  | Draft | Rapporteur: Jae Young Ahn, ETRI (ahnjy@etri.re.kr )
TR-0037 | Smart Farm Example using MQTT Binding | v0.1.0 | V2.0.0 | Approved | Rapporteur: Ting Martin Miao
TR-0038 | Developer guide-Implementing security example | v0.4.0 |  | Draft | Rapporteur: Rapporteur: Francois Ennesser, & Laurent Velez
TR-0039 | Developer guide-SDT-based implementation | v0.0.5 | V2.0.0 | Approved | Rapporteur: Patricia Martigne & Laurent Velez
TR-0040 | Trust management in oneM2M | v0.0.2 |  | Draft | Rapporteur: Jae Young Ahn, ETRI (ahnjy@etri.re.kr )
TR-0041 | Decentralized Authentication | v0.4.0 |  | Approved | Rapporteur: Jie SHI (Huawei Technologies Co.,Ltd (CCSA))
TR-0042 | WOT Interworking | v0.2.0 |  | Draft | Rapporteur: Yongjing Zhang, zhangyongjing@huawei.com
TR-0043 | Modbus Interworking | v0.1.0 |  | Draft | Rapporteur: Qiuting Li, li.qiuting@zte.com.cn
TR-0044 | Heterogeneous identification service in oneM2M system | v0.0.1 |  | Draft | Rapporteur: Yuan TAO (Computer Network Information Center&Chinese Academy of Sciences Guangzhou Sub-center)
TR-0045 | Developer Guide: Implementing Semantics | v0.3.1 | V2.0.0 | Approved | Rapporteur: Martin Bauer (NEC Europe Ltd. (ETSI))
TR-0046 | Study on Disaster Alert Service Enabler | v0.0.1 |  | Draft | Rapporteur: SeungMyeong JEONG (KETI)
TR-0047 | Developer Guide of 3GPP Interworking | v0.0.1 |  | Draft | Rapporteur: BEI XU (Huawei Telecommunication)
TR-0048 | oneM2M App-ID Registry Function | v0.0.4 |  | Approved | Rapporteur: Shelby Kiewel (iconectiv) | Release 3
TR-0049 | Industrial Domain Information Mapping and Semantics Support | v0.0.1 |  | Draft | Rapporteur: Chengsui Lu (Hitachi (China) Research & Development Corporation)
TR-0050 | Attribute Based Access Control Policy | v0.2.0 |  | Draft | Rapporteur: Wei Zhou (Datang Telecom Technology@Industry Holdings Co., LTD)
TR-0051 | oneM2M API Guide | v0.0.2 |  | Draft | Rapporteur: Laurent VELEZ (European Telecommunications Standards Institute (ETSI))
TR-0052 | Study on Edge and Fog Computing in oneM2M systems | v0.0.1 |  | Draft | Rapporteur: Kenichi YAMAMOTO (KDDI Corporation)

## ADM
Nr | Title | latest version | status | comment
ADM-0001 | oneM2M Work Programme | v34.0.0 | Draft | version number reflects corresponding # of TP meeting
ADM-0002 | oneM2M Partnership Agreement-V2_0 | v2 | Approved
ADM-0003 | oneM2M-Drafting-Rules | v1 | Approved
ADM-0004 | Method of Work | v1.4.0 | Approved
ADM-0005 | oneM2M Working Procedures | v7.0 | Draft
ADM-0006 | Business Card Policy | v1.0.3 | Draft
ADM-0007 | Release Control Document-Aubergine | v1.0.0 | Draft
ADM-0008 | Release 1 Control Document | v1.0.0 | Draft
ADM-0009 | Test Event Working Procedure | v0.1 | Draft
ADM-0010 | Release 2 Description Document | v0.4.0 | Draft
ADM-0011 | Release 2 Control Document | v2.0.0 | Approved
ADM-0012 | Release 2A Control Document | v2.0.0 | Approved | V2.0.0 approval @TP34 opening

## Release 2A
Release 2A ratified at TP34
Technical Specifications and Reports as defined in R2A control document - ADM-0012
TS 0001 - Functional Architecture, V2.18.1
TS 0002 - Requirements, V2.10.2
TS 0003 - Security Solutions, V2.12.1
TS 0004 - Service Layer Core Protocol, V2.16.1
TS 0005 - Management enablement (OMA), V2.0.2
TS 0006 - Management enablement (BBF), V2.2.1
TS 0007 – Service Components, V2.0.2
TS 0008 - CoAP Protocol Binding, V2.6.1
TS 0009 - HTTP Protocol Binding, V2.13.1
TS 0010 - MQTT Protocol Binding, V2.7.1
TS 0011 – Common Terminology, V2.8.1
TS-0012 – Base Ontology, V2.2.2
TS-0013- Interoperability Testing, V2.3.2
TS-0014 - LWM2M Interworking, V2.0.1
TS-0015 – Testing Framework, V2.0.1
TS-0020 - WebSocket Protocol Binding, V2.0.2
TS-0021 - oneM2M and AllJoyn Interworking, V2.0.1
TS-0022 - Field Device Configuration-V2.3.1
TS-0023 - Home Appliances Information Model and Mapping, V2.0.2
TS-0024 - OIC Interworking, V2.0.2
TS-0025 – Product Profiles, V2.0.0
TS-0032 – MAF and MEF Interface Specification-V2.1.0
TR-0001 Use Cases Collection, V2.4.2
TR-0008 Security, V2.0.1
TR-0018 Industrial Domain Enablement, V2.5.2
TR-0025 Application developer guide, V2.0.2
TR-0034 CoAP binding and long polling for temperature monitoring, V2.0.0
TR-0035 Device management use case, V2.0.0
TR-0037 Smart farm example using MQTT binding, V2.0.0
TR-0039 Developer guide-SDT-based implementation, V2.0.0
TR-0045 Implementing semantics, V2.0.0
Deliverables that are not ready for ratification @ TP34:
TS-0031 Feature Catalouge was approved atTP34. After successful editHelp check it will be ratified as TS-0031 V2.0.0 (either via email approval or at TP35 opening) and added to Release 2A. Revised version of Release 2A Control Document will be approved.
TR-0007 Study on Abstraction and Semantics Enablement, V2.11.2. - requires updates (use of normative language) before ratification.

## Timeline R3, R4
Release-3 and Release-4 high-level time-line

## Progress
oneM2M Release schedule
Release 3 Freeze Dates*: Stage 1 TP#27 - Stage 2 TP#30** - Stage 3 TP#35
Work Item Progress
WI number | Title | % completion TP17 | % completionTP18 | % completion TP19 | % completion TP20 | % completion TP21 | % completion TP22 | % completion TP23 | % completion TP24 | % completion TP25 | % completion TP26 | % completion TP27 | % completion TP28 | % completion TP29 | % completion TP30 | % completion TP31 | % completion TP32 | % completion TP33 | % completion TP34
WI-0021 | Secure Environment Abstraction | 10% | 20% | 25% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 40% | 40% | 40% | 40% | 50% | 50% | 80% | 90%
WI-0030 | M2M Application & Field Domain Component Configuration | 5% | 30% | 35% | 45% | 50% | 50% | 60% | 95% | 70% | 80% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
WI-0031 | Optimized Group-based Operation | 10% | 20% | 30% | 30% | 50% | 70% | 80% | 80% | 80% | 80% | 80% | 90% | 90% | 95% | 95% | 95% | 95% | 95%
WI-0034 | Study of re-usable service layer context &Transaction enablement | 0% | 10% | 15% | 20% | 20% | 20% | 50% | 50% | 90% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
WI-0035 | Action Triggering | 0% | 10% | 20% | 30% | 40% | 40% | 80% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95%
WI-0046 | Vehicular domain enablement |  |  |  | 5% | 20% | 40% | 40% | 50% | 65% | 70% | 80% | 85% | 90% | 95% | 55% | 60% | 60% | 65%
WI-0047 | DDS usage in oneM2M system | [6 empty] | 0% | 5% | 20% | 30% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50%
WI-0048 | OSGi Interworking | [6 empty] | 0% | 5% | 5% | 5% | 5% | 15% | 20% | 60% | 60% | 95% | 95% | 95%
WI-0052 | LWM2M DM & Interworking Enhancements | [7 empty] | 0% | 5% | 10% | 40% | 80% | 95% | 95% | 100% | 100% | 100% | 100%
WI-0053 | Rel-3 Enhancements on Semantic Support | [7 empty] | 0% | 5% | 20% | 25% | 30% | 35% | 60% | 80% | 95% | 95% | 5% | Enhanced scope. R4 development starts at TP33; R3 completed!
WI-0054 | Developers guide series | [7 empty] | 0% | 1% | 10% | 10% | 60% | 75% | 85% | 90% | 92% | 93% | 95%
WI-0055 | Product Profiles & Feature Catalog | [7 empty] | 0% | 10% | 15% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | 100%
WI-0056 | Evolution of Proximal IoT Interworking | [7 empty] | 0% | 5% | 10% | 15% | 30% | 40% | 80% | 80% | 85% | 85% | 95%
WI-0057 | TEF Interface | [7 empty] | 0% | 5% | 40% | 45% | 85% | 95% | 100% | 100% | 100% | 100% | 100%
WI-0058 | 3GPP and Cellular IoT Interworking | [7 empty] | 0% | 10% | 15% | 30% | 40% | 50% | 85% | 90% | 90% | 95% | 95%
WI-0059 | OPC-UA Interworking | [7 empty] | 0% | 15% | 30% | 50% | 75% | 90% | 95% | 95% | 95% | 100% | 100%
WI-0061 | Distributed Authorization | [7 empty] | 0% | 10% | 35% | 70% | 70% | 85% | 90% | 100% | 100% | 100% | 100%
WI-0062 | Service Layer Forwarding | [7 empty] | 0% | 5% | 25% | 50% | 90% | 90% | 90% | 100% | 100% | 100% | 100%
WI-0063 | Release 3 Enhancements on Base Ontology and Ontology based Interworking | [7 empty] | 0% | 5% | 15% | 20% | 50% | 55% | 75% | 90% | 95% | 95% | 99%
WI-0064 | Adaptation of oneM2M for Smart City | [8 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 20% | 20% | 20%
WI-0065 | Trust Management in oneM2M | [8 empty] | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 20% | 20%
WI-0066 | Decentralized Authentication | [9 empty] | 0% | 15% | 40% | 70% | 70% | 70% | 70% | 75% | 75%
WI-0067 | UICC Framework Public Key Enhancements (UPK) | [9 empty] | 0% | 0% | 40% | 85% | 90% | 95% | 100% | 100% | 100%
WI-0068 | GlobalPlatform Interworking (GPI) | [9 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
WI-0069 | Heterogeneous identification service in oneM2M system | [9 empty] | 0% | 0% | 0% | 60% | 60% | 60% | 60% | 90% | 90%
WI-0070 | Disaster Alert Service Enabler (DASE) | [10 empty] | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10%
WI-0071 | oneM2M and W3C Web of Things Interworking (WOTIWK) | [10 empty] | 0% | 5% | 10% | 10% | 10% | 10% | 15% | 25%
WI-0072 | Modbus interworking | [10 empty] | 0% | 0% | 60% | 60% | 60% | 60% | 60% | 60%
WI-0073 | App-ID Registry Function | [13 empty] | 0% | 10% | 30% | 30% | 100%
WI-0075 | Industrial Domain Information Model Mapping and Semantics Support | [14 empty] | 0% | 5% | 10% | 10%
WI-0076 | Lightweight oneM2M Services | [14 empty] | 0% | 0% | 0% | 5%
WI-0077 | Attribute Based Access Control Policy | [14 empty] | 0% | 0% | 15% | 15%
WI-0078 | oneM2M API guide | [15 empty] | 0% | 0% | 0%
WI-0080 | Edge and Fog Computing | [16 empty] | 0% | 5%
WI-0081 | Smart Device Template 4.0 | [16 empty] | 0% | 0%
WI-0082 | 3GPP V2X Interworking | [16 empty] | 0% | 5%
WI-0083 | oneM2M Service Subscribers and Users | [16 empty] | 0% | 5%
WI-0084 | SDT based Information Model and Mapping for Vertical Industries | [17 empty] | 0%
* Reassessment of Stage 3 milestone at TP#33
** Frozen with Exceptions: Exceptions frozen at TP31

## Progress Testing
Testing
Work Item Completion
WI number | Title | % completion TP17 | % completionTP18 | % completion TP19 | % completion TP20 | % completion TP21 | % completion TP22 | % completion TP23 | % completion TP24 | % completion TP25 | % completion TP26 | % completion TP27 | % completion TP28 | % completion TP29 | % completion TP30 | % completion TP31 | % completion TP32 | % completion TP33 | % completion TP33
WI-0032 | Conformance Test | 5% | 10% | 15% | 35% | 39% | 43% | 43% | 43% | 46% | 50% | 50% | 60% | 62% | 93% | 96% | 97% | 100% | 100%
WI-0051 | Security Functions Conformance Testing | [7 empty] | 0% | 5% | 5% | 5% | 15% | 15% | 30% | 67% | 100% | 100% | 100%
WI-0060 | Interoperability testing Release 2 | [7 empty] | 0% | 10% | 10% | 10% | 70% | 90% | 90% | 90% | 92% | 92% | 92%
WI-0074 | Conformance Test Specifications Release 2 | [13 empty] | 0% | 0% | 0% | 0% | 0%

## Association WT WIs
Work Tracks as defined in TP-2016-188R01
1.Work Track 1, “Market Adoption Track”
a.Task on Essential Corrections & Small Technical Enhancements [1a]
b.Task on development and/or enhancements of guidelines and/or TSs and best practices documents for easier implementation and take-up of oneM2M technology [1b]
c.Task on testing [1c]
d.Task on completion of well-progressed Release-2 Work Items [1d]
2.Work Track 2, “Industrial IoT and smart cities”
a.Task on reach out to IIoT & smart city experts & descriptions of deployments in IIoT/smart cities based on oneM2M [2a]
b.Task on improvement and addition of requirements for the IIoT and smart Cities [2b]
c.Task on studies on new features (targeting TRs for now) [2c]
3.Work Track 3, “Forward Looking Areas” [3]
Initial proposed association of WT with WIs:
Work Track | WI number | WI - name | % completion TP28
1a | WI-0049 | Maintenance of oneM2M Release 1 and 2 | n.a.
1a | WI-0050 | Small Technical Enhancements of oneM2M Release 3 | n.a.
1b | WI-0048 | OSGi Interworking | 15%
1b | WI-0052 | LWM2M DM & Interworking Enhancements | 80%
1b | WI-0054 | Developers guide series | 10%
1b | WI-0055 | Product Profiles & Feature Catalog | 30%
1b | WI-0056 | Evolution of Proximal IoT Interworking | 30%
1b | WI-0062 | Service Layer Forwarding | 90%
1b | WI-0063 | Release 3 Enhancements on Base Ontology and Generic Interworking | 50%
1b | WI-0066 | Decentralized Authentication | 40%
1c | WI-0032 | Conformance Test | 60%
1c | WI-0051 | Security Functions Conformance Testing | 15%
1c | WI-0060 | Interoperability testing Release 2 | 70%
1d | WI-0019 | Dynamic Authorization for IoT | 100%
1d | WI-0021 | Secure Environment Abstraction | 40%
1d | WI-0030 | M2M Application & Field Domain Component Configuration | 100%
1d | WI-0031 | Optimized Group-based Operation | 90%
1d | WI-0034 | Study of re-usable service layer context &Transaction enablement | 95%
1d | WI-0035 | Action Triggering | 95%
1d | WI-0037 | 3GPP Rel13 Interworking | 100%
1d | WI-0040 | Web-Socket-Binding | 100%
1d | WI-0045 | Addition of Interoperable Privacy Profiles to oneM2M Security Solutions TS 0003 | 100%
1d | WI-0053 | Rel-3 Enhancements on Semantic Support | 30%
1d | WI-0057 | TEF Interface | 85%
1d | WI-0058 | Interworking with 3GPP networks | 40%
1d | WI-0061 | Distributed Authorization | 70%
2a | WI-0047 | DDS usage in oneM2M system | 30%
2a | WI-0059 | OPC-UA Interworking | 75%
2a | WI-0064 | Adaptation of oneM2M for Smart City | 5%
2b | WI-0069 | Heterogen. identificat. service in oneM2M system | 0%
2b | WI-0072 | Modbus interworking | 0%
2c | WI-0046 | Vehicular domain enablement | 85%
2c | WI-0065 | Trust Management in oneM2M | 10%
3 | WI-0067 | UICC Public Key Enhancements | 40%
3 | WI-0068 | GlobalPlatform Interworking | 0%
3 | WI-0070 | Disaster Alert Service Enabler | 0%
3 | WI-0071 | oneM2M and W3C Web of Things Interworking | 5%

## History
History of Change
V0.0.0 | 2013-08-05 | First draft of new Work Programme Report
V0.1.0 | 2013-08-08 | Incorporation of Raporteur updates
V7.0.0 | 2013-10-18 | First draft of administrative perm document "oneM2M-ADM-0001-oneM2M_Work_Programme-V7_00_00"
V8.0.0 | 2013-12-12 | Input to TP#8 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - register ADM Text Part adapted to official ADM template (oneM2M-Template-ADM-20131008.doc)
V9.0.0 | 2014-02-21 | Input to TP#9 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0005R01 into register ADM Text Part
V10.0.0 | 2014-04-11 | Input to TP#10 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - conversion TR-0004 into TS-0011 according to CR TP-2014-0028 - update target dates for TS-0003 according to CR TP-2014-0029R1 - update target dates for TS-0007 according to CR TP-2014-0408 - update target dates for TR-0009 according to CR TP-2014-0417
V11.0.0 |  | Input to TP#11 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0008R01 into register ADM Text Part- update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E
V12.0.0 | 2014-08-01 | Input to TP#12 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - approved deliverables deleted from tracking registers B, C, D, E - new WI16 (TR 0012) incorporated
V17.0.0 | 2015-06-04 | Input post TP#17 : - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V17.1.0 | 2015-07-15 | Input prior TP18: - new register: R2 timeline - register WIs: added column level of completeness as of TP17
V18.0.0 | 2015-07-24 | Input TP#18 : - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated - added Annex F WI Progress and new Register Progress
V18.1.0 | 2015-08-20 | progress update for WI-0033 and update of TR and TS list
V19.0.0 | 2015-09-11 | Input TP#19 : - update with latest WI status including added column supporting companies - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated - added Annex G: Progress Testing
V19.1.0 | 2015-10-14 | update of WIs with recently uploaded TRs and TSs
V19.2.0 | 2015-10-22 | update of WIs and TRs/TSs list with recently uploaded TRs and TSs
V19.3.0 | 2015-11-02 | update of TR and TS list
V20.0.0 | 2015-11-13 | Input TP#20: - updated with latest WI status including progress and timeline
V20.1.0 | 2015-12-14 | update of TR and TS list with latest versions, as well as WI-0046 with TR number
V21.0.0 | 2016-01-22 | Input TP#21: - updated with latest WI status including progress
V21.1.0 | 2016-03-11 | update of TR and TS list with latest versions. Update WI-0017
V22.0.0 | 2016-04-08 | Input TP#22: - updated with latest WI status including progress
V22.1.0 | 2016-04-27 | updated WI scheules according to latest approved changes
V23.0.0 | 2016-05-22 | Input TP#23 : - update with latest WI status including closure of WI-0001 - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V23.1.0 | 2016-06-08 | update of TR and TS list with latest versions
V24.0.0 | 2016-07-22 | Input TP#24 : - update with latest WI status - updated the registers (new register: Association of Work Tracks and WIs) - new WIs incorporated
V24.1.0 | 2016-10-05 | Input TP#24.1 : - update with latest WI status - updated TR and TS lists
V24.2.0 | 2016-10-11 | added TS-0030 and corrections to Work Track and Work Item association
V25.0.0 | 2016-10-21 | Input TP#24.1 : - update with latest WI status - updated TR and TS lists - re-arranged document - active and closed Wis are listed in dedicated registers
V25.1.0 | 2016-11-23 | update of TR and TS lists
V25.2.0 | 2016-11-23 | change of rapporteur from Jessie to Xubei (Echo) - both Huawei
V25.3.0 | 2016-11-29 | updated TR and TS lists - correction of rapporteurs
V26.0.0 | 2016-12-09 | Input TP#26: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V26.1.0 | 2017-01-19 | updated the registers : Wis, TSs, TRs,
V26.2.0 | 2017-02-07 | updated the register TSs - adjusted company affiliation for rapporteurs
V27.0.0 | 2017-02-17 | Input TP#27: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V27.1.0 | 2017-02-28 | update with latest WI status updated the registers Actice WI. TS, TR, ADM
V27.2.0 | 2017-03-17 | update with latest WI status, clarified table showing TS release versions and added rapporteurs updated the registers Actice WI, TS, TR,ADM
V27.3.0 | 2017-03-23 | updated the registers Actice WI, TS, TR,ADM
V27.4.0 | 2017-03-24 | updated the registers Actice WI, TS, TR,ADM
V28.0.0 | 2017-03-31 | Input TP#28: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs
V28.1.0 | 2017-05-09 | update with latest WI status updated the registers new WIs, TSs, TRs, ADMs
V28.2.0 | 2017-05-12 | update with latest WI status updated the registers new WIs, TSs, TRs, ADMs
V29.0.0 | 2017-06-08 | Input TP#29: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs
V29.1.0 | 2017-06-27 | updated with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V29.2.0 | 2017-07-03 | updated with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V29.3.0 | 2017-07-06 | updated with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V30.0.0 | 2017-07-20 | Input TP#30: - update with latest WI status - 2 new WIs and WI updates for WI-46, WI-56, WI-66 - updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V30.1.0 | 2017-09-04 | update with latest WI status updated the registers new: TSs, TRs, ADMs
V30.2.0 | 2017-09-12 | update with latest WI status updated the registers new: TSs, TRs, ADMs
V31.0.0 | 2017-09-22 | Input TP#31: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V31.1.0 | 2017-11-02 | update with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V31.2.0 | 2017-11-06 | update with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V32.0.0 | 2017-11-28 | Input TP#32: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V32.2.0 | 2018-01-09 | update with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V33.0.0 | 2018-01-24 | Input TP#33: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V33.1.0 | 2018-03-08 | update with latest WI status; Release 2A deliverables for ratification. updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V34.0.0 | 2018-03-23 | Input TP#34: - update with latest WI status - updated the registers :active Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..