## ADM-0001 v55.0.0
Administrative Document
ADM-0001-V-55.0.0
oneM2M Work Programme
11.07.2022
Copyright Notification
No part may be reproduced except as authorized by written permission.
The copyright and the foregoing restriction extend to reproduction in all media.
This document is intended for distribution only to oneM2M Participants.
© oneM2M Partners Type 1 (ARIB, ATIS, CCSA, ETSI, TIA, TSDSI, TTA, TTC)
Conventions
Scaling of level of completeness
• Value range from 0% - 100%, no special scaling requested. Highest level achievable in a WG is 95%
• Measurement will be against milestone “Approval” listed in the agreed respective Work Item (meaning that 100% completeness must be achieved for reaching this milestone)
• Expected levels of completeness at milestones:
Start - 0%
First draft / skeleton - 10%
Freeze - 90%
WG decision: “ready for approval” - 95%
Approval (by TP) - 100%
Please see also the WPM portal for the latest work program status.
http://member.onem2m.org/Application/documentapp/downloadLatestRevision/?docId=3491

## WIs
At the TP#38 a new WG structure was approved. Primary responsible WG map as follows: WG1 old => WG1; WG2 old => WG2; WG3 old=> WG2; WG4 old=> WG2; WG5old => WG1 or WG2; WG6 old=> WG3
WI number | Title | Ver | Status | Deliverables | Title | Start | Change Control | Freeze | Approval | primary responsible new WGs | Comment | Supporting Companies
WI-0001 | Requirements | v1.4 | Closed | TS-0002 | Requirements |  |  |  |  | WG1 | Rapporteur TS-0002: Yu Qi, Huawei;Lijing, Huawei; WI closed at TP#23;
|  |  |  | TR-0001 | Use Cases Collection |  |  |  |  | WG1 | Rapporteur: Catalina Mladin, InterDigital
WI-0002 | Architecture | v1.4 | Closed | TS-0001 | Functional Architecture |  |  |  |  | WG2 | Rapporteur: Rajesh Bhalla, ZTE & Yingjie Hong, ZTE (CCSA)
|  |  |  | TR-0002 | Architecture Analysis Part1 |  |  |  |  | WG2 | Rapporteur: Richard Brennan, Telxxis
|  |  |  | TR-0003 | Architecture Analysis Part2 |  |  |  |  | WG2 | Rapporteur: Phillip Brown, InterDigital
WI-0003 | VocabPrinciples | v1.4 | Closed | TS-0011 | Common Terminology | TP#2 | TP#3 | TP#11 | TP#12 | WG1 | Rapporteur: Roland Hechwartner, Deutsche Telekom | AT&T (ATIS), Deutsche Telekom (ETSI), Qualcomm Inc. (TIA), InterDigital Communications (TIA), Telecom Italia (ETSI), Vodafone (ETSI), Huawei Device Company (TIA), Intel (TIA), Sprint (TIA) , NEC Corporation (TTC), NEC Europe (ETSI)
|  |  |  | TR-0005 | Roles and Focus Areas | TP#2 | TP#3 | TP#11 | TP#12 | WG1 | Rapporteur: Josef Blanz, Qualcomm; TR-0005 - expected to be progressed; Then close of WI. WI closed at TP#25
WI-0004 | Management_Capability_Enablement_Technologies | v1.1 | Closed | TR-0006 | Study of Capability Enablement Technologies for Consideration by oneM2M | TP#3 | TP#7 | TP#7 | TP#8 | WG5 | Rapporteur: Jiaxin Yin, Huawei. WI closed at TP#25 | Huawei (CCSA), NEC (ETSI), NEC (TTC), Alcatel-Lucent (ATIS), InterDigital (ETSI), Eurecom
WI-0005 | Abstraction & Semantics Capability Enablement | v1.3 | Closed | TR-0007 | Study of Abstraction and Semantics Enablements | TP#16 | n.a. | TP#19 | TP#20 | WG5 | Rapporteur: Joerg Swetina, NEC. WI closed at TP#25
|  |  |  | TS-0012 | Base Ontology | TP#16 | TP#18 | TP#19 | TP#20 | WG5 | TS-0012 is developed under WI-0025 (Generic Interworking with Area Networks)
|  |  |  | TS-0002 | Requirements | TP#16 | n.a. | TP#18 | TP#19 | WG1 | Rapporteur: Yu Qi, Huawei
|  |  |  | TS-0001 | Functional Architecture | TP#18 | n.a. | TP#20 | TP#21 | WG2
|  |  |  | TS-0003 | oneM2M Security Solutions | TP#18 | n.a. | TP#20 | TP#21 | WG4
|  |  |  | TS-0004 | Service Layer Core Protocol | TP#20 | n.a. | TP#22 | TP#23 | WG3 | and related protocol bindings
WI-0006 | Device_Gateway_Class | v1.3 | Closed | TR-0010 | [6 empty] | Rapporteur: Hongbeom Ahn, LGE
WI-0007 | Security | v1.4 | Closed | TR-0008 | Analysis of security solutions | TP#5 | TP#9 | TP#9 | TP#10 | WG4 | Rapporteur: Claus Dietze (G&D)
|  |  |  | TS-0003 | Security Solutions | TP#6 | TP#10 | TP#10 | TP#11 | WG4 | Rapporteurs: Claus Dietze (G&D)
WI-0008 | Protocol-TR | v1.2 | Closed | TR-0009 | Protocol Analysis | TP#5 | TP#9 | TP#9 | TP#10 | WG3 | Rapporteur: Richard Brennan, Telxxis. WI closed at TP25
WI-0009 | Protocol-Development | v1.4 | Closed | TS-0004 | Service Layer Protocol Core Specification | TP#5 | TP#11 | TP#11 | TP#12 | WG3
WI-0010 | Management Enablement | v1.1 | Closed | TS-0005 | Management enablement (OMA) | TP#8 | TP#11 | TP#11 | TP#12 | WG5 | Rapporteur: SeungKyu Park, LG Electronics, Jiaxin Yin, Huawei; The work in the WI is based on the work in WG2 and has different focus compared to WG3. WI closed at TP25 | Alcatel-Lucent (ETSI), Huawei Technologies Co., Ltd. (CCSA, ETSI), InterDigital Communications (ATIS), LG Electronics (TTA), NEC Europe (ETSI), Samsung Electornics (ETSI)
|  |  |  | TS-0006 | Management enablement (BBF) | TP#8 | TP#11 | TP#11 | TP#12 | WG5 | Rapporteur: Tim Carey, Alcatel-Lucent; The work in the WI is based on the work in WG2 and has different focus compared to WG3
WI-0011 | Service_Component_Architecture | v2.1 | Closed | TS-0007 | Service Components | TP#9 | TP#15 | TP#15 | TP#17 | WG2 | Rapporteur: Tim Carey, Alcatel-Lucent. WI closed at TP25 | Alcatel-Lucent; AT&T; Verizon; Ericsson; ZTE; Orange; LG Electronics
WI-0012 | ProCoapBinding | v1.1 | Closed | TS-0008 | CoAP Protocol Binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | Rapporteur: SeongYoon Kim, LGE
WI-0013 | ProHttpBinding | v1.1 | Closed | TS-0009 | HTTP Protocol Binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | Rapporteur: SeungMyeong Jeong, LGE
WI-0014 | ProMQTTBinding | v1.1 | Closed | TS-0010 | MQTT protocol binding | TP#9 | TP#11 | TP#11 | TP#12 | WG3 | Rapporteur: Peter Niblett, IBM | CISCO (ATIS/ETSI), Telefon AB LM Ericsson (ETSI), IBM (ETSI), Qualcomm (ARIB/ETSI), Sierra Wireless SA (ETSI), Telecom Italia SpA (ETSI)
|  |  |  | TR-0011 | MQTT Protocol Interworking Study | TP#9 | TP#11 | TP#11 | TP#12 | WG2 | Rapporteur: Peter Niblett, IBM
WI-0015 | Use Cases Collection | v1.2 | Active | TR-0001 | Use Cases Collection | TP#8 | TP#8 | n.a. | n.a. | WG1 | Rapporteur: Catalina Mladin, InterDigital; The “Freeze” and “Approval” dates in the above schedule will be determined when the Requirements TS “Freeze” and “Approval” dates are established. | Sprint; Huawei; NEC; Telecom Italia; ZTE
WI-0016 | End-to-End Security and Group Authentication | v2.5.0 | Closed | TR-0012 | End-to-End Security and Group Authentication | TP#12 | TP#22 | TP#23 | TP#24 | WG4 | Rapporteur: ZUO Min (China Mobile) and QI Minpeng (China Mobile) for “End-to-End Security and Group Authentication”. Closed at TP25 | British Telecom, China Mobile, CATT, Hitachi, Huawei, LG Electronics, Qualcomm
|  |  |  | CRs to TS 0002 | End-to-End Security and Group Authentication requirements | n.a. | n.a. | n.a. | TP#18 | WG1
|  |  |  | CRs to TS 0001 | oneM2M Function Architecture changes related to End-to-End Security and Group Authentication | n.a. | n.a. | n.a. | TP#21 | WG2
|  |  |  | CRs to TS-0003 | End-to-End Security and Group Authentication security spcifications | n.a. | n.a. | n.a. | TP#22 | WG4
|  |  |  | CRs to TS-0004 | oneM2M Core Protocol changes related to End-to-End Security and Group Authentication | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0017 | Home Domain Enablement | v2.4.0 | Closed | TR-0013 | Home Domain Enablement | TP#13 | -- | TP#17 | TP#22 | WG1 | Rapporteur: Sungchan Choi, KETI & Dongjoo KIM, LGE; Secondary responsibility by WG2, WG3, WG4, WG5. WI closed at TP 25 | KETI, LGE, ETRI, SK Telecom, LG uplus, nTels, KCA, Kaonmedia, Haier, InterDigital,NTT, KDDI, Fujitsu, Hitachi, NEC, Orange, Samsung Electronics
|  |  |  | TR-0017 | Home Domain Abstract Information Model | TP#16 |  | TP#20 | TP#21 | WG5
|  |  |  | TS-0023 | Home Appliances Information Model and Mapping | TP#19 | -- | TP#22 | TP#23 | WG5/WG3
|  |  |  | TS-0002 | Normative CRs to Requirements | n.a. | n.a. | n.a. | TP#18 | WG1
|  |  |  | TS-0001 | Normative CRs to Functional Architecture | n.a. | n.a. | n.a. | TP#21 | WG2
|  |  |  | TS-0004 | Normative CRs to Core Protocol | n.a. | n.a. | n.a. | TP#21 | WG3
WI-0018 | oneM2M and AllJoyn Interworking | v1.3.0 | Closed | TR-0014 | oneM2M and AllJoyn Interworking | TP#14 | - | TP#18 | TP#19 | WG2 | WI Rapporteur: SeungMyeong JEONG, LG Electronics | LG Electronics, Qualcomm, LG U+, Haier, AT&T, Huawei, ALU
|  |  |  | TS-0021 | oneM2M and AllJoyn Interworking | TP#19 |  | TP#22 | TP#23 | WG2 | WI closed at TP#25
|  |  |  | CRs to TS-0001 | Normative texts to include the solutions studied in the TR-0014 | n.a. | n.a. | n.a. |  | WG2
|  |  |  | CRs to TS-0004 | Normative texts to include the solutions studied in the TR-0014 | n.a. | n.a. | n.a. |  | WG3
WI-0019 | Dynamic Authorization for IoT | v1.4.0 | Closed | TR-0019 | Dynamic Authorization for IoT | TP#12 | TP#22 | TP#23 | TP#24 | WG4 | Rapporteur: Phil Hawkes, Qualcomm; | Gemalto NV, LG Electronics, CATT, Interdigital, Qualcomm, Oberthur Technologies, Giesecke & Devrient
|  |  |  | CRs to TS 0002 | Dynamic Authorization requirements | n.a. | n.a. | n.a. | TP#18 | WG1 | WI-0019: Dynamic Authorization for IoT: 75% • 55% completion of TR-0019 “Dynamic Authorization for IoT”. No change: It is at 55% complete, • 90% completion of changes TS-0001 Functional Architecture. Previously at 0%. • 90% completion of stage 2 changes to TS-0003 Security. Previously at 0%. • The remaining 25% is for work on TR-0019 and stage 3 work in TS-0003 and TS-0004.
|  |  |  | CRs toTS 0001 | oneM2M Function Architecture changes related to Dynamic Authorization | n.a. | n.a. | n.a. | TP#21 | WG2
|  |  |  | CRs toTS-0003 | Dynamic Authorization security spcifications | n.a. | n.a. | n.a. | TP#22 | WG4 | If needed, this deadline can slip to TP 23
|  |  |  | CRs toTS-0004 | oneM2M Core Protocol changes related to Dynamic Authorization | n.a. | n.a. | n.a. | TP#23 | WG3 | WI closed at TP#27
WI-0020 | Service_Layer_API | v1.0.0 | Closed | TR-0015 | Service Layer API Core Principles | TP#15 | - | TP#18 | TP#19 | WG3 | Rapporteur: vacant; @TP22assessment: potential candidate WI for OSGi collaboration. WI closed at TP#25 | Sierra Wireless, Ericsson, LG Electronics, ZTE, Interdigital, AT&T, NEC, Hitachi
|  |  |  | TR-00xx | Service Layer API C Language Binding | TP#15 | - | TP#18 | TP#19 | WG3 | Rapporteur: vacant
WI-0021 | Secure Environment Abstraction | v1.5.0 | Closed | TS-0016 | Secure Environment Abstraction | TP#15 | TP#26 | TP#31 | TP#32 | WG2 | Rapporteur: François Ennesser, Gemalto (ETSI); updated at TP29 | Giesecke & Devrient, Gemalto NV, Oberthur Technologies, Interdigital, CATT, LG Electronics
|  |  |  | CRs toTS 0002 | Secure Environment Abstraction requirements | n.a. | n.a. | n.a. | TP#24 | WG1
|  |  |  | CRs toTS 0001 | oneM2M Function Architecture changes related to Secure Environment Abstraction | n.a. | n.a. | n.a. | TP#28 | WG2
|  |  |  | CRs toTS-0003 | Secure Environment Abstraction security spcifications | n.a. | n.a. | n.a. | TP#31 | WG2
|  |  |  | CRs toTS-0004 | oneM2M Core Protocol changes related to Secure Environment Abstraction | n.a. | n.a. | n.a. | TP#32 | WG2
WI-0022 | Interoperability Testing | v1.1.0 | Closed | TS-0013 | Interoperability Testing | n.a. | n.a. | n.a. | TP#25 | WG6 | Rapporteur: Laurent Velez, ETSI. WI closed at TP#25 | KETI, KCA, NEC, InterDigital
WI-0023 | Authorization Architecture & Access Control Policy | v1.5.0 | Closed | TR-0016 | Authorization Architecture and Policies | TP#15 | TP#21 | TP#22 | TP#23 | WG4 | Wei Zhou, Datang (CCSA); Secondary responsibility WG3, WG2. WI closed at TP#25 | Datang, China Unicom, CATR, ZTE , Huawei, Haier, Gemalto NV
|  |  |  | CRs to TS 0002 | Authorization Architecture and Policies requirements | n.a. | n.a. | n.a. | TP#18 | WG1
|  |  |  | CRs to TS 0001 | oneM2M Function Architecture changes related to End-to- Authorization Architecture and Policies | n.a. | n.a. | n.a. | TP#21 | WG2
|  |  |  | CRs to TS-0003 | Authorization Architecture and Policies security spcifications | n.a. | n.a. | n.a. | TP#22 | WG4
|  |  |  | Crs to TS-0004 | oneM2M Core Protocol changes related to Authorization Architecture and Policies | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0024 | LWM2M Interworking | v0.1.1 | Closed | TS-0014 | LWM2M Interworking | TP#16 | TP#21 | TP#21 | TP#23 | WG2 | Rapporteur: Timothy Carey, Alcatel-Lucent ; TS is expected to incorporate Architecture Work. | Alcatel-Lucent (TIA, ATIS), Gemalto (ETSI), Eurecom (ETSI) Huawei (CCSA), LG Electronics (TTA), InterDigital (ATIS), Sierra Wireless (ETSI), Ericsson (ETSI), KDDI (TTC)
|  |  |  | CRs to TS-0002 | oneM2M Requirements | TP#16 | n.a. | TP#19 | n.a. | WG1 | Change Requests to Requirements TS-0002 For LWM2M Interworking Requirements
|  |  |  | CRs to TS-0001 | Modifications to the oneM2M Architecture is not expected. |  |  |  |  | WG2 | WI closed at TP#25
|  |  |  | CRs to TS-0004 | Modifications to the oneM2M Protocols is not epected |  |  |  |  | WG3
|  |  |  | CRs to TR-0001 | Modifications to Use cases is not expected |  |  |  |  | WG1
WI-0025 | Generic Interworking | v2.1 | Closed | CRs to TR-0007 | CRs to include elaboration / enhancements for interworking (IPEs) | TP#15 | n.a. | TP#17 | TP#18 | WG5 | Rapporteur: Joerg Swetina, NEC | NEC, China Unicom, Modacom, KETI, EURECOM, InterDigital, Alcatel-Lucent
|  |  |  | CRs toTS-0002 | CRs to include additional interworking reqs. | TP#15 | n.a. | TP#17 | TP#17 | WG1 | WI closed at TP#25
|  |  |  | CRs toTS-0012 | oneM2M_Base_Ontology | TP#15 | TP#18 | TP#19 | TP#20 | WG5
|  |  |  | CRs toTS-0001 | CRs to include functionality of IPEs | TP#17 | n.a. | TP#19 | TP#20 | WG2 | … exception needed for ARC part
|  |  |  | CRs toTS-0003 | CRs to include security enhancements for support of IPEs | TP#17 | n.a. | TP#19 | TP#20 | WG4
|  |  |  | CRs toTS-0004 | CRs to include protocol enhancements for support of IPEs | TP#19 | n.a. | TP#20 | TP#21 | WG3
WI-0026 | Efficient Communications | v1.0.0 | Closed | CRs to TR-0001 | Use Cases Collection | TP#15 | n.a. | TP#17 | TP#18 | WG1 | Rapporteur: Josef Blanz, Qualcomm | Qualcomm, Sierra Wireless, Gemalto, Telia Sonera, Deutsche Telekom, Orange, KDDI, Interdigital
|  |  |  | CRs to TS-0002 | Requirements | TP#15 | n.a. | TP#17 | TP#18 | WG1 | WI closed at TP#25
|  |  |  | CRs to TS-0001 | Functional Architecture | TP#16 | n.a. | TP#18 | TP#19 | WG2
|  |  |  | CRs to TS-0004 | Protocols TSs | TP#16 | n.a. | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0008 | Protocol Binding TSs | TP#16 | n.a. | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0009 | Protocol Binding TSs | TP#16 | n.a. | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0010 | Protocol Binding TSs | TP#16 | n.a. | TP#20 | TP#21 | WG3
|  |  |  | CRs to TS-0005 | Management TSs | TP#16 | n.a. | TP#20 | TP#21 | WG5
|  |  |  | CRs to TS-0006 | Management TSs | TP#16 | n.a. | TP#20 | TP#21 | WG5
WI-0027 | Testing Framework | v1.1.0 | Closed | TS-0015 | Test framework defining methodology for testing oneM2M specifications | TP#16 | TP#18 | TP#23 | TP#23 | WG6 | Rapporteur: Jiaxin Yin , Huawei Technologies. WI closed at TP#25 | KETI, Dt&C, Huawei Technologies, LG Electronics, iconectiv, Sierra Wireless
WI-0028 | Industrial Domain Enablement | v1.4.1 | Closed | TR-0018 | Industrial Domain Enablement | TP#16 | TP#20 | TP#20 | TP#21 | WG1 | Rapporteur: Miao Jiang, Hitachi (China) Research &Development Corporation (CCSA), Toshiko Matsumoto, Hitachi (TTC), and Yanping Jiang, Huawei (CCSA). WI closed at TP#25 | Hitachi, Huawei, KDDI, Telecom Itallia SpA, NTT, NEC, InterDigital, KETI, Federal Network Agency (BNetzA)
|  |  |  | CRs to TS-0002 |  |  | n.a. | n.a. | TP#18 | WG1
|  |  |  | CRs toTS-0001 | Architecture impact from industrial domain enablement | n.a. | n.a. | n.a. |  | WG2
|  |  |  | CRs toTS-0004 | Protocol impact from industrial domaine enablement | n.a. | n.a. | n.a. |  | WG3
WI-0029 | App-ID Clarification | v1.1.0 | Closed | CRs to TS-0001 | App-Id clarification | n.a. | n.a. | n.a. | TP#20 | WG2 | Rapporteur: Darold Hemphill, iconectiv | Fujitsu Ltd. (TTC), iconectiv (ATIS), Gemalto (ETSI),Sierra Wireless (ETSI)
|  |  |  | CRs to TS-0002 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG1 | WI closed at TP#25
|  |  |  | CRs to TS-0003 | App-Id clarification | n.a. | n.a. | n.a. | TP#23 | WG4
|  |  |  | CRs to TS-0004 | App-Id clarification | n.a. | n.a. | n.a. | TP#23 | WG3
|  |  |  | CRs to TS-0011 | App-Id clarification | n.a. | n.a. | n.a. | TP#18 | WG1
WI-0030 | M2M Application & Field Domain Component Configuration | v1.1.1 | Closed | CRs to TS-0002 | Requirements regarding Device/Component Configuration | n.a. | n.a. | n.a. | TP#18 | REQ/ARC/SEC/MAS | Rapporteur: Shingo Fujimoto, FUJITSU. Closed @ TP#37 | FUJITSU(TTC), Deutsche Telekom AG (ETSI), Telecom Italia SpA (ETSI), InterDigital Communications (TIA), Alcatel-Lucent (TIA)
|  |  |  | TS-0022 | Field Device Configuration | TP#19 | TP#22 | TP#22 | TP#24 | WG5 | Impacted WGs: ARC, PRO, SEC, TST; additional rapporteur for TS-0004: Nobuyuki Uchida, Qualcomm
WI-0031 | Optimized Group-based Operation | v2.0.0 | Closed | CRs to TS-0002 | Group enhancement requirements | n.a. | n.a. | n.a. | TP#19 | WG1 | Rapporteur: Jiaxin Yin, Huawei Technologies Co., Ltd. | Huawei Technologies Co., Ltd.; InterDigital; KETI; China Unicom
|  |  |  | CRs to TS-0001 | Enhancement in architecture | n.a. | n.a. | n.a. | TP#28 | WG2 | approval milestone updated TP26
|  |  |  | CRs to TS-0004 | Enhancement in protocol | n.a. | n.a. | n.a. | TP#31 | WG3 | approval milestone updated TP26
|  |  |  | CRs to TR-0001 | Group related use cases | n.a. | n.a. | n.a. | TP#19 | WG1 | WI closed @ TP38
|  |  |  | CRs to TR-00012 | Potential CR related to group authentication | n.a. | n.a. | n.a. | TP#19 | WG4
WI-0032 | Conformance Test | v2.0.0 | Closed | TS-0017 | Implementation Conformance Statements | TP#17 | TP#21 | TP#22 | TP#29 | WG6 | Rapporteur: Martin MIAO, KETI; rapporteur and approval date updated TP26. WI closed at TP#32 | Huawei Technologies Co., Ltd., KETI, TTA, Telecom Italia, China Unicom, Dt&C, NTT
|  |  |  | TS-0018 | Test Suite Structure and Test Purposes | TP#17 | TP#21 | TP#24 | TP#29 | WG6 | Rapporteur: Martin MIAO, KETI
|  |  |  | TS-0019 | Abstract Test Suite and Implementation eXtra Information for Test | TP#19 | TP#23 | TP#24 | TP#29 | WG6 | Rapporteur: Laurent Velez, ETSI
WI-0033 | Supporting Time Series Data | v0.0.1 | Closed | TS-0001 | Architecture to support the integrity of data collection monitoring in oneM2M | n.a. | n.a. | n.a. | TP#22 | WG2 | Rapporteur: Qi Yu, Huawei Technologies Co., Ltd | Huawei Technologies, Hitachi , Haier, China Unicom, China academy of information and communications technology
|  |  |  | TS-0004 | Procedure and data type to support the integrity of data collection monitoring in oneM2M | n.a. | n.a. | n.a. | TP#23 | WG3 | WI closed at TP#25
WI-0034 | Study of re-usable service layer context &Transaction enablement | v2.0.1 | Closed | TR-0020 | Study of service transactions and re-usable service layer context | TP#17 | TP#20 | TP#29 | TP#30 | WG2 | Rapporteurs: Qiuting Li, ZTE & Jiaxin Yin, Huawei Freeze and approval milestone updated TP27. WI closed at TP#32 | LGE, ZTE, InterDigital, Spirent, Huawei, IBM, ALU, KETI, nTels
|  |  |  | CRs to TS-0001 | Architecture to support transaction in oneM2M | n.a. | n.a. | n.a. | TP#28 | WG2 | approval milestone updated TP26
|  |  |  | CRs to TS-0004 | Procedure and data type to support transaction in oneM2M | n.a. | n.a. | n.a. | TP#31 | WG3 | approval milestone updated TP26
|  |  |  | CRs to TS-0001 | Architecture to support multimedia streaming session in oneM2M | n.a. | n.a. | n.a. | TP#31 | WG2 | approval milestone updated TP27
|  |  |  | CRs to TS-0004 | Procedure and data type to support multimedia streaming session in oneM2M | n.a. | n.a. | n.a. | TP#32 | WG3 | approval milestone updated TP27
WI-0035 | Action Triggering | v2.1.0 | Closed | TR-0021 | Study of the action triggering in M2M | TP#18 | TP#25 | TP#26 | TP#33 | WG2 | Rapporteur: Jiaxin Yin, Huawei; update Approval date @TP32. WI closed @ TP38 | Huawei Technologies Co., Ltd.; Fujitsu; LGE; Qualcomm
|  |  |  | CRs to TS0001 | New resources definition to support action triggering | n.a. | n.a. | n.a. | TP#28 | WG2 | approval date updated TP26
|  |  |  | CRs to TS0004 | Procedure and data type definition to support action triggering | n.a. | n.a. | n.a. | TP#31 | WG3 | approval date updated TP26
WI-0036 | Update Security Analysis TR for Release 2 | v0.0.1 | Closed | TR-0008 | Outcome of the Release 2 specific threat analysis | n.a. | n.a. | n.a. | TP#19 | WG4 SEC | Rapporteur: Dragan Vujcic, Oberthur Technologies | Giesecke & Devrient, Gemalto, BT Group, Oberthur Technologies, Datang
|  |  |  | TS-0003 | Impact of Release 2 Threat Analysis | n.a. | n.a. | n.a. | TP#20 | WG4 | WI closed at TP#25
|  |  |  | TS-0001 | Architecture impact (if any) | n.a. | n.a. | n.a. | TP#20 | WG2
|  |  |  | TS-0004 | Protocol impact (if any) | n.a. | n.a. | n.a. | TP#21 | WG3
WI-0037 | 3GPP_Rel13_IWK | v1.1.0 | Closed | TR-0024 | 3GPP Rel-13 Interworking | TP#17 | n.a. | TP#21 | TP#23 | WG2 | Rapporteur: Shao Weixiang (ZTE), WI closed at TP#25 | Intel, AT&T, ZTE, Telecom Italia, Sierra Wireless, NEC, Huawei, LG Electronics, China Unicom, Qualcomm, KDDI, Orange
|  |  |  | CRs to TS-0001 |  | n.a. | n.a. | n.a. | TP#23 | WG2 | Depending on the conclusion of TR-0024
WI-0038 | Maintenance of oneM2M release 1 (REL1_MNT) | v0.0.1 | Closed | CRs to Rel1 TSs | Maintenance of oneM2M Release 1 Specifications (REL1_MNT) | n.a. | n.a. | n.a. |  | TP | Maintenance of oneM2M Release 1 Specifications (REL1_MNT) | WI closed at TP#25
WI-0039 | Small Technical Enhancements of oneM2M release 2 Specifications (REL2_STE) | v0.0.1 | Closed | CRs to Rel2 TSs | Small Technical Enhancements of oneM2M Release 2 Specifications (REL2_STE) | n.a. | n.a. | n.a. |  | TP | Small Technical Enhancements of oneM2M Release 2 Specifications (REL2_STE) | WI closed at TP#25
WI-0040 | Web-Socket-Binding | v0.0.1 | Closed | TS-0020 | WebSocket protocol binding | TP#18 | TP#20 | TP#22 | TP#23 | WG3 | Rapporteur: Shingo Fujimoto, Fujitsu. WI closed at TP#25 | FUJITSU(TTC), Qualcomm Inc.(TIA), Huawei(CCSA/ETSI), SIERRA WIRELESS(ETSI), Telecom Italia(ETSI), InterDigital (ATIS)
WI-0041 | Subscription Notification | v0.0.1 | Closed | CRs to TS-0001 | subscription/notification mechanism non-blocking communication mechanism | n.a. | n.a. | n.a. | TP#20 | WG2 | Rapporteur: SeungMyeong Jeong, LGE | LG Electronics, Huawei Technologies, Qualcomm, Ericsson
|  |  |  | CRs to TS-0004 | subscription/notification mechanism non-blocking communication mechanism | n.a. | n.a. | n.a. | TP#21 | WG3 | WI closed at TP#25
WI-0042 | Application developer guide | v1.0.0 | Closed | TR-0025 | Application developer guide | TP#19 | TP#22 | TP#23 | TP#25 | WG6 | Rapporteur: Laurent Velez (ETSI). WI closed at TP#25 | KETI, LAAS-CNRS, Huawei Technologies Co. Ltd, iconectiv, Fujitsu Ltd., LG Electronics, KDDI Corporation
WI-0043 | Continuation & integration of HGI Smart Home activities | v1.3.0 | Closed | TR-0022 | Continuation & integration of HGI Smart Home activities | TP#19 | - | TP#21 | TP#24 | WG5 | Rapporteur: Patricia Martigne (Orange); Some HGI SH items are expected to be forwarded to different oneM2M WGs, but WG5 has the responsibility to keep track of the whole transfer. Version v1.3.0 comes from the need to : - take into account the newly created WI on “oneM2M and OSGi Alliance interworking” approved at TP#23 interim Plenary and the late CRs to TR-0022 that were approved at TP#23, thus moving the Approval date of the final version of TR-0022 to TP#24; - create a new TR for HGI requirements gap analysis towards oneM2M specifications. Completion % for WI-0043 upgraded to 85% which reflected the TR-0022 status at TP#23 closing. With the introduction of a new TR in WI-0043 update at TP#23, the % of completion will be reset back to 10% at the TP#24 opening meeting (TR-0022 would probably be 100% while the new TR will be just a skeleton). WI closed at TP#25 | Orange, Huawei, DT, NEC, Telecom Italia, Modacom, AT&T
|  |  |  | TR-00xy | HGI requirements gap analysis | TP#24 | - | TP#26 | TP#27 | WG5
|  |  |  | CRs to TR-0007 | CR to Abstraction & Semantic TR to take into account HGI SH architecture deliverable |  | n.a. | n.a. | TP#20 | WG5
|  |  |  | CRs to TR-0017 | CR to Home Information Model TR based on HGI SDT evolution |  | n.a. | n.a. | TP#20 | WG5
|  |  |  | CRs to TS-0001 | CR to oneM2M architecture based on analysis detailed in TR-0022 |  | n.a. | n.a. | TP#26 | WG2
|  |  |  | CRs to TS-0023 | CR to Home Abstract Information model to take into account HGI SDT |  | n.a. | n.a. | TP#21 | WG5
|  |  |  | CRs to TS-0012 | CR to oneM2M base ontology |  | n.a. | n.a. | TP#21 | WG5
|  |  |  | CRs to TS-0002 | additional requirements from HGI requirements analysis |  |  |  | TP#26 | WG1
|  |  |  | CRs to TS-0022 | additional requirements from HGI requirements analysis |  |  |  | TP#26 | WG5
|  |  |  | CRs to TS-0005 | additional requirements from HGI requirements analysis |  |  |  | TP#26 | WG5
|  |  |  | CRs to TS-0006 | additional requirements from HGI requirements analysis |  |  |  | TP#26 | WG5
WI-0044 | oneM2M OIC Interworking | v1.1.0 | Closed | CRs to TS-0002 | Requirements for information model | n.a. | n.a. | n.a. | TP#18 | WG1 | Rapporteur: Kiran Vedula, Samsung Electronics. WI closed at TP#25 | Samsung Electronics, Intel, Fujitsu, MODACOM, DT&C, KDDI, TeliaSonera, IFAST, Orange, KETI, MediaTek, HITACHI, Cisco
|  |  |  | TR-0023 | oneM2M and OIC Interworking | TP#18 | - | TP#20 | TP#21 | WG2
|  |  |  | TS-0024 | oneM2M and OIC Interworking | TP#20 | n.a. | TP#21 | TP#22 | WG2
|  |  |  | CRs to TS-0001 | oneM2M functional architecture | n.a. | n.a. | n.a. | TP#21 | WG2
|  |  |  | CRs to TS-0004 | Service layer core specification | n.a. | n.a. | n.a. | TP#23 | WG3
WI-0045 | Addition of Interoperable Privacy Profiles to oneM2M Security Solutions TS 0003 | v1.0.0 | Closed | CRs to TS-0003 | 1. To store and process privacy preferences in an interoperable manner. 2. To support privacy profiles at various levels to care for conditions of legal requirements, manufacturers, and data subjects. 3. To prioritise privacy profiles where there is a conflict between profiles | TP#19 | n.a. | n.a. | TP#23 | WG4 | Rapporteur: Colin Blanchard, BT Group . WI closed at TP#25 | BT Group Plc.; Cadzow Communications Consulting Ltd.; Datang Telecom Technology@Industry Holdings Co., LTD; KDDI Corporation
WI-0046 | Vehicular domain enablement | v3.0.0 | Closed | TS-0036 | Advanced Vehicular Domain Enablement | TP#31 | n.a. | TP#44 | TP#45 | WG1,WG2 | Rapporteurs:Kenichi Yamamoto (KDDI) & Lu LiuCatalina Mladin (Convida). changed Rapporteur TP30. * Completion level at TP30 closing 95%. For TP31 opening 50%-due to enhancement of scope at TP30. WI scope enhanced at TP38 => copletion down to 50%, schedule updated. TP40 => change rapporteur TP42 => change rapporteur, remove TS-0036; WI closed @ TP47 | Hitachi, KDDI, Toyota ITC, Huawei Technologies, Co. Ltd., LG Electronics, NEC, China Unicom, Samsung, AT&T, Convida (added TP30); added at TP38: Hyundai Motors, KT.
|  |  |  | CRs to TR-0026 | Enhancement on usecases, potential requiremetns, key issues and solutions. | TP#31 | n.a. | n.a. | TP#45 | WG1,WG2
|  |  |  | CRs to TS-0001 | Enhancement on Functional Architecture | n.a. | n.a. | n.a. | TP#45 | WG2
WI-0047 | DDS usage in oneM2M system | V0.1.0 | Closed | TR-0027 | DDS usage in oneM2M system | TP#23 | TP#27 | TP#29 | TP#30 | WG2 | Rapporteurs: SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr Xu Bei (Echo), Huawei, echo.xubei@huawei.com | KETI, Huawei, Hitachi, China Unicom, BOE
|  |  |  | CRs to TS-0001 | Functional Architecture changes for DDS | t.b.d. | t.b.d. | t.b.d. | t.b.d. | WG2
|  |  |  | CRs to TS-0004 | Service Layer Core Protocol changes for DDS | t.b.d. | t.b.d. | t.b.d. | t.b.d. | WG2
|  |  |  | CRs to TS-0002 | Requirements | t.b.d. | t.b.d. | t.b.d. | t.b.d. | WG1
|  |  |  | CRs to TS-0003 | Security Solutions changes for DDS | t.b.d. | t.b.d. | t.b.d. | t.b.d. | WG2
WI-0048 | OSGi Interworking | v0.1.0 | Closed | TR-0028 | Analysis on the interworking between oneM2M and OSGi Alliance | TP#24 | TP#27 | TP#29 | TP#30 | WG2 (WG3, WG5) | Rapporteur: Jiaxin Yin (Huawei Technologies Co.,Ltd.); updated at TP29. Closed @ TP#37 | Huawei Technologies Co., Ltd., Orange, DT, NTT, NEC, AT&T, China Unicom, CATR
|  |  |  | TS-0035 | OSGi Interworking | TP#29 | TP#30 | TP#30 | TP#31 | WG2 (WG5)
|  |  |  | CRs to TS-0001 | Potential change to oneM2M resources for the mapping of attributes and metadata as well as to oneM2M procedures for lifecycle management of services related to mapping if needed | n.a. | n.a. | n.a. | TP#30 | WG2 (WG3)
|  |  |  | CRs to TS-0004 | Potential change to data types and formats for mapping if needed | n.a. | n.a. | n.a. | TP#31 | WG3
WI-0049 | Rel-1 & 2 & 3 Maintenance | v0.0.2 | Active | CRs R1&R2&R3 TSs | Maintenance CRs to oneM2M Release 1, 2 and 3 Specifications (REL1&2&3_MNT) | TP#24 | n.a. | n.a. | n.a. | n.a. | n.a. incl. maintenance for R3 - update @TP37 | Deutsche Telekom, KDDI, LGE, Sierra Wireless, AT&T, KETI, Huawei, ZTE, Qualcomm
WI-0050 | Rel-3 Small Technical Enhancements | v0.0.1 | Closed | CRs to R3 TSs | Small Technical Enhancements CRs to oneM2M Rel 3 Specifications (REL3_STE) | TP#25 | n.a. | n.a. | n.a. | n.a. | n.a. | Deutsche Telekom, KDDI, LGE, Sierra Wireless, AT&T, KETI, Huawei, ZTE
WI-0051 | Security Functions Conformance Testing | v0.0.2 | Closed | TS-0027 | Security Implementation Conformance Statements | TP#25 | TP#28 | TP#36 | TP#40 | WG 3 | Rapporteur: Franck Le Gall (Easy Global Market); schedule updated TP35. Closed @ TP40, work scope moved into WI-0085. | Easy Global Market, Gemalto, Giesecke & Devrient, Cadzow Communications Consulting
|  |  |  | TS-0028 | Security Test Suite Structure and Test Purposes | TP#25 | TP#28 | TP#36 | TP#40 | WG 3 | Rapporteur: Franck Le Gall
|  |  |  | TS-0029 | Security Abstract Test Suite and Implementation eXtra Information for Test | TP#25 | TP#28 | TP#36 | TP#40 | WG 3 | Rapporteur: Miguel Reina Ortega
WI-0052 | LWM2M DM & Interworking Enhancements | v1.1.0 | Closed | TR-0031 | LWM2M DM and Interworking Enhancements | TP#25 | TP#26 | TP#28 | TP#29 | WG 5 | Rapporteur: Dale Seed, InterDigital (Dale.Seed@InterDigital.com) | InterDigital, Huawei, Gemalto, Siera Wireless, NEC
|  |  |  | CRs to TS-0014 | LWM2M Interworking Enhancements | TP#25 | n.a. | n.a. | TP#31 | WG2, WG5 | Closed @ TP#37
|  |  |  | CRs to TS-0005 | Completes and extensible LWM2M Object support | TP#25 | n.a. | n.a. | TP#31 | WG5
WI-0053 | Enhancements on Semantic Support | v0.0.4 | Active | TS-0034 | Semantics Support in oneM2M | TP#25 | TP#28 | TP#44 | TP#45 | WG2 (WG1) | WI Rapporteur: Chonggang Wang, Convida (Wang.Chonggang@convidawireless.com); Editor: Chonggang Wang (Convida). At TP33 update for R4: Changed name and extended scope of WI to R4. R3 enhancements finalized. Decided to start reporting R4 progress at 0%. At TP36.1 updates: new Rapporteur; and Editor for TR-0033 Xu Li (Convida), clarification on scope. Schedule update @ TP40 | NEC, Orange, AT&T, Deutsche Telekom, Hitachi, Pineone, China Unicom, Convida Wireless, Huawei, Eurecom, Modacom, KETI, Nokia
|  |  |  | TR-0033 | Study on Enhanced Semantic Enablement | TP#25 | TP#28 | TP#44 | TP#45 | WG2 (WG1)
|  |  |  | CRs to TS-0001 | Enhancements to TS-0001 | TP#36 | n.a. | n.a. | TP#41 | WG2
|  |  |  | CRs to TS-0004 | Enhancements to TS-0004 | TP#36 | n.a. | n.a. | TP#41 | WG2
WI-0054 | Developers’ guide series | v2.1.0 | Active | TR-0025 | Application developer guide: Light control example using HTTP binding | TP#25 | TP#26 | TP#27 | TP#29 | WG 3 | WI Rapporteur: Laurent Velez (ETSI, laurent.velez@etsi.org); Editor: Laurent Valez | Sensinov, Gemalto, KETI, Easy Global Market, InterDigital, Cadzow Communications, BT, Huawei, Eurecom, SyncTechno Inc, AT&T, Deutsche Telekom AG, Nokia, Orange, KDDI Corporation, NEC
|  |  |  | TR-0034 | Application developer guide: Temperature monitoring example using CoAP binding | TP#25 | TP#28 | TP#30 | TP#32 | WG 3 | Rapporteur: Shane He
|  |  |  | TR-0038 | Developer guide: Implementing security example | TP#25 | TP#28 | TP#30 | TP#32 | WG 3 (WG2) | Rapporteur: Francois Ennesser, & Laurent Velez
|  |  |  | TR-0045 | Developer guide: Implementing Semantics | TP#25 | TP#28 | TP#30 | TP#32 | WG 3 (WG1) | Rapporteur: Martin Bauer (NEC Europe Ltd. (ETSI))
|  |  |  | TR-00xx | Application developer guide: Interworking Proxy Entity example use case | TP#25 | TP#28 | TP#30 | TP#32 | WG 3 (WG2) | Rapporteur: Mahdi Ben Alaya & Laurent Velez
|  |  |  | TR-0035 | Developer guide: Device Management use case | TP#25 | TP#28 | TP#30 | TP#32 | WG 3 (WG2) | Rapporteur: Jiaxin Yin
|  |  |  | TR-0037 | Developer guide: smart farm example using MQTT binding | TP#25 | TP#28 | TP#30 | TP#32 | WG 3 | Rapporteur: Ting Martin Miao
|  |  |  | TR-0047 | Developer guide: 3GPP interworking example | TP#25 | TP#28 | TP#30 | TP#32 | WG 3 (WG2) | Rapporteur: Lijing & Patricia Martigne & James Hu
|  |  |  | TR-0039 | Developer guide: SDT-based implementation | TP#27 | TP#29 | TP#30 | TP#32 | WG 3 (WG1) | Rapporteur: Maciej Goluch (maciej.goluch@orange.com) & Laurent Velez; Change of Rapporteur TP30
WI-0055 | Product Profiles & oneM2M Features | v1.0.0 | Closed | TR-0029 | Methodology of product profiles definition | TP#25 | TP#30 | TP#31 | TP#31 | WG6 | WI Rapporteur: Jiaxin Yin, Huawei Technologies Co., Ltd., yinjiaxin@huawei.com; SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr. Updated name change and Milestones at TP26 | Huawei Technologies Co.,Ltd., KETI, DT, InterDigital, Qualcomm, Spirent, AT4Wireless, UL, R&S, Anritsu, AT&T, NEC, LG U+
|  |  |  | TS-0025 | Definition of Product Profiles in oneM2M | TP#25 | TP#30 | TP#33 | TP#34 | WG6 (WG2, WG3, WG4, WG5) | Jiaxin Yin, Huawei Technologies Co., Ltd.,; Renamed to "Product Profiles" at TP 33; adjusted freeeze and approval milestone
|  |  |  | TS-0031 | oneM2M fFeatures Catalogue | TP#25 | TP#30 | TP#33 | TP#34 | WG2 (WG3, WG6) | SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr; Renamed to Feature Catalogue at TP33; adjusted freeeze and approval milestone
WI-0056 | Evolution of Proximal IoT Interworking | v1.1.0 | Closed | TS-0033 | Proximal IoT Interworking Framework | TP#25 | TP#28 | TP#31 | TP#33 | WG2 | Rapporteur: Josef Blanz, Qualcomm Inc. (TIA); Updated schedule at TP30; Change of name of TS-0033 at TP31; as well as update of apporoval dates. WI closed @ TP38 | Qualcomm, Huawei, KETI, LGE, Deutsche Telekom, Orange, Sierra Wireless, AT&T, Gemalto, Interdigital, Nokia
|  |  |  | CRs to TS-0001 |  | TP#25 | n.a. | n.a. | TP#30 | WG2
|  |  |  | CRs to TS-0004 |  | TP#25 | n.a. | n.a. | TP#32 | WG3
|  |  |  | CRs to TS-0014 |  | TP#25 | n.a. | n.a. | TP#33 | WG2
|  |  |  | CRs to TS-0021 |  | TP#25 | n.a. | n.a. | TP#31 | WG2
|  |  |  | CRs to TS-0024 |  | TP#25 | n.a. | n.a. | TP#32 | WG2
|  |  |  | CRs to TS-0023 |  | TP#25 | n.a. | n.a. | TP#32 | WG5
WI-0057 | TEF Interface | v0.0.3 | Closed | TS-0032 | MAF and MEF Interface Specification | TP#25 | TP#29 | TP#29 | TP#30 | WG4 | Rapporteur: Wolfgang Granzow, Qualcomm, wgranzow@qti.qualcomm.com ; Phil Hawkes, Qualcomm, phawkes@qti.qualcomm.com; TEF… Trust Enabling Function; schedule update TP29. Closed @ TP#37 | Qualcomm Inc., InterDigital, Datang, Gemalto, BT Group
|  |  |  | CRs to TS-0003 | Mapping of MEF and MAF procedures to TEF interface | TP#25 | n.a. | n.a. | TP#26 | WG4
|  |  |  | CRs to TS-0004 | (possibly impacted) new data types in the m2m: namespace | TP#25 | n.a. | n.a. | TP#25 | WG3(WG4)
|  |  |  | CRs to TS-0001 | Introduction of Mtef reference point | TP#25 | n.a. | n.a. | TP#25 | WG2 (WG4,WG3)
|  |  |  | CRs to TS-0022 | Configuration parameters provisioned to Enrollees | TP#25 | n.a. | n.a. | TP#25 | WG5 (WG4)
WI-0058 | Interworking with 3GPP networks | v0.5.0 | Active | TS-0026 | 3GPP Interworking | TP#25 | n.a. | TP#45 | TP#46 | WG2 | co-rapporteurs: Xubei "Echo" (Huawei), Patricia Martigne (Orange), Kenichi YamamotoBei (Echo) Xu ((KDDIHuawei)), Marianne Mohali Patricia Martigne (Orange), James Hu (AT&T); and Shao Weixiang (ZTE Corporation) as a rapporteur of TR-0024 (WI-0037). WI updated: to include 3GPP as well as Cellular IoT Interworking at TP 25. Renamed WI at TP27. Updated schedule at TP29; update TP34 (i.e. timeline adjusted to 3GPP Rel15 => new milestones freeze and approval; Justification and scope update) AT TP35 reset progress to 50% Timeline updated @ TP42, Change to Rapporteur list @ TP43 | Orange, AT&T, Deutsche Telekom, Huawei, KDDI, Sierra Wireless, Sensinov, Oberthur Technologies, Gemalto, ZTE Corporation, Nokia, NEC, KT, Convida Wireless
|  |  |  | CRs to TS-0001 | TBD | TP#25 | n.a. | n.a. | TP#45 | WG2
|  |  |  | CRs to TS-0004 | TBD | TP#25 | n.a. | n.a. | TP#45 | WG2
|  |  |  | CRs to TS-0003 | TBD | TP#25 | n.a. | n.a. | TP#44 | WG2
|  |  |  | CRs to TR-0047 | CR to the developer’s guideline related to 3GPP interworking | TP#25 | n.a. | n.a. | TP#45 | WG3
|  |  |  | CRs to TR-0024 | CR to the 3GPP interworking | TP#25 | n.a. | n.a. | TP#44 | WG2 | Link to WI-0037
WI-0059 | OPC-UA Interworking | v0.0.1 | Closed | CRs to TR-0018 | Add additional section describing existing OPC-UA information model and the interworking methods. | TP#25 | n.a. | n.a. | TP#29 | WG2 | Rapporteur: Miao Jiang, Hitachi (China) Research &Development Corporation (CCSA), miaojiang@hitachi.cn. Chengsui Lu, Hitachi (China) Research&Development Corporation (CCSA), cslu@hitachi.cnn. (changed at TP28) Closed @ TP#37 | Federal Network Agency (BNetzA), Deutsche Telekom (DT), KDDI, Fujitsu, Anritsu Corporation, KETI, Huawei, InterDigital, Hitachi
|  |  |  | CRs to TS-0012 | Base ontology extension from existing industrial domain information model or ontologies | TP#25 | n.a. | n.a. | TP#29 | WG5
|  |  |  | CRs to TR-0007 | Enhancements on semantic modeling and ontologies or semantic annotation | TP#25 | n.a. | n.a. | TP#26 | WG5
|  |  |  | CRs to TS-0030 | Enhancements on generic interworking | TP#25 | n.a. | n.a. | TP#27 | WG5
|  |  |  | CRs to TS-0001 | Enhancements on architecture based on mapping OPC-UA data to oneM2M resources | TP#25 | n.a. | n.a. | TP#28 | WG5
WI-0060 | Interoperability testing Release 2 | V0.0.1 | Active | TS-0013 | Interoperability Testing | TP#24 | TP#28 | TP#29 | TP#30 | WG3 | Rapporteur: Laurent Velez | KETI, InterDigital, Sensinov, Huawei, Qualcomm inc
WI-0061 | Distributed Authorization | v0.0.1 | Closed | CRs to TS 0001 | Architecture, resources, procedures and policies related to authorization | TP#25 | n.a. | n.a. | TP#28 | WG2/WG4 | Rapporteur: Wei Zhou, Datang (CCSA).Closed @ TP#37 | Datang, CMCC, InterDigital, Huawei, KDDI, Qualcomm Inc., BT, Gemalto NV, ZTE, CATR
|  |  |  | CRs to TS-0003 | Architecture, resources, procedures and policies related to authorization | TP#26 | n.a. | n.a. | TP#29 | WG4
|  |  |  | CRs to TS-0004 | Resources, procedures and data types related to authorization | TP#27 | n.a. | n.a. | TP#29 | WG3/WG4
WI-0062 | Service Layer Forwarding | v0.0.1 | Closed | TR-0030 | Service Layer Forwarding | TP#25 | TP#26 | TP#27 | TP#28 | WG2 (WG3) | Rapporteur: Dale Seed, InterDgital (Dale.Seed@InterDigital.com). Closed @ TP#37 | InterDigital, Huawei, Sensinov, KETI, Siera Wireless
|  |  |  | CRs to TS0001 | Changes/additions to existing resource types and/or parameters to support service layer forwarding | TP#25 | n.a. | n.a. | TP#30 | WG2
|  |  |  | CRs to TS0004 | Procedure and data type definition to support service layer forwarding | TP#25 | n.a. | n.a. | TP#30 | WG3
WI-0063 | Release 3 Enhancements on Base Ontology and Ontology based Interworking | v3.0.0 | Closed | TS-0030 | Ontology based Interworking | TP#25 | TP#28 | TP#31 | TP#32 | WG5 | WI Rapporteur: Change of WI Rapportuer at TP31: Joerg Swetina, NEC, (joerg.swetina@neclab.eu); Editor (TS Ontology based Interworking): Jaeho Lee (Pineone). Change of both WI name and TS-0030 approved at TP31 (see TP-2017-0276).Closed @ TP#37 | NEC, Orange, AT&T, Deutsche Telekom, Hitachi, Pineone, KETI
|  |  |  | CRs to TS-0012 | Extracting Ontology based Interworking from the Base Ontology specification into a new TS | TP#24 | n.a. | n.a. | TP#25 | WG5
|  |  |  | CRs to TS-0012 | Additions / changes to the Base Ontology | TP#24 | n.a. | n.a. | TP#31 | WG5
WI-0064 | Adaptation of oneM2M for Smart City | v0.2.0 | Active | TR-0036 | Adaptation of oneM2M for Smart City | TP#25 | TP#28 | TP#43 | TP#44 | WG2 | WI Rapporteur: Jae Young Ahn, ETRI (ahnjy@etri.re.kr ) and SeungMyeong JEONG, KETI (sm.jeong@keti.re.kr); update at TP29; Schedule update TP35, TP40, TP41 | ETRI, NEC, iconectiv, Modacom, KT, HERIT, ORANGE, TIM
|  |  |  | CRs to | TS-0002 | TP#25 |  |  |  | WG1
|  |  |  | CRs to | TS-0001 | TP#25 |  |  |  | WG2
|  |  |  | CRs to | TS-0003 | TP#25 |  |  | TP#32 | WG2
WI-0065 | Trust Management in oneM2M | v1.0.0 | Closed | TR-0040 | Trust management in oneM2M | TP#25 | TP#37 | TP#38 | TP#39 | WG2 | WI Rapporteur: Jae Young Ahn, ETRI (ahnjy@etri.re.kr ); At TP33 updated schedule: change, freeze and approval date | ETRI, KT, HERIT, Cadzow Communications Consulting Ltd., iconectiv, Nokia, TIM, Huawei
WI-0066 | Decentralized Authentication | v1.0.0 | Closed | TR-0041 | Decentralized Authentication | TP#26 | TP#34 | TP#34 | TP#35 | WG2 | WI Rapporteurs: Guilin Wang, Huawei, wang.guilin@huawei.com (WG4) Jie Shi, Huawei, shi.jie1@huawei.com (WG4). Changed Change Control, Freeze and Approval Milestones at TP30. R4 timing. | Huawei, Datang, Cadzow Communications Consulting Ltd, iconectiv, ETRI
|  |  |  | CRs to | TS-0003 | TP#26 | n.a. | n.a. | TP#34 | WG2
|  |  |  | CRs to | TS-0002 | TP#26 | n.a. | n.a. | TP#34 | WG2
WI-0067 | UICC Framework Public Key Enhancements (UPK) | v0.0.3 | Closed | CRs to TS-0003 | Public Key Framework for UICC | TP#26 | n.a. | n.a. | TP#30 | WG4 | WI Rapporteur: François Ennesser, Gemalto (ETSI); Approval date change approved TP28. WI closed at TP#32 | Gemalto, Oberthur Technologies, Qualcomm Inc., Huawei, Datang
WI-0068 | GlobalPlatform Interworking (GPI) | v1.0.0 | Closed | TS-00yx | GlobalPlatform Interworking | TP#26 | TP#37 | TP#37 | TP#38 | WG2 | WI Rapporteur: François Ennesser, Gemalto (ETSI); changed milestone dates at TP29. at TP33: revised schedule, clarification of scope and addition of supporting companies. | GlobalPlatform, Gemalto, Qualcomm Inc., Huawei, Orange, Giesecke + Devrient Mobile Security; (added TP33)
|  |  |  | CRS to TS-0003 | GlobalPlatform Interworking enhancements | TP#26 | n.a. | n.a. | TP#35 | WG2
|  |  |  | CRS to TS-0001 | GlobalPlatform Interworking integration | TP#26 | n.a. | n.a. | TP#35 | WG2
|  |  |  | CRS to TS-0005 | GlobalPlatform Interworking impact | TP#26 | n.a. | n.a. | TP#36 | WG2
|  |  |  | CRS to TS-0006 | GlobalPlatform Interworking impact | TP#26 | n.a. | n.a. | TP#36 | WG2
|  |  |  | CRS to TS-0014 | GlobalPlatform Interworking impact | TP#26 | n.a. | n.a. | TP#36 | WG2
|  |  |  | CRS to TS-0022 | GlobalPlatform Interworking impact | TP#26 | n.a. | n.a. | TP#36 | WG1
WI-0069 | Physical Object Heterogeneous identification and tracking services in oneM2M system | v2.0.0 | Active | TR-0044 | Physical object heterogeneous identification and tracking in oneM2M | TP#27 | TP#41 | TP#43 | TP#44 | WG2 (WG1) | WI Rapporteur: Bo Yuan, Computer network information center, Chinese academy of sciences, yuanbo@cnic.cn (WG1) Yuan Tao, Computer network information center, Chinese academy of sciences Guangzhou sub-center, taoyuan@cnicg.cn (WG2, WG3, WG4, WG5). At TP33 Changed milestones for TR: change , freez and approval date. At TP38 added supporting company, changed name of WI and enhanced scope, updated schedule. | Computer Network Information Center, Chinese Academy of Sciences (CNIC); Computer Network Information Center, Chinese Academy of Sciences Guangzhou sub-center (CNICG); China Academy of Telecommunication Research of MIIT; Hitachi; Datang, Convida Wireless
|  |  |  | CRS to TR-0001 | Use Case Intelligence agricultural product traceability | TP#27 | n.a. | n.a. |  | WG1
|  |  |  | CRS to TS-0001 | Architecture to support the heterogeneous identification service in oneM2M | TP#27 | n.a. | n.a. |  | WG2
|  |  |  | CRS to TS-0004 | Procedure and data type to support the heterogeneous identification service in oneM2M | TP#27 | n.a. | n.a. |  | WG2
|  |  |  | CRS to TS-0003 | Security impact of heterogeneous identification | TP#27 | n.a. | n.a. |  | WG2
WI-0070 | Public Warning Service Enabler | v0.0.3 | Active | TR-0046 | Study on Disaster Alert Public Warning Service Enabler | TP#28 | n.a. | TP#43 | TP#44 | WG1 | WI Rapporteur: SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr, TaeHyun KIM, SyncTechno, thyun.kim@synctechno.com; TP35: Schedule update and addition of TS Public Safety Information Model and Mapping. Change of WI name and changes to name of TR and TS @ TP37 TP40：update schedule. TP42: TR-0046 APPROVED. @TP43 New name for TS | KETI, SyncTechno, NTT, Huawei, ZTE, Qualcomm, KDDI
|  |  |  | TS-00vw | Public Safety Warning Data Information Model and Mapping; IoT Public Warning Service Enablement | TP#43 | n.a. | TP#45 | TP#46 | WG1
|  |  |  | CR to TR-0001 | Use case addition or updates | TP#28 | n.a. | n.a. |  | WG1
|  |  |  | CR to TS-0002 | New requirements | TP#28 | n.a. | n.a. |  | WG1
|  |  |  | CR to TS-0001 | Functional architecture enhancements | TP#28 | n.a. | n.a. |  | WG2
|  |  |  | CR to TS-0004 | Core protocol enhancements | TP#28 | n.a. | n.a. |  | WG2
|  |  |  | CR to TS-0003 | Security solutions enhancements | TP#28 | n.a. | n.a. |  | WG2
WI-0071 | oneM2M and W3C Web of Things Interworking (WOTIWK) | v0.0.1 | Closed | TR-0042 | WoT Interworking | TP#28 | TP#31 | TP#47 | TP#48 | WG2 | WI Rapporteur: Yongjing Zhang, zhangyongjing@huawei.com; WI closed @ TP44 Schedule updated @TP40 | Huawei Technologies Co., Ltd. (CCSA), NEC (ETSI), Convida Wireless (ETSI), China Unicom (CCSA), China Telecom (CCSA), Hitachi (TTC), Deutsche Telekom AG (ETSI), LGE (TTA)
WI-0072 | Modbus interworking | v1.0.0 | Active | TS-00xx | Modbus interworking | TP#43 | TP#45 | TP#45 | TP#46 | WG2 | WI Rapporteur: Qiuting Li, li.qiuting@zte.com.cn, JaeSeung Song (KETI), jssong@sejong.ac.kr TP40：update rapporteur & milestones; TP43: added new TS as deliverable as well as deleted reference to CRs to specifications. New schedule | ZTE, Datang, BOE, Hitachi, Computer Network Information Center, Chinese Academy of Sciences (CNIC);
|  |  |  | TR-0043 | Modbus Interworking | TP#28 | TP#41 | TP#42 | TP#43 | WG2
|  |  |  | CR to TS-0002 | Requirements |  | n.a. | n.a. |  | WG1
|  |  |  | CR to TS-0004 | Service Layer Core Protocol changes for supporting Modbus interworking |  | n.a. | n.a. |  | WG2
|  |  |  | CR to TS-0033 | Proximal IoT Interworking for supporting Modbus interworking |  | n.a. | n.a. |  | WG2
WI-0073 | App-ID Registry Function | v1.0.0 | Closed | TR-0048 | oneM2M App-ID Registry Function | TP#30 |  | TP#33 | TP#34 | WG1,WG2 (WG3,4,5) | WI Rapporteur: Shelby Kiewel (iconectiv). Closed @ TP#37 | iconectiv , Convida, BT Group, Qualcomm, Gemalto, Huawei, Sensinov
|  |  |  | CR to TS-0001 | Architecture | TP#30 | n.a. | n.a. | TP#34 | WG2
|  |  |  | CR to TS-0002 | Requiremnts | TP#30 | n.a. | n.a. | TP#34 | WG1
|  |  |  | CR to TS-0003 | Security Solutions | TP#30 | n.a. | n.a. | TP#34 | WG4
|  |  |  | CR to TS-0032 | MAF and MEF Interface Specification | TP#30 | n.a. | n.a. | TP#34 | WG4
|  |  |  | CR to TS-0022 | Field Device Configuration | TP#30 | n.a. | n.a. | TP#34 | WG5
WI-0074 | Conformance Test Specifications Release 2 | v1.0.0 | Closed | CRs to TS-0017 | Implementation Conformance Statements | TP#31 | TP#35 | TP#36 | TP#40 | WG3 | WI Rapporteur: Laurent Velez; Rapporteur TS: KETI & Laurent Velez | Huawei Technologies Co., Ltd., KETI, TTA, Convida Wireless, Sensinov, Spirent, NTT, Rohde-Schwarz
|  |  |  | CRs to TS-0018 | Test Suite Structure and Test Purposes | TP#31 | TP#35 | TP#36 | TP#40 | WG3 | Rapporteur: KETI & Laurent Velez
|  |  |  | CRs to TS-0019 | Abstract Test Suite and Implementation eXtra Information for Test | TP#31 | TP#35 | TP#36 | TP#40 | WG3 | Rapporteur: Miguel Angel Reina Ortega
WI-0075 | Industrial Domain Information Model Mapping and Semantics Support | v0.0.5 | Closed | TR-0049 | Industrial Domain Information Model Mapping and Semantics Support | TP#32 | n.a. | TP#46 | TP#47 | WG1 (WG2) | WI Rapporteurs: Zhirong Zeng, Hitachi (China) Research & Development Corporation (CCSA), zrzeng@hitachi.cn, Chengsui Lu, Hitachi (China) Research & Development Corporation (CCSA), cslu@hitachi.cn. WI approved at TP31. Schedule update at TP35. Rapporteur updated at TP#41. schedule update @TP43. WI closed@TP47 | Hitachi, KDDI, NTT, Deutsche Telekom, Convida Wireless, NEC, Huawei, ZTE, CNICG, added at TP32
|  |  |  | CRs to TS-0001 | Normative CRs to the Functional Architecture | TP#32 | n.a. | n.a. | TP#44 | WG2
|  |  |  | CRs to TS-0004 | Normative CRs to the Core Protocol | TP#32 | n.a. | n.a. | TP#44 | WG2
|  |  |  | CRs to TR-0018 | Informative CRs to the general description on industrial data models | TP#32 | n.a. | n.a. | TP#44 | WG1
|  |  |  | CRs to TR-0033 | Informative CRs to the enhancement on semantic support | TP#32 | n.a. | n.a. | TP#44 | WG2
|  |  |  | CRs to TS-0034 | Normative CRs to the enhancement on semantic support | TP#32 | n.a. | n.a. | TP#44 | WG2
WI-0076 | Lightweight oneM2M Services | V0.0.2 | Active | TR-0053 | Lightweight oneM2M Services | TP#32 | n.a. | TP#44 | TP#45 | WG2,(WG1) | WI Rapportuer: Dale Seed (Convida). WI approved at TP31; schedule updated @TP37, TP42 | Convida, Qualcomm Inc, NEC, Sensinov, iconectiv, Huawei, Nokia, KETI
|  |  |  | CRs to TS-0001 | Enhancements to TS-0001 | TP#32 | n.a. | n.a. | TP#38 | WG2
|  |  |  | CRs to TS-0003 | Enhancements to TS-0003 | TP#32 | n.a. | n.a. | TP#38 | WG2
|  |  |  | CRs to TS-0004 | Enhancements to TS-0004 | TP#32 | n.a. | n.a. | TP#38 | WG3
WI-0077 | Attribute Based Access Control Policy | V0.0.5 | Active | TR-0050 | Attribute Based Access Control Policy | TP#32 | TP#39 | TP#44 | TP#45 | WG2 | WI Rapportuer: Wei Zhou, Datang (CCSA). WI approved at TP31; Schedule update @TP37, TP40, TP43 | Datang, CATR, ZTE, CNIC, Huawei, Gemalto, BT, KDDI, ORANGE
|  |  |  | CRs to TS-0001 | Architecture, resources and procedures related to access control policy and access control policy management. | TP#32 | n.a. | n.a. | TP#38 | WG2
|  |  |  | CRs to TS-0003 | Architecture, resources and procedures related to access control policy and access control policy management. | TP#32 | n.a. | n.a. | TP#38 | WG2
|  |  |  | CRs to TS-0004 | Resources, procedures and data types related to access control policy and access control policy management. | TP#32 | n.a. | n.a. | TP#38 | WG2
WI-0078 | oneM2M API guide | V0.0.1 | Active | TR-0051 | oneM2M API guide | TP#32 | TP#36 | TP#38 | TP#40 | WG3 | WI Rapporteur: Laurent Velez | KETI, ATT, Sensinov, Convida Wireless, NTT, Deutsche Telekom
WI-0079 | Rel-4 Small Technical Enhancements | V0.0.1 | Active | CRs to R4 TSs | Small Technical Enhancements CRs to oneM2M Rel 4 Specifications (REL4_STE) | TP#32 | n.a. | n.a. | n.a. | n.a. | n.a. | AT&T, Convida, Deutsche Telekom, NEC, Nokia
WI-0080 | Study on Edge and Fog Computing in oneM2M systems | V2.0.2 | Active | TR-0052 | Study on Edge and Fog Computing in oneM2M systems | TP#33 |  | TP#47 | TP#48 | WG2 (WG1) | WI Rapporteur: Kenichi Yamamoto (KDDI), Lu Liu (Convida) WID updated to v2.0 @TP#39 Change rapporteur @ TP#42: updated milestones @TP45 | KDDI, Huawei, Hitachi, TNO, Convida, NEC Europe, NEC Europe, NTT, BOE, Gemalto, Qualcomm, AT&T, KETI, TIM, Cisco, Nokia,, Hyundai Motors
|  |  |  | CRs to TS-0001 | Enhancements to TS-0001 |  |  |  | TP#47 | WG2
|  |  |  | CRs to TS-0002 | Enhancements to TS-0002 |  |  |  | TP#47 | WG1
|  |  |  | CRs to TS-0003 | Enhancements to TS-0003 |  |  |  | TP#47 | WG2
|  |  |  | CRs to TR-0001 | Enhancements to TR-0001 |  |  |  | TP#47 | WG1
|  |  |  | CRs to TR-0018 | Enhancements to TR-0018 |  |  |  | TP#47 | WG1
|  |  |  | CRs to TR-0026 | Enhancements to TR-0026 |  |  |  | TP#47 | WG1
WI-0081 | Smart Device Template 4.0 | V1.0.1 | Closed | CRs to TS-0023 | CR on SDT based IM updates or enhancements | TP#33 | n.a. | n.a. | TP#45 | WG1 | WI Rapporteur: Andreas Kraft (Deutsche Telekom, a.kraft@telekom.de) Schedule update @ TP40, TP43; WI closed @ TP47 | Deutsche Telekom, Huawei, Orange, NEC
WI-0082 | 3GPP V2X Interworking | V1.0.0 | Closed | TR-0055 | 3GPP V2X Interworking | TP#33 | n.a. | TP#47 | TP#48 | WG2 | WI Rapporteur: Bei (Echo) Xu (Huawei); Schedule update @TP40; WI closed @ TP44 | Huawei Technologies, Co. Ltd., Hitachi, China Unicom, AT&T, Convida, Deutsche Telekom, KDDI, Orange
WI-0083 | oneM2M Service Subscribers and Users | V1.0.0 | Active | TR-0054 | oneM2M Service Subscribers and Users | TP#33 | n.a. | TP#44 | TP#45 | WG2 (WG1) | WI Rapporteur: Dale Seed (Convida) Schedule update @ TP40 | Convida Wireless, NEC, Gemalto, KDDI, KETI
|  |  |  | CRs to TS-0001 | Enhancements to TS-0001 | TP#33 |  |  | TP#45 | WG 2
|  |  |  | CRs to TS-0003 | Enhancements to TS-0003 | TP#33 |  |  | TP#45 | WG 2
|  |  |  | CRs to TS-0004 | Enhancements to TS-0004 | TP#33 |  |  | TP#45 | WG 2
|  |  |  | CRs to TR-0001 | Additional usecases to TR-0001 | TP#33 |  |  | TP#45 | WG 1
WI-0084 | SDT based Information Model and Mapping for Vertical Industries | V0.0.2 | Closed | CRs to TS-0023 | CRs on HAIM updates or enhancements | TP#35 | n.a. | n.a. | TP#45 | WG 1 | WI Rapporteur: Leila Lebrun (leila.lebrun@orange.com), Andreas Kraft (Deutsche Telekom, andreas.kraft@t-systems.com) + Andrew Min-gyu Han, Hansung University; Schedule & rapporteurs update @ TP40, and @ TP43; WI closed@TP84 | Orange, Deutsche Telekom, Huawei, Telecom Italia, NTT
|  |  |  | CRs to TS-0023 | CRs on ModuleClasses and Device descriptions for other service domains | TP#35 | n.a. | n.a. | TP#45 | WG 1
WI-0085 | Conformance Test Specifications Release 3 | v1.0.0 | Active | CRs to TS-0017 | Implementation Conformance Statements | TP#35 | TP#39 | TP#43 | TP#44 | WG 3 | Rapporteur: In Song Lee & Miguel Angel Reina Ortega Schedule update @ TP41 | KETI, Convida Wireless, Sensinov, Spirent, NTT
|  |  |  | CRs to TS-0018 | Test Suite Structure and Test Purposes | TP#35 | TP#39 | TP#43 | TP#44 | WG 3 | Rapporteur: In Song Lee & Miguel Angel Reina Ortega Schedule update @ TP41
|  |  |  | CRs to TS-0019 | Abstract Test Suite and Implementation eXtra Information for Test | TP#35 | TP#39 | TP#43 | TP#44 | WG 3 | WI Rapporteur: Miguel Angel Reina Ortega Schedule update @ TP41
WI-0086 | Conformance Test Specifications Release 4 | V1.0.0 | Active | CRs to TS-0017 | Implementation Conformance Statements | TP#38 | TP#46 | TP#47 | TP#48 | WG 3 | Rapporteur: In Song Lee & Miguel Angel Reina Ortega Schedule update @ TP41 | KETI, Convida Wireless, Sensinov, Spirent, NTT
|  |  |  | CRs to TS-0018 | Test Suite Structure and Test Purposes | TP#38 | TP#46 | TP#47 | TP#48 | WG 3 | Rapporteur: In Song Lee & Miguel Angel Reina Ortega Schedule update @ TP41
|  |  |  | CRs to TS-0019 | Abstract Test Suite and Implementation eXtra Information for Test | TP#38 | TP#46 | TP#47 | TP#48 | WG 3 | WI Rapporteur: Miguel Angel Reina Ortega (ETSI) Schedule update @ TP41
WI-0087 | Summary of differences between Rel-2A & Rel-3 | V1.0.1 | Closed | TR-0056 | Differences between Release 2A and Release3 | TP#35 | n.a. | TP#38 | TP#39 | WG 2 (WG 1,6) | WI Rapporteur: Kei Harada (NTT): Schedule updated @TP37 | NTT, Huawei, KDDI, KT, KETI
WI-0088 | M2M/IoT Application and Component Configuration | V0.0.1 | Closed | CRs to TS-0022 | Improvements and enhancements of configuration and security mechanism | TP#36 | n.a. | n.a. | TP#39 | WG 2 (WG 1,6) | WI Rapporteur: Saïd Gharout, ORANGE, said.gharout@orange.com; WI closed @ TP44 | ORANGE, Qualcomm, KT, Telecom Italia, Deutsche Telekom, Iconectiv, Convida Wireless, Gemalto, AT&T, Huawei
WI-0089 | Getting started with oneM2M | V1.0.1 | Active | TR-0057 | Getting started with oneM2M | TP#37 | TP#42 | TP#43 | TP#45 | WG 2 (all WG) | WI Rapporteur: SeungMyeong Jeong, KETI Laurent Velez, ETSI, laurent.velez@etsi.org | Convida, NTT, Deutsche Telekom, Huawei, Sensinov, KETI
WI-0090 | oneM2M and Zigbee interworking | V0.0.1 | Active | TR-00xy | oneM2M and Zigbee Interworking | TP#37 | n.a. | TP#43 | TP#45 | WG 2 (WG1) | WI Rapporteur: Omar Elloumi, Nokia | Nokia, Convida, Huawei, Orange, KETI, Qualcomm, Sensinov, DT
|  |  |  | TS-00xy | oneM2M and Zigbee Interworking | TP#37 | n.a. | TP#43 | TP#45 | WG 2 (WG1)
|  |  |  | CRs to TS-0001 | oneM2M functional Architecture | TP#37 |  |  | TP#45 | WG 2
WI-0091 | oneM2M Services and Platforms Discovery | V0.0.1 | Active | TR-0059 | oneM2M Services and Platforms Discovery | TP#37 |  | TP#42 | TP#43 | WG 2 | WI Rapporteur: Youngjin Na (Hyundai Mortor), JaeSeung Song (KETI) Schedule update @TP40 | Hyundai Motors, Convida, KETI, Huawei, SyncTechno
|  |  |  | CRs to TS-0001 | oneM2M requirements |  |  |  | TP#42 | WG 1
|  |  |  | CRs to TS-0001 | oneM2M functional architecture |  |  |  | TP#43 | WG 2
|  |  |  | CRs to TS-0001 | oneM2M service layer protocol |  |  |  | TP#43 | WG 2
WI-0092 | Railway Domain Enablement (RAILDE) | V0.0.3 | Active | TR-0058 | Railway Domain Enablement | TP#38 | TP#45 | TP#47 | TP#48 | WG 1 | WI Rapporteur: Andrew Min-gyu Han, Hansung University Schedule update @TP40, additional supporter LGU+, @TP43: Schedule udate and additional impacted TSs; TP46: schedule updated; | Hansung University, ETRI, KT, KETI, Huawei,, LGU+
|  |  |  | CRs to TS-0023 | SDT based Information Model and Mapping for Vertical Industries | TP#38 |  |  |  | WG 1
|  |  |  | CRs to TS-0001 | Functional Architecture enhancement |  |  |  |  | WG 2
|  |  |  | CRs to TS-0002 | New requirements |  |  |  |  | WG 1
WI-0093 | Action Triggering Enhancements | v1.0.0 | Active | TR-0060 | Study of action triggering enhancements | TP#39 | n.a. | n.a. | TP#43 | WG 2 | Rapporteur: SeungMyeong Jeong, KETI, sm.jeong@keti.re.kr. WI approved @ TP38 | KETI, Huawei Technologies Co., Ltd, Qualcomm, Convida Wireless, Sensinov
|  |  |  | CRs to TS0001 | New resource types, attributes or parameters definition to support action triggering | n.a. | n.a. | n.a. | TP#28 | WG2
|  |  |  | CRs to TS0004 | Procedure and data type definition to support action triggering | n.a. | n.a. | n.a. | TP#31 | WG 2
WI-0094 | Ontologies for Smart City Services (OSCS) | v1.0.0 | Active | TR-0061 | Study on the Development of Ontologies for Smart City Services | TP#39 | TP#40 | TP#53 | TP#54 | WG 1 | Rapporteur: Insong Lee (KETI, insong@keti.re.kr) . WI approved @ TP39, Schedule update @ TP41; Schedule update TP43; Schedule updated TP48; | KETI, Telecom Italia, Hyundai Motors, Hansung University, Synchtechno, Huawei, BT
|  |  |  | CRs to TS0012 |  | n.a. | n.a. | n.a. | n.a.
|  |  |  | CRs to TS0023 |  | n.a. | n.a. | n.a. | n.a.
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations (eDPR) | v1.0.0 | Active | TR-0062 | oneM2M System Enhancement to Support Privacy Data Protection Regulations (eDPR) | TP#42 | - | TP#45 | TP#46 | WG 2 | Rapporteur: JaeSeung Song (KETI) WI approved @ TP42. | Hyundai Motor, KETI, BT, SynchTechno, Hansung University, EGM
|  |  |  | CRs to TS-0002 | oneM2M requirements |  |  |  | TP#46 | WG 1
|  |  |  | CRs to TS-0001 | oneM2M functional architecture |  |  |  | TP#46 | WG 2
|  |  |  | CRs to TS-0003 | oneM2M security solution |  |  |  | TP#46 | WG 2
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | v1.0.0 | Active | TR-0063 | Effective IoT Communication to Protect 3GPP Networks | TP#43 | - | TP#51 | TP#52 | WG 2 | Rapporteur: Bob Flynn (Convida) WI approved @ TP43. WI schedule updated TP48 | Deutsche Telekom, QualComm, BT, Convida, AT&T, Orange, TIM, Nokia, Hansung University, Hyundai Motors
|  |  |  | CRs to TS-0001 | oneM2M functional architecture | TP#43 | - | - | TP#51 | WG 2
|  |  |  | CRs to TS-0004 | oneM2M Service Layer Core Protocol Specification | TP#43 | - | - | TP#51 | WG 2
|  |  |  | CRs to TS-0003 | oneM2M security solution | TP#43 | - | - | TP#51 | WG 2
|  |  |  | CRs to TR-0047 | Developer Guide of 3GPP Interworking | TP#43 | - | - | TP#51 | WG 3
|  |  |  | CRs to TR-0024 | 3GPP Rel-13 Interworking R4 | TP#43 | - | - | TP#51 | WG 2
|  |  |  | CRs to TS-0025 | Definition of Product Profiles | TP#43 | - | - | TP#51 | WG 3
WI-0097 | Interoperability testing Release 3 | V0.0.1 | Active | CRs to TS-0013 | Interoperability Testing | TP#44 | TP#45 | TP#46 | TP#48 | WG 3 | Rapporteur: Laurent Velez, ETSI (laurent.velez@etsi.org) WI approved at TP43 | Hansung University, KETI, Convida, Sensinov, SyncTechno Inc
WI-0098 | IoT for Smart Lifts | V0.0.1 | Active | CRs to TR-0001 | Smart Lifts Use cases and roles | TP#45 |  |  |  | WG 1 | Rapporteur: Massimo Vanetti, SBS (massimovanetti@gmail.com) WI approved at TP44 | SBS, TIM-Telecom Italia, Sensinov, Nokia, TNO, Huawei Technologies Sweden
|  |  |  | CRs to TS-0002 | Smart Lifts requirements | TP#46 |  |  |  | WG 1
|  |  |  | CRs to TS-0030 | Smart lifts data model and references | TP#47 |  |  |  | WG 1
|  |  |  | CRs to TS-0034 | Smart lifts data model and references | TP#47 |  |  |  | WG 1
WI-0099 | Management Object Migration | V0.0.1 | Active | TR-00XX | Management Object Migration | TP#45 | TP#47 | TP#48 | TP#49 | WG 1 / WG 2 | Marianne Mohali, Orange (marianne.mohali@orange.com) WI approved at TP44 | Orange, Deutsche Telekom, Sensinov, TIM, SBS, Bundesnetzagentur
|  |  |  | CRs to TS-0023 | Update SDT Device Management to cover MO functional scope | TP#49
WI-0100 | oneM2M and SensorThings API | V0.0.1 | Active | TR-0065 | Study of SensorThings API Interworking | TP#45 | TP#50 | TP#50 | TP#51 | WG2 | Ingo Friese, Deutsche Telekom ingo.friese@telekom.de; Andreas Neubacher, Deutsche Telekom, andreas.neubacher@magenta.at WI approved at TP44; Schedule updated @ TP48 | Deutsche Telekom, ORANGE, Nokia, Convida Wireless, IBM
|  |  |  | TS-00XX | SensorThings API Interworking | TP#47 | TP#52 | TP#52 | TP#53 | WG2
|  |  |  | CRs to TS-0023 | additional module classes and devices | TP#49 |  |  | TP#53 | WG 1
WI-0101 | Advanced Semantic Discovery | v0.0.1 | Active | CRs to TR-0001 | Initial Advanced Semantic Discovery use cases and Advanced Semantic Discovery use cases | TP#45 |  |  | TP#46 | WG1 | WI approved @ TP45; Rapporteur: SeungMyeong Jeong (KETI) | INRIA, KETI, SBS, TIM, UPM
|  |  |  | CRs to TS-0002 | Advanced Semantic Discovery requirements | TP#45 |  |  | TP#46 | WG1
|  |  |  | CRs to TS-0001 | Stage 2 - Initial Advanced Semantic Discovery | TP#45 |  |  | TP#48 | WG2
|  |  |  | CRs to TS-0004 | Stage 2 - Advanced Semantic Discovery | TP#45 |  |  | TP#50 | WG2
WI-0102 | System enhancements to support Data License Management | v0.0.1 | Active | TR-0066 | oneM2M System Enhancement to Support Data License Management (DLM) | TP#45 |  | TP#48 | TP#49 | WG2 | WI approved @ TP45; Rapporteurs: Minbyeong Lee (Hyundai Motors) and JaeSeung Song (KETI) | Hyundai Motors, KETI, Deutsche Telecom, Telecom Italia, Convida Wireless, BT, Orange
|  |  |  | CRs to TS-0002 | oneM2M requirements | TP#45 |  |  | TP#49 | WG1
|  |  |  | CRs to TS-0001 | oneM2M functional architecture | TP#45 |  |  | TP#49 | WG2
WI-0103 | oneM2M API_Guide Rel 3 | v0.0.1 | Active | TR-0051 | oneM2M API guide | TP#47 | TP#50 | TP#52 | TP#53 | WG3 | WI approved @ TP46; Rapporteur: Laurent Velez (ETSI, laurent.velez@etsi.org) | Hansung University, KETI, ETRI, Nokia, Deutsche Telekom
WI-0104 | SDT based Information Model and Mapping for Vertical Industries – SIMVI | v0.0.1 | Active | CRs to TS-0023 | SDT based Information Model and Mapping for Vertical Industries – SIMVI | TP#50 | TP#53 | TP#54 | TP#56 | WG3 | WI approved @ TP49; Rapporteur: Laurent Velez (ETSI, laurent.velez@etsi.org) | Hansung University, Deutsche Telekom, Orange, Exacta GSS
WI-0105 | System enhancements to support AI capabilities | v0.0.1 | Active | TR-00xx | System enhancements to support AI capabilities | TP#50 | TP#53 | TP#54 | TP#55 | WG1 | WI approved @ TP50; Rapporteur: JaeSeung Song (KETI), jssong@sejong.ac.kr | KETI, Hyundai Motors, Exacta GSS, Deutsche Telekom, SBS, Nokia, Hansung University, Orange, Convida Wireless
|  |  |  | TS-00xx | System enhancements to support AI capabilities | TP#54 | TP#57 | TP#58 | TP#59 | WG2 | WI approved @ TP50; Rapporteur: JaeSeung Song (KETI), jssong@sejong.ac.kr | KETI, Hyundai Motors, Exacta GSS, Deutsche Telekom, SBS, Nokia, Hansung University, Orange, Convida Wireless
WI-0106 | Interoperability testing Release 4 | v0.0.1 | Active | CRs to TS-0013 | Interoperability testing Release 4 | TP#51 | TP#55 | TP#57 | TP#58 | WG3 | WI approved @ TP49; Rapporteur: Laurent Velez (ETSI, laurent.velez@etsi.org) | Hansung University, Deutsche Telekom, Orange, Exacta GSS
WI-0107 | Developers guide series | v0.0.1 | Active | CRs to TS-0013 | Developers guide series | TP#52 | TP#56 | TP#57 | TP#58 | WG3 | WI approved @ TP52; Rapporteur: Xavier Piednoir (ETSI, xavier.piednoir@etsi.org) | Exacta GSS, Deutsche Telekom, Orange, KETI, Hansung University
WI-0108 | Conformance Test Maintenance | v0.0.1 | Active | CRs to TS-0017 CRs to TS-0018 CRs to TS-0019 | Conformance Test Maintenance | TP#53 | TP#55 | TP#56 | TP#57 | WG3 | WI approved @ TP53; Rapporteur: In Song LEE (KETI), Miguel Angel REINA ORTEGA (ETSI) | Exacta, Deutsche Telekom, C-DOT, Hansung University
WI-0109 | IPE-based Device Management with FlexContainers | v0.0.1 | Active | CRs to TS-00xx | IPE-based Device Management with FlexContainers | TP#53 | TP#56 | TP#57 | TP#58 | ALL | WI approved @ TP53; Rapporteur: Marianne Mohali, Orange, Marianne.mohali@orange.com | Orange, Hansung University, Exacta GSS, Deutsche Telekom, Nokia

## WI Progress
WI# | Title | Status | Overdue | WG | Rel | TP#17 | TP#18 | TP#19 | TP#20 | TP#21 | TP#22 | TP#23 | TP#24 | TP#25 | TP#26 | TP#27 | TP#28 | TP#29 | TP#30 | TP#31 | TP#32 | TP#33 | TP#34 | TP#35 | TP#36 | TP#37 | TP#38 | TP#39 | TP#40 | TP#41 | TP#42 | TP#43 | TP#44 | TP#45 | TP#46 | TP#47 | TP#48 | TP#49 | TP#50 | TP#51 | TP#52 | TP#53 | TP#54 | TP#55 | Freeze | Approval | @ | TP#55
WI-0015 | Use Cases Collection | Active | N | RDM | Generic | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | FALSE | FALSE
WI-0021 | Secure Environment Abstraction | Closed |  | SDS | R3 | 10% | 20% | 25% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 40% | 40% | 40% | 40% | 50% | 50% | 80% | 90% | 90% | 90% | 90% | 90% | 95% | 100% | [10 empty] | n.a. | n.a. | n.a. | n.a. | n.a. | FALSE | FALSE
WI-0030 | M2M Application & Field Domain Component Configuration | Closed |  |  |  | 5% | 30% | 35% | 45% | 50% | 50% | 60% | 95% | 70% | 80% | 85% | 100% | [27 empty] | FALSE | FALSE
WI-0031 | Optimized Group-based Operation | Closed |  |  |  | 10% | 20% | 30% | 30% | 50% | 70% | 80% | 80% | 80% | 80% | 80% | 90% | 90% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 100% | [17 empty] | FALSE | FALSE
WI-0032 | Conformance Test | Closed |  |  |  | 5% | 10% | 15% | 35% | 39% | 43% | 43% | 43% | 46% | 50% | 50% | 60% | 62% | 93% | 96% | 97% | 100% | [22 empty] | FALSE | FALSE
WI-0034 | Study of re-usable service layer context &Transaction enablement | Closed |  |  |  | 0% | 10% | 15% | 20% | 20% | 20% | 50% | 50% | 90% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 100% | [19 empty] | FALSE | FALSE
WI-0035 | Action Triggering | Closed |  |  |  | 0% | 10% | 20% | 30% | 40% | 40% | 80% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 100% | [17 empty] | FALSE | FALSE
WI-0046 | Vehicular domain enablement | Closed | N | RDM | R4 |  |  |  | 5% | 20% | 40% | 40% | 50% | 65% | 70% | 80% | 85% | 90% | 95% | 55% | 60% | 60% | 65% | 70% | 75% | 80% | 50% | 50% | 75% | 80% | 85% | 90% |  | 91% | 91% | 100% | [8 empty] | FALSE | FALSE
WI-0047 | DDS usage in oneM2M system | Closed |  | SDS | Stalled | [6 empty] | 0% | 5% | 20% | 30% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | [15 empty] | FALSE | FALSE
WI-0048 | OSGi Interworking | Closed | [9 empty] | 0% | 5% | 5% | 5% | 5% | 15% | 20% | 60% | 60% | 95% | 95% | 95% | 100% | [20 empty] | FALSE | FALSE
WI-0049 | Rel-1 & 2 & 3 Maintenance | Active | N | TP | Generic | [7 empty] | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | FALSE | FALSE
WI-0050 | Rel-3 Small Technical Enhancements | Closed | N | TP | R3 | [7 empty] | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | [16 empty] | FALSE | FALSE
WI-0051 | Security Functions Conformance Testing | Closed |  | TDE | Stalled | [7 empty] | 0% | 5% | 5% | 5% | 15% | 15% | 30% | 67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | [17 empty] | FALSE | FALSE
WI-0052 | LWM2M DM & Interworking Enhancements | Closed | [10 empty] | 0% | 5% | 10% | 40% | 80% | 95% | 95% | 100% | [24 empty] | FALSE | FALSE
WI-0053 | Enhancements on Semantic Support | Closed | N | SDS | R4 | [7 empty] | 0% | 5% | 20% | 25% | 30% | 35% | 60% | 80% | 95% | 95% | 5% | 10% | 15% | 20% | 25% | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% | [9 empty] | FALSE | FALSE
WI-0054 | Developers’ guide series | Closed | Y | TDE | Generic | [7 empty] | 0% | 1% | 10% | 10% | 60% | 75% | 85% | 90% | 92% | 93% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 95% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | 100% | 100% | [5 empty] | FALSE | FALSE
WI-0055 | Product Profiles & oneM2M Features | Closed | [10 empty] | 0% | 10% | 15% | 30% | 30% | 30% | 30% | 30% | 30% | 100% | [22 empty] | FALSE | FALSE
WI-0056 | Evolution of Proximal IoT Interworking | Closed | [10 empty] | 0% | 5% | 10% | 15% | 30% | 40% | 80% | 80% | 85% | 85% | 95% | 95% | 95% | 95% | 100% | [17 empty] | FALSE | FALSE
WI-0057 | TEF Interface | Closed | [10 empty] | 0% | 5% | 40% | 45% | 85% | 95% | 100% | [25 empty] | FALSE | FALSE
WI-0058 | Interworking with 3GPP networks | Closed | N | SDS | R4 | [7 empty] | 0% | 10% | 15% | 30% | 40% | 50% | 85% | 90% | 90% | 95% | 95% | 50% | 50% | 50% | 55% | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% | [9 empty] | FALSE | FALSE
WI-0059 | OPC-UA Interworking | Closed | [10 empty] | 0% | 15% | 30% | 50% | 75% | 90% | 95% | 95% | 95% | 100% | [22 empty] | FALSE | FALSE
WI-0060 | Interoperability testing Release 2 | Closed | Y | TDE | R2 | [7 empty] | 0% | 10% | 10% | 10% | 70% | 90% | 90% | 90% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 92% | 95% | 100% | 100% | [5 empty] | FALSE | FALSE
WI-0061 | Distributed Authorization | Closed | [10 empty] | 0% | 10% | 35% | 70% | 70% | 85% | 90% | 100% | [24 empty] | FALSE | FALSE
WI-0062 | Service Layer Forwarding | Closed | [10 empty] | 0% | 5% | 25% | 50% | 90% | 90% | 90% | 100% | [24 empty] | FALSE | FALSE
WI-0063 | Release 3 Enhancements on Base Ontology and Ontology based Interworking | Closed | [10 empty] | 0% | 5% | 15% | 20% | 50% | 55% | 75% | 90% | 95% | 95% | 99% | 99% | 100% | [19 empty] | FALSE | FALSE
WI-0064 | Adaptation of oneM2M for Smart City | Active | Y | SDS | R4 | [8 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 20% | 20% | 20% | 30% | 30% | 30% | 30% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | FALSE | FALSE
WI-0065 | Trust Management in oneM2M | Closed |  | SDS | Stalled | [8 empty] | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | [15 empty] | FALSE | FALSE
WI-0066 | Decentralized Authentication | Closed |  | SDS | R4 | [9 empty] | 0% | 15% | 40% | 70% | 70% | 70% | 70% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 75% | 100% | [14 empty] | FALSE | FALSE
WI-0067 | UICC Framework Public Key Enhancements (UPK) | Closed | [12 empty] | 0% | 0% | 40% | 85% | 90% | 95% | 100% | [23 empty] | FALSE | FALSE
WI-0068 | GlobalPlatform Interworking (GPI) | Closed |  | SDS | Stalled | [9 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [15 empty] | FALSE | FALSE
WI-0069 | Physical Object Heterogeneous identification and tracking services in oneM2M system | Active | Y | SDS | R4 | [9 empty] | 0% | 0% | 0% | 60% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | 90% | 40% | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | FALSE | FALSE
WI-0070 | Public Warning Service Enabler | Closed | N | RDM | R4 | [10 empty] | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 15% | 25% | 30% | 40% | 80% | 90% |  |  | 40% | 40% | 95% | 95% | 95% | 100% | [5 empty] | FALSE | FALSE
WI-0071 | oneM2M and W3C Web of Things Interworking (WOTIWK) | Closed | N | SDS | R4 | [10 empty] | 0% | 5% | 10% | 10% | 10% | 10% | 15% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | [11 empty] | FALSE | FALSE
WI-0072 | Modbus interworking | Closed | N | SDS | R4 | [10 empty] | 0% | 0% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% | [9 empty] | FALSE | FALSE
WI-0073 | App-ID Registry Function | Closed | [16 empty] | 0% | 10% | 30% | 30% | 100% | [21 empty] | FALSE | FALSE
WI-0074 | Conformance Test Specifications Release 2 | Closed |  | TDE | R2 | [13 empty] | 0% | 0% | 0% | 0% | 0% | 40% | 80% | 80% | 80% | 95% | 100% | [15 empty] | FALSE | FALSE
WI-0075 | Industrial Domain Information Model Mapping and Semantics Support | Closed | N | RDM | R4 | [14 empty] | 0% | 5% | 10% | 10% | 20% | 25% | 25% | 30% | 50% | 50% | 50% | 50% | 60% |  | 90% | 100% | [9 empty] | FALSE | FALSE
WI-0076 | Lightweight oneM2M Services | Closed | N | SDS | R4 | [14 empty] | 0% | 0% | 0% | 5% | 10% | 10% | 15% | 15% | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% | 90% | 93% | 97% | 97% | 100% |  |  |  |  | FALSE | FALSE
WI-0077 | Attribute Based Access Control Policy | Closed | N | SDS | R4 | [14 empty] | 0% | 0% | 15% | 15% | 20% | 20% | 35% | 50% | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% | 93% | 95% | 97% | 97% | 100% |  |  |  |  | FALSE | FALSE
WI-0078 | oneM2M API guide | Closed | Y | TDE | Generic | [15 empty] | 0% | 0% | 0% | 0% | 90% | 90% | 92% | 96% | 96% | 96% | 97% | 97% | 97% | 97% | 100% | [9 empty] | FALSE | FALSE
WI-0079 | Rel-4 Small Technical Enhancements | Active | N | TP | R4 | [15 empty] | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. | n.a. |  |  |  |  | FALSE | FALSE
WI-0080 | Study on Edge and Fog Computing in oneM2M systems | Closed | N | SDS | R4 | [16 empty] | 0% | 5% | 15% | 20% | 25% | 27% | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% | 90% | 95% | 97% | 97% | 100% |  |  |  |  | FALSE | FALSE
WI-0081 | Smart Device Template 4.0 | Closed | N | RDM | R4 | [16 empty] | 0% | 0% | 5% | 25% | 25% | 40% | 60% | 70% | 80% | 80% | 85% |  | 95% | 100% | [9 empty] | FALSE | FALSE
WI-0082 | 3GPP V2X Interworking | Closed | N | SDS | R4 | [16 empty] | 0% | 5% | 10% | 10% | 10% | 10% | 15% | 18% | 20% | 20% | 20% | 20% | [11 empty] | FALSE | FALSE
WI-0083 | oneM2M Service Subscribers and Users | Closed | N | SDS | R4 | [16 empty] | 0% | 5% | 10% | 10% | 15% | 25% | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% | 90% | 90% | 91% | 95% | 100% |  |  |  |  | FALSE | FALSE
WI-0084 | SDT based Information Model and Mapping for Vertical Industries | Closed | N | RDM | R4 | [17 empty] | 0% | 5% | 25% | 25% | 35% | 40% | 40% | 55% | 60% | 70% |  | 85% | 95% | 98% | 100% | 100% | 100% | [5 empty] | FALSE | FALSE
WI-0085 | Conformance Test Specifications Release 3 | Closed | N | TDE | R3 | [18 empty] | 0% | 0% | 0% | 0% | 10% | 60% | 60% | 70% | 75% | 85% | 92% | 92% | 92% | 95% | 97% | 99% | 99% | 99% | 99% | 100% | 100% | FALSE | FALSE
WI-0086 | Conformance Test Specifications Release 4 | Active | Y | TDE | R4 | [18 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 30% | 40% | 50% | 50% | 65% | 95% | 95% | 97% | 97% | FALSE | FALSE
WI-0087 | Summary of differences between Rel-2A & Rel-3 | Closed |  | SDS | R2A-3 | [18 empty] | 0% | 0% | 30% | 95% | 100% | [16 empty] | FALSE | FALSE
WI-0088 | M2M/IoT Application and Component Configuration | Closed | Y | SDS | R4 | [18 empty] | 0% | 5% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | 15% | [11 empty] | FALSE | FALSE
WI-0089 | Getting started with oneM2M | Active | Y | SDS | Generic | [20 empty] | 0% | 0% | 20% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 25% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | FALSE | FALSE
WI-0090 | oneM2M and Zigbee interworking | Active | Y | SDS | R4 | [20 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | FALSE | FALSE
WI-0091 | oneM2M Services and Platforms Discovery | Active | Y | SDS | R4 | [20 empty] | 0% | 0% | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | FALSE | FALSE
WI-0092 | Railway Domain Enablement (RAILDE) | Closed | N | RDM | R4 | [20 empty] | 0% | 0% | 10% | 25% | 25% | 35% | 45% |  | 50% | 50% | 70% | 70% | 70% | 90% | 90% | 100% | 100% | 100% | 100% | FALSE | FALSE
WI-0093 | Action Triggering Enhancements | Active | Y | SDS | R4 | [21 empty] | 0% | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | 91% | 93% | 93% | 97% | 97% | 97% | 97% | FALSE | FALSE
WI-0094 | Ontologies for Smart City Services (OSCS) | Active | Y | RDM | R4 | [22 empty] | 5% | 10% | 10% | 10% | 40% | 40% | 40% | 40% | 40% | 65% | 65% | 65% | 65% | 65% | 65% | 70% | 70% | FALSE | FALSE
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations (eDPR) | Active | N | SDS | R5 | [25 empty] | 0% | 0% | 30% | 50% | 55% | 65% | 65% | 65% | 65% | 65% | 70% | 70% | 70% | 70% | FALSE | FALSE
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | Active | N | SDS | R5 | [26 empty] | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | FALSE | FALSE
WI-0097 | Interoperability testing Release 3 | Closed | N | TDE | R3 | [26 empty] | 0% | 30% | 30% | 30% | 90% | 92% | 95% | 95% | 95% | 95% | 99% | 100% | 100% | FALSE | FALSE
WI-0098 | IoT for Smart Lifts | Active | Y | RDM | R4 | [27 empty] | 5% | 20% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | FALSE | FALSE
WI-0099 | Management Object Migration | Closed | N | RDM | R5 | [27 empty] | 0% | 5% | 30% | 50% | 50% | 55% | 90% | 100% |  |  |  |  | FALSE | FALSE
WI-0100 | oneM2M and SensorThings API | Active | N | SDS | R5 | [28 empty] | 5% | 5% | 15% | 20% | 20% | 20% | 25% | 25% | 40% | 50% | 50% | FALSE | FALSE
WI-0101 | Advanced Semantic Discovery | Active | N | RDM | R5 | [28 empty] | 10% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 60% | 60% | 60% | FALSE | FALSE
WI-0102 | System enhancements to support Data License Management | Active | N | SDS | R5 | [29 empty] | 5% | 15% | 30% | 40% | 45% | 45% | 50% | 50% | 50% | 50% | FALSE | FALSE
WI-0103 | oneM2M API_Guide Rel 3 | Active | N | TDE | R3 | [30 empty] | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 40% | 40% | FALSE | FALSE
WI-0104 | SDT based Information Model and Mapping for Vertical Industries – SIMVI | Active | N | RDM | R5 | [30 empty] | 0% | 0% | 0% | 10% | 15% | 20% | 20% | 20% | 20% | FALSE | FALSE
WI-0105 | System enhancements to support AI capabilities | Active | N | RDM | R5 | 0% | 10% | 10% | FALSE | FALSE | [28 empty] | 0% | 20% | 55% | 60% | 70% | 70% | FALSE | TRUE
WI-0106 | Interoperability testing Release 4 | Active | N | TDE | R5 | 0% | 10% | 10% | FALSE | FALSE | [29 empty] | 0% | 0% | 0% | 0% | 0% | FALSE | FALSE
WI-0107 | Developers guide series | Active | N | SDS | R5 | [29 empty] | 5% | 15% | 30% | 40% |  |  | 0% | 0% | 40% | 40% | FALSE | FALSE
WI-0108 | Conformance Test Maintenance | Active | N | TDE | R5 | [30 empty] | 0% | 0% | 10% |  |  |  | 0% | 0% | 0% | FALSE | FALSE
WI-0109 | IPE-based Device Management with FlexContainers | Active | N | RDM | R5 | [30 empty] | 0% | 0% | 0% |  |  |  | 5% | 30% | 30% | FALSE | FALSE
| #N/A | #N/A
| #N/A | #N/A
| #N/A | #N/A
| #N/A | #N/A
| Freeze Date (should >= 90%) | #N/A
| Approval Date (should >= 95%) | #N/A
| Closed | #N/A

## TSs (hidden)
Nr | Title | 1st appr. Rel 1 | latest ratified Rel1 version | latest Rel1 | Ratified Rel 2 | latest Version Rel 2 | Release 2A ratified TP34 | Rel3 Pre-ratified | Rel3 ratified | latest Version Rel 3 | Version Rel 4 | Rapporteur | Comment
TS-0001 | Functional Architecture | v1.6.0 | v1.13.1 | v1.18.0 | v2.10.0 | v2.23.0 | v2.18.1 |  |  | v3.15.0 | v4.0.0 | Weixiang Shao, ZTE | Change of Rapporteur TP33
TS-0002 | Requirements | v1.0.1 |  | v1.0.1 | v2.7.1 | v2.10.2 | v2.10.2 |  |  | v3.1.2 | v4.6.0 | Xubei (Echo), Huawei | Change of Rapporteur at TP#25
TS-0003 | Security Solutions | v1.0.1 | v1.4.2 | v1.7.0 | v2.4.1 | v2.14.0 | v2.13.0 |  |  | v3.10.2 |  | Wolfgang Granzow, Qualcomm, Qualcomm | Change of Rapporteur post TP30
TS-0004 | Service Layer Core Protocol | v1.0.1 | v1.6.0 | v1.13.0 | v2.7.1 | v2.21.0 | v2.16.1 |  |  | v3.11.1 |  | Nobuyuki Uchida, Qualcomm | change of Rapporteur after TP27
TS-0005 | Management Enablement (OMA) | v1.0.1 | v1.4.1 | v1.4.1 | v2.0.0 | v2.0.1 | v2.0.2 |  |  | v3.5.1 |  | SeungKyu Park, LG Electronics & Jiaxin Yin, Huawei
TS-0006 | Management enablement (BBF) | v1.0.1 | v1.1.4 | v1.1.4 | v2.0.1 | v2.2.0 | v2.2.1 |  |  | v3.6.2 |  | Tim Carey, Nokia
TS-0007 | Service Components | n.a. |  | n.a. | v2.0.0 | v2.0.2 | v2.0.2 |  |  |  |  | Tim Carey, Nokia
TS-0008 | CoAP Protocol Binding | v1.0.1 | v1.3.2 | v1.6.0 | v2.0.0 | v2.7.0 | v2.6.1 |  |  | v3.3.1 |  | Jiaxin Yin , Huawei Technologies
TS-0009 | HTTP Protocol Binding | v1.0.1 | v1.5.1 | v1.10.0 | v2.6.1 | v2.15.0 | v2.13.1 |  |  | v3.2.1 |  | SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr
TS-0010 | MQTT protocol binding | v1.0.1 | v1.5.1 | v1.8.0 | v2.4.1 | v2.8.0 | v2.7.1 |  |  | v3.0.1 |  | Peter Niblett, IBM
TS-0011 | Common Terminology | v1.2.1 |  | v1.4.0 | v2.4.1 | v2.8.0 | v2.8.1 |  |  | v3.0.1 | v4.0.0 | Roland Hechwartner, Deutsche Telekom
TS-0012 | Base Ontology |  | n.a. | n.a. | v2.0.0 | v2.2.1 | v2.2.2 |  |  | v3.7.3 |  | Joerg Swetina, NEC
TS-0013 | Interoperability Testing |  | v1.0.0 | v1.4.0 | v2.0.0 | v2.6.0 | v2.3.2 |  |  |  |  | Laurent Velez, ETSI
TS-0014 | LWM2M Interworking |  |  | v0.14.0 | v2.0.0 | v2.2.0 | v2.0.1 |  |  | v3.1.1 |  | Timothy Carey, Nokia
TS-0015 | Testing Framework |  |  | v0.5.1 | v2.0.0 | v2.0.0 | v2.0.1 |  |  |  |  | Jiaxin Yin , Huawei Technologies
TS-0016 | Secure Environment Abstraction | [8 empty] | v3.0.2 |  | François Ennesser, Gemalto (ETSI)
TS-0017 | Implementation Conformance Statements |  |  | v1.0.2 |  | v2.0.0 |  |  |  | v0.2.0 |  | Insong Lee, KETI | change of Rapporteur
TS-0018 | Test Suite Structure and Test Purposes |  |  | v1.2.2 | v2.0.0 | v2.8.0 |  |  |  | v3.0.0 |  | Insong Lee, KETI | change of Rapporteur
TS-0019 | Abstract Test Suite & implementation eXtra Information for Test |  |  | v1.0.0 |  | v2.2.0 |  |  |  | v0.6.0 |  | Miguel Angel Reina Ortega, ETSI
TS-0020 | WebSocket Protocol Binding |  |  |  | v2.0.0 | v2.3.0 | v2.0.2 |  |  | v3.0.1 |  | Wolfgang Granzow, Qualcomm | new rapporteur at TP30
TS-0021 | oneM2M and AllJoyn Interworking |  |  |  | v2.0.0 | v2.0.0 | v2.0.1 |  |  |  |  | SeungMyeong Jeong, LGE
TS-0022 | Field Device Configuration |  |  |  |  | v2.4.0 | v2.3.1 |  |  | v3.0.1 | V4.0.0 | Wolfgang Granzow, Qualcomm | change of rapporteur
TS-0023 | SDT based Information Model and Mapping for Vertical Industries |  |  |  | v2.0.0 | v2.0.1 | v2.0.2 |  |  | v3.7.3 | v4.1.0 | Andreas Kraft (Deutsche Telekom); Pawel Strzemecki (ORANGE), | new Rapporteur TP33; Name change with V4.0.0 Version from earlier "Home Appliances Information Model and Mapping"
TS-0024 | OCF Interworking |  |  |  | v2.0.0 | v2.0.1 | v2.0.2 |  |  | v3.2.2 |  | Kiran Vedula, Samsung; Josef Blanz, Qualcomm | Name changed with v3.0.0 to OCF Interworking
TS-0025 | Product Profiles | [5 empty] | v2.0.0 |  |  | v2.0.0 |  | Jiaxin Yin, Huawei Technologies Co., Ltd.,Keebum Kim, (TTA) | renamed at TP33; TS-0025 to be added to R2A -if applicable. Changed Rapporteur at TP38
TS-0026 | 3GPP Interworking* | [8 empty] | v3.0.0 |  | Xubei (Echo), Huawei; James Hu, AT&T | *at TP25: According to WI-0058 update name changed to 3GPP Interworking; changed Rapporteur Jessie to Xubei
TS-0027 | Security Implementation Conformance Statements |  |  |  |  | v0.0.1 | [5 empty] | Rapporteur: Franck Le Gall (Easy Global Market)
TS-0028 | Security Test Suite Structure and Test Purposes |  |  |  |  | v0.0.1 | [5 empty] | Rapporteur: Franck Le Gall (Easy Global Market)
TS-0029 | Security Abstract Test Suite and Implementation eXtra Information for Test |  |  |  |  | v0.0.1 | [5 empty] | Rapporteur: Miguel Reina Ortega
TS-0030 | Ontology based Interworking | [8 empty] | v3.0.2 |  | Rapporteur: Joerg Swetina, NEC
TS-0031 | Feature Catalogue |  |  |  |  | v2.3.0 | v2.0.0 |  |  | v3.0.1 |  | Bob Flynn (Bob.Flynn@InterDigital.com) | renamed at TP33; At TP34:TS-0031 was approved atTP34. After successful editHelp check it will be ratified as TS-0031 V2.0.0 (either via email approval or at TP35 opening) and added to Release 2A. Revised version of Release 2A Control Document will be approved. Change of Rapporteur (Nov 2018)
TS-0032 | MAF and MEF Interface Specification | [5 empty] | v2.1.0 |  |  | v3.0.0 |  | Rapporteur: Wolfgang Granzow, Qualcomm, wgranzow@qti.qualcomm.com
TS-0033 | Proximal IoT Interworking Framework | [8 empty] | v0.1.1 |  | Josef Blanz, Qualcomm | with V0.1.1 TS renamed to Interworking Framework
TS-0034 | Semantics Support | [8 empty] | v3.0.1 |  | Editor: Chonggang Wang (Convida)
TS-0035 | OSGi Interworking | [8 empty] | v3.0.0 |  | Editor: Jiaxin Yin (Huawei Technologies Co.,Ltd.)
TS-0036 | Advanced Vehicular Domain Enablement | [8 empty] | v0.0.1 |  | Editor: Kenichi YAMAMOTO (KDDI Corporation),Catalina Mladin (Convida Wireless), Victor Kueh (Huawei Technologies)
Approved and Ratified
*Release 2A ratified at TP34. See ADM-0012-Release 2A Control document V2.0.0

## TRs (hidden)
Nr | Title | latest version | Release 2A | status | Rapporteur | comment
TR-0001 | Use Cases Collection | v4.3.0 | V2.4.2 | Approved | Catalina Mladin, InterDigital
TR-0002 | Architecture Analysis Part1 | v0.2.0 |  | Approved | Richard Brennan, Telxxis
TR-0003 | Architecture Analysis Part 2 | v0.5.0 |  | Approved | Phillip Brown, InterDigital
TR-0004 | Definitions and Acronyms | v0.4.0 |  | Stable Draft | n.a. | obsolete; content moved to TS-0011 Common Terminology
TR-0005 | Roles and Focus Areas | v0.0.4 |  | Draft | Josef Blanz, Qualcomm
TR-0006 | Study of Management Capability Enablement | v0.5.1 |  | Approved | Jiaxin Yin, Huawei
TR-0007 | Study on Abstraction and Semantics Enablement | v2.11.1 |  | Approved | Joerg Swetina, NEC
TR-0008 | Security | v2.0.0 | V2.0.1 | Approved | François Ennesser, Gemalto
TR-0009 | Protocol Analysis | v0.7.0 |  | Approved | Richard Brennan, Telxxis
TR-0010 | Device_Gateway_Classification | v0.0.0 |  | Draft | Hongbeom Ahn, LGE | WI-0006 obsolete. TR not started
TR-0011 | MQTT Protocol Interworking Study | v0.1.0 |  | Draft | Peter Niblett, IBM
TR-0012 | End-to-End-Security and Group Authentication | v2.0.0 |  | Approved | Ziyao Cheng, China Mobile
TR-0013 | Home Domain Enablement | v1.0.0 |  | Approved | Sungchan Choi, KETI & Dongjoo KIM, LGE
TR-0014 | oneM2M AllJoyn Interworking | v0.4.0 |  | Draft | SeungMyeong JEONG, KETI | To be adjusted to naming convention: AllJoyn Interworking
TR-0015 | Service Layer API Core Principles | v0.1.0 |  | Draft | Xuan He, Hitachi
TR-0016 | Authorization Architecture and Access Control Policy | v2.0.0 |  | Approved | Wei Zhou, Datang
TR-0017 | Home Domain Abstract Information Model | v2.0.0 |  | Approved | Sungchan Choi, KETI & Dongjoo KIM, LGE
TR-0018 | Industrial Domain Enablement | v4.0.0 | V2.5.2 | Approved | Miao Jiang, Hitachi (China) Research &Development Corporation (CCSA), miaojiang@hitachi.cn. Chengsui Lu, Hitachi (China) Research &Development Corporation (CCSA), cslu@hitachi.cn | new rapporteur at TP28
TR-0019 | Dynamic_Authorization | v2.0.0 |  | Approved | Phil Hawkes, Qualcomm | Ratified at TP#27
TR-0020 | Study of service transactions and re-usable service layer context | v0.8.0 |  | Draft | Qiuting Li, ZTE
TR-0021 | Study of the action triggering in M2M | v0.5.0 |  | Draft | Jiaxin Yin, Huawei Technologies Co.,Ltd
TR-0022 | Continuation and Integration of HGI Smart Home activities | v2.0.0 |  | Approved | Patricia Martigne, ORANGE
TR-0023 | oneM2M and OIC Interworking | v0.2.0 |  | Draft | Kiran Vedula, Samsung Electronics | To be adjusted to naming convention: OIC Interworking
TR-0024 | 3GPP Interworking | v2.4.0 |  | Approved | Shao Weixiang, ZTE
TR-0025 | Application Developer Guide | v2.0.1 | V2.0.2 | Approved | Laurent Velez, ETSI
TR-0026 | Vehicular Domain Enablement | v4.5.0 |  | Approved | Kenichi Yamamoto, KDDI, Catalina Mladin (Convida Wireless), Victor Kueh (Huawei Technologies); Adjusted list of rapporteurs in V37.1.0 | Approved at TP31
TR-0027 | DDS usage in oneM2M | v0.2.0 |  | Draft | Bei Xu (Echo), Huawei
TR-0028 | Analysis on the interworking between oneM2M and OSGi Alliance | v0.1.0 |  | Draft | Jiaxin Yin (Huawei Technologies Co.,Ltd.)
TR-0029 | Methodology of product profiles definition | v0.0.1 |  | Draft | Jiaxin Yin, Huawei Technologies Co., Ltd.,
TR-0030 | Service Layer Forwarding | v0.3.0 |  | Draft | Rapporteur: Dale Seed, InterDgital (Dale.Seed@InterDigital.com)
TR-0031 | LWM2M DM & Interworking Enhancements | v0.5.0 |  | Draft | Rapporteur: Dale Seed, InterDgital (Dale.Seed@InterDigital.com)
TR-0032 | Platform features catalogue | v0.0.1 |  | Draft | Editor: SeungMyeong JEONG, KETI, sm.jeong@keti.re.kr | obsolete
TR-0033 | Study on Enhanced Semantic Enablement | v4.2.2 |  | Draft | Editor: Xu Li (Convida) | Change of Rapporteur TP36.1
TR-0034 | Temperature monitoring example using CoAP binding | v2.1.0 | V2.0.0 | Approved | Rapporteur: Shane He
TR-0035 | Developer guide of device management | v0.2.1 | V2.0.0 | Approved | Rapporteur: Jiaxin Yin
TR-0036 | Smart City | v0.3.0 |  | Draft | Rapporteur: Jae Young Ahn, ETRI (ahnjy@etri.re.kr )
TR-0037 | Smart Farm Example using MQTT Binding | v0.1.0 | V2.0.0 | Approved | Rapporteur: Ting Martin Miao
TR-0038 | Developer guide-Implementing security example | v0.5.0 |  | Approved | Rapporteur: Rapporteur: Francois Ennesser, & Laurent Velez
TR-0039 | Developer guide-SDT-based implementation | v0.0.5 | V2.0.0 | Approved | Rapporteur: Patricia Martigne & Laurent Velez
TR-0040 | Trust management in oneM2M | v0.0.2 |  | Draft | Rapporteur: Jae Young Ahn, ETRI (ahnjy@etri.re.kr )
TR-0041 | Decentralized Authentication | v0.4.0 |  | Approved | Rapporteur: Jie SHI (Huawei Technologies Co.,Ltd (CCSA))
TR-0042 | WOT Interworking | v0.4.0 |  | Draft | Rapporteur: Yongjing Zhang, zhangyongjing@huawei.com
TR-0043 | Modbus Interworking | v0.1.0 |  | Draft | Rapporteur: Qiuting Li, li.qiuting@zte.com.cn
TR-0044 | Heterogeneous identification service in oneM2M system | v0.5.0 |  | Draft | Rapporteur: Yuan TAO (Computer Network Information Center&Chinese Academy of Sciences Guangzhou Sub-center)
TR-0045 | Developer Guide: Implementing Semantics | v0.3.1 | V2.0.0 | Approved | Rapporteur: Martin Bauer (NEC Europe Ltd. (ETSI))
TR-0046 | Study on Disaster Alert Service Enabler | v0.0.1 |  | Draft | Rapporteur: SeungMyeong JEONG (KETI)
TR-0047 | Developer Guide of 3GPP Interworking | v0.1.2 |  | Draft | Rapporteur: BEI XU (Huawei Telecommunication)
TR-0048 | oneM2M App-ID Registry Function | v0.0.4 |  | Approved | Rapporteur: Shelby Kiewel (iconectiv) | Release 3
TR-0049 | Industrial Domain Information Mapping and Semantics Support | v0.2.0 |  | Draft | Rapporteur: Chengsui Lu (Hitachi (China) Research & Development Corporation)
TR-0050 | Attribute Based Access Control Policy | v0.7.0 |  | Draft | Rapporteur: Wei Zhou (Datang Telecom Technology@Industry Holdings Co., LTD)
TR-0051 | oneM2M API Guide | v0.5.0 |  | Draft | Rapporteur: Laurent VELEZ (European Telecommunications Standards Institute (ETSI))
TR-0052 | Study on Edge and Fog Computing in oneM2M systems | v0.6.0 |  | Draft | Rapporteur: Kenichi YAMAMOTO (KDDI Corporation), Catalina Mladin (Convida Wireless)
TR-0053 | Lightweight oneM2M Services | v0.2.0 |  | Draft | Rapporteur: Dale Seed (Convida Wireless LLC)
TR-0054 | oneM2M Service Subscribers and Users | v0.4.0 |  | Draft | Rapporteur: Dale Seed (Convida Wireless LLC)
TR-0055 | 3GPP V2X Interworking | v0.2.0 |  | Draft | Rapporteur: BEI XU (Huawei Telecommunication (India) Co. Pvt. Ltd.)
TR-0056 | Summary of Differences between Rel-2A & Rel-3 | v0.2.0 |  | Draft | Rapporteur: Kei Harada (Nippon Telegraph and Telephone Corp. (NTT))
TR-0057 | Getting started with oneM2M | v0.2.0 |  | Draft | Rapporteur: Laurent VELEZ (ETSI)
TR-0058 | Railway Domain Enablement | v0.0.1 |  | Draft | Rapporteur: Andrew Min-gyu Han (Hansung University (TTA))
TR-0059 | Services and Platforms Discovery | v0.1.0 |  | Draft | Rapporteur: JaeSeung Song (KETI)
TR-0060 | Study of action triggering enhancements | v0.0.1 |  | Draft | Rapporteur: SeungMyeong Jeong, KETI, sm.jeong@keti.re.kr.
TR-0061 | Study_on_ontologies_for_Smart_City_Services | v0.0.1 |  | Draft | Rapporteur: Insong Lee (KETI, insong@keti.re.kr)

## Transpositions (hidden)
Register - Ratified Releases and transpositions
Content: This register lists all Technical Specifications and Technical Reports and shows all ratified releases as well as the transpositions by the Partner Type 1 and the ITU-T SG. **For the latest status of partner transpositions see http://onem2m.org/technical/partner-transpositions
Deliverables | Release 3 ratified at TP38** | Partner Transpositions | Release 2A ratified at TP34** | Partner transpositions |  |  |  |  | Release 2 ratified at TP24.1 | Partner Transpositions** |  |  |  |  | ITU-T | Release 1 ratified @ TP22 | Partner Transpositions |  |  |  |  | Release 1 ratified at TP15.1 | Partner Transpositions
Technical Specifications | Technical Specifications and Reports as defined in R3 control document ADM-0017 Release 3 Control Document V3.0.0 |  | Technical Specifications and Reports as defined in R2A control document ADM-0012 Release 2A Control Document V2.1.0 | ATIS | ETSI | TSDSI | TTA | TTC | Technical Specifications and Reports as defined in R2 control document ADM-0011 Release 2 Control Document V2.0.0 | ATIS | ETSI | TSDSI | TTA | TTC | SG 20: Y.4500.x series | Technical Specifications ratified @TP 22 | ATIS | ETSI | TSDSI | TTA | TTC | Technical Specifications as defined in ADM-0008 Release 1 Control Document V1.0.0 | ATIS | ETSI | TIA | TSDSI | TTA | TTC
TS-0001 Functional Architecture | TS 0001 - Functional Architecture, V3.13.2 |  | TS 0001 - Functional Architecture, V2.18.1 |  |  |  |  | TS-M2M-0001v2.18.1 | TS 0001 - Functional Architecture, V2.10.0 | ATIS.oneM2M.TS0001V2100-2016 | TS 118 101 V.2.10.0 | TSDSI STD T1.oneM2M TS-0001-2.10.0 V1.0.0 | TTAT.MM-TS.0001 v2.10.0 | TS-M2M-0001v2.10.0 | Y.4500.1: oneM2M – Functional architecture | TS 0001 - Functional Architecture, V1.13.1 |  | TS 118 101 V1.1.0 |  | TTAT.MM-TS.0001 v1.13.1 | TS-M2M-0001v1.13.1 | TS 0001 - Functional Architecture, V1.6.1 | ATIS.oneM2M.TS0001V161-2015 | TS 118 101 V1.0.0 | TIA-5022.001 |  | TTAT.MM-TS.0001 v1.6.1 | TS-M2M-0001v1.6.1
TS-0002 Requirements | TS 0002 - Requirements, V3.1.2 |  | TS 0002 - Requirements, V2.10.2 |  |  |  |  | TS-M2M-0002v2.10.2 | TS 0002 - Requirements, V2.7.1 | ATIS.oneM2M.TS0002V271-2016 | TS 118 102 V2.7.1 | TSDSI STD T1.oneM2M TS-0002-2.7.1 V1.0.0 | TTAT.MM-TS.0002 v2.7.1 | TS-M2M-0002v2.7.1 | Y.4500.2: oneM2M - Requirements | [6 empty] | TS 0002 - Requirements, V1.0.1 | ATIS.oneM2M.TS0002V101-2015 | TS 118 102 V1.0.0 | TIA-5022.002 |  | TTAT.MM-TS.0002 v1.0.1 | TS-M2M-0002v1.0.1
TS-0003 Security Solutions | TS 0003 - Security Solutions, V3.10.2 |  | TS 0003 - Security Solutions, V2.12.1 |  |  |  |  | TS-M2M-0003v2.12.1 | TS 0003 - Security Solutions, V2.4.1 | ATIS.oneM2M.TS0003V241-2016 | TS 118 103 V2.4.1 | TSDSI STD T1.oneM2M TS-0003-2.4.1 V1.0.0 | TTAT.MM-TS.0003 v2.4.1 | TS-M2M-0003v2.4.1 | (Y.4500.3: oneM2M – Security Solutions) comment resolution ongoing | TS 0003 - Security Solutions, V1.4.2 |  | TS 118 103 V1.1.0 |  | TTAT.MM-TS.0003 v1.4.2 | TS-M2M-0003v1.4.2 | TS 0003 - Security Solutions, V1.0.1 | ATIS.oneM2M.TS0003V101-2015 | TS 118 103 V1.0.0 | TIA-5022.003 |  | TTAT.MM-TS.0003 v1.0.1 | TS-M2M-0003v1.0.1
TS-0004 Service Layer Core Protocol | TS 0004 - Service Layer Core Protocol, V3.11.0 |  | TS 0004 - Service Layer Core Protocol, V2.16.1 |  |  |  |  | TS-M2M-0004v2.16.1 | TS 0004 - Service Layer Core Protocol, V2.7.1 | ATIS.oneM2M.TS0004V271-2016 | TS 118 104 V2.7.1 | TSDSI STD T1.oneM2M TS-0004-2.7.1 V1.0.0 | TTAT.MM-TS.0004 v2.7.1 | TS-M2M-0004v2.7.1 | Y.4500.4: oneM2M – Service layer core protocol specification | TS 0004 - Service Layer Core Protocol, V1.6.0 |  | TS 118 104 V1.1.0 |  | TTAT.MM-TS.0004 v1.6.0 | TS-M2M-0004v1.6.0 | TS 0004 - Service Layer Core Protocol, V1.0.1 | ATIS.oneM2M.TS0004V101-2015 | TS 118 104 V1.0.0 | TIA-5022.004 |  | TTAT.MM-TS.0004 v1.0.1 | TS-M2M-0004v1.0.1
TS-0005 Management Enablement (OMA) | TS-0005 Management Enablement (OMA), V3.4.2 |  | TS 0005 - Management enablement (OMA), V2.0.2 |  |  |  |  | TS-M2M-0005v2.0.2 | TS 0005 - Management Enablement (OMA), V2.0.0 | ATIS.oneM2M.TS0005V200-2016 | TS 118 105 V2.0.0 | TSDSI STD T1.oneM2M TS-0005-2.0.0 V1.0.0 | TTAT.MM-TS.0005 v2.0.0 | TS-M2M-0005 v2.0.0 | Y.4500.5: oneM2M management enablement (OMA) | TS 0005 - Management enablement (OMA), V1.4.1 |  | TS 118 105 V1.1.0 |  | TTAT.MM-TS.0005 v1.4.1 | TS-M2M-0005v1.4.1 | TS 0005 - Management enablement (OMA), V1.0.1 | ATIS.oneM2M.TS0005V101-2015 | TS 118 105 V1.0.0 | TIA-5022.005 |  | TTAT.MM-TS.0005 v1.0.1 | TS-M2M-0005v1.0.1
TS-0006 Management enablement (BBF) | TS-0006 Management enablement (BBF), 3.6.2 |  | TS 0006 - Management enablement (BBF), V2.2.1 |  |  |  |  | TS-M2M-0006v2.2.1 | TS 0006 - Management Enablement (BBF), V2.0.1 | ATIS.oneM2M.TS0006V201-2016 | TS 118 106 V2.0.1 | TSDSI STD T1.oneM2M TS-0006-2.0.1 V1.0.0 | TTAT.MM-TS.0006 v2.0.1 | TS-M2M-0006 v2.0.1 | Y.4500.6: oneM2M management enablement (BBF) | TS 0006 - Management enablement (BBF), V1.1.4 |  | TS 118 106 V1.1.0 |  | TTAT.MM-TS.0006 v1.1.4 | TS-M2M-0006v1.1.4 | TS 0006 - Management enablement (BBF), V1.0.1 | ATIS.oneM2M.TS0006V101-2015 | TS 118 106 V1.0.0 | TIA-5022.006 |  | TTAT.MM-TS.0006 v1.0.1 | TS-M2M-0006v1.0.1
TS-0007 Service Components |  |  | TS 0007 – Service Components, V2.0.2 |  |  |  |  | TS-M2M-0007v2.0.2 | TS 0007 - Service Components, V2.0.0 | ATIS.oneM2M.TS0007V200-2016 |  | TSDSI STD T1.oneM2M TS-0007-2.0.0 V1.0.0 | TTAT.MM-TS.0007 v2.0.0 | TS-M2M-0007 v2.0.0
TS-0008 CoAP Protocol Binding | TS-0008 CoAP Protocol Binding, V3.3.1 |  | TS 0008 - CoAP Protocol Binding, V2.6.1 |  |  |  |  | TS-M2M-0008v2.6.1 | [6 empty] | Y.4500.8: oneM2M – CoAP protocol binding [=> v1.0.1] | TS 0008 - CoAP Protocol Binding, V1.3.2 |  | TS 118 108 V1.1.0 |  | TTAT.MM-TS.0008 v1.3.2 | TS-M2M-0008v1.3.2 | TS 0008 - CoAP Protocol Binding, V1.0.1 | ATIS.oneM2M.TS0008V101-2015 | TS 118 108 V1.0.0 | TIA-5022.008 |  | TTAT.MM-TS.0008 v1.0.1 | TS-M2M-0008v1.0.1
TS-0009 HTTP Protocol Binding | TS-0009 HTTP Protocol Binding, V3.2.0 |  | TS 0009 - HTTP Protocol Binding, V2.13.1 |  |  |  |  | TS-M2M-0009v.2.13.1 | TS 0009 - HTTP Protocol Binding, V2.6.1 | ATIS.oneM2M.TS0009V261-2016 | TS 118 109 V2.6.1 | TSDSI STD T1.oneM2M TS-0009-2.6.1 V1.0.0 | TTAT.MM-TS.0009 v2.6.1 | TS-M2M-0009 v2.6.1 | Y.4500.9: oneM2M – HTTP protocol binding | TS 0009 - HTTP Protocol Binding, V1.5.1 |  | TS 118 109 V1.1.0 |  | TTAT.MM-TS.0009 v1.5.1 | TS-M2M-0009v1.5.1 | TS 0009 - HTTP Protocol Binding, V1.0.1 | ATIS.oneM2M.TS0009V101-2015 | TS 118 109 V1.0.0 | TIA-5022.009 |  | TTAT.MM-TS.0009 v1.0.1 | TS-M2M-0009v1.0.1
TS-0010 MQTT protocol binding | TS-0010 MQTT protocol binding, V3.0.2 |  | TS 0010 - MQTT Protocol Binding, V2.7.1 |  |  |  |  | TS-M2M-0010v2.7.1 | TS 0010 - MQTT Protocol Binding, V2.4.1 | ATIS.oneM2M.TS0010V241-2016 | TS 118 110 V2.4.1 | TSDSI STD T1.oneM2M TS-0010-2.4.1 V1.0.0 | TTAT.MM-TS.0010 v2.4.1 | TS-M2M-0010 v2.4.1 | Y.4500.10: oneM2M – MQTT protocol binding | TS 0010 - MQTT Protocol Binding, V1.5.1 |  | TS 118 110 V1.1.0 |  | TTAT.MM-TS.0010 v1.5.1 | TS-M2M-0010v1.5.1 | TS 0010 - MQTT Protocol Binding, V1.0.1 | ATIS.oneM2M.TS0010V101-2015 | TS 118 110 V1.0.0 | TIA-5022.010 |  | TTAT.MM-TS.0010 v1.0.1 | TS-M2M-0010v1.0.1
TS-0011 Common Terminology | TS-0011 Common Terminology, V3.0.2 |  | TS 0011 – Common Terminology, V2.8.1 |  |  |  |  | TS-M2M-0011v2.8.1 | TS 0011 - Common Terminology, V2.4.1 | ATIS.oneM2M.TS0011V241-2016 | TS 118 111 V2.4.1 | TSDSI STD T1.oneM2M TS-0011-2.4.1 V1.0.0 | TTAT.MM-TS.0011 v2.4.1 | TS-M2M-0011 v2.4.1 | Y.4500.11: oneM2M – Common terminology | TS 0011 – Common Terminology, V1.2.1 | [5 empty] | TS 0011 – Common Terminology, V1.2.1 | ATIS.oneM2M.TS0011V121-2015 | TS 118 111 V1.0.0 | TIA-5022.0011 |  | TTAT.MM-TS.0011 v1.2.1 | TS-M2M-0011v1.2.1
TS-0012 Base Ontology | TS-0012 Base Ontology, V3.7.3 |  | TS-0012 – Base Ontology, V2.2.2 |  |  |  |  | TS-M2M-0012v2.2.2 | TS 0012 - oneM2M Base Ontology, V2.0.0 | ATIS.oneM2M.TS0012V200-2016 | TS 118 112 V2.0.0 | TSDSI STD T1.oneM2M TS-0012-2.0.0 V1.0.0 | TTAT.MM-TS.0012 v2.0.0 | TS-M2M-0012 v2.0.0 | Y.4500.12: oneM2M base ontology
TS-0013 Interoperability Testing |  |  | TS-0013- Interoperability Testing, V2.3.2 |  |  |  |  | TS-M2M-0013v2.3.2 | [6 empty] | Y.4500.13: oneM2M – Interoperability testing [=> v1.0.0] | TS 0013 - Interoperability testing, V1.0.0 |  | TS 118 113 V1.0.0 |  | TTAT.MM-TS.0013 v1.0.0 | TS-M2M-0013v1.0.0
TS-0014 LWM2M Interworking | TS-0014 LWM2M Interworking, V3.1.1 |  | TS-0014 - LWM2M Interworking, V2.0.1 |  |  |  |  | TS-M2M-0014v2.0.1 | TS 0014 - LWM2M Interworking, V2.0.0 | ATIS.oneM2M.TS0014V200-2016 | TS 118 114 V2.0.0 | TSDSI STD T1.oneM2M TS-0014-2.0.0 V1.0.0 | TTAT.MM-TS.0014 v2.0.0 | TS-M2M-0014 v2.0.0 | Y.4500.14: oneM2M – LwM2M interworking
TS-0015 Testing Framework |  |  | TS-0015 – Testing Framework, V2.0.1 |  |  |  |  | TS-M2M-0015v2.0.1 | TS 0015 - Testing Framework, V2.0.0 | ATIS.oneM2M.TS0015V200-2016 | TS 118 115 V2.0.0 | TSDSI STD T1.oneM2M TS-0015-2.0.0 V1.0.0 | TTAT.MM-TS.0015 v2.0.0 | TS-M2M-0015 v2.0.0 | Y.4500.15: oneM2M – Testing framework
TS-0016 Secure Environment Abstraction | TS-0016 – Secure Environment Abstraction V 3.0.2
TS-0017 Implementation Conformance Statements
TS-0018 Test Suite Structure and Test Purposes
TS-0019 Abstract Test Suite & implementation eXtra Information for Test
TS-0020 WebSocket Protocol Binding | TS-0020 -– WebSocket Protocol Binding, V 3.0.1 |  | TS-0020 - WebSocket Protocol Binding, V2.0.2 |  |  |  |  | TS-M2M-0020v2.1.2 | TS 0020 - Websocket Protocol Binding, V2.0.0 | ATIS.oneM2M.TS0020V200-2016 | TS 118 120 V2.0.0 | TSDSI STD T1.oneM2M TS-0020-2.0.0 V1.0.0 | TTAT.MM-TS.0020 v2.0.0 | TS-M2M-0020 v2.0.0 | Y.4500.20: oneM2M – WebSocket protocol binding
TS-0021 oneM2M and AllJoyn Interworking |  |  | TS-0021 - oneM2M and AllJoyn Interworking, V2.0.1 |  |  |  |  | TS-M2M-0021v2.0.1 | TS 0021 - oneM2M and AllJoyn Interworking, V2.0.0 | ATIS.oneM2M.TS0021V200-2016 | TS 118 121 V2.0.0 | TSDSI STD T1.oneM2M TS-0021-2.0.0 V1.0.0 | TTAT.MM-TS.0021 v2.0.0 | TS-M2M-0021 v2.0.0
TS-0022 Field Device Configuration | TS-0022 -– Field Device Configuration-V 3.0.1 |  | TS-0022 - Field Device Configuration-V2.3.1 |  |  |  |  | TS-M2M-0022v2.3.1 | [6 empty] | Y.4500.22: oneM2M – Field device configuration
TS-0023 Home Appliances Information Model and Mapping (R2 & R3) TS-0023 SDT-based Information Model and Mapping for Vertical Industries (R4) | TS-0023 -– Home Appliances Information Model and Mapping, V 3.7.3 |  | TS-0023 - Home Appliances Information Model and Mapping, V2.0.2 |  |  |  |  | TS-M2M-0023v2.0.2 | TS 0023 - Home Appliances Information Model and Mapping, V2.0.0 | ATIS.oneM2M.TS0023V200-2016 | TS 118 123 V2.0.0 | TSDSI STD T1.oneM2M TS-0023-2.0.0 V1.0.0 | TTAT.MM-TS.0023 v2.0.0 | TS-M2M-0023 v2.0.0 | Y.4500.23: oneM2M – Home appliances information model and mapping
TS-0024 OCF Interworking | TS-0024 -– OCF Interworking, V 3.2.2 |  | TS-0024 - OIC Interworking, V2.0.2 |  |  |  |  | TS-M2M-0024v2.0.2 | TS 0024 - OIC Interworking, V2.0.0 | ATIS.oneM2M.TS0024V200-2016 | TS 118 124 V2.0.0 | TSDSI STD T1.oneM2M TS-0024-2.0.0 V1.0.0 | TTAT.MM-TS.0024 v2.0.0 | TS-M2M-0024 v2.0.0
TS-0025 Product Profiles |  |  | TS-0025 – Product Profiles, V2.0.0 |  |  |  |  | TS-M2M-0025v2.0.0
TS-0026 3GPP Interworking* | TS-0026 – 3GPP Interworking V3.0.0
TS-0027 Security Implementation Conformance Statements
TS-0028 Security Test Suite Structure and Test Purposes
TS-0029 Security Abstract Test Suite and Implementation eXtra Information for Test
TS-0030 Ontology based Interworking | TS-0030 – Ontology Based Interworking V 3.0.3
TS-0031 Feature Catalogue | TS-0031 -– Feature Catalogue V 3.0.0 |  | TS-0031 - Feature Catalouge, V2.0.0*
TS-0032 MAF and MEF Interface Specification | TS-0032 – MAF and MEF Interface Specification V 3.0.1 |  | TS-0032 – MAF and MEF Interface Specification-V2.1.0 |  |  |  |  | TS-M2M-0032v2.1.0
TS-0033 Interworking Framework | TS-0033 – Interworking Framework V 3.0.0
TS-0034 Semantics Support | TS-0034 – Semantics Support V 3.0.0
TS-0035 OSGi Interworking | TS-0035 – OSGi Interworking V 3.0.0
TS-0036 Advanced Vehicular Domain Enablement
Technical Reports | Technical Reports as defined in R2A control document ADM-0017 Release 3 Control Document V3.1.1 |  | Technical Reports as defined in R2A control document ADM-0012 Release 2A Control Document V2.1.0 | ATIS | ETSI | TSDSI | TTA | TTC | Technical Reports as defined in R2A control document ADM-0012 Release 2A Control Document V2.1.0 | ATIS | ETSI | TSDSI | TTA | TTC | published oneM2M specs as ITU-T are known as Y.4500.x series and can be consulted under this link: https://www.itu.int/rec/T-REC-Y/en |  | ATIS | ETSI | TSDSI | TTA | TTC | Technical Reports ratified later than @TP15.1 | ATIS | ETSI | TIA | TSDSI | TTA | TTC
TR-0001 Use Cases Collection | TR-0001 Use Cases Collection, V3.4.2 |  | TR-0001 Use Cases Collection, V2.4.2 |  |  |  |  | TR-M2M-0001v2.4.2 | TR 0001 - Use Cases Collection, V2.4.1 | ATIS.oneM2M.TR0001V241-2016 |  | TSDSI STD T1.oneM2M TR-0001-2.4.1 V1.0.0 | TTAT.MM-TR.0001 v2.4.1 | TR-M2M-0001v2.4.1 | [7 empty] | TR-0001 Use Cases Collection, V0.0.5 |  | TR 118 501 V1.0.0 |  |  | TTAT.MM-TR.0001 v0.0.5 | TR-M2M-0001 v0.0.5
TR-0002 Architecture Analysis - Part 1: Analysis of architectures proposed for consideration by oneM2M | [21 empty] | TR-0002 Architecture Analysis - Part 1: Analysis of architectures proposed for consideration by oneM2M, V0.2.0 |  | TR 118 502 V1.0.0 |  |  | TTAT.MM-TR.0002 v0.2.0 | TR-M2M-0002 v0.2.0
TR-0003 Architecture Analysis - Part 2: Study for the merging of architectures proposed for consideration by oneM2M | [21 empty] | TR-0003 Architecture Analysis - Part 2: Study for the merging of architectures proposed for consideration by oneM2M, V0.5.0 |  | TR 118 503 V1.0.0 |  |  | TTAT.MM-TR.0003 v0.5.0 | TR-M2M-0003 v0.5.0
TR-0006 Study of Management Capability Enablement Technologies for Consideration by oneM2M | [21 empty] | TR-0006 Study of Management Capability Enablement Technologies for Consideration by oneM2M, V0.5.1 |  | TR 118 506 V1.0.0 |  |  | TTAT.MM-TR.0006 v0.5.1 | TR-M2M-0006 v0.5.1
TR 0007 - Study of Abstraction and Semantics Enablements | [8 empty] | TR 0007 - Study of Abstraction and Semantics Enablements, V2.11.1 | ATIS.oneM2M.TR0007V2111-2016 |  | TSDSI STD T1.oneM2M TR-0007-2.11.1 V1.0.0 | TTAT.MM-TR.0007 2.11.1 | TR-M2M-0007 2.11.1 | [7 empty] | TR-0007 Study of Abstraction and Semantics Enablements, V1.0.0 |  |  |  |  | TTAT.MM-TR.0007 v1.0.0 | TR-M2M-0007 v1.0.0
TR-0008 Security |  |  | TR-0008 Security, V2.0.1 |  |  |  |  | TR-M2M-0008v2.0.1 | TR 0008 - Security, V2.0.0 | ATIS.oneM2M.TR0008V200-2016 |  | TSDSI STD T1.oneM2M TR-0008-2.0.0 V1.0.0 | TTAT.MM-TR.0008 v2.0.0 | TR-M2M-0008 v2.0.0 | [7 empty] | TR-0008 Analysis of Security Solutions for the oneM2M System, V1.0.0 |  | TR 118 508 V1.0.0 |  |  | TTAT.MM-TR.0008 v1.0.0 | TR-M2M-0008 v1.0.0
TR-0009 Protocol Analysis | [21 empty] | TR-0009 Protocol Analysis, V0.7.0 |  |  |  |  | TTAT.MM-TR.0009 v0.7.0 | TR-M2M-0009 v0.7.0
TR 0012 - oneM2M End-to-End Security and Group Authentication, V2.0.0 | [8 empty] | TR 0012 - oneM2M End-to-End Security and Group Authentication, V2.0.0 | ATIS.oneM2M.TR0012V200-2016 | TR 118 512 V2.0.0 | TSDSI STD T1.oneM2M TR-0012-2.0.0 V1.0.0 | TTAT.MM-TR.0012 v2.0.0 | TR-M2M-0012 v2.0.0
TR 0016 - Study of Authorization Architecture for Supporting Heterogeneous Access Control Policies | [8 empty] | TR 0016 - Study of Authorization Architecture for Supporting Heterogeneous Access Control Policies, V2.0.0 | ATIS.oneM2M.TR0016V200-2016 | TR 118 516 V2.0.0 | TSDSI STD T1.oneM2M TR-0016-2.0.0 V1.0.0 | TTAT.MM-TR.0016 v2.0.0 | TR-M2M-0016 v2.0.0
TR 0017 - Home Domain Abstract Information Model | [8 empty] | TR 0017 - Home Domain Abstract Information Model, V2.0.0 | ATIS.oneM2M.TR0017V200-2016 | TR 118 517 V2.0.0 | TSDSI STD T1.oneM2M TR-0017-2.0.0 V1.0.0 | TTAT.MM-TR.0017 v2.0.0 | TR-M2M-0017 v2.0.0
TR-0018 Industrial Domain Enablement |  |  | TR-0018 Industrial Domain Enablement, V2.5.2 |  |  |  |  | TR-M2M-0018v2.5.2 | TR 0018 - Industrial Domain Enablement, V2.0.0 | ATIS.oneM2M.TR0018V200-2016 | TR 118 518 V2.0.0 | TSDSI STD T1.oneM2M TR-0018-2.0.0 V1.0.0 |  | TR-M2M-0018v2.0.0
TR 0019 - Dynamic Authorization for IoT | [8 empty] | TR 0019 - Dynamic Authorization for IoT, V2.0.0 | ATIS.oneM2M.TR0019V200-2016 |  | TSDSI STD T1.oneM2M TR-0019-2.0.0 V1.0.0
TR 0022 - Continuation & integration of HGI Smart Home activities | [8 empty] | TR 0022 - Continuation & integration of HGI Smart Home activities, V2.0.0 | ATIS.oneM2M.TR0022V200-2016 | TR 518 522 V2.0.0 | TSDSI STD T1.oneM2M TR-0022-2.0.0 V1.0.0 | TTAT.MM-TR.0022 v2.0.0 | TR-M2M-0022 v2.0.0
TR-0025 Application developer guide |  |  | TR-0025 Application developer guide, V2.0.2 |  |  |  |  | TR-M2M-0025v2.0.2 | [7 empty] | TR-0025 - Application Developer Guide, V1.0.0 |  | TR 118 525 V1.0.0 |  | TTAT.MM-TR.0025 v1.0.0 | TR-M2M-0025v1.0.0
TR-0026 Vehicular Domain Enablement | TR-0026 Vehicular Domain Enablement, V 3.0.1
TR-0033 Study on Enhanced Semantic Enablement | TR-0033 Study on Enhanced Semantic Enablement, V 3.0.0
TR-0034 CoAP binding and long polling for temperature monitoring |  |  | TR-0034 CoAP binding and long polling for temperature monitoring, V2.0.0 |  |  |  |  | TR-M2M-0034v2.0.0
TR-0035 Device management use case |  |  | TR-0035 Device management use case, V2.0.0 |  |  |  |  | TR-M2M-0035v2.0.0
TR-0037 Smart farm example using MQTT binding |  |  | TR-0037 Smart farm example using MQTT binding, V2.0.0 |  |  |  |  | TR-M2M-0037v2.0.0
TR-0039 Developer guide-SDT-based implementation |  |  | TR-0039 Developer guide-SDT-based implementation, V2.0.0 |  |  |  |  | TR-M2M-0039v2.0.0
TR-0045 Implementing semantics |  |  | TR-0045 Implementing semantics, V2.0.0 |  |  |  |  | TR-M2M-0045v2.0.0

## History
History of Change
V0.0.0 | 2013-08-05 | First draft of new Work Programme Report
V0.1.0 | 2013-08-08 | Incorporation of Raporteur updates
V7.0.0 | 2013-10-18 | First draft of administrative perm document "oneM2M-ADM-0001-oneM2M_Work_Programme-V7_00_00"
V8.0.0 | 2013-12-12 | Input to TP#8 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - register ADM Text Part adapted to official ADM template (oneM2M-Template-ADM-20131008.doc)
V9.0.0 | 2014-02-21 | Input to TP#9 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0005R01 into register ADM Text Part
V10.0.0 | 2014-04-11 | Input to TP#10 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - conversion TR-0004 into TS-0011 according to CR TP-2014-0028 - update target dates for TS-0003 according to CR TP-2014-0029R1 - update target dates for TS-0007 according to CR TP-2014-0408 - update target dates for TR-0009 according to CR TP-2014-0417
V11.0.0 |  | Input to TP#11 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0008R01 into register ADM Text Part- update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E
V12.0.0 | 2014-08-01 | Input to TP#12 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - approved deliverables deleted from tracking registers B, C, D, E - new WI16 (TR 0012) incorporated
V17.0.0 | 2015-06-04 | Input post TP#17 : - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V17.1.0 | 2015-07-15 | Input prior TP18: - new register: R2 timeline - register WIs: added column level of completeness as of TP17
V18.0.0 | 2015-07-24 | Input TP#18 : - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated - added Annex F WI Progress and new Register Progress
V18.1.0 | 2015-08-20 | progress update for WI-0033 and update of TR and TS list
V19.0.0 | 2015-09-11 | Input TP#19 : - update with latest WI status including added column supporting companies - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated - added Annex G: Progress Testing
V19.1.0 | 2015-10-14 | update of WIs with recently uploaded TRs and TSs
V19.2.0 | 2015-10-22 | update of WIs and TRs/TSs list with recently uploaded TRs and TSs
V19.3.0 | 2015-11-02 | update of TR and TS list
V20.0.0 | 2015-11-13 | Input TP#20: - updated with latest WI status including progress and timeline
V20.1.0 | 2015-12-14 | update of TR and TS list with latest versions, as well as WI-0046 with TR number
V21.0.0 | 2016-01-22 | Input TP#21: - updated with latest WI status including progress
V21.1.0 | 2016-03-11 | update of TR and TS list with latest versions. Update WI-0017
V22.0.0 | 2016-04-08 | Input TP#22: - updated with latest WI status including progress
V22.1.0 | 2016-04-27 | updated WI scheules according to latest approved changes
V23.0.0 | 2016-05-22 | Input TP#23 : - update with latest WI status including closure of WI-0001 - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V23.1.0 | 2016-06-08 | update of TR and TS list with latest versions
V24.0.0 | 2016-07-22 | Input TP#24 : - update with latest WI status - updated the registers (new register: Association of Work Tracks and WIs) - new WIs incorporated
V24.1.0 | 2016-10-05 | Input TP#24.1 : - update with latest WI status - updated TR and TS lists
V24.2.0 | 2016-10-11 | added TS-0030 and corrections to Work Track and Work Item association
V25.0.0 | 2016-10-21 | Input TP#24.1 : - update with latest WI status - updated TR and TS lists - re-arranged document - active and closed Wis are listed in dedicated registers
V25.1.0 | 2016-11-23 | update of TR and TS lists
V25.2.0 | 2016-11-23 | change of rapporteur from Jessie to Xubei (Echo) - both Huawei
V25.3.0 | 2016-11-29 | updated TR and TS lists - correction of rapporteurs
V26.0.0 | 2016-12-09 | Input TP#26: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V26.1.0 | 2017-01-19 | updated the registers : Wis, TSs, TRs,
V26.2.0 | 2017-02-07 | updated the register TSs - adjusted company affiliation for rapporteurs
V27.0.0 | 2017-02-17 | Input TP#27: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs - new WIs incorporated
V27.1.0 | 2017-02-28 | update with latest WI status updated the registers Actice WI. TS, TR, ADM
V27.2.0 | 2017-03-17 | update with latest WI status, clarified table showing TS release versions and added rapporteurs updated the registers Actice WI, TS, TR,ADM
V27.3.0 | 2017-03-23 | updated the registers Actice WI, TS, TR,ADM
V27.4.0 | 2017-03-24 | updated the registers Actice WI, TS, TR,ADM
V28.0.0 | 2017-03-31 | Input TP#28: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs
V28.1.0 | 2017-05-09 | update with latest WI status updated the registers new WIs, TSs, TRs, ADMs
V28.2.0 | 2017-05-12 | update with latest WI status updated the registers new WIs, TSs, TRs, ADMs
V29.0.0 | 2017-06-08 | Input TP#29: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs
V29.1.0 | 2017-06-27 | updated with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V29.2.0 | 2017-07-03 | updated with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V29.3.0 | 2017-07-06 | updated with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V30.0.0 | 2017-07-20 | Input TP#30: - update with latest WI status - 2 new WIs and WI updates for WI-46, WI-56, WI-66 - updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V30.1.0 | 2017-09-04 | update with latest WI status updated the registers new: TSs, TRs, ADMs
V30.2.0 | 2017-09-12 | update with latest WI status updated the registers new: TSs, TRs, ADMs
V31.0.0 | 2017-09-22 | Input TP#31: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V31.1.0 | 2017-11-02 | update with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V31.2.0 | 2017-11-06 | update with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V32.0.0 | 2017-11-28 | Input TP#32: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V32.2.0 | 2018-01-09 | update with latest WI status updated the registers new: Wis, TSs, TRs, ADMs
V33.0.0 | 2018-01-24 | Input TP#33: - update with latest WI status - updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V33.1.0 | 2018-03-08 | update with latest WI status; Release 2A deliverables for ratification. updated the registers new: Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V34.0.0 | 2018-03-23 | Input TP#34: - update with latest WI status - updated the registers :active Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V34.1.0 | 2018-05-08 | update with latest WI status updated the registers :active Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V34.2.0 | 2018-05-09 | update with latest WI status updated the registers :active Wis, TSs, TRs, ADMs,
V35.0.0 | 2018-05-25 | Input TP#35: - update with latest WI status - updated the registers :active Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing..
V36.0.0 | 2018-07-24 | Input TP#36: - update with latest WI status - updated the registers :active Wis, TSs, TRs, ADMs, added release ratifications and corresponding transpositions to partner type 1 and ITU-T, Timeline, Progress, Progress testing..
V36.1.0 | 2018-08-16 | update with latest WI status updated the registers :active Wis, TSs, TRs, ADMs, added release ratifications and corresponding transpositions to partner type 1 and ITU-T, Timeline, Progress, Progress testing.
V36.2.0 | 2018-08-28 | update with latest WI status updated the registers : active Wis, TSs, TRs, ADMs.
V36.4.0 | 2018-09-10 | update with latest WI status updated the registers : active Wis, TSs, TRs, ADMs.
V37.0.0 | 2018-10-08 | Input TP#37: - update with latest WI status - updated the registers :active Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing. Added new register for ratified releases and transpositions of TSs and TRs. Removed registers
V37.1.0 | 2018-11-15 | update with latest WI status updated the registers : active Wis, TSs, TRs, ADMs.
V37.2.0 | 2018-12-02 | update with latest WI status updated the registers : active Wis, TSs, TRs, ADMs.
V38.0.0 | 2018-12-08 | Input TP#38: - update with latest WI status - updated the registers :active Wis, TSs, TRs, ADMs, Timeline, Progress, Progress testing. Added new register for ratified releases and transpositions of TSs and TRs. Removed registers
V38.1.0 | 2019-01-15 | update with latest WI status updated the registers : active Wis, TSs, TRs, ADMs.
V38.2.0 | 2019-02-15 | update with latest WI status updated the registers : active Wis, TSs, TRs, ADMs.
V39.0.0 | 2019-05-05 | update with latest WI status after TP#39 updated the registers : active Wis, TSs, TRs, ADMs. Update the cover sheet Merge sheets: "Progress" & "Progress Testing" as "WI Progress", additional columns for reporting WG, target release, status; automated color code, Merge Sheets: "Active WIs" & "Closed WIs" into "WIs", and remove column "% completion" Update release timeline
V40.0.0 | 2019-05-24 | update with latest WI status after TP#40 updated the registers : active Wis, Update the cover sheet, "release timeline" Hide sheets: "TR", "TS", "Transpotation" which are maintained online now.
V41.0.0 | 2019-07-12 | update with latest WI status after TP#41
V42.0.0 | 2019-09-27 | update with latest WI status after TP#42
V42.0.1 | 2019-10-08 | fix bugs of the spreadsheet
V43.0.0 | 2019-12-06 | update with latest WI status after TP#43
V44.0.0 | 2020-04-21 | update with latest WI status after TP 44
V48.0.0 | 2021-01-29 | update with the WI status after TP48 incl updates of TP45,TP46 and TP47; removed dashboard.
V49.2.0 | 2021-02-09 | update with the WI status after TP49
V50.0.0 | 2021-05-10 | update with the WI status after TP49
V50.1.0 | 2021-06-03 | update with the WI status after TP50
V50.1.1 | 2021-06-03 | fix editorials of the spreadsheet
V50.1.2 | 2021-06-03 | fix editorials of the spreadsheet
V51.0.0 | 2021-08-30 | update with the WI status after TP51
V52.0.0 | 2021-11-29 | Input the WI status for TP52
V52.0.0 | 2022-02-18 | Input the WI status for TP53