## ADM Text Part
Administrative Document
oneM2M-ADM-0001-V-11.0.0
Working Title: oneM2M Work Programme
2014-06-13
Copyright Notification
No part may be reproduced except as authorized by written permission.
The copyright and the foregoing restriction extend to reproduction in all media.
This document is intended for distribution only to oneM2M Participants.
© oneM2M Partners Type 1 (ARIB, ATIS, CCSA, ETSI, TIA, TTA, TTC)
Contents
1 Scope ……………………………………………………………….……………………….Page 3
2 References …………………………………………………………..…………...………….Page 3
2.1 Normative References …………………………………………………….………………...………….Page 3
2.2 Informative References ………………………………………………………...…………...………….Page 3
3 Definitions, symbols, abbreviations and acronyms ………………………….…..………….Page 3
3.1 Definitions …………………………….…………………………………………………….....……….Page 3
3.2 Symbols …………………………….………………………………………………………….……….Page 3
3.3 Abbreviations, acronyms……………………………………………………………….…………….Page 3
4 Conventions …………………………………………………………………..…………….Page 3
5 oneM2M Work Programme ……………………..…………………………..…………….Page 3
Annex A: Work Programme Overview …….…………………………….……………….…..Register B
Annex B: Charts …………………………………………..………………………...…….…..Register C
Annex C: Form for updating planning …….………………………………...…………….…..Register D
Annex D: Calculations of data ………………...………………….…………………….….....Register E
Annex E: Approved deliverables ………………..……………….……………….……….…..Register F
History of Change …………………………………………………….……….……………..Register A
1 Scope
The present document is the “oneM2M Work Programme” referred to in Articles 31 in the Working Procedures Document [1], and addresses the Work Item reporting process within the Technical Plenary, its subordinate groups and the Secretariat to accomplish the tasks extracted from Article 12. In addition, the present document addresses processes to accomplish tasks not specifically identified in the Working Procedures Document but considered essential to the efficient operation of the Technical Plenary.
2 References
2.1 Normative References
The following standards contain provisions, which, through reference in this text, constitute provisions of the present document. At the time of publication, the versions indicated were valid. All standards are subject to revision, and parties to agreements based on the present document are encouraged to investigate the possibility of applying the most recent editions of the standards indicated below. References are either non specific or specific (identified by date of publication, edition, version, etc.) or non specific. For a non specific reference, the latest version applies. For a specific reference, subsequent revisions do not apply. [1] oneM2M Partnership Agreement [2] oneM2M Working Procedures Document [3] Drafting Rules
2.2 Informative References
The following referenced documents are not necessary for the application of the present document but they assist the user with regard to a particular subject area.
[i.1] oneM2M Drafting Rules (http://member.onem2m.org/Static_pages/Others/Rules_Pages/oneM2M-Drafting-Rules-V1_0.doc)
3 Definitions, symbols, abbriviations and accronyms
For the present document the following apply:
3.1 Definitions
Approval means the decision of the Technical Plenary that a deliverable is ready for getting ratified in order to publish it (see process description in [2]).
Change Control means the decision of a Working Group that the content of a draft deliverable is sufficiently advanced that it will utilize the Change Control process (see process description in [2]).
Drafting means the editorial phase of a deliverable until it is placed under Change Control (see process description in [2]).
Forecast means the date estimation (best guess) for the required milestones of a deliverable based on the current state of it taking into account the level of completeness, risks and uncertainties
Freeze means the decision of a Working Group that the technical content of a draft deliverable is complete (given consideration of the Work Item scope and workplan), and it is frozen for further technical input (see process description in [2])
Level of completeness means the estimation of how much of a deliverable has been already drafted in relation to the expected total amount being necessary for the approval
Milestone dates means dates for the main process corner stones of a deliverable specified in the respective Work Item documents (see process description in [2])
Start means the beginning of drafting a deliverable
Target means a requested date for a deliverable which is specified in the respective Work Item document for all its main milestones
TP#n-1 means the last Technical Plenary meeting before the current one. The current one is the basis for an update of the Work Programme.
3.2 Symbols
none
3.3 Abbreviations, acronyms
ARC Architecture
Doc_ID Document Identifier
MAS Management, Abstraction and Semantics
REQ Requirements
SEC Security
TP Technical Plenary
TS Technical Specification
WI Work Item
WG Working Group
4 Conventions
Work Programme updates
Annex C - Form for updating planning (Register D) - serves for updating forecasts of milestone dates and level of completeness by the respective rapporteurs of the deliverables. For this purpose only the green marked entry cells are used. The dates in the target columns are taken from the actual revisions of the approved respective Work Item documents.
Scaling of level of completeness
• Value range from 0% - 100%, no special scaling requested. Highest level achievable in a WG is 95%
• Measurement will be against milestone “Approval” listed in the agreed respective Work Item (meaning that 100% completeness must be achieved for reaching this milestone)
• Expected levels of completeness at milestones:
Start - 0%
First draft / skeleton - 10%
Freeze - 90%
WG decision: “ready for approval” - 95%
(shall be achieved for the deliverable being presented to Technical Plenary for approval, rest of 5 % is considered as remaining editorial effort for producing the final revision, which is candidate for TP ratification, candidate for getting published by the Partners Type 1)
Approval (by TP) - 100%
5 oneM2M Work Programme

## A-History of Change
History of Change
V0.0.0 | 2013-08-05 | First draft of new Work Programme Report
V0.1.0 | 2013-08-08 | Incorporation of Raporteur updates
V7.0.0 | 2013-10-18 | First draft of administrative perm document "oneM2M-ADM-0001-oneM2M_Work_Programme-V7_00_00"
V8.0.0 | 2013-12-12 | Input to TP#8 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - register ADM Text Part adapted to official ADM template (oneM2M-Template-ADM-20131008.doc)
V9.0.0 | 2014-02-21 | Input to TP#9 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0005R01 into register ADM Text Part
V10.0.0 | 2014-04-11 | Input to TP#10 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - conversion TR-0004 into TS-0011 according to CR TP-2014-0028 - update target dates for TS-0003 according to CR TP-2014-0029R1 - update target dates for TS-0007 according to CR TP-2014-0408 - update target dates for TR-0009 according to CR TP-2014-0417
V11.0.0 | 2014-06-13 | Input to TP#11 closing session: - update of register "D-Entry Form" based on Rapporteurs' forecasts - incorporation of TP_WPM-2014-0008R01 into register ADM Text Part- update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E

## B-WP Overview
|  |  |  | one M2M Work Programme Status: | 2014-06-13 (closing of TP11)
Work Item number | Primary responsible | Doc Type | Doc number | Title | Rapporteur | Milestone dates | [6 empty] | Level of completeness
[6 empty] | Start | Change Control |  | Freeze |  | Approval
[7 empty] | Target | Forecast | Target | Forecast | Target | Forecast
[6 empty] | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date
WI0002 |  |  |  | oneM2M Architecture
| WG2 - ARC | TS | TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 3 | 8 | 9 | 8 | 9 | 10 | 11 | 95%
[6 empty] | 2013-01-23 | 2013-12-09 | 2014-02-17 | 2013-12-09 | 2014-02-17 | 2014-04-07 | 2014-06-09
WI0003 |  |  |  | Vocabulary, Roles and Focus Areas for oneM2M Technical Work
| WG1 - REQ | TR | TS-0011(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 90%
[6 empty] | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
| WG1 - REQ | TR | TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2 | 3 | 4 | 11 | 12 | 12 | 13 | 35%
[6 empty] | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-09-22
WI0005 |  |  |  | oneM2M Abstraction and Semantics Capability Enablement
| WG5 -MAS | TR | TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 3 | 11 | 11 | 11 | 12 | 12 | 12 | 80%
[6 empty] | 2013-01-23 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28
WI0006 |  |  |  | oneM2M Device/Gateway Classification
| WG2 - ARC | TR | TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 8 | 10 | 13 | 11 | 14 | 12 | 15 | 0%
[6 empty] | 2013-12-09 | 2014-04-07 | 2014-09-22 | 2014-06-09 | 2014-11-10 | 2014-07-28 | 2015-01-19
WI0007 |  |  |  | OneM2M Security Preliminary Investigations
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WG4 - SEC | TS | TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 6 | 11 | 11 | 11 | 11 | 12 | 12 | 90%
[6 empty] | 2013-08-05 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0008 |  |  |  | OneM2M Protocol Development
| WG3 - PRO | TR | TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 5 | 9 | 9 | 9 | 9 | 11 | 11 | 95%
[6 empty] | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-06-09 | 2014-06-09
WI0009 |  |  |  | Protocol Analysis
| WG3 - PRO | TS | TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 5 | 11 | 12 | 11 | 12 | 12 | 12 | 45%
[6 empty] | 2013-06-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28
WI0010 |  |  |  | Management enablement
| WG5 -MAS | TS | TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 60%
[6 empty] | 2013-12-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28
| WG5 -MAS | TS | TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 70%
[6 empty] | 2013-12-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28
WI0011 |  |  |  | Service Component Architecture V1.0
| WG2 -ARC | TS | TS-0007(WG2) | oneM2M Service Components | Tim Carey, Alcatel Lucent | 9 | 15 | 15 | 15 | 15 | 17 | 17 | 25%
[6 empty] | 2014-02-17 | 2015-01-19 | 2015-01-19 | 2015-01-19 | 2015-01-19 | 2015-05-18 | 2015-05-18
WI0012 |  |  |  | Developing RESTful CoAP Protocol Binding
| WG3 -PRO | TS | TS-0008(WG3) | CoAP Protocol Binding Technical Specification | SeongYoon KIM, LG Electronics | 9 | 11 | 12 | 11 | 12 | 12 | 12 | 25%
[6 empty] | 2014-02-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28
WI0013 |  |  |  | Developing RESTful HTTP Protocol Binding
| WG3 -PRO | TS | TS-0009(WG3) | HTTP Protocol Binding Technical Specification | SeungMyeong Jeong, LG Electronics | 9 | 11 | 12 | 11 | 12 | 12 | 12 | 40%
[6 empty] | 2014-02-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28
WI0014 |  |  |  | Developing MQTT Protocol Binding
| WG3 -PRO | TS | TS-0010(WG3) | MQTT Protocol Binding Technical Specification | Peter Niblett, IBM | 9 | 11 | 12 | 11 | 12 | 12 | 12 | 45%
[6 empty] | 2014-02-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28
| WG3 -PRO | TR | TR-0011(WG2) | MQTT Protocol Interworking Study | Peter Niblett, IBM | 9 | 11 | 12 | 11 | 12 | 12 | 13 | 0%
[6 empty] | 2014-02-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-09-22
WI0015 |  |  |  | oneM2M Use Case Continuation
| WG1 -REQ | TR | TR-0001V2(WG1) | Use Case | Phil Jacobs, Cisco | 8 | 8 | 8 | 15 | 0 | 0 | 0 | 0%
[6 empty] | 2013-12-09 | 2013-12-09 | 2013-12-09 | 2015-01-19
Note on J7: Same as freezing 1st release of TS on requirements and architecture (probably TP #6)

## C-Charts
V1.0.0 TP#12
TP#11
V1.1.0 TP#15

## D-Entry Form
| one M2M Work Programme Status: | 2014-06-13 (closing of TP11)
Doc_ID | Title | Rapporteur | Milestone dates | [6 empty] | Level of completeness
|  |  | Start | Change Control |  | Freeze |  | Approval
|  |  |  | Target | Forecast | Target | Forecast | Target | Forecast
| Requirements | WG1 - REQ | TP# | TP# | TP# | TP# | TP# | TP# | TP#
TR-0001V2(WG1) | Use Case | Phil Jacobs, Cisco | 8 | 8 | 8 | 15
TS-0011(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 90%
TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2 | 3 | 4 | 11 | 12 | 12 | 13 | 35%
| Architecture | WG2 - ARC
TS-0007(WG2) | oneM2M Service Components | Tim Carey, Alcatel Lucent | 9 | 15 | 15 | 15 | 15 | 17 | 17 | 25%
TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 8 | 10 | 13 | 11 | 14 | 12 | 15 | 0%
TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 3 | 8 | 9 | 8 | 9 | 10 | 11 | 95%
TR-0011(WG2) | MQTT Protocol Interworking Study | Peter Niblett, IBM | 9 | 11 | 12 | 11 | 12 | 12 | 13 | 0%
| Protocols | WG3 - PRO
TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 5 | 9 | 9 | 9 | 9 | 11 | 11 | 95%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 5 | 11 | 12 | 11 | 12 | 12 | 12 | 45%
TS-0008(WG3) | CoAP Protocol Binding Technical Specification | SeongYoon KIM, LG Electronics | 9 | 11 | 12 | 11 | 12 | 12 | 12 | 25%
TS-0009(WG3) | HTTP Protocol Binding Technical Specification | SeungMyeong Jeong, LG Electronics | 9 | 11 | 12 | 11 | 12 | 12 | 12 | 40%
TS-0010(WG3) | MQTT Protocol Binding Technical Specification | Peter Niblett, IBM | 9 | 11 | 12 | 11 | 12 | 12 | 12 | 45%
| Security | WG4 - SEC
TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 6 | 11 | 11 | 11 | 11 | 12 | 12 | 90%
| Management, Abstraction and Semantics | WG5 - MAS
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 3 | 11 | 11 | 11 | 12 | 12 | 12 | 80%
TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 60%
TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 70%
Note on D13: Drafting start after TS-0001 Change Control
Note on E28: The TR should be put under change control and frozen one meeting before the last TP meeting of the oneM2M release
Note on G28: The TR should be put under change control and frozen one meeting before the last TP meeting of the oneM2M release
Note on I28: The TR should be approved at the last TP meeting of the oneM2M release

## E-Calculations
Do not delete this block structure
TP meeting dates
TP#1 | 2012-09-24
TP#2 | 2012-12-10
TP#3 | 2013-01-23
TP#4 | 2013-04-15
TP#5 | 2013-06-17
TP#6 | 2013-08-05
TP#7 | 2013-10-14
TP#8 | 2013-12-09
TP#9 | 2014-02-17
TP#10 | 2014-04-07
TP#11 | 2014-06-09
TP#12 | 2014-07-28
TP#13 | 2014-09-22
TP#14 | 2014-11-10
TP#15 | 2015-01-19
TP#16 | 2015-03-16
TP#17 | 2015-05-18
TP#18 | 2015-07-20
TP#19 | 2015-09-07
TP#20 | 2015-11-16
Do not delete this block structure
The following table is the 1:1 copy of the Entry-Form, it converts TP numbers into date format (yyyy-mm-dd) and additionally (manually) stores level of completeness of the last 2 reportings
0 | one M2M Work Programme Status: | 2014-06-13 (closing of TP11) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Doc_ID | Title | Rapporteur | Milestone dates | 0 | 0 | 0 | 0 | 0 | 0 | Level of completeness | Level of completeness (TP#n-1) | Level of completeness (TP#n-2)
0 | 0 | 0 | Start | Change Control | 0 | Freeze | 0 | Approval | 0 | 0
0 | 0 | 0 | 0 | Target | Forecast | Target | Forecast | Target | Forecast | 0
0 | Requirements | WG1 - REQ | TP# | TP# | TP# | TP# | TP# | TP# | TP# | 0
TR-0001V2(WG1) | Use Case | Phil Jacobs, Cisco | 2013-12-09 | 2013-12-09 | 2013-12-09 | 2015-01-19 | 0 | 0 | 0 | 0% | 0% | 0%
TS-0011(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 90% | 50% | 45%
TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-09-22 | 35% | 35% | 35%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
0 | Architecture | WG2 - ARC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TS-0007(WG2) | oneM2M Service Components | Tim Carey, Alcatel Lucent | 2014-02-17 | 2015-01-19 | 2015-01-19 | 2015-01-19 | 2015-01-19 | 2015-05-18 | 2015-05-18 | 25% | 15% | 10%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 2013-12-09 | 2014-04-07 | 2014-09-22 | 2014-06-09 | 2014-11-10 | 2014-07-28 | 2015-01-19 | 0% | 0% | 0%
TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 2013-01-23 | 2013-12-09 | 2014-02-17 | 2013-12-09 | 2014-02-17 | 2014-04-07 | 2014-06-09 | 95% | 90% | 90%
TR-0011(WG2) | MQTT Protocol Interworking Study | Peter Niblett, IBM | 2014-02-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-09-22 | 0% | 0% | 0%
0 | Protocols | WG3 - PRO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-06-09 | 2014-06-09 | 95% | 90% | 60%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 2013-06-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 45% | 35% | 20%
TS-0008(WG3) | CoAP Protocol Binding Technical Specification | SeongYoon KIM, LG Electronics | 2014-02-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 25% | 20% | 10%
TS-0009(WG3) | HTTP Protocol Binding Technical Specification | SeungMyeong Jeong, LG Electronics | 2014-02-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 40% | 25% | 10%
TS-0010(WG3) | MQTT Protocol Binding Technical Specification | Peter Niblett, IBM | 2014-02-17 | 2014-06-09 | 2014-07-28 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 45% | 35% | 30%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
0 | Security | WG4 - SEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 2013-08-05 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 90% | 60% | 35%
0 | Management, Abstraction and Semantics | WG5 - MAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 2013-01-23 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 80% | 60% | 50%
TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 2013-12-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 60% | 40% | 10%
TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 2013-12-09 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 2014-07-28 | 70% | 40% | 10%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
The following table prepares the Gant Chart and the chart for deliverable completeness based on the table above. It contains only formulars for calculation.
Exception: columns for Level of completenes history (TP#n-1, TP#n-2) have to be updated manually for each new update of Work Programme
Grouping (level 1) shows only deliverables allocated to the Initial Release, also in the charts
Doc ID | Title | Doc ID | Start | Drafting | Delay | Change Control | Delay | Freeze | Delay | Level of completeness (actual) | Level of completeness (TP#n-1) | Level of completeness (TP#n-2)
Requirements |  | Requirements
TR-0001V2(WG1) | Use Case | TR-0001V2(WG1) | 2013-12-09 | 0 | 0 | 406 | 0 | 0 | 0 | 0% | 0% | 0%
TS-0011(WG1) | Definition and Acronyms | TS-0011(WG1) | 2012-12-10 | 44 | 82 | 420 | 0 | 49 | 0 | 90% | 50% | 45%
TR-0005(WG1) | Roles and Focus Areas | TR-0005(WG1) | 2012-12-10 | 44 | 82 | 420 | 49 | 0 | 56 | 35% | 35% | 35%
| 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Architecture |  | Architecture
TS-0007(WG2) | oneM2M Service Components | TS-0007(WG2) | 2014-02-17 | 336 | 0 | 0 | 0 | 119 | 0 | 25% | 15% | 10%
| 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TR-0010(WG2) | oneM2M Device/Gateway Classification | TR-0010(WG2) | 2013-12-09 | 119 | 168 | 0 | 49 | 0 | 70 | 0% | 0% | 0%
TS-0001(WG2) | oneM2M Functional Architecture | TS-0001(WG2) | 2013-01-23 | 320 | 70 | 0 | 0 | 49 | 63 | 95% | 90% | 90%
TR-0011(WG2) | MQTT Protocol Interworking Study | TR-0011(WG2) | 2014-02-17 | 112 | 49 | 0 | 0 | 0 | 56 | 0% | 0% | 0%
Protocols |  | Protocols
TR-0009(WG3) | one M2M Protocol Analysis | TR-0009(WG3) | 2013-06-17 | 245 | 0 | 0 | 0 | 112 | 0 | 95% | 90% | 60%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | TS-0004(WG3) | 2013-06-17 | 357 | 49 | 0 | 0 | 0 | 0 | 45% | 35% | 20%
TS-0008(WG3) | CoAP Protocol Binding Technical Specification | TS-0008(WG3) | 2014-02-17 | 112 | 49 | 0 | 0 | 0 | 0 | 25% | 20% | 10%
TS-0009(WG3) | HTTP Protocol Binding Technical Specification | TS-0009(WG3) | 2014-02-17 | 112 | 49 | 0 | 0 | 0 | 0 | 40% | 25% | 10%
TS-0010(WG3) | MQTT Protocol Binding Technical Specification | TS-0010(WG3) | 2014-02-17 | 112 | 49 | 0 | 0 | 0 | 0 | 45% | 35% | 30%
| 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
Security |  | Security
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TS-0003(WG4) | One M2M Security solutions | TS-0003(WG4) | 2013-08-05 | 308 | 0 | 0 | 0 | 49 | 0 | 90% | 60% | 35%
Management, Abstraction and Semantics |  | Management, Abstraction and Semantics
| 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | TR-0007(WG5) | 2013-01-23 | 502 | 0 | 0 | 49 | 0 | 0 | 80% | 60% | 50%
TS-0005(WG5) | Management enablement (OMA) | TS-0005(WG5) | 2013-12-09 | 231 | 0 | 0 | 0 | 0 | 0 | 60% | 40% | 10%
TS-0006(WG5) | Management enablement (BBF) | TS-0006(WG5) | 2013-12-09 | 231 | 0 | 0 | 0 | 0 | 0 | 70% | 40% | 10%
Axis options
| Minimum: 41160 | 41400
| Maximum: 42000 | 42240
Main interval: 120
Assisting interval: 30

## F-Approved Deliverables
Name | Version | Work Item | TP approval date | Forwarded to SC for publication
oneM2M-TR-0002-Architecture_Analysis_Part_1 | V-0.2.0 | WI0002 | 2013-08-05 | 2013-10-14
oneM2M-TR-0003-Architecture_Analysis_Part_2 | V-0.5.0 | WI0002 | 2013-08-05 | 2013-10-14
oneM2M-TS-0002-Requirements | V0.6.2 | WI0001 | 2013-10-17 | 2013-11-22
oneM2M-TR-0001-Use Case | V0.0.5 | WI0001 | 2013-10-17 | 2013-11-22
oneM2M-TR-0006-Study of Management Capability Enablement | V0.5.1 | WI0004 | 2013-12-13 | 2013-12-17
oneM2M-TR-0008-Analysis of security solutions for oneM2M system | V1.0.0 | WI0007 | 2014-04-11 | 2014-06-02