## ADM Text Part
Administrative Document
oneM2M-ADM-0001-V-8.0.0
Working Title: oneM2M Work Programme
13 December 2013
Copyright Notification
No part may be reproduced except as authorized by written permission.
The copyright and the foregoing restriction extend to reproduction in all media.
This document is intended for distribution only to oneM2M Participants.
© oneM2M Partners Type 1 (ARIB, ATIS, CCSA, ETSI, TIA, TTA, TTC)
Contents
1 Scope ……………………………………………………………….……………………….Page 3
2 References …………………………………………………………..…………...………….Page 3
2.1 Normative References …………………………………………………….………………...………….Page 3
2.2 Informative References ………………………………………………………...…………...………….Page 3
3 Definitions, symbols, abbreviations and acronyms ………………………….…..………….Page 3
3.1 Definitions …………………………….…………………………………………………….....……….Page 3
3.2 Symbols …………………………….………………………………………………………….……….Page 3
3.3 Abbreviations …………………………………………………………………………….…………….Page 3
3.4 Acronyms ………………………………………………………………………………..…………….Page 3
4 Conventions …………………………………………………………………..…………….Page 3
5 oneM2M Work Programme ……………………..…………………………..…………….Page 3
Annex A: Work Programme Overview …….…………………………….……………….…..Register B
Annex B: Charts …………………………………………..………………………...…….…..Register C
Annex C: Form for updating planning …….………………………………...…………….…..Register D
Annex D: Calculations of data ………………...………………….…………………….….....Register E
Annex E: Approved deliverables ………………..……………….……………….……….…..Register F
History of Change …………………………………………………….……….……………..Register A
1 Scope
The present document provides …
2 References
References are either specific (identified by date of publication and/or edition number or version number) or non specific. For specific references,only the cited version applies. For non-specific references, the latest version of the referenced document (including any amendments) applies.
2.1 Normative References
The following referenced documents are necessary for the application of the present document. Not applicable.
2.2 Informative References
The following referenced documents are not necessary for the application of the present document but they assist the user with regard to a particular subject area.
[i.1] oneM2M Drafting Rules (http://member.onem2m.org/Static_pages/Others/Rules_Pages/oneM2M-Drafting-Rules-V1_0.doc)
3 Definitions, symbols, abbriviations and accronyms
3.1 Definitions
For the purposes of the present document, the [following] terms and definitions [given in ... and the following] apply:
<defined term>: <definition>
3.2 Symbols
<symbol> <Explanation>
3.3 Abbreviations
For the purposes of the present document, the [following] abbreviations [given in ... and the following] apply:
<ABBREVIATION1> <Explanation>
3.4 Acronyms
For the purposes of the present document, the [following] abbreviations [given in ... and the following] apply:
<ACRONYM1> <Explanation>
4 Conventions
The key words “Shall”, ”Shall not”, “May”, ”Need not”, “Should”, ”Should not” in this document are to be interpreted as described in the oneM2M Drafting Rules [i.1]
5 oneM2M Work Programme

## A-History of Change
History of Change
V0.0.0 | 2013-08-05 | First draft of new Work Programme Report
V0.1.0 | 2013-08-08 | Incorporation of Raporteur updates
V7.0.0 | 2013-10-18 | First draft of administrative perm document "oneM2M-ADM-0001-oneM2M_Work_Programme-V7_00_00"
V8.0.0 | 2013-12-12 | Input to TP#8 closing session: - update of register "F-Approved Deliverables" - approved deliverables deleted from tracking registers B, C, D, E - update of register "D-Entry Form" based on Rapporteurs' forcasts - register ADM Text Part adapted to official ADM template (oneM2M-Template-ADM-20131008.doc)

## B-WP Overview
|  |  |  | one M2M Work Programme Status: | 2013-12-13 (closing of TP8)
Work Item number | Primary responsible | Doc Type | Doc number | Title | Rapporteur | Milestone dates | [6 empty] | Level of completeness
[6 empty] | Start | Change Control |  | Freeze |  | Approval
[7 empty] | Target | Forecast | Target | Forecast | Target | Forecast
[6 empty] | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date | TP no. / date
WI0001 |  |  |  | oneM2M Requirements
| WG1 - REQ | TR | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
| WG1 - REQ | TR |  | Benefits of oneM2M technology | Phil Hawkes, Qualcomm | TP#1 | TP#2 | TP#2 | TP#2 | forwarded to SC MARCOM for further use
[6 empty] | 2012-09-24 | 2012-12-10 | 2012-12-10 | 2012-12-10
| WG1 - REQ | TS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
[6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
WI0002 |  |  |  | oneM2M Architecture
| WG2 - ARC | TS | TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 3 | 8 | 9 | 8 | 9 | 10 | 10 | 70%
[6 empty] | 2013-01-23 | 2013-12-09 | 2014-02-17 | 2013-12-09 | 2014-02-17 | 2014-04-07 | 2014-04-07
WI0003 |  |  |  | Vocabulary, Roles and Focus Areas for oneM2M Technical Work
| WG1 - REQ | TR | TR-0004(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 45%
[6 empty] | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
| WG1 - REQ | TR | TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 30%
[6 empty] | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0004 |  |  |  | Study of Management Capability Enablement Technologies for Consideration by oneM2M
| WG5 -MAS | TR | TR-0006(WG5) | Study of Management Capability Enablement Technologies for consideration by oneM2M | Jiaxin (Jason) Yin, Huawei | 3 | 7 | 7 | 7 | 7 | 8 | 8 | 95%
[6 empty] | 2013-01-23 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-12-09 | 2013-12-09
WI0005 |  |  |  | oneM2M Abstraction and Semantics Capability Enablement
| WG5 -MAS | TR | TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 3 | 11 | 11 | 11 | 11 | 12 | 12 | 45%
[6 empty] | 2013-01-23 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0006 |  |  |  | oneM2M Device/Gateway Classification
| WG2 - ARC | TR | TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 8 | 10 | 10 | 11 | 11 | 12 | 12 | 0%
[6 empty] | 2013-12-09 | 2014-04-07 | 2014-04-07 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0007 |  |  |  | OneM2M Security Preliminary Investigations
| WG4 - SEC | TR | TR-0008(WG4) | Analysis of security solutions for oneM2M system | Claus Dietze, Giesecke & Devrient | 5 | 9 | 9 | 9 | 9 | 10 | 10 | 65%
[6 empty] | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-04-07 | 2014-04-07
| WG4 - SEC | TS | TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 6 | 10 | 10 | 10 | 10 | 11 | 11 | 25%
[6 empty] | 2013-08-05 | 2014-04-07 | 2014-04-07 | 2014-04-07 | 2014-04-07 | 2014-06-09 | 2014-06-09
WI0008 |  |  |  | OneM2M Protocol Development
| WG3 - PRO | TR | TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 5 | 9 | 9 | 9 | 9 | 10 | 10 | 33%
[6 empty] | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-04-07 | 2014-04-07
WI0009 |  |  |  | Protocol Analysis
| WG3 - PRO | TS | TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 5 | 11 | 11 | 11 | 11 | 12 | 12 | 20%
[6 empty] | 2013-06-17 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
WI0010 | NEW |  |  | Management enablement
| WG5 -MAS | TS | TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 0%
[6 empty] | 2013-12-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
| WG5 -MAS | TS | TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 0%
[6 empty] | 2013-12-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28
Note on J19: Same as freezing 1st release of TS on requirements and architecture (probably TP #6)

## C-Charts
Release 1 TP#12
TP#7

## D-Entry Form
| one M2M Work Programme Status: | 2013-12-13 (closing of TP8)
Doc ID | Title | Rapporteur | Milestone dates | [6 empty] | Level of completeness
|  |  | Start | Change Control |  | Freeze |  | Approval
|  |  |  | Target | Forecast | Target | Forecast | Target | Forecast
| WG1 - REQ |  | TP# | TP# | TP# | TP# | TP# | TP# | TP#
TR-0004(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 45%
TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2 | 3 | 4 | 11 | 11 | 12 | 12 | 30%
WG2 - ARC
TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 8 | 10 | 10 | 11 | 11 | 12 | 12 | 0%
TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 3 | 8 | 9 | 8 | 9 | 10 | 10 | 70%
WG3 - PRO
TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 5 | 9 | 9 | 9 | 9 | 10 | 10 | 33%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 5 | 11 | 11 | 11 | 11 | 12 | 12 | 20%
WG4 - SEC
TR-0008(WG4) | Analysis of security solutions for oneM2M system | Claus Dietze, Giesecke & Devrient | 5 | 9 | 9 | 9 | 9 | 10 | 10 | 65%
TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 6 | 10 | 10 | 10 | 10 | 11 | 11 | 25%
WG5 - MAS
TR-0006(WG5) | Study of Management Capability Enablement Technologies for consideration by oneM2M | Jiaxin (Jason) Yin, Huawei | 3 | 7 | 7 | 7 | 7 | 8 | 8 | 95%
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 3 | 11 | 11 | 11 | 11 | 12 | 12 | 45%
TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 0%
TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 8 | 11 | 11 | 11 | 11 | 12 | 12 | 0%
Note on D13: Drafting start after TS-0001 Change Control
Note on E23: The TR should be put under change control and frozen one meeting before the last TP meeting of the oneM2M release
Note on G23: The TR should be put under change control and frozen one meeting before the last TP meeting of the oneM2M release
Note on I23: The TR should be approved at the last TP meeting of the oneM2M release

## E-Calculations
Do not delete this block structure
TP meeting dates
TP#1 | 2012-09-24
TP#2 | 2012-12-10
TP#3 | 2013-01-23
TP#4 | 2013-04-15
TP#5 | 2013-06-17
TP#6 | 2013-08-05
TP#7 | 2013-10-14
TP#8 | 2013-12-09
TP#9 | 2014-02-17
TP#10 | 2014-04-07
TP#11 | 2014-06-09
TP#12 | 2014-07-28
TP#13 | 2014-09-22
TP#14 | 2014-11-10
TP#15 | 2015-01-19
TP#16 | 2015-03-16
TP#17 | 2015-05-18
TP#18 | 2015-07-20
TP#19 | 2015-09-07
TP#20 | 2015-11-16
Do not delete this block structure
The following table is the 1:1 copy of the Entry-Form, it converts TP numbers into date format (yyyy-mm-dd) and additionally (manually) stores level of completeness of the last 2 reportings
0 | one M2M Work Programme Status: | 2013-12-13 (closing of TP8) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Doc ID | Title | Rapporteur | Milestone dates | 0 | 0 | 0 | 0 | 0 | 0 | Level of completeness | Level of completeness (TP#n-1) | Level of completeness (TP#n-2)
0 | 0 | 0 | Start | Change Control | 0 | Freeze | 0 | Approval | 0 | 0
0 | 0 | 0 | 0 | Target | Forecast | Target | Forecast | Target | Forecast | 0
0 | WG1 - REQ | 0 | TP# | TP# | TP# | TP# | TP# | TP# | TP# | 0
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
TR-0004(WG1) | Definition and Acronyms | Roland Hechwartner, Deutsche Telekom | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 45% | 40% | 40%
TR-0005(WG1) | Roles and Focus Areas | Josef Blanz, Qualcomm | 2012-12-10 | 2013-01-23 | 2013-04-15 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 30% | 30% | 20%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 95% | 80%
0 | WG2 - ARC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
TR-0010(WG2) | oneM2M Device/Gateway Classification | Hongbeom Ahn, LG Infocomm | 2013-12-09 | 2014-04-07 | 2014-04-07 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 0% | 0% | 0%
TS-0001(WG2) | oneM2M Functional Architecture | Rajesh Bhalla, ZTE George Foti, Ericsson | 2013-01-23 | 2013-12-09 | 2014-02-17 | 2013-12-09 | 2014-02-17 | 2014-04-07 | 2014-04-07 | 70% | 55% | 40%
0 | WG3 - PRO | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
TR-0009(WG3) | one M2M Protocol Analysis | Philip Jacobs, Cisco, Richard Brennan, Telxxis | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-04-07 | 2014-04-07 | 33% | 15% | 20%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | Shingo Fujimoto, Fujitsu | 2013-06-17 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 20% | 20% | 20%
0 | WG4 - SEC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
TR-0008(WG4) | Analysis of security solutions for oneM2M system | Claus Dietze, Giesecke & Devrient | 2013-06-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-02-17 | 2014-04-07 | 2014-04-07 | 65% | 60% | 40%
TS-0003(WG4) | One M2M Security solutions | Claus Dietze, Giesecke & Devrient | 2013-08-05 | 2014-04-07 | 2014-04-07 | 2014-04-07 | 2014-04-07 | 2014-06-09 | 2014-06-09 | 25% | 10% | 0%
0 | WG5 - MAS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TR-0006(WG5) | Study of Management Capability Enablement Technologies for consideration by oneM2M | Jiaxin (Jason) Yin, Huawei | 2013-01-23 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-10-14 | 2013-12-09 | 2013-12-09 | 95% | 90% | 80%
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | Joerg Swetina, NEC | 2013-01-23 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 45% | 40% | 20%
TS-0005(WG5) | Management enablement (OMA) | SeungKyu Park (LG Electronics), Jiaxin Yin (Huawei Technologies) | 2013-12-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 0% | 0% | 0%
TS-0006(WG5) | Management enablement (BBF) | Timothy Carey (Alcatel-Lucent) | 2013-12-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-06-09 | 2014-07-28 | 2014-07-28 | 0% | 0% | 0%
The following table prepares the Gant Chart and the chart for deliverable completeness based on the table above. It contains only formulars for calculation.
Doc ID | Title | Doc ID | Start | Drafting | Delay | Change Control | Delay | Freeze | Delay | Level of completeness (actual) | Level of completeness (TP#n-1) | Level of completeness (TP#n-2)
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TR-0004(WG1) | Definition and Acronyms | TR-0004(WG1) | 2012-12-10 | 44 | 82 | 420 | 0 | 49 | 0 | 45% | 40% | 40%
TR-0005(WG1) | Roles and Focus Areas | TR-0005(WG1) | 2012-12-10 | 44 | 82 | 420 | 0 | 49 | 0 | 30% | 30% | 20%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0% | 0%
TR-0010(WG2) | oneM2M Device/Gateway Classification | TR-0010(WG2) | 2013-12-09 | 119 | 0 | 63 | 0 | 49 | 0 | 0% | 0% | 0%
TS-0001(WG2) | oneM2M Functional Architecture | TS-0001(WG2) | 2013-01-23 | 320 | 70 | 0 | 0 | 49 | 0 | 70% | 55% | 40%
TR-0009(WG3) | one M2M Protocol Analysis | TR-0009(WG3) | 2013-06-17 | 245 | 0 | 0 | 0 | 49 | 0 | 33% | 15% | 20%
TS-0004(WG3) | OneM2M Service Layer Protocol and API Specification | TS-0004(WG3) | 2013-06-17 | 357 | 0 | 0 | 0 | 49 | 0 | 20% | 20% | 20%
TR-0008(WG4) | Analysis of security solutions for oneM2M system | TR-0008(WG4) | 2013-06-17 | 245 | 0 | 0 | 0 | 49 | 0 | 65% | 60% | 40%
TS-0003(WG4) | One M2M Security solutions | TS-0003(WG4) | 2013-08-05 | 245 | 0 | 0 | 0 | 63 | 0 | 25% | 10% | 0%
TR-0006(WG5) | Study of Management Capability Enablement Technologies for consideration by oneM2M | TR-0006(WG5) | 2013-01-23 | 264 | 0 | 0 | 0 | 56 | 0 | 95% | 90% | 80%
TR-0007(WG5) | Study of Abstraction and Semantics Enablements | TR-0007(WG5) | 2013-01-23 | 502 | 0 | 0 | 0 | 49 | 0 | 45% | 40% | 20%
TS-0005(WG5) | Management enablement (OMA) | TS-0005(WG5) | 2013-12-09 | 182 | 0 | 0 | 0 | 49 | 0 | 0% | 0% | 0%
TS-0006(WG5) | Management enablement (BBF) | TS-0006(WG5) | 2013-12-09 | 182 | 0 | 0 | 0 | 49 | 0 | 0% | 0% | 0%
Axis options
Minimum: 41160
Maximum: 42000
Main interval: 120
Assisting interval: 30

## F-Approved Deliverables
Name | Version | Work Item | TP approval date | Forwarded to SC for publication
oneM2M-TR-0002-Architecture_Analysis_Part_1 | V-0.2.0 | WI0002 | 2013-08-05 | 2013-10-14
oneM2M-TR-0003-Architecture_Analysis_Part_2 | V-0.5.0 | WI0002 | 2013-08-05 | 2013-10-14
oneM2M-TS-0002-Requirements | V0.6.2 | WI0001 | 2013-10-17 | 2013-11-22
oneM2M-TR-0001-UseCase | V0.0.5 | WI0001 | 2013-10-17 | 2013-11-22