## comments
|  | Spectification Reviewed: | TS-0001-oneM2M-Functional-Architecture-V-2014-08
|  | Your Organization Name: | US Department of Transportation, Intelligent Transportation Systems Join Program Office (ITS-JPO)
|  | Contact email: | walton.fehr@dot.gov; steve.sill@dot.gov
Your reference (optional) | E/T | Section | Page | Line | Comment | Status | Check for TP#15
| E | 5.1 | 18 | Figure 5.1.-1 | The lowest box is labeled 'Network Services Layer', but the accompanying text refers to 'Underlying Network Services Layer'. If 'Underlying' is important enough to be capitalized, it should be in the picture. | Contribution before TP#15 Omar Elloumi | Done by the contribution ARC-2014-1674
| T | 5.2.2.5 | 20 |  | This section has no reference in the accompanying diagram. Since Mch is defined in 12.2.1, this reference point definition belongs there | Contribution: move definition of Mch to section 12 and add a section 5.2.2.5 "Other reference points" that points to Mch, Ms, Mp, … + remove explicit reference to "charging" in the note under the figure Omar Elloumi | Done by the contribution ARC-2014-1674
| T | 6.1 | 21 | Figure 6.1-1 | The terms 'infrastructure domain' and 'field domain' should be defined. In some technical spaces, those two terms have the same meaning | No action but answer: this is in TS-0011; add text in section 3 to explicitly refer to TS-0011 - by Guang | terms will be added
| T | 6.5.1 | 39 |  | Requiring public DNS usage for interM2M communications may compromise the privacy of the stakeholder owning the registered node. This section implies that the only way for interM2M communications to occur requires public DNS registration. Since a business relationship is also required to support interM2M communications, it is not clear why public DNS is absolutely required. Defense in depth implies that unless the M2M IN wanted to be accessible to *everyone*, they should provide their connectivity information (e.g., IP address) to their partner IN stakeholder and not be forced to register in a public DNS. | answer: this is correct, we'll look into that aspect later on | Not Done
| T | 6.5.2 | 40 |  | The process for interaction between domains requires the target CSE to provide all access control. This in effect allows a non-permitted or hostile actor to engage directly with the CSE, potentially denying service to authorized users. Suggest considering some level of access control at the IN. | Send that to WG4 | Not Done (Check with WG4)
| T | 10.1 | 139 |  | CREATE could fail because of a lack of capacity at the target. The request originator should be informed of the status of the CREATE request, including this type of failure or any other exception. | Answer: this is correct, if there is no capacity anymore then an error will be returned + send to WG3 | Done unsupported resource (5001)
| E |  | 140 |  | Rapporteur notes are sprinkled throughout the document, typically colored red.; presumably they will be removed once document finalized, but the ones on this page are not colored red and so read as though they might be part of the text. | We're working on it | Not Done

## guidelines
This sheet, guidelines, is provided for inormation and may be deleted prior to submission.
Column Name | Description
Your reference (optional) | Typically an integer to facilitate reference to the specific comment. May be left blank. If left blank, may be populated during the oneM2M comment review process
E/T | An inidcation of whether, in the view of the author, the comment is editorial or has potential technical impact. E - editorial T - potential technical impact
Section | The section number in the oneM2M Specification to which the comment applies. E.g. 2.2
Page | The page number, as printed at the bottom of the page of the Specification to which the comment applies.
Line | The line number as printed on the page of the Specification to which the comment applies
Comment | The actual comment. This may be text in the cell, or be a reference to an attached file. Attached files should be used if the comment does not easily fit in the cell. If attached files are used, the Excel sheet and all referenced files must be packaged as a zip archive.
Attached Filename (if applicable) | The name of a file that contains the comment.