## Sheet1
Ref. | Type | Description | Comment | Responsible WG | Target TS | Issue Owner | CR | Status
INT-3-1 | Issue | Root element issue in Request Primitive | The root element should be present, but we should double check this in PRO. | PRO | TS-0004 | Wolfgang Granzow, Qualcomm
INT-3-2 | Issue | Root element issue in Response Primitive | The root element should be present as in the request. | PRO | TS-0004 | Wolfgang Granzow, Qualcomm
INT-3-3 | Issue | Old version short names still used in some HTTP binding examples | Yes, figure A-1.1 needs to be updated. | PRO | TS-0009 | Nobu Uchida, Qualcomm
INT-3-4 | Issue | CSEBase name shortcut “dot” issue | Use of "." is compliant with RFC 2396 (URI). Every URL parser should be able to handle it. Of course, at one point of URL processing, the "." shortcut has to be replaced by a full name. Not sure if this is not possible in postman or jessy web servers. If this is indeed not possible, then these tools might just be inappropriate. | ARC | TS-0001 | Josef Blanz, Qualcomm
INT-3-5 | Issue | Attributes cardinality inconsistency in <Container> resource | Suggest to change TS-0001 to make those three attributes mandatory. | ARC w/ PRO | TS-0001
INT-3-6 | Issue | Confusing text in create <Request> Procedure | The suggested changes seem good. | ARC w/ PRO | TS-0001 TS-0004
INT-3-7 | Issue | Are resource identifiers and primitive attributes case sensitive? | Yes, resource identifier and resourcename should be case sensitive. | ARC | TS-0001
INT-3-8 | Issue | AccessControlOriginators “all” or “*” ? | This is obviosly redundant. Maybe better to remove the keyword "all". | ARC w/ PRO | TS-0001 TS-0004
INT-3-9 | Issue | MQTT topic name format |  | PRO | TS-0010 | Peter Niblett, IBM
INT-3-10 | Issue | Typos and Incorrect formats of absolute addresses in some examples | Yes, the example should be corrected. | ARC w/ PRO | TS-0001 TS-0004
INT-3-11 | Issue | Update acpi check both privileges and selfPrivilges? | The selfPrivilges are applicable to accessControlPolicy resource itself as well as accessControlPolicyIDs attribute. Clarification needed. | ARC | TS-0010
INT-3-12 | Issue | Virtual resource short or long names? | Only long name is allowed for virtual resources. See clause 6.8 of TS-0004. TST would like PRO to recondier since some implementaion is using shornames. | PRO | TS-0004
INT-3-13 | Issue | Enable short names in cbor serialization in TS-0004 | Short names are to be used for CBOR as for JSON. Better to have explicit statement in TS-0004. | PRO | TS-0004
INT-3-14 | Issue | Request Reachability attribute for AE issue |  | ARC | TS-0001
INT-3-15 | optimization | oneM2M versioning |  | ARC w/ PRO | TS-0001
INT-3-16 | optimization | Reduce addressing complexity |  | ARC | TS-0001
INT-3-17 | optimization | Back annotate resource addresses in ARC from PRO bindings |  | ARC w/ PRO | TS-0001
INT-3-18 | optimization | XSD validation and attribute order |  | PRO | TS-0004
INT-3-19 | optimization | ADN addressing methods |  | ARC | TS-0001
INT-3-20 | optimization | Default response content in Creation Request |  | ARC | TS-0001
INT-3-21 | optimization | Default response content of delete operation |  | ARC | TS-0001
INT-3-22 | optimization | Default response content of update operation |  | ARC | TS-0001
INT-3-23 | optimization | Unstructured addressing for CSEBase resource |  | ARC | TS-0001
INT-3-24 | optimization | TS-0013 document improvements |  | TST | TS-0013