## Sheet1
Ref. | Type | Description | Comment | Responsible WG | Target TS | Issue Owner | CR | Status
INT-3-1 | Issue | Root element issue in Request Primitive | root element for XML not JSON | PRO | TS-0004 TS-0020 | Wolfgang | PRO-2016-0486-CR_TS0004_rootElement_in_primitives PRO-2016-0487-CR_TS0004_rootElement_in_primitives_(R1_mirror) PRO-2016-0488-CR_TS0020_rootElement_in_primitives
INT-3-2 | Issue | Root element issue in Response Primitive | root element for XML not JSON | PRO | TS-0004 TS-0020
INT-3-3 | Issue | Old version short names still used in some HTTP binding examples | The short name shall be rcn | PRO | TS-0009 | Nobu | PRO-2016-0483-TS-0009_Result_Content_correction_R1 PRO-2016-0482-TS-0009_Result_Content_correction_R2
INT-3-4 | Issue | CSEBase name shortcut “dot” issue | choose alternative character | ARC |  | Mahdi
INT-3-5 | Issue | Attributes cardinality inconsistency in <Container> resource | Keep it optional, but clarify what it means when they aren't there, and the circumstances in which the hosting CSE will omit them | PRO | TS-0004 | Bob | PRO-2016-0489-container_procedures_mni_mbs_mia
INT-3-6 | Issue | Confusing text in create <Request> Procedure |  | ARC w/ PRO |  | Bob
INT-3-7 | Issue | Are resource identifiers and primitive attributes case sensitive? | case sensitive | PRO |  | Seung Myeong
INT-3-8 | Issue | AccessControlOriginators “all” or “*” ? | Syntax work needed | ARC w/ PRO w / SEC |  | discuss at joint SEC/PRO | PRO-2016-0485-Access_Control_Originators
INT-3-9 | Issue | MQTT topic name format | Fix the confusing sentences | PRO | TS-0010 | Bob | PRO-2016-0490-mqtt_address_binding_clarification
INT-3-10 | Issue | Typos and Incorrect formats of absolute addresses in some examples |  | ARC w/ PRO |  | Mahdi
INT-3-11 | Issue | Update acpi check both privileges and selfPrivilges? |  | ARC
INT-3-12 | Issue | Virtual resource short or long names? |  | PRO |  | SeungMyeong | PRO-2016-0481-short_name_for_virtual_resource_addressing_(Rel-1)
INT-3-13 | Issue | Enable short names in cbor serialization in TS-0004 | add "or CBOR" | PRO | TS-0004 | Nobu | PRO-2016-0484-TS-0004_CBOR_short_name_clarification_R2
INT-3-14 | Issue | Request Reachability attribute for AE issue |  | ARC
INT-3-15 | optimization | oneM2M versioning |  | PRO w/ARC |  | Discuss on conference call
INT-3-16 | optimization | Reduce addressing complexity |  | ARC
INT-3-17 | optimization | Back annotate resource addresses in ARC from PRO bindings | ARC to propose new introducer characters instead of // and / | ARC w/ PRO
INT-3-18 | optimization | XSD validation and attribute order |  | PRO
INT-3-19 | optimization | ADN addressing methods |  | ARC
INT-3-20 | optimization | Default response content in Creation Request |  | ARC
INT-3-21 | optimization | Default response content of delete operation |  | ARC
INT-3-22 | optimization | Default response content of update operation |  | ARC
INT-3-23 | optimization | Unstructured addressing for CSEBase resource |  | ARC
INT-3-24 | optimization | TS-0013 document improvements |  | TST