## Sheet1
Ref. | Type | Description | Comment | Responsible WG | Target TS | Issue Owner | CR | Status
INT-3-1 | Issue | Root element issue in Request Primitive | root element for XML not JSON | PRO | TS-0004 TS-0020 | Wolfgang | PRO-2016-0486-CR_TS0004_rootElement_in_primitives PRO-2016-0487-CR_TS0004_rootElement_in_primitives_(R1_mirror) PRO-2016-0488-CR_TS0020_rootElement_in_primitives | Done
INT-3-2 | Issue | Root element issue in Response Primitive | root element for XML not JSON | PRO | TS-0004 TS-0020
INT-3-3 | Issue | Old version short names still used in some HTTP binding examples | The short name shall be rcn | PRO | TS-0009 | Nobu | PRO-2016-0483-TS-0009_Result_Content_correction_R1 PRO-2016-0482-TS-0009_Result_Content_correction_R2 | Done
INT-3-4 | Issue | CSEBase name shortcut “dot” issue | Use "-" character instead of . | ARC | TS-0001 TS-0004 | Mahdi/Peter | ARC-2016-0546-Replace_CSEBase_resource_name_shortcut (R2) PRO-2016-0495-Replace_CSEBase_resource_name_shortcut_-_R2 | ARC CR Agreed
INT-3-5 | Issue | Attributes cardinality inconsistency in <Container> resource | Keep it optional, but clarify what it means when they aren't there, and the circumstances in which the hosting CSE will omit them | PRO | TS-0004 | Bob | PRO-2016-0489-container_procedures_mni_mbs_mia | Under discussion
INT-3-6 | Issue | Confusing text in create <Request> Procedure |  | ARC w/ PRO |  | Bob | ARC-2016-0540R01-create_request_procedure (R2) ARC-2017-0021-create_request_procedures_R3 | ARC CR Agreed (R2)
INT-3-7 | Issue | Are resource identifiers and primitive attributes case sensitive? | case sensitive | PRO |  | Seung Myeong |  | CR needed
INT-3-8 | Issue | AccessControlOriginators “all” or “*” ? | Syntax work needed | ARC w/ PRO w / SEC |  | discuss at joint SEC/PRO | PRO-2016-0485-Access_Control_Originators | Under discussion
INT-3-9 | Issue | MQTT topic name format | Fix the confusing sentences | PRO | TS-0010 | Bob | PRO-2016-0490-mqtt_address_binding_clarification | Done
INT-3-10 | Issue | Typos and Incorrect formats of absolute addresses in some examples |  | ARC w/ PRO |  | Mahdi |  | Need to check PRO docs
INT-3-11 | Issue | Update acpi check both privileges and selfPrivilges? |  | ARC
INT-3-12 | Issue | Virtual resource short or long names? |  | PRO |  | SeungMyeong | PRO-2016-0481-short_name_for_virtual_resource_addressing_(Rel-1) ARC-2017-0002-CR_for_virtual_resource_name_(Rel-1) ARC-2017-0003-CR_for_virtual_resource_name_(Rel-2) ARC-2017-0004-CR_for_virtual_resource_name_(Rel-3) | Agreed in principle. Detailed CR needed
INT-3-13 | Issue | Enable short names in cbor serialization in TS-0004 | add "or CBOR" | PRO | TS-0004 | Nobu | PRO-2016-0484-TS-0004_CBOR_short_name_clarification_R2 | Done
INT-3-14 | Issue | Request Reachability attribute for AE issue |  | ARC
INT-3-15 | optimization | oneM2M versioning |  | PRO w/ARC |  | Discuss on conference call | ARC-2017-0006-versionHandling | Under discussion
INT-3-16 | optimization | Reduce addressing complexity |  | ARC
INT-3-17 | optimization | Back annotate resource addresses in ARC from PRO bindings | ARC to propose new introducer characters instead of // and / | ARC w/ PRO
INT-3-18 | optimization | XSD validation and attribute order | Request is to allow resource attributes to appear in any order | PRO | TS-0004 | SeungMyeong | PRO-2016-0438-ordering_in_XML_(R1) PRO-2016-0439-ordering_in_XML_(R2) | Not yet discussed
INT-3-19 | optimization | ADN addressing methods |  | ARC
INT-3-20 | optimization | Default response content in Creation Request |  | ARC | TS-0001 TS-0004 | Seung Myeong | ARC-2016-0543-default_Content_in_CUD_response_(Rel-2) | Under discussion
INT-3-21 | optimization | Default response content of delete operation |  | ARC
INT-3-22 | optimization | Default response content of update operation |  | ARC
INT-3-23 | optimization | Unstructured addressing for CSEBase resource |  | ARC
INT-3-24 | optimization | TS-0013 document improvements |  | TST