## summary
Definitions
Minor: no discussion required from the group. Rapporteur can go ahead and make the change. Acceptance of change will be agreed by the WG prior to finalizing the draft
Minor+: some minimal discussion may be required and rapporteur can then go ahead and make the change. Acceptance of change will be agreed by the WG prior to finalizing the draft
Major: discussion required among contributors, wg members, or both. There is a need to drive to nearly final verbiage, which will need to be agreed by the wg prior to final draft.
Count of Issue types
minor | 52
minor+ | 3
major | 22
Issue Resolution Tracking
Resolved issues | 50
Partially Resolved | 6
Unresolved | 21
completion | 64.94%

## issues
Requirement ID/Line Number | Problem type | Issue Level | Proposed Resolution(Sprint) | Proposed Resolution(Huawei) | Proposed Resolution (Huawei - Jason Yin) | Issue owner | Issue resolved
51 | Editoral | minor |  | This present document contains an informative functional role model and normative technical requirements for oneM2M. |  |  | yes
60 | Editorial | minor | Insert proper reference in Section 2.1 | [1] oneM2M TR 0004XXXX, “oneM2M Definitions and Acronyms” [2] 3GPP TS 22.368, "Service requirements for Machine-Type Communications (MTC); Stage 1" |  |  | yes
68 | Editorial | minor | Insert proper reference in Section 2.2 | change to [i.1] oneM2M Drafting Rules (http://member.onem2m.org/Static_pages/Others/Rules_Pages/oneM2M-Drafting-Rules-V1_0.doc) [i.2] ETSI TS102 689 V1.1.1, Machine-to-Machine communications (M2M);M2M service requirements? |  |  | yes
76 | Editorial | minor | M2M Appliction definition needs to be updated with the latest definition |  |  |  | yes
85 | Editorial | minor |  | M2M Application Service definition needs to be updated with the latest definition |  |  | yes
81-82 | Editorial | Major | M2M Service is not an AGREED definition from the Definitions TR. Remove pending agreement on a definition. |  |  |  | no
84-85 | Editorial | minor | M2M Application Service provider definition needs to be updated with the latest definition No need to change. |  |  |  | yes
86-87 | Editorial | Major | M2M Services Capability Set is not an AGREED definition from the Definitinos TR. Remove pending agreement on a definition. |  |  |  | no
91-92 | Editorial | Major | M2M Service Capability is not an AGREED definition from the Definitinos TR. Remove pending agreement on a definition. |  |  |  | no
94 | Editorial | minor | Underlying Network definition needs to be updated with the latest definition | delete Editorial'Note of Underlying network. |  |  | yes
95 | Editorial | minor |  | M2M Service Provider definition needs to be updated with the latest definition |  |  | yes
97 | Editor's note | minor | User definition needs to be updated with the latest definition | delete Editorial'Note of User |  |  | yes
104 | Editor's note | minor |  | delete Editorial'Note of M2M system |  |  | yes
Section 3.1 | Editorial | minor |  | Adjust the order of definition based on capital |  |  | yes
134 | Editor's note | minor+ | Remove. |  |  |  | yes
Section 3.1 | Editorial | minor | Add definition of M2M Area Network |  |  |  | yes
111 to 114 section 3.3 Abbreviations | Editoral | minor |  | Addind the folowing abbreviations: CHA: Continua Health Alliance GSMA: Global System for Mobile Communications Association HSM: Hardware Security Module OMA:Open Mobile Alliance SMS: Short Message Service USSD: Unstructured Supplementary Service Data |  |  | yes
OSR-001 | Editorial/definition | Major | What do we mean by IP Access? Should we define this to be more clear? | Do we need define "Network domain" and "Device domain"? For example: Network domain refers to the infrastructure node of oneM2M Device domain refers to Application dedicated/Application service/ middle node of oneM2M. |  |  | no
OSR-001 | Editorial | Major | Network Domain and Device Domain are not defined anywhere. |  |  |  | no
OSR-003 | Editor's note | Major | Session needs to be defined. |  |  |  | no
OSR-006 | Editorial | minor | Need to add a NOTE: The set of features or APIs to be supported depends on the M2M Service Capabilities and access to available APIs. |  |  |  | yes
OSR-008 | Editorial | minor | should "device" be "M2M Device"? |  |  |  | yes
OSR-009 | Editor's note | minor+ | Remove. |  |  |  | no
OSR-012 | Editorial | Major | M2M Services needs to be defined. See OSR-017, which delineates some of this. |  |  |  | no
OSR-017 | Complex Requirement | Major | Needs to be split in two. | Replace "shall be able to" with shall be capable of |  | Laurent Laporte | partial
OSR-018 | Editorial | minor | change "Underlying cellular Networks" to "cellular Underlying Networks". | Replace "shall be able to" with shall be capable of |  | YuQi | partial
OSR-018 | Complex Requirement | Major |  | Modified by 359R04 and 358R01 at TP#6. Need confirm how to modify this requirement. |  | YuQi | no
OSR-019 | Editorial | minor+ | Phrase at the end of the requirement should be removed. It is meaningless as it stands. "For delivery to one or more M2M Gateways, M2M Services Infrastructure, or M2M Application Infrastructure" |  |  |  | no
OSR-023 | Editor's note | Major | M2M Service Subscription needs to be defined. | Replace "shall be able to" with shall be capable of |  |  | partial
OSR-024 | Editorial | minor | should "device" be "M2M Device"? | Replace "shall be able to" with shall be capable of |  |  | yes
OSR-025 | Editorial | minor |  | Replace "shall be able to" with shall be capable of |  |  | yes
OSR-026 | Editorial | minor | should "device" be "M2M Device"? | Replace "shall be able to" with shall be capable of |  |  | yes
OSR-028 | Editorial | minor | should "application" be "M2M Application"? |  |  |  | yes
OSR-032 | Editor's note | Major | Event Categorization needs to be defined. |  |  |  | no
OSR-035 | Editorial | minor | should "application" be "M2M Application"? |  |  |  | yes
OSR-035 | Editorial | Major | The second sentence seems to be more of a note than necessary for the requirment. Should we remove it? Or make it a note? |  |  |  | no
OSR-036 | Editoral | minor |  | The oneM2M system should provide mechanisms to accept requests from M2M application service providers for compute/analytics services. |  |  | yes
OSR-041 | Editorial | Major | What do we mean by interface? Need clarification. The context seems to imply an API. | The M2M System shall provide a mechanism, which supports the addition of new M2M Services without impact to oneM2M interface interoperability |  |  | partial
OSR-042 | Complex Requirement | Major | This seems like two requirements. |  |  | Laurent Laporte | no
OSR-049OSR-50 | Editorial | Major | need to define Infrastructure Domain or change to a different noun. | Add definition of "Infrastructure Domain".How to deal with "field domian" |  |  | yes
OSR-49 OSR-053 | Editorial | minor | Need to rewrite. … control) when sharing data among applications… to … control) among applications." | Do not know how to modify? |  |  | yes
OSR-062 OSR-058 | Editorial | Major | Need to define Common Service Functions |  |  |  | no
OSR-065 | Editoral | minor |  | The oneM2M System shall be able to provide mechanisms to accept M2M Applications for distribution, from M2M application service providers. |  |  | yes
OSR-066 | Editoral | minor |  | The oneM2M System shall be able to support the placement and operation of M2M Applications in selected M2M nodes per criteria requested by M2M Applications service providers, subject to access rights. |  |  | yes
OSR-067 | Editorial | Major | M2M Service Layer either needs a definition or needs to be replaced with a suitable noun | The oneM2M System shall be able to take operational and management action as requested by M2M Applications. |  |  | partial
OSR-070 | Editorial | minor |  | Need add definition of M2M Service Administrative State&M2M Service Operational Status. |  |  | yes
OSR-071 | Editoral | minor |  | Replace "shall be able to" with "should be able to" |  |  | yes
MGR-002 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-003 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-004 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-005 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-006 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-008 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-009 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-010 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-011 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
MGR-012 | Editorial | minor | should "device" be "M2M Device"? |  | device should be used |  | yes
| Editorial | Major | Should we have a definition for "device"? | How about use M2M device definition? M2M Device: physical equipment with communication capabilities, providing computing and/or sensing and/or actuation services. An M2M Device hosts one or more M2M Applications or other applications and can contain implementations of CSE functionalities. |  |  | no
CHG-001 | Editorial | Major | Needs to be split in two. |  |  |  | no
CHG-005 | Editorial | Major | Needs to be split in two. |  |  |  | no
OPR-003 | Editorial | minor |  | Replace "shall be able to" with shall be capable of |  |  | yes
OPR-005 | Editorial | Major | needs to be rewritten | The M2M System shall be able to exchange information with M2M Applications related to usage and traffic characteristics of M2M Devices or M2M Gateways by the M2M Application. This information includes the following features for a M2M Device: • Time controlled devices to send or receive data only during defined time intervals Note: “Low mobility” and “Time controlled” are is equivalent to the MTC Features specified in [i.x] (section 7.2 of 3GPP TS 22.368) |  |  | partial
SER-006 | Editorial | minor | What do we mean by "m2m security association"? |  |  |  | no
SER-011 | Editorial | minor | Should "stakeholder" be "M2M Stakeholder"? |  |  |  | yes
SER-013 | Editoral | minor |  | The M2M Systemservice shall be able to provide the mechanism for integrity-checking on boot, periodically on run-time, and on software upgrades for software/hardware/firmware component(s) on M2M Device(s). |  |  | yes
SER-015 | Editor's note | minor | Not clear why User definition needs to be further refined. |  |  |  | yes
SER-015 | Editor's note | minor | Make sure User definition is in the definition section in the TS |  |  |  | yes
SER-016 | Editor's note | minor | What do we mean by "m2m service layer"? |  |  |  | no
SER-017 | Editor's note | minor | What do we mean by "m2m service layer"? |  |  |  | no
SER-018 | Editor's note | minor | Stakeholder is defined in the Definitions TR. The requirement should use M2M Stakeholder. |  |  |  | yes
SER-018 | Editor's note | minor | Need to add M2M Stakeholder to the definition section in the TS. |  |  |  | yes
SER-023 | Editorial | minor | Rewrite from "If a HSM is supported the M2M Device should use HSM (Hardware Security Module) to provide security level consistent with the requirement supported by the M2M System." to "If a Hardware Security Module (HSM) is supported, the M2M Device should use the HSM to provide security level consistent with the requirement supported by the M2M System." |  |  |  | yes
SER-025 | Editorial | minor | Should "stakeholder" be "M2M Stakeholder"? |  |  |  | yes
SER-025 | Editor's note | minor | Stakeholder is defined in the Definitions TR. The requirement should use M2M Stakeholder. |  |  |  | yes
ABR-002 | Editor's note | minor | Information model defined. |  |  |  | yes
ABR-002 | Editor's note | Major | Meta-data still needs a definition. |  |  |  | no
NFR-001 | Editoral | minor |  | Continua Health Alliance is incorporating a RESTful approach to its design. To support CHA, oneM2M should consider RESTful styles and approaches while designing the oneM2M architecture. |  |  | Yes
Note on A1: Huawei: Please put the Line Number or Requirment ID which need be modified.
Note on B1: Huawei: Problem type may include: 1.Editorial 2.Complex Requirement 3.Grammatical 4.editor's note 5.section not needed
Note on H1: Huawei: The issue resolved choices are: -yes -no -partial

## dropdown
Editorial | yes
Complex Requirement | no
Grammatical | partial
editor's note
section not needed