## 2013-02-28
one M2M Work Program Status: 2013-02-28
Work Item number | Working Group |  | Title | Start Date | Agreement Date |  | Change Control Start |  | Freeze Date |  | Approval | Target Release | Rapporteur
[5 empty] | Target | Forecast | Target | Forecast | Target | Forecast
WI0001 |  |  | oneM2M Requirements
| WG1 - REQ | TR | oneM2M use case collection | TP#1 | TP#2 |  |  |  | TP#3 |  |  |  | Anu Appaji, Intel
| WG1 - REQ | TR | Benefits of oneM2M technology | TP#1 | TP#2 |  |  |  | TP#2 |  |  |  | Phil Hawkes, Qualcomm
| WG1 - REQ | TS | M2M Requirements | TP#2 | TP#3 |  |  |  | TP#4 |  |  |  | Linyi Tian, Huawei
WI0002 |  |  | oneM2M Architecture
| WG2 - ARC | TR | Part 1: Analysis of the architectures proposed for transfer to oneM2M | TP#1 | TP#2 |  |  |  | TP#2 |  |  |  | Richard Brennan, Telxxis
| WG2 - ARC | TR | Part 2 Study for the merging of architectures proposed for transfer to oneM2M and resolve critical potential gaps | TP#2 | TP#3 |  |  |  | TP#3 |  |  |  | Phillip Brown, InterDigital
| WG2 - ARC | TS | M2M Architecture | TP#3 | TP#4 |  |  |  | TP#6 |  |  |  | Rajesh Bhalla, ZTE George Foti, Ericsson
WI0003 |  |  | Vocabulary, Roles and Focus Areas for oneM2M Technical Work
| TP (WG1) | TR | Definition and Acronyms | TP#2 |  |  | TP#3 |  | Same as freezing 1st release of oneM2M |  |  |  | Roland Hechwartner, T-mobile
| TP (WG1) | TR | Roles and Focus Areas | TP#2 |  |  | TP#3 |  | TP#6 |  |  |  | Josef Blanz, Qualcomm
Note on J14: Same as freezing 1st release of TS on requirements and architecture (probably TP #6)
Note on J19: Same as freezing 1st release of TS on requirements and architecture (probably TP #6)