## Tabelle1
Report at oneM2M TP#5 & Interim report from WG-5
Part A: Executive Summary for Plenary
1. Input TR-0006 v0.1.2 (Management TR) & TR-0007 v0.2.0 (Abstraction & Semantics TR) are agreed as baselines for further contribution
2. Management Study TR (WI-0004) progressed with multiple contributions covering BBF TR069, OMA DM1.3, LWM2M, DM2.0. New schedule is set as to postpone the ChangeControl and Freeze dates to TP#7.
3. Semantics TR (WI-0005) received only 1 input contribution on Semantics Use Case. Lack of input on existing technology investigation especially on Abstraction aspects. Milstones need to be updated and the prediction is to be finished at least 2-TP later than the Management TR.
4. Requirements related to MAS aspects are mostly accepted by the joint WG1-WG5 sessions.
5. The basic idea of developing the deployment scenarios and a generalized maangement architecture in Management TR is accepted by joint the WG2-WG5 session
6. Interim Conference Calls are arranged as 2 calls for Management (on Friday) and 2 for Abstraction/Semantics (on Tuesday, as needed depending on received contributions). See details in D-WG5-0001
A1. Documents NOT AGREED in WG (to be presented to Plenary for discussion).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A2. Documents NOT AGREED in WG (noted / postponed / not treated etc).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-MAS-2013-0042 | OMA DM requirements gap analysis | Huawei Technologies UK (ETSI);Huawei Technologies Co.,Ltd (CCSA) | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0043 | Introduction to OMA DM 2.0 | LG Electronics | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0048 | OMA DM LWM2M requirements gap analysis | LG Electronics | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0053 | OMA DM 2.0 Gap Analysis | LG Electronics | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0038R01 | Requirements for Abstraction and Semantics Enablement | NEC, Samsung SDS, InterDigital, LG Electronics | Draft | Withdrawn | TS-0002 | 0.3.0 |  | 1 | WI-0001
oneM2M-REQ-2013-0351 | Semantics requirments and definitions | InterDigital | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001 | To be harmonized with other contributions and comments received.Revision is to be discussion in WG1-WG5 joint sessoin.
oneM2M-MAS-2013-0041 | Opened ABS related requirements | NEC, Samsung SDS, InterDigital, LG Electronics | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001 | To be harmonized with other contributions and comments received. Only ABS-X1 is kept for further update. ABS-X2,ABS-X3 is to be merged with REQ-0351.Revision is to be discussion in WG1-WG5 joint sessoin.
oneM2M-MAS-2013-0047 | Home_Environment_Monitoring_Service_using_semantic_mash-up | Modacom | Draft | Noted | TR-0007 | 0.2.0 |  | 1 | WI-0005 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0044R01 | Application Structure for Smart Metering Service | JNU, KCA(TTA) | Draft | Postponed | [5 empty] | postponed to WG5 ordinary conf-calls
oneM2M-MAS-2013-0045 | Pricing Policy of Demand Response of Home Appliances in Smart Grid | JNU, KCA(TTA) | Draft | Postponed | [5 empty] | postponed to WG5 ordinary conf-calls
oneM2M-MAS-2013-0056 | Proposal of a cloud-based presentation and application framework for developing and deploying Web of Things Applications | KAIST, KCA(TTA) | Draft | Postponed | [5 empty] | postponed to WG5 ordinary conf-calls
oneM2M-MAS-2013-0043R01 | Introduction to OMA DM 2.0 | LG Electronics | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0047R01 | Home_Environment_Monitoring_Service_using_semantic_mash-up | Modacom | Draft | Noted | TR-0007 | 0.2.0 |  | 1 | WI-0005
oneM2M-MAS-2013-0057 | Progressing the Work on the Management TR-0006 | Timothy Carey - ALU | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | 2 interim meetings are reserved for Management TR. ALU will start with the deployment secenarios and generalized management architecture. Further mapping to different technologies will be based on the generalized management architecture
oneM2M-MAS-2013-0050R01 | Revised-WI-0005-Abstraction_&_Semantics_Capability_Enablement | NEC | Draft | Noted | TR-0007 | 0.2.0 |  | 1 | WI-0005 | revision will be made for TP closing session.
A3. Documents AGREED in WG
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-MAS-2013-0052R02 | WG5 Agenda | Chair/Vice-Chair | Agenda | Agreed
oneM2M-MAS-2013-0052R04 | WG5 Agenda | Chair/Vice-Chair | Agenda | Agreed
oneM2M-MAS-2013-0040 | Minutes-2013-06-04 | Secretary | Minutes | Agreed
oneM2M-TR-0006 | Study of Management Capability Enablement Technologies for Consideration by oneM2M | Jiaxin Yin (Huawei Technologies UK (ETSI)) | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-TR-0007 | Study_on_Abstraction_and_Semantics_Enablement-V0_2_0 | Jaeseung Song (NEC Europe Ltd.) | Draft | Agreed | TR-0007 | 0.2.0 |  | 1 | WI-0005
oneM2M-MAS-2013-0051 | Latest_ABS_TR_V0_2_0 | Jaeseung Song (NEC Europe Ltd.) | Draft | Agreed | TR-0007 | 0.2.0 |  | 1 | WI-0005
oneM2M-MAS-2013-0031R03 | BBF TR-069 Technology – Management TR Section 6 Gap Analysis | Timothy Carey - ALU | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004 | preagreed with editorial changes (add conclusion sentence in analysis section.)
oneM2M-MAS-2013-0031R04 | BBF TR-069 Technology – Management TR Section 6 Gap Analysis | Timothy Carey - ALU | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004 | Further input on terminologies.
oneM2M-MAS-2013-0042R02 | OMA DM requirements gap analysis | Huawei Technologies UK (ETSI);Huawei Technologies Co.,Ltd (CCSA) | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0043R02 | Introduction to OMA DM 2.0 | LG Electronics | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004 | with clarification of DM 2.0 standard objects.
oneM2M-MAS-2013-0048R01 | OMA DM LWM2M requirements gap analysis | LG Electronics | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0053R01 | OMA DM 2.0 Gap Analysis | LG Electronics | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0047R02 | Home_Environment_Monitoring_Service_using_semantic_mash-up | Modacom | Draft | Agreed | TR-0007 | 0.2.0 |  | 1 | WI-0005
A4. WG Actions:
REFERENCE | WHAT | WHO | STATUS
A-MAS-2013-0001
A5. WG Decisions:
REFERENCE | WHAT
D-WG5-0001 | Future Ordinary Conference Calls - Tuesday, July 2, 1:00-3:00 pm UTC (Abstraction/Semantics) - Tuesday, July 9, 1:00-3:00pm UTC (Abstraction/Semantics) - Friday, July 19, 1:00-3:00 pm UTC (Management) - Friday, July 26, 1:00-3:00 pm UTC (Management)
A6. WG Information to Plenary (AoB):
<Text>
<Text>
<Text>
Part B: List of all contributions to the WG meeting
Working area to be used during the WG meeting
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
WG5 session
oneM2M-MAS-2013-0052R01 | WG5 Agenda | Chair/Vice-Chair | Agenda | Noted
oneM2M-MAS-2013-0052R02 | WG5 Agenda | Chair/Vice-Chair | Agenda | Agreed
oneM2M-MAS-2013-0052R04 | WG5 Agenda | Chair/Vice-Chair | Agenda | Agreed
oneM2M-MAS-2013-0040 | Minutes-2013-06-04 | Secretary | Minutes | Agreed
oneM2M-TR-0006 | Study of Management Capability Enablement Technologies for Consideration by oneM2M | Jiaxin Yin (Huawei Technologies UK (ETSI)) | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-TR-0007 | Study_on_Abstraction_and_Semantics_Enablement-V0_2_0 | Jaeseung Song (NEC Europe Ltd.) | Draft | Agreed | TR-0007 | 0.2.0 |  | 1 | WI-0005
oneM2M-MAS-2013-0051 | Latest_ABS_TR_V0_2_0 | Jaeseung Song (NEC Europe Ltd.) | Draft | Agreed | TR-0007 | 0.2.0 |  | 1 | WI-0005
oneM2M-MAS-2013-0031R02 | BBF TR-069 Technology – Management TR Section 6 Gap Analysis | Timothy Carey - ALU | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0031R03 | BBF TR-069 Technology – Management TR Section 6 Gap Analysis | Timothy Carey - ALU | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004 | preagreed with editorial changes (add conclusion sentence in analysis section.)
oneM2M-MAS-2013-0042 | OMA DM requirements gap analysis | Huawei Technologies UK (ETSI);Huawei Technologies Co.,Ltd (CCSA) | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0043 | Introduction to OMA DM 2.0 | LG Electronics | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0048 | OMA DM LWM2M requirements gap analysis | LG Electronics | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0053 | OMA DM 2.0 Gap Analysis | LG Electronics | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0038R01 | Requirements for Abstraction and Semantics Enablement | NEC, Samsung SDS, InterDigital, LG Electronics | Draft | Withdrawn | TS-0002 | 0.3.0 |  | 1 | WI-0001
oneM2M-REQ-2013-0351 | Semantics requirments and definitions | InterDigital | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001 | To be harmonized with other contributions and comments received.Revision is to be discussion in WG1-WG5 joint sessoin.
oneM2M-MAS-2013-0041 | Opened ABS related requirements | NEC, Samsung SDS, InterDigital, LG Electronics | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001 | To be harmonized with other contributions and comments received. Only ABS-X1 is kept for further update. ABS-X2,ABS-X3 is to be merged with REQ-0351.Revision is to be discussion in WG1-WG5 joint sessoin.
oneM2M-MAS-2013-0047 | Home_Environment_Monitoring_Service_using_semantic_mash-up | Modacom | Draft | Noted | TR-0007 | 0.2.0 |  | 1 | WI-0005 | R01 is forseen in closing session on Thursday.
oneM2M-MAS-2013-0044R01 | Application Structure for Smart Metering Service | JNU, KCA(TTA) | Draft | Postponed | [5 empty] | postponed to WG5 ordinary conf-calls
oneM2M-MAS-2013-0045 | Pricing Policy of Demand Response of Home Appliances in Smart Grid | JNU, KCA(TTA) | Draft | Postponed | [5 empty] | postponed to WG5 ordinary conf-calls
oneM2M-MAS-2013-0056 | Proposal of a cloud-based presentation and application framework for developing and deploying Web of Things Applications | KAIST, KCA(TTA) | Draft | Postponed | [5 empty] | postponed to WG5 ordinary conf-calls
oneM2M-MAS-2013-0042R02 | OMA DM requirements gap analysis | Huawei Technologies UK (ETSI);Huawei Technologies Co.,Ltd (CCSA) | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0031R04 | BBF TR-069 Technology – Management TR Section 6 Gap Analysis | Timothy Carey - ALU | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0043R01 | Introduction to OMA DM 2.0 | LG Electronics | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0043R02 | Introduction to OMA DM 2.0 | LG Electronics | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004 | with clarification of DM 2.0 standard objects.
oneM2M-MAS-2013-0048R01 | OMA DM LWM2M requirements gap analysis | LG Electronics | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0053R01 | OMA DM 2.0 Gap Analysis | LG Electronics | Draft | Agreed | TR-0006 | 0.1.2 |  | 1 | WI-0004
oneM2M-MAS-2013-0047R01 | Home_Environment_Monitoring_Service_using_semantic_mash-up | Modacom | Draft | Noted | TR-0007 | 0.2.0 |  | 1 | WI-0005
oneM2M-MAS-2013-0047R02 | Home_Environment_Monitoring_Service_using_semantic_mash-up | Modacom | Draft | Agreed | TR-0007 | 0.2.0 |  | 1 | WI-0005
oneM2M-WI-0004 | Management_Capability_Enablement_Technologies | RAPPORTUER | WI |  | TR-0006 | 0.1.2 |  | 1 | WI-0004 | Decision: Change Control/Freeze Date is set to TP#7. Approval by TP#8. WG5 should fininsh section 7 by TP#6. A corresponding TP contribution will be submitted to closing plenary.
oneM2M-MAS-2013-0057 | Progressing the Work on the Management TR-0006 | Timothy Carey - ALU | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | 2 interim meetings are reserved for Management TR. ALU will start with the deployment secenarios and generalized management architecture. Further mapping to different technologies will be based on the generalized management architecture
oneM2M-WI-0005 | Abstraction & Semantics Capability Enablement | RAPPORTUER | WI |  | TR-0007 | 0.2.0 |  | 1 | WI-0005 | Abstraciton/Semantics TR is lacking of contribution and predicted to be finished at least 2-TP later than the Management TR.
oneM2M-MAS-2013-0050R01 | Revised-WI-0005-Abstraction_&_Semantics_Capability_Enablement | NEC | Draft | Noted | TR-0007 | 0.2.0 |  | 1 | WI-0005 | revision will be made for TP closing session.
WG1-WG5 joint session (FOR INFORMATION ONLY. See normative results in WG1 report)
oneM2M-REQ-2013-0173R04 | Input Requirements for M2M Service Provisioning for Equipment with Built-in M2M Device | China Telecom, Huawei | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001
oneM2M-REQ-2013-0173R05 | Input Requirements for M2M Service Provisioning for Equipment with Built-in M2M Device | China Telecom, Huawei | Draft | Agreed | TS-0002 | 0.3.0 |  | 1 | WI-0001 | ONLY HLR-A （with modification） is agreed.
oneM2M-REQ-2013-0313R01 | Input requirements on management | Huawei Technologies UK (ETSI);Huawei Technologies Co.,Ltd (CCSA) | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001
oneM2M-REQ-2013-0313R02 | Input requirements on management | Huawei Technologies UK (ETSI);Huawei Technologies Co.,Ltd (CCSA) | Draft | Agreed | TS-0002 | 0.3.0 |  | 1 | WI-0001 | All requirements except for MGR-X3 are agreed.
oneM2M-REQ-2013-0375 | Input_requirements_on_management | Huawei. | Draft | Agreed | TS-0002 | 0.3.0 |  | 1 | WI-0001
oneM2M-REQ-2013-0345 | Consolidated ABS-related requirements from WG5 | NEC, Samsung SDS, InterDigital, LG Electronics | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001
oneM2M-REQ-2013-0345R01 | Consolidated ABS-related requirements from WG5 | NEC, Samsung SDS, InterDigital, LG Electronics | Draft | Agreed | TS-0002 | 0.3.0 |  | 1 | WI-0001 | move definitions to another CR contributions for USE CASE TR. Remove ABS-01.
oneM2M-REQ-2013-0351R02 | Semantics requirments and definitions | InterDigital | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001
oneM2M-REQ-2013-0351R03 | Semantics requirments and definitions | InterDigital | Draft | Agreed | TS-0002 | 0.3.0 |  | 1 | WI-0001 | semantics inference is removed.Definitions shall go to definition TR CR
oneM2M-MAS-2013-0041R01 | Opened ABS related requirements | NEC, Samsung SDS, InterDigital, LG Electronics | Draft | Noted | TS-0002 | 0.3.0 |  | 1 | WI-0001 | lack of originator's clarification on the meaning of semantics usage for "management operations"
WG2-WG5 joint session (FOR INFORMATION ONLY. See normative results in WG2 report)
oneM2M-MAS-2013-0046 | Device Management Deployments In oneM2m | Timothy Carey, ALU | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | Agreed in principle to document the content into TR-0006
oneM2M-MAS-2013-0049 | Device Management Deployments In oneM2m | Sierra Wireless | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | Agreed in principle to document the content into TR-0006
oneM2M-MAS-2013-0033R01 | Proposal for a Device Management Generalized Architecture | Timothy Carey - ALU | Draft | Noted | TR-0006 | 0.1.2 |  | 1 | WI-0004 | Agreed in principle to document a generalized architecture for management in TR-0006 section 7.

## Tabelle2
oneM2M IPR STATEMENT
Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by all provisions of IPR policy of the admitting Partner Type 1 and permission that all communications and statements, oral or written, or other information disclosed or presented, and any translation or derivative thereof, may without compensation, and to the extent such participant or attendee may legally and freely grant such copyright rights, be distributed, published, and posted on oneM2M’s web site, in whole or in part, on a non-exclusive basis by oneM2M or oneM2M Partners Type 1 or their licensees or assignees, or as oneM2M SC directs.