## Tabelle1
WG4 Report on SEC#8.0 meeting sessions to oneM2M TP#8
Part A: Executive Summary for Plenary
Some progress on TR-0008 and TS-0003
Many issues identifiedduring discussions, leading to 7 new Action Items assigned
Access Control and Authorization: Agreement on terminology and notions, discussions on models to formalize
Proposal developed to progress SEC CSF description and improve efficiency in future meetings
A1. Documents NOT AGREED in WG (to be presented to Plenary for discussion).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A2. Documents NOT AGREED in WG (noted / postponed / not treated etc).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-SEC-2013-0081R01 | Access Control Framework Thoughts | Phil Hawkes, Qualcomm |  | noted
oneM2M-SEC-2013-0077 | Authorization Procedure | FUJITSU |  | noted | TS-0001
oneM2M-SEC-2013-0076 | oneM2M Access Control System Discussion | CATT | Draft | noted
oneM2M-SEC-2013-0069 | security service resource | FUJITSU |  | noted | TS-0001 |  |  |  |  | Consider revision in TS-0003
oneM2M-SEC-2013-0068 | Access Control Model and associated Terminology | OBERTHUR Technologies |  | noted | [5 empty] | Further contrib to TR-0004 needed
oneM2M-SEC-2013-0067R01 | Access Control Status Report | OBERTHUR Technologies |  | noted | [5 empty] | Priorities to be discussed further
oneM2M-SEC-2013-0052R01 | Post-Provisioning Phases | Phil Hawkes, Qualcomm |  | noted | [5 empty] | Further discuss in teleconference
oneM2M-ARC-2013-0531R01 | Service Bootstrapping | NEC, KDDI |  | noted | TS-0001 |  |  |  |  | Revised to SEC-0080
oneM2M-ARC-2013-0585 | Access Control for CREATE operations | LG Electronics |  | noted | [5 empty] | Contribute in WI-0007
oneM2M-ARC-2013-0543 | App-Inst-ID and CSE-ID assignment | LG Electronics |  | noted | [5 empty] | Needs further discussions, see action
oneM2M-SEC-2013-0080 | Service Bootstrapping Procedures | NEC, KDDI | Draft | withdrawn | TR-0008
oneM2M-ARC-2013-0531R01 | Service Bootstrapping | NEC, KDDI |  | withdrawn | TS-0001 |  |  |  |  | Revised to SEC-0080
oneM2M-SEC-2013-0064R01 | Security CSF High Level Architecture Figure | CATT, CATR |  | noted | TS-0003
oneM2M-SEC-2013-0078 | Security Architecture Diagram | FUJITSU | Draft | noted | TS-0003
oneM2M-SEC-2013-0084 | Considerations regarding handling of tokens | Fujitsu |  | noted | [5 empty] | Options to be compared
oneM2M-SEC-2013-0083 | Way forward on Access Control | OBERTHUR Technologies |  | noted | [5 empty] | Revision to be presented to WG2
A3. Documents AGREED in WG
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-REQ-2013-0425R01 | Further Security terminology | Gemalto |  | agreed to go to WG1 | TR-0004 |  |  |  |  | R02 agreed by WG1
oneM2M-REQ-2013-0426R03 | Notions for access control and authorization | Gemalto |  | agreed to go to WG1 | TR-0005 |  |  |  |  | Agreed by WG1
oneM2M-SEC-2013-0075R01 | Clean up Security TS | Giesecke & Devrient |  | agreed | TS-0003
oneM2M-SEC-2013-0071R02 | Introductory Section for Access Control Managemnt | OBERTHUR Technologies |  | agreed | TR-0008
oneM2M-SEC-2013-0066R01 | Bootstrapping Definition | LG Electronics |  | agreed | TS-0003
oneM2M-SEC-2013-0070R03 | GBA framework | Gemalto | Draft | agreed | TS-0003
oneM2M-SEC-2013-0082R01 | GBA Description for TR-0008 | Gemalto | Draft | agreed | TR-0008
oneM2M-SEC-2013-0072R03 | Security Requirements for Token based RBAC | Alcatel-Lucent | Draft | agreed | TR-0008
oneM2M-SEC-2013-0073R04 | Security CSF Architecture Figure | Giesecke & Devrient, Oberthur Technologies, CATT | Draft | agreed | TS-0003
A4. WG Actions:
REFERENCE | WHAT | WHO | STATUS
A-WG4-TP7-003 | Clarify preferred framework to describe security functionalitiess and align with other CSFs especially Session Establishment | Interested companies to contribute | OPEN
A-WG4-TP8-001 | Complete the work on PKI-based and GBA-based bootstrapping specifications | Lead Qualcomm, Gemalto | OPEN
A-WG4-TP8-005 | Specify the hop-by-hop (node to adjacent node) security | Lead Qualcomm | OPEN
A-WG4-TP8-002 | Develop a vision towards end-to-end security | Lead Gemalto | OPEN
A-WG4-TP8-003 | Specify credential management (high Priority) | Lead SeongYoon Kim, LG Electronics + Phil Hawkes, Qualcomm | OPEN
A-WG4-TP8-004 | Specify the interaction of security with the initial registration call flow (the later being the responsibility of ARC) | Lead Suresh Nair + Colin Blanchard | OPEN
A-WG4-TP8-006 | Specify token interactions with authentication | Lead Dragan Vujcic, Oberthur Technologies | OPEN
A-WG4-TP8-007 | Clarify the authentication of Aes, CSEs and Nodes: For example, is an AE authenticated to the CSE in the same node? | Lead SeongYoon Kim, LG Electronics | OPEN
A5. WG Decisions:
REFERENCE | WHAT
D-WG4-001
A6. WG Information to Plenary (AoB):
Part B: List of all contributions to the WG4 SEC#8.0 meeting
Working area to be used during the WG meeting; Only latest versions may be reflected
For Security related contributions allocated to other WGs, see the respective WG report
WG4 SEC#8.0 meeting contributions
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-SEC-2013-0082R01 | GBA Description for TR-0008 | Gemalto | Draft | agreed | TR-0008
oneM2M-SEC-2013-0082 | GBA Description for TR-0008 | Gemalto | Draft | noted | TR-0008
oneM2M-SEC-2013-0083 | Way forward on Access Control | OBERTHUR Technologies |  | noted | [5 empty] | Revision to be presented to WG2
oneM2M-SEC-2013-0081R01 | Access Control Framework Thoughts | Phil Hawkes, Qualcomm |  | noted
oneM2M-SEC-2013-0081 | Access Control Framework Thoughts | Phil Hawkes, Qualcomm |  | noted
oneM2M-SEC-2013-0080 | Service Bootstrapping Procedures | NEC, KDDI | Draft | withdrawn | TR-0008
oneM2M-SEC-2013-0079R01 | Agenda AdHoc AR_ACL_RBAC 2013_12_10 | OBERTHUR Technologies | Draft | noted
oneM2M-SEC-2013-0079 | Agenda AdHoc AR_ACL_RBAC 2013_12_10 | OBERTHUR Technologies | Draft | noted
oneM2M-SEC-2013-0078 | Security Architecture Diagram | FUJITSU | Draft | noted | TS-0003
oneM2M-SEC-2013-0077 | Authorization Procedure | FUJITSU |  | noted | TS-0001
oneM2M-SEC-2013-0076 | oneM2M Access Control System Discussion | CATT | Draft | noted
oneM2M-SEC-2013-0075R01 | Clean up Security TS | Giesecke & Devrient |  | agreed | TS-0003
oneM2M-SEC-2013-0075 | Clean up Security TS | Giesecke & Devrient |  | noted | TS-0003
oneM2M-SEC-2013-0074R05 | SEC8.0 Agenda | WG Chair (Gemalto) |  | agreed
oneM2M-SEC-2013-0074R04 | SEC8.0 Agenda | WG Chair (Gemalto) |  | agreed
oneM2M-SEC-2013-0074R03 | SEC8.0 Agenda | WG Chair (Gemalto) |  | agreed
oneM2M-SEC-2013-0074R02 | SEC8.0 Agenda | WG Chair (Gemalto) |  | noted
oneM2M-SEC-2013-0074R01 | SEC8.0 Agenda | WG Chair (Gemalto) |  | noted
oneM2M-SEC-2013-0074 | SEC8.0 Agenda | WG Chair (Gemalto) |  | noted
oneM2M-SEC-2013-0073R04 | Security CSF Architecture Figure | Giesecke & Devrient, Oberthur Technologies, CATT | Draft | agreed | TS-0003
oneM2M-SEC-2013-0073R03 | Security CSF Architecture Figure | Giesecke & Devrient, Oberthur Technologies, CATT | Draft | noted | TS-0003
oneM2M-SEC-2013-0073R02 | Security CSF Architecture Figure | Giesecke & Devrient, Oberthur Technologies, CATT | Draft | noted | TS-0003
oneM2M-SEC-2013-0073R01 | Security CSF Architecture Figure | Giesecke & Devrient, Oberthur Technologies |  | noted | TS-0003
oneM2M-SEC-2013-0073 | Security CSF Architecture Figure | Giesecke & Devrient |  | noted | TS-0003
oneM2M-SEC-2013-0072R03 | Security Requirements for Token based RBAC | Alcatel-Lucent | Draft | agreed | TR-0008
oneM2M-SEC-2013-0072R02 | Security Requirements for Token based RBAC | Alcatel-Lucent | Draft | noted | TR-0008
oneM2M-SEC-2013-0072R01 | Security Requirements for OAuth based RBAC | Alcatel-Lucent |  | noted | TR-0008
oneM2M-SEC-2013-0072 | Security Requirements for OAuth based RBAC | Alcatel-Lucent |  | noted | TS-0003
oneM2M-SEC-2013-0071R02 | Introductory Section for Access Control Managemnt | OBERTHUR Technologies |  | agreed | TR-0008
oneM2M-SEC-2013-0071R01 | Introductory Section for Access Control Managemnt | OBERTHUR Technologies |  | noted | TR-0008
oneM2M-SEC-2013-0071 | Introductory Section for Access Control Managemnt | OBERTHUR Technologies |  | noted | TR-0008
oneM2M-SEC-2013-0070R03 | GBA framework | Gemalto | Draft | agreed | TS-0003
oneM2M-SEC-2013-0070R02 | GBA framework | Gemalto | Draft | noted | TS-0003
oneM2M-SEC-2013-0070R01 | GBA framework | Gemalto |  | noted | TS-0003
oneM2M-SEC-2013-0070 | GBA framework | Gemalto |  | noted | TS-0003
oneM2M-SEC-2013-0069 | security service resource | FUJITSU |  | noted | TS-0001 |  |  |  |  | Consider revision in TS-0003
oneM2M-SEC-2013-0068 | Access Control Model and associated Terminology | OBERTHUR Technologies |  | noted | [5 empty] | Further contrib to TR-0004 needed
oneM2M-SEC-2013-0067R01 | Access Control Status Report | OBERTHUR Technologies |  | noted | [5 empty] | Priorities to be discussed further
oneM2M-SEC-2013-0067 | Access Control Status Report | OBERTHUR Technologies |  | noted
oneM2M-SEC-2013-0066R01 | Bootstrapping Definition | LG Electronics |  | agreed | TS-0003
oneM2M-SEC-2013-0066 | Bootstrapping Definition | LG Electronics |  | noted | TS-0003
oneM2M-SEC-2013-0065 | Access Control Mechanism for User | LG Electronics | Draft | noted
oneM2M-SEC-2013-0064R01 | Security CSF High Level Architecture Figure | CATT, CATR |  | noted | TS-0003
oneM2M-SEC-2013-0064 | Security CSF High Level Architecture Figure | CATT, CATR |  | noted | TS-0003
oneM2M-SEC-2013-0052R01 | Post-Provisioning Phases | Phil Hawkes, Qualcomm |  | noted | [5 empty] | Further discuss in teleconference
oneM2M-REQ-2013-0425R01 | Further Security terminology | Gemalto |  | agreed to go to WG1 | TR-0004 |  |  |  |  | R02 agreed by WG1
oneM2M-REQ-2013-0426R03 | Notions for access control and authorization | Gemalto |  | agreed to go to WG1 | TR-0005 |  |  |  |  | Agreed by WG1
oneM2M-ARC-2013-0531R01 | Service Bootstrapping | NEC, KDDI |  | withdrawn | TS-0001 |  |  |  |  | Revised to SEC-0080
oneM2M-ARC-2013-0585 | Access Control for CREATE operations | LG Electronics |  | noted | [5 empty] | Contribute in WI-0007
oneM2M-ARC-2013-0543 | App-Inst-ID and CSE-ID assignment | LG Electronics |  | noted | [5 empty] | Needs further discussions, see action
oneM2M-SEC-2013-0084 | Considerations regarding handling of tokens | Fujitsu |  | noted | [5 empty] | Options to be compared

## Tabelle2
oneM2M IPR STATEMENT
Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by all provisions of IPR policy of the admitting Partner Type 1 and permission that all communications and statements, oral or written, or other information disclosed or presented, and any translation or derivative thereof, may without compensation, and to the extent such participant or attendee may legally and freely grant such copyright rights, be distributed, published, and posted on oneM2M’s web site, in whole or in part, on a non-exclusive basis by oneM2M or oneM2M Partners Type 1 or their licensees or assignees, or as oneM2M SC directs.