## Tabelle1
Report at oneM2M TP#7 & Interim report from WG-3
Part A: Executive Summary for Plenary
Progress on both Work-Items WI-0008 TR-0009 & WI-0009 TS-0004
WI-0008 TR-0009 reasonable progress 33% complete & WI-0009 TS-0004 5%; discussion to restucture into several Work-items/deliverables
two new Binding Work-items working group consent on proceeding on HTTP & MQTT
Feasible in October TP.9 for shared room with WG-2 to avoid overlap.
Planning for next Meeting(s)
Proposed Interim meetings between TP#8 and TP#9 (Febuary 09) - Tuesdays
· PRO8.1 Tuesday – 1:00 pm UTC, January 07 (World on standard time)
· PRO8.2 Tuesday – 1:00 pm UTC, January 14 (World on standard time)
· PRO8.3 Tuesday – 1:00 pm UTC, January 21 (World on standard time)
· PRO8.4 Tuesday – 1:00 pm UTC, January 28 (World on standard time)
Face to Face
· PRO9.0 Week 17-21 February 2014; Mobile Alabama
A1. Documents NOT AGREED in WG (to be presented to Plenary for discussion).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-PRO-2013-0098R01 | Draft WI for MQTT protocol binding | IBM |  | Agreed to be revised & presented in Plenary | TS-000x | V0.0.0 |  |  | WI-000x | Some discussion about the relation to the Architecture
A2. Documents NOT AGREED in WG (noted / postponed / not treated etc).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-PRO-2013-0095R01 | Delivery-related_primitives | QUALCOMM Japan Inc. |  | postponed to PRO8.1 | TS-0004 | V0.1.2 |  |  | WI-0009
oneM2M-PRO-2013-0094R01 | Attributes_for_delivery_resource_type | QUALCOMM Japan Inc. |  | postponed to PRO8.1 | TS-0004 | V0.1.2 |  |  | WI-0009
oneM2M-PRO-2013-0093R01 | Attributes_for_request_resource_type | QUALCOMM Japan Inc. |  | postponed to PRO8.1 | TS-0004 | V0.1.2 |  |  | WI-0009
A3. Documents AGREED in WG
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-PRO-2013-0092R01 | CR Common Data Type | FUJITSU |  | agreed | TS-0004 | V0.1.2 |  |  | WI-0009 | More description is needed on the references to common data types & additional complex & informational data types in the protocol, and the precidence in case of errors & inconsistencies
oneM2M-PRO-2013-0091R02 | RESTful Network APIs | LGE, AT&T |  | agreed | TR-0009 | V0.3.3 |  |  | WI-0008 | Maintenance of oneAPI of GSMA is by OMA
oneM2M-PRO-2013-0087 | DDS Update | Cisco Systems |  | Agreed | TR-0009 | V0.3.3 |  |  | WI-0008
oneM2M-PRO-2013-0084R01 | UPnP Cloud | Cisco Systems |  | Agreed | TR-0009 | V0.3.3 |  |  | WI-0008 | Some discussion about the relation to the Architecture
oneM2M-PRO-2013-0097R01 | Drafting new WI for HTTP Protocol Binding | FUJITSU, LGE |  | Agreed to go to plenary | TS-000x | V0.0.0 |  |  | WI-000x
oneM2M-PRO-2013-0098R01 | Draft WI for MQTT protocol binding | IBM |  | Agreed to be revised & presented in Plenary | TS-000x | V0.0.0 |  |  | WI-000x | Some discussion about the relation to the Architecture
A4. WG Actions:
REFERENCE | WHAT | WHO | STATUS
A-PRO-2013-0002
A5. WG Decisions: See agreed Documents
REFERENCE | WHAT
D-WG<no.>
D-WG<no.>
A6. WG Information to Plenary (AoB):
<Text>
<Text>
Part B: List of all contributions to the WG meeting
Working area to be used during the WG meeting
WG3 PRO#3 meeting contributions
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-PRO-2013-0096R02 | WG3 Agenda | WG3 Chairman |  | Agreed |  |  |  |  | n/a
oneM2M-PRO-2013-0089 | Minutes-2013-11-27 | Secretary |  | Agreed |  |  |  |  | n/a
oneM2M-PRO-2013-0095 | Delivery-related_primitives | QUALCOMM Japan Inc. |  | Noted | TS-0004 | V0.1.2 |  |  | WI-0009 | needs work; may be an intro to the primatives currentlt too early to use & too much duplication with Stage 2.
oneM2M-PRO-2013-0095R01 | Delivery-related_primitives | QUALCOMM Japan Inc. |  | postponed to PRO8.1 | TS-0004 | V0.1.2 |  |  | WI-0009
oneM2M-PRO-2013-0094 | Attributes_for_delivery_resource_type | QUALCOMM Japan Inc. |  | Noted | TS-0004 | V0.1.2 |  |  | WI-0009 | Needs revision off line much duplication with Sage 2
oneM2M-PRO-2013-0094R01 | Attributes_for_delivery_resource_type | QUALCOMM Japan Inc. |  | postponed to PRO8.1 | TS-0004 | V0.1.2 |  |  | WI-0009
oneM2M-PRO-2013-0093 | Attributes_for_request_resource_type | QUALCOMM Japan Inc. |  | Noted | TS-0004 | V0.1.2 |  |  | WI-0009 | Corrections required Extra Mnc' coluns to Table x-1; Fixes to Table x-2; too early to decide to copy from WG2.
oneM2M-PRO-2013-0093R01 | Attributes_for_request_resource_type | QUALCOMM Japan Inc. |  | postponed to PRO8.1 | TS-0004 | V0.1.2 |  |  | WI-0009
oneM2M-PRO-2013-0092 | CR Common Data Type | FUJITSU |  | Noted | TS-0004 | V0.1.2 |  |  | WI-0009 | Needs revision off-line much duplication with Sage 2; lack of clarity where in calls out to xml scripts
oneM2M-PRO-2013-0092R01 | CR Common Data Type | FUJITSU |  | agreed | TS-0004 | V0.1.2 |  |  | WI-0009 | More description is needed on the references to common data types & additional complex & informational data types in the protocol, and the precidence in case of errors & inconsistencies
oneM2M-PRO-2013-0091R1 | RESTful Network APIs | LGE, AT&T |  | Noted | TR-0009 | V0.3.3 |  |  | WI-0008 | Needs refercences & editorial numbering.
oneM2M-PRO-2013-0091R02 | RESTful Network APIs | LGE, AT&T |  | agreed | TR-0009 | V0.3.3 |  |  | WI-0008 | Maintenance of oneAPI of GSMA is by OMA
oneM2M-PRO-2013-0087 | DDS Update | Cisco Systems |  | Agreed | TR-0009 | V0.3.3 |  |  | WI-0008
oneM2M-PRO-2013-0084R01 | UPnP Cloud | Cisco Systems |  | Agreed | TR-0009 | V0.3.3 |  |  | WI-0008 | Some discussion about the relation to the Architecture
oneM2M-PRO-2013-0097 | Drafting new WI for HTTP Protocol Binding | FUJITSU, LGE |  | Revised | TS-000x | V0.0.0 |  |  | WI-000x | Some discussion about the exclusive list of bullest points, to be revies to be nor exclusive.
oneM2M-PRO-2013-0097R01 | Drafting new WI for HTTP Protocol Binding | FUJITSU, LGE |  | Agreed to go to plenary | TS-000x | V0.0.0 |  |  | WI-000x
oneM2M-PRO-2013-0098 | Draft WI for MQTT protocol binding | IBM |  | Revised | TS-000x | V0.0.0 |  |  | WI-0008 | Some discussion about the need to study options - separate to have a analysis TR on lagacy & a Binding TS
oneM2M-PRO-2013-0098R01 | Draft WI for MQTT protocol binding | IBM |  | Agreed to be revised & presented in Plenary | TS-000x | V0.0.0 |  |  | WI-000x | Some discussion about the relation to the Architecture
oneM2M-PRO-2013-0099 | Output_Draft_TR-0009_Protocol_Analysis_v034 | Co-Rapporteurs - Richard Brennan - Telxxis, Phil Jacobs - Cisco |  | Agreed for 1 week review as output baseline | TR-0009 | V0.3.4 |  |  | WI-0008

## Tabelle2
oneM2M IPR STATEMENT
Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by all provisions of IPR policy of the admitting Partner Type 1 and permission that all communications and statements, oral or written, or other information disclosed or presented, and any translation or derivative thereof, may without compensation, and to the extent such participant or attendee may legally and freely grant such copyright rights, be distributed, published, and posted on oneM2M’s web site, in whole or in part, on a non-exclusive basis by oneM2M or oneM2M Partners Type 1 or their licensees or assignees, or as oneM2M SC directs.