## Tabelle1
Report at oneM2M TP#9 & Interim report from WG-3
Part A: Executive Summary for Plenary
Progress on 4 of 5 Work-Items WI-0008 TR-00009, WI-0009 TS-0004, WI-0012 TS-0008 & WI-0014 TS-0010
WI-0008 TR-0009 reasonable progress 60% complete & WI-0009 TS-0004 20%
Bindngs WI-0012 TS-0008 CoAP 10% complete; WI-0013 TS-0009 HTTP 10% complete; MQTT WI-0014 TS-0010 30%
Feasible in April TP.10 for shared room with WG-2 to avoid overlap, if the Stage 3 is to be complete in August 2014 attention must shift to WG3 at TP.10.
Planning for next Meeting(s)
Conference Calls
· PRO9.1 Tuesday – 1:00 pm UTC, March 04 (World on standard time)
North America on daylight saving time after 9 March
· PRO9.2 Tuesday – 1:00 pm UTC, March 11
(NA on daylight saving time/RoW on Standard time)
· PRO9.3 Tuesday – 1:00 pm UTC, March 18
(NA on daylight saving time/RoW on Standard time)
· PRO9.4 Tuesday – 1:00 pm UTC, March 25
(NA on daylight saving time/RoW on Standard time)
Europe on Summer time after 30 March
Face to Face
· PRO10.0 Week 07-11 April 2014, Berlin, Germany.
A1. Documents NOT AGREED in WG (to be presented to Plenary for discussion).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A2. Documents NOT AGREED in WG (noted / postponed / not treated etc).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
PRO-2014-0023R02 | CoAP Protocol Binding | Hitachi(China)R&D Corp. |  | Postponed | TS-0008 | V0.1.0 |  |  | WI-0012
A3. Documents AGREED in WG
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-PRO-2013-0026R01 | Minutes-2014-01-28 | Secretary |  | Agreed |  |  |  |  | n/a
PRO-2014-0028 | Draft CoreProt-TS V.0.2.1 | Core Protocol TS Rapportuer |  | agreed as input baseline | TS-0004 | V0.2.0 |  |  | WI-0009
version 0.2.2 to be output |  |  |  | Before PRO9.1 | TS-0004 | V0.2.1 |  |  | WI-0009
PRO-2014-0031R01 | Proposed changes against TS-0004 v0.2.1 | Qualcomm Incorporated |  | Agreed | TS-0004 | V0.2.1 |  |  | WI-0009
PRO-2014-0033R01 | Conversion Rule | FUJITSU |  | Agreed | TS-0004 | V0.2.1 |  |  | WI-0009
PRO-2014-0030 | Bluetooth revisions | LM Ericsson |  | Agreed | TR-0009 | V0.4.0 |  |  | WI-0008
Version 0.4.1 to be frozen |  |  |  |  | TR-0009 | V0.4.1 |  |  | WI-0008
PRO-2014-0109 | Version 0.4.1 to be frozen | Rapporteur |  | agreed & Frozen | TR-0009 | V0.4.1 |  |  | WI00008
PRO-2014-0107R01 | HTTPbbiding TORs | FUJITSU |  | Agreed | TS-0009 | V0,1.0 |  |  | WI-0013
PRO-2014-0035R03 | MQTT protocol binding TS baseline draft | MQTT Protocol TS Rapporteur |  | Agreed | TS-0010 | V0.0.0 |  |  | WI-0014
PRO-2014-0108R01 | MQTT protocol binding Clause 5 & 6 | IBM |  | Agreed | TS-0010 | V0.1.0 |  |  | WI-0014
A4. WG Actions:
REFERENCE | WHAT | WHO | STATUS
A-PRO-2013-0002
A5. WG Decisions: See agreed Documents
REFERENCE | WHAT
D-WG<no.>
D-WG<no.>
A6. WG Information to Plenary (AoB):
<Text>
<Text>
Part B: List of all contributions to the WG meeting
Working area to be used during the WG meeting
WG3 PRO#3 meeting contributions
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
oneM2M-PRO-2013-0036R02 | WG3 Agenda | WG3 Chairman |  | Agreed |  |  |  |  | n/a
oneM2M-PRO-2013-0026R01 | Minutes-2014-01-28 | Secretary |  | Agreed |  |  |  |  | n/a
PRO-2014-0028 | Draft CoreProt-TS V.0.2.1 | Core Protocol TS Rapportuer |  | agreed as input baseline | TS-0004 | V0.2.0 |  |  | WI-0009
version 0.2.2 to be output |  |  |  | Before PRO9.1 | TS-0004 | V0.2.1 |  |  | WI-0009
PRO-2014-0031R01 | Proposed changes against TS-0004 v0.2.1 | Qualcomm Incorporated |  | agreed | TS-0004 | V0.2.1 |  |  | WI-0009
PRO-2014-0033 | Conversion Rule | FUJITSU |  | noted | TS-0004 | V0.2.1 |  |  | WI-0009
PRO-2014-0033R01 | Conversion Rule | FUJITSU |  | Agreed | TS-0004 | V0.2.1 |  |  | WI-0009
PRO-2014-0030 | Bluetooth revisions | LM Ericsson |  | Agreed | TR-0009 | V0.4.0 |  |  | WI-0008
Version 0.4.1 to be frozen |  |  |  | By end on Meeting | TR-0009 | V0.4.1 |  |  | WI-0008
PRO-2014-0109 | Version 0.4.1 to be frozen | Rapporteur |  | Agreed | TR-0009 | V0.4.1 |  |  | WI00008
PRO-2014-0023R01 | CoAP Protocol Binding | Hitachi(China)R&D Corp. |  | noted | TS-0008 | V0.1.0 |  |  | WI-0012 | need alignment of stucture with TS-0010 & not repreat CoAP message specification
PRO-2014-0023R02 | CoAP Protocol Binding | Hitachi(China)R&D Corp. |  | Postponed | TS-0008 | V0.1.0 |  |  | WI-0012
PRO-2014-0107 | HTTPbbiding TORs | FUJITSU |  | noted | TS-0009 | V0,1.0 |  |  | WI-0013
PRO-2014-0107R01 | HTTPbbiding TORs | FUJITSU |  | Agreed | TS-0009 | V0,1.0 |  |  | WI-0013
PRO-2014-0035R01 | MQTT protocol binding TS baseline draft | MQTT Protocol TS Rapporteur |  | noted | TS-0010 | V0.0.0 |  |  | WI-0014 | Skeletom & Clause 5.1 agreed
PRO-2014-0035R02 | MQTT protocol binding TS baseline draft | MQTT Protocol TS Rapporteur |  | noted | TS-0010 | V0.0.0 |  |  | WI-0014
PRO-2014-0035R03 | MQTT protocol binding TS baseline draft | MQTT Protocol TS Rapporteur |  | Agreed | TS-0010 | V0.0.0 |  |  | WI-0014
PRO-2014-0108 | MQTT protocol binding Clause 5 & 6 | IBM |  | noted | TS-0010 | V0.1.0 |  |  | WI-0014
PRO-2014-0108R01 | MQTT protocol binding Clause 5 & 6 | IBM |  | Agreed | TS-0010 | V0.1.0 |  |  | WI-0014

## Tabelle2
oneM2M IPR STATEMENT
Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by all provisions of IPR policy of the admitting Partner Type 1 and permission that all communications and statements, oral or written, or other information disclosed or presented, and any translation or derivative thereof, may without compensation, and to the extent such participant or attendee may legally and freely grant such copyright rights, be distributed, published, and posted on oneM2M’s web site, in whole or in part, on a non-exclusive basis by oneM2M or oneM2M Partners Type 1 or their licensees or assignees, or as oneM2M SC directs.