## Tabelle1
WG4 Report on SEC#9.0 meeting sessions to oneM2M TP#9
Part A: Executive Summary for Plenary
Freeze status reached for TR-0008 Security Analysis
Integration with Srchitecture (TS-0001) achieved
A1. Documents NOT AGREED in WG (to be presented to Plenary for discussion).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A2. Documents NOT AGREED in WG (noted / postponed / not treated etc).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
SEC-2014-0220R01 | Service Access Credential | FUJITSU | Draft | Noted
SEC-2014-0219 | authenticateAndRegisterCmd Resource and Procedures | Phil Hawkes, Qualcomm |  | Noted | [5 empty] | Teleconferences
SEC-2014-0217 | serviceUse resource | FUJITSU |  | Noted
SEC-2014-0058R01 | Security Association Establishment Procedure description | Gemalto |  | Noted | [5 empty] | Teleconferences
SEC-2014-0057 | Application Instantiation procedure description | Gemalto |  | Noted | [5 empty] | Teleconferences
SEC-2014-0056R01 | Remote provisioning procedure description | Gemalto |  | Noted | [5 empty] | Teleconferences
SEC-2014-0054 | Access Control Managemnt text proposal for ARC TS | OBERTHUR Technologies |  | Noted | [5 empty] | Integrated in 59R5
SEC-2014-0053 | Initial Attachemnt | OBERTHUR Technologies |  | Noted
SEC-2014-0052 | Initial Attach Re-Attach and Resource Access | OBERTHUR Technologies |  | Noted
SEC-2014-0051R02 | Briefing Flows for Security TS | Phil Hawkes, Qualcomm |  | Noted | [5 empty] | Teleconferences
SEC-2014-0050R02 | Attachment Flow Diagrams for Security TS | Phil Hawkes, Qualcomm |  | Noted | [5 empty] | Teleconferences
SEC-2014-0047R02 | Key hierarchy | Morpho Cards, Gemalto |  | Noted | [5 empty] | Teleconferences
SEC-2014-0046 | Authorization Procedure Description for Security TS | CATT |  | Noted | [5 empty] | Teleconferences
SEC-2014-0043 | access-key and access-token | FUJITSU | Draft | Noted
SEC-2014-0021R01 | Access Management Update | FUJITSU, LGE |  | Noted
A3. Documents AGREED in WG
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
SEC-2014-0218R01 | TR update | Giesecke & Devrient, Rapporteur |  | Agreed | TR-0008
SEC-2014-0216R03 | Security alignments on M2M Identifiers | Francois Ennesser (Gemalto) |  | Agreed by WG4 | TS-0001
SEC-2014-0059R11 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies | Draft | Agreed by WG4 | TS-0001
SEC-2014-0055R04 | MAS and MTF description | Gemalto, Oberthur Technologies |  | Agreed | TS-0003
SEC-2014-0049 | Completion of countermeasures | Giesecke & Devrient |  | Agreed | TR-0008
SEC-2014-0048R01 | editorial clean up TR0008 | Giesecke & Devrient, Gemalto |  | Agreed | TR-0008
SEC-2014-0045R02 | SEC CSF Authorization Description Update for Security TS | CATT |  | Agreed | TS-0003
SEC-2014-0044R03 | SEC CSF Architecture Figure Update for Security TS | CATT |  | Agreed | TS-0003
A4. WG Actions:
REFERENCE | WHAT | WHO | STATUS
A-WG4-TP7-003 | Clarify preferred framework to describe security functionalitiess and align with other CSFs especially Session Establishment | Interested companies to contribute | OPEN
A-WG4-TP8-001 | Complete the work on PKI-based and GBA-based bootstrapping specifications | Lead Qualcomm, Gemalto | OPEN
A-WG4-TP8-005 | Specify the hop-by-hop (node to adjacent node) security | Lead Qualcomm | OPEN
A-WG4-TP8-002 | Develop a vision towards end-to-end security | Lead Gemalto | OPEN
A-WG4-TP8-003 | Specify credential management (high Priority) | Lead SeongYoon Kim, LG Electronics + Phil Hawkes, Qualcomm | OPEN
A-WG4-TP8-006 | Specify token interactions with authentication | Lead Dragan Vujcic, Oberthur Technologies | OPEN
A5. WG Decisions:
REFERENCE | WHAT
D-WG4-001 | Put content of TR-0008 under Freeze and Change Control
A6. WG Information to Plenary (AoB):
Part B: List of all contributions to the WG4 SEC#8.0 meeting
Working area to be used during the WG meeting; Only latest versions may be reflected
For Security related contributions allocated to other WGs, see the respective WG report
WG4 SEC#9.0 meeting contributions
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
SEC-2014-0220R01 | Service Access Credential | FUJITSU | Draft | Noted
SEC-2014-0220 | Service Access Credential | FUJITSU |  | Noted
SEC-2014-0219 | authenticateAndRegisterCmd Resource and Procedures | Phil Hawkes, Qualcomm |  | Noted
SEC-2014-0218R01 | TR update | Giesecke & Devrient, Rapporteur |  | Agreed
SEC-2014-0218 | TR update | Giesecke & Devrient, Rapporteur |  | Noted
SEC-2014-0217 | serviceUse resource | FUJITSU |  | Noted
SEC-2014-0216R02 | Security alignments on M2M Identifiers | Francois Ennesser (Gemalto) | Draft | Noted, R3 agreed (cf WG2)
SEC-2014-0216R01 | Security alignments on M2M Identifiers | Francois Ennesser (Gemalto) |  | Agreed by WG4
SEC-2014-0216 | Security alignments on M2M Identifiers | Francois Ennesser (Gemalto) |  | Noted
SEC-2014-0059R10 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies | Draft | Noted, R11 agreed (cf WG2)
SEC-2014-0059R09 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Agreed
SEC-2014-0059R08 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0059R07 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0059R06 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0059R05 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0059R04 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0059R03 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0059R02 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0059R01 | High level description of Security Procedures for ARC TS | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0059 | High level description of Security Procedures for ARC TS | Gemalto |  | Noted
SEC-2014-0058R01 | Security Association Establishment Procedure description | Gemalto |  | Noted
SEC-2014-0058 | Security Association Establishment Procedure description | Gemalto |  | Noted
SEC-2014-0057 | Application Instantiation procedure description | Gemalto |  | Noted
SEC-2014-0056R01 | Remote provisioning procedure description | Gemalto |  | Noted
SEC-2014-0056 | Remote provisioning procedure description | Gemalto |  | Noted
SEC-2014-0055R04 | MAS and MTF description | Gemalto, Oberthur Technologies |  | Agreed
SEC-2014-0055R03 | MAS and MTF description | Gemalto, Oberthur Technologies | Draft | Noted
SEC-2014-0055R02 | MAS and MTF description | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0055R01 | MAS and MTF description | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0055 | MAS and MTF description | Gemalto, Oberthur Technologies |  | Noted
SEC-2014-0054 | Access Control Managemnt text proposal for ARC TS | OBERTHUR Technologies |  | Noted
SEC-2014-0053 | Initial Attachemnt | OBERTHUR Technologies |  | Noted
SEC-2014-0052 | Initial Attach Re-Attach and Resource Access | OBERTHUR Technologies |  | Noted
SEC-2014-0051R02 | Briefing Flows for Security TS | Phil Hawkes, Qualcomm |  | Noted
SEC-2014-0051R01 | Briefing Flows for Security TS | Phil Hawkes, Qualcomm |  | Noted
SEC-2014-0051 | Briefing Flows for Security TS | Phil Hawkes, Qualcomm |  | Noted
SEC-2014-0050R02 | Attachment Flow Diagrams for Security TS | Phil Hawkes, Qualcomm |  | Noted
SEC-2014-0050R01 | Attachment Flow Diagrams for Security TS | Phil Hawkes, Qualcomm |  | Noted
SEC-2014-0050 | Architecture Flow Diagrams for Security TS | Phil Hawkes, Qualcomm |  | Noted
SEC-2014-0049 | Completion of countermeasures | Giesecke & Devrient |  | Agreed
SEC-2014-0048R01 | editorial clean up TR0008 | Giesecke & Devrient, Gemalto |  | Agreed
SEC-2014-0048 | editorial clean up TR0008 | Giesecke & Devrient, Rapporteur |  | Noted
SEC-2014-0047R02 | Key hierarchy | Morpho Cards, Gemalto |  | Noted
SEC-2014-0047R01 | Key hierarchy | Morpho Cards, Gemalto |  | Noted
SEC-2014-0047 | Key hierarchy | Morpho Cards, Gemalto |  | Noted
SEC-2014-0046 | Authorization Procedure Description for Security TS | CATT |  | Noted
SEC-2014-0045R02 | SEC CSF Authorization Description Update for Security TS | CATT |  | Agreed
SEC-2014-0045R01 | SEC CSF Authorization Description Update for Security TS | CATT |  | Noted
SEC-2014-0045 | SEC CSF Authorization Description Update for Security TS | CATT |  | Noted
SEC-2014-0044R03 | SEC CSF Architecture Figure Update for Security TS | CATT |  | Agreed
SEC-2014-0044R02 | SEC CSF Architecture Figure Update for Security TS | CATT |  | Noted
SEC-2014-0044R01 | SEC CSF Architecture Figure Update for Security TS | CATT |  | Noted
SEC-2014-0044 | SEC CSF Architecture Figure Update for Security TS | CATT |  | Noted
SEC-2014-0043 | access-key and access-token | FUJITSU | Draft | Noted
SEC-2014-0021R01 | Access Management Update | FUJITSU, LGE |  | Noted
SEC-2014-0007R06 | SEC # 9 Agenda | WG Chair | Draft
SEC-2014-0007R05 | SEC # 9 Agenda | WG Chair | Draft
SEC-2014-0007R04 | SEC # 9 Agenda | WG Chair | Draft
SEC-2014-0007R03 | SEC # 9 Agenda | WG Chair | Draft
SEC-2014-0007R02 | SEC # 9 Agenda | WG Chair | Draft
SEC-2014-0007R01 | SEC # 9 Agenda | WG Chair | Draft
SEC-2014-0007 | SEC # 9 Agenda | WG Chair | Draft

## Tabelle2
oneM2M IPR STATEMENT
Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by all provisions of IPR policy of the admitting Partner Type 1 and permission that all communications and statements, oral or written, or other information disclosed or presented, and any translation or derivative thereof, may without compensation, and to the extent such participant or attendee may legally and freely grant such copyright rights, be distributed, published, and posted on oneM2M’s web site, in whole or in part, on a non-exclusive basis by oneM2M or oneM2M Partners Type 1 or their licensees or assignees, or as oneM2M SC directs.