## Tabelle1
Report at oneM2M TP#10 & Interim report from WG-3
Part A: Executive Summary for Plenary
Progress on 4 of 5 Work-Items WI-0008 TR-00009, WI-0009 TS-0004, WI-0012 TS-0008 & WI-0014 TS-0010
WI-0008 TR-0009 reasonable progress 90% complete & WI-0009 TS-0004 35%
Bindngs WI-0012 TS-0008 CoAP 20% complete; WI-0013 TS-0009 HTTP 25% complete; MQTT WI-0014 TS-0010 35%
In the main for June TP.11 for shared room with WG-2 to avoid overlap, if the Stage 3 is to be complete in August 2014 attention has shifted to WG3 at TP.10.
Planning for next Meeting(s)
Conference Calls
· PRO10.1 Tuesday – 1:00 pm UTC, April 22 (World on summer time)
· PRO10.2 Tuesday – 1:00 pm UTC, April 29
· PRO10.3 Tuesday – 12:00 noon UTC, May 06
· PRO10.4 Tuesday – 12:00 noon UTC, May 13
· PRO10.5 Wednesday – 12:00 noon UTC, May 14
· PRO10.6 Tuesday – 12:00 noon UTC, May 20
& Wednesday May 21 (with SEC - 1:00 pm UTC)
· PRO10.7 Tuesday – 12:00 noon UTC, 27 May
& Monday May 26 (with MAS - 1:00 pm UTC)
· PRO10.8 Ad’hoc Tuesday – 12:00noon UTC, 03 June 2014
Face to Face
· PRO11.0 Week 09-13 June 2014, Xi’an China
· PRO11.1 interim ad'hoc Monday 16-Wednesday 18June China (Beijing).
· PRO11.x interim Wednesday 23-Friday 25 July ETSI (Sophia-Antipolis).
A1. Documents NOT AGREED in WG (to be presented to Plenary for discussion).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
A2. Documents NOT AGREED in WG (noted / postponed / not treated etc).
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
PRO-2014-0139 | Device triggering for 3GPP presentation | NEC |  | noted | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0141R01 | TS-00004 Outline | LM Ericsson | 2014-03-28 12:05 | noted | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0152 | group-management-procedures | Huawei Technologies Co. |  | Noted to be revised aliged with 150R01 & 151R01 | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0154R02 | mgmtCmd | InterDigital Communications | 2014-03-30 21:40 | Noted | TS-0004 | V0.3.2 |  |  | WI-0009 | this seems to be a good structure & proposal - we have not yet agreed the stucture. Updated for conference call.
PRO-2014-0156 | Discussion on energy efficient protocols | Institut Mines-Telecom |  | noted | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0158R01 | Basic Data and Enumeration Type | LG Electronics | 2014-03-31 06:42 | noted | TS-0004 | V0.3.2 |  |  | WI-0009 | For Conference call
PRO-2014-0161R01 | CRUD mapping on HTTP | FUJITSU | 2014-03-31 09:27 | withdrawn | TS-0009 | V0.1.0 |  |  | WI-0013 | Merger with 0149R01
PRO-2014-0167R02 | Generic primitives and procedures | QUALCOMM Incorporated | 2014-04-03 | Noted | TS-0004 | V0.3.2 |  |  | WI-0009 | to be merged into 0172R01
PRO-2014-0170 | HTTP M2M Data related procedures | FUJITSU | 2014-04-06 14:57 | Noted | TS-0009 | V0.1.0 |  |  | WI-0013 | example that may be brought back
PRO-2014-0177 | Template for oneM2M Resource Type Definition Example | FUJITSU | 2014-04-08 | Noted | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0178 | MQTT Protocol Output draft v1.1 | Rapporteur | 2014-04-02 12:26 | Noted | TS-0010 | V0.1.1 |  |  | WI-0014
A3. Documents AGREED in WG
A3. Documents AGREED in WG
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
PRO-2014-0128R02 | ISA100.11a Analysis | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0128R03 | ISA100.11a Analysis | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0132R01 | WirelessHART Analysis | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0135 | DNP3 and oneM2M Requirements | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0136 | Modbus | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0137 | XMPP | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0138 | CoAP | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0146 | Support for Bluetooth | LM Ericsson | 2014-03-28 17:10 | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0163 | HTTP-REST Analysis | FUJITSU | 2014-04-01 14:57 | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0176 | TR-0009 v05.2 output 90% complete draft | Rapporteur | 2014-04-08 | Agreed | TR-0009 | V0.5.2 |  |  | WI-0008
PRO-2014-0142R03 | XML Schema Change Request | IBM | 2014-03-27 19:32 | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0144R01 | Device triggering for 3GPP | NEC |  | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0145R02 | Core Protocol TS Restructuring | FUJITSU | 2014-03-28 12:34 | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0150R01 | primitives | Huawei Technologies Co. |  | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0151R01 | common-operations | Huawei Technologies Co. |  | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0153R03 | Identifiers | NEC | 2014-03-30 18:07 | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0157R01 | Proposal for design principles and requirements on energy efficient protocols | KETI |  | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0172R01 | Template for oneM2M Resource Type Definition | FUJITSU | 2014-04-08 | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0180R01 | TS-00004 Output draft at v0.3.3 | Rapporteur | 2014-04-08 | Agreed | TS-0004 | V0.3.3 |  |  | WI-0009 | to be revised for conference call
PRO-2014-0131R02 | HTTP overview | FUJITSU | 2014-03-31 08:50 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0147 | HTTP_binding_TS_clause2_clause3 | LG Electronics | 2014-03-29 07:46 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0148R01 | HTTP_binding_TS_clause5 | LG Electronics | 2014-03-29 07:46 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0149R02 | HTTP_binding_TS_clause6_clause7 | LG Electronics | 2014-03-29 07:47 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0159R02 | HTTP Authentication | FUJITSU | 2014-03-31 08:50 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0160R02 | WebSocket based Notification | FUJITSU | 2014-03-31 10:47 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0165R02 | MQTT Protocol Binding Scenarios | KETI | 2014-04-02 12:26 | Agreed | TS-0010 | V0.1.1 |  |  | WI-0014
PRO-2014-0179 | MQTT Protocol Output draft v1.2 | Rapporteur | 2014-04-02 12:26 | Agreed | TS-0010 | V0.1.1 |  |  | WI-0014
A4. WG Actions:
REFERENCE | WHAT | WHO | STATUS
A-PRO-2014-0005 | Call for volunteers/Issues list on TS-0004 PRO-2014-0113R06 | WG Chairman | ongoing
A5. WG Decisions: See agreed Documents
REFERENCE | WHAT
D-WG<no.>
D-WG<no.>
A6. WG Information to Plenary (AoB):
<Text>
<Text>
Part B: List of all contributions to the WG meeting
Working area to be used during the WG meeting
WG3 PRO#3 meeting contributions
Doc-Number | Title | Source | Type (Draft, Change Request, other) | WG disposition (Agreed, Noted, Postponed, Withdrawn) | Spec number (or title) | Spec Revision# | CR# | Release | Work Item | Notes
PRO-2014-140R01 | WG3 Agenda | WG3 Chairman |  | Agreed |  |  |  |  | n/a
PRO-2014-130 | Minutes-2014-03-25 | Secretary |  | Agreed |  |  |  |  | n/a
PRO-2014-166 | Minutes-2014-03-28 | Secretary |  | Agreed |  |  |  |  | n/a
PRO-2014-0128R02 | ISA100.11a Analysis | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0128R03 | ISA100.11a Analysis | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0132R01 | WirelessHART Analysis | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0135 | DNP3 and oneM2M Requirements | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0136 | Modbus | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0137 | XMPP | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0138 | CoAP | Mukesh Taneja |  | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0146 | Support for Bluetooth | LM Ericsson | 2014-03-28 17:10 | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0156 | Discussion on energy efficient protocols | Institut Mines-Telecom |  | noted | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0163 | HTTP-REST Analysis | FUJITSU | 2014-04-01 14:57 | Agreed | TR-0009 | V0.5.1 |  |  | WI-0008
PRO-2014-0176 | TR-0009 v05.2 output 90% complete draft | Rapporteur | 2014-04-08 | Agreed | TR-0009 | V0.5.2 |  |  | WI-0008
PRO-2014-0139 | Device triggering for 3GPP presentation | NEC |  | noted | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0141 | TS-00004 Outline | LM Ericsson | 2014-03-27 17:28 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0141R01 | TS-00004 Outline | LM Ericsson | 2014-03-28 12:05 | noted | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0142 | XML Schema Change Request | IBM | 2014-03-27 19:32 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0142R01 | XML Schema Change Request | IBM | 2014-03-27 19:32 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0142R02 | XML Schema Change Request | IBM | 2014-03-27 19:32 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0142R03 | XML Schema Change Request | IBM | 2014-03-27 19:32 | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0144R01 | Device triggering for 3GPP | NEC |  | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0145 | Core Protocol TS Restructuring | FUJITSU | 2014-03-28 12:34 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009 | 2 Options for stucture
PRO-2014-0145R01 | Core Protocol TS Restructuring | FUJITSU | 2014-03-28 12:34 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009 | 2 Options for stucture
PRO-2014-0145R02 | Core Protocol TS Restructuring | FUJITSU | 2014-03-28 12:34 | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009 | 2 Options for stucture
PRO-2014-0150 | primitives | Huawei Technologies Co. |  | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0150R01 | primitives | Huawei Technologies Co. |  | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0151 | common-operations | Huawei Technologies Co. |  | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0151R01 | common-operations | Huawei Technologies Co. |  | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0152 | group-management-procedures | Huawei Technologies Co. |  | Noted to be revised aliged with 150R01 & 151R01 | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0153 | Identifiers | NEC | 2014-03-30 18:07 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009 | to be revised in drafting session
PRO-2014-0153R02 | Identifiers | NEC | 2014-03-30 18:07 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0153R03 | Identifiers | NEC | 2014-03-30 18:07 | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0154 | mgmtCmd | InterDigital Communications | 2014-03-30 21:40 | Noted: to be alinged with the Stage 2 mgmtCmd & the stucture to be agreed in WG3- to be revised | TS-0004 | V0.3.2 |  |  | WI-0009 | this seems to be a good structure & proposal - we have not yet agreed the stucture
PRO-2014-0154R02 | mgmtCmd | InterDigital Communications | 2014-03-30 21:40 | Noted | TS-0004 | V0.3.2 |  |  | WI-0009 | this seems to be a good structure & proposal - we have not yet agreed the stucture. Updated for conference call.
PRO-2014-0155 | execInstance | InterDigital Communications | 2014-03-30 21:40 | Noted: to be alinged with the Stage 2 MO Exec Intance & the stucture to be agreed in WG3- to be revised | TS-0004 | V0.3.2 |  |  | WI-0009 | Add a choice between data types. Updated for conference call.
PRO-2014-0157 | Proposal for design principles and requirements on energy efficient protocols | KETI |  | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0157R01 | Proposal for design principles and requirements on energy efficient protocols | KETI |  | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0158 | Basic Data and Enumeration Type | LG Electronics | 2014-03-31 06:42 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0158R01 | Basic Data and Enumeration Type | LG Electronics | 2014-03-31 06:42 | noted | TS-0004 | V0.3.2 |  |  | WI-0009 | For Conference call
PRO-2014-0162 | Applicability of Primitives | Philip Jacobs |  | noted | TS-0004 | V0.3.2 |  |  | WI-0009 | material largly agreed for the drafting session
PRO-2014-0164 | Delivery-related primitives and procedures | QUALCOMM |  | Withdrawn | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0167R01 | Generic primitives and procedures | QUALCOMM Incorporated | 2014-04-03 | noted | TS-0004 | V0.3.2 |  |  | WI-0009 | to be revised in drafting session
PRO-2014-0167R02 | Generic primitives and procedures | QUALCOMM Incorporated | 2014-04-03 | noted | TS-0004 | V0.3.2 |  |  | WI-0009 | to be merged into 0172R01
PRO-2014-0172 | Template for oneM2M Resource Type Definition | FUJITSU | 2014-04-08 | Revised | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0172R01 | Template for oneM2M Resource Type Definition | FUJITSU | 2014-04-08 | Agreed | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0177 | Template for oneM2M Resource Type Definition Example | FUJITSU | 2014-04-08 | Noted | TS-0004 | V0.3.2 |  |  | WI-0009
PRO-2014-0180R01 | TS-00004 Output draft at v0.3.3 | Rapporteur | 2014-04-08 | Agreed | TS-0004 | V0.3.3 |  |  | WI-0009 | to be revised for conference call
PRO-2014-0131R02 | HTTP overview | FUJITSU | 2014-03-31 08:50 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0147 | HTTP_binding_TS_clause2_clause3 | LG Electronics | 2014-03-29 07:46 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0148 | HTTP_binding_TS_clause5 | LG Electronics | 2014-03-29 07:46 | Revised | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0148R01 | HTTP_binding_TS_clause5 | LG Electronics | 2014-03-29 07:46 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0149 | HTTP_binding_TS_clause6_clause7 | LG Electronics | 2014-03-29 07:47 | Revised, delayed until decision on TS-0009 | TS-0009 | V0.1.0 |  |  | WI-0013 | merger with 0161R01
PRO-2014-0149R01 | HTTP_binding_TS_clause6_clause7 | LG Electronics | 2014-03-29 07:47 | Revised | TS-0009 | V0.1.0 |  |  | WI-0013 | merger with 0161R01
PRO-2014-0149R02 | HTTP_binding_TS_clause6_clause7 | LG Electronics | 2014-03-29 07:47 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013 | merger with 0161R01
PRO-2014-0159 | HTTP Authentication | FUJITSU | 2014-03-31 08:50 | Revised | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0159R01 | HTTP Authentication | FUJITSU | 2014-03-31 08:50 | Noted in JM Wg3/4 | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0159R02 | HTTP Authentication | FUJITSU | 2014-03-31 08:50 | Revised | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0159R02 | HTTP Authentication | FUJITSU | 2014-03-31 08:50 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0160 | WebSocket based Notification | FUJITSU | 2014-03-31 10:47 | Revised | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0160R01 | WebSocket based Notification | FUJITSU | 2014-03-31 10:47 | Revised | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0160R03 | WebSocket based Notification | FUJITSU | 2014-03-31 10:47 | Agreed | TS-0009 | V0.1.0 |  |  | WI-0013
PRO-2014-0161 | CRUD mapping on HTTP | FUJITSU | 2014-03-31 09:27 | Revised, delayed until decision on TS-0009 | TS-0009 | V0.1.0 |  |  | WI-0013 | Merger with 0149R01
PRO-2014-0161R01 | CRUD mapping on HTTP | FUJITSU | 2014-03-31 09:27 | withdrawn | TS-0009 | V0.1.0 |  |  | WI-0013 | Merger with 0149R01
PRO-2014-0170 | HTTP M2M Data related procedures | FUJITSU | 2014-04-06 14:57 | Noted | TS-0009 | V0.1.0 |  |  | WI-0013 | example that may be brought back
PRO-2014-0165 | MQTT Protocol Binding Scenarios | KETI | 2014-04-02 12:26 | Revised | TS-0010 | V0.1.1 |  |  | WI-0014
PRO-2014-0165R01 | MQTT Protocol Binding Scenarios | KETI | 2014-04-02 12:26 | Revised | TS-0010 | V0.1.1 |  |  | WI-0014
PRO-2014-0165R02 | MQTT Protocol Binding Scenarios | KETI | 2014-04-02 12:26 | Agreed | TS-0010 | V0.1.1 |  |  | WI-0014
PRO-2014-0178 | MQTT Protocol Output draft v1.1 | Rapporteur | 2014-04-02 12:26 | Noted | TS-0010 | V0.1.1 |  |  | WI-0014
PRO-2014-0179 | MQTT Protocol Output draft v1.2 | Rapporteur | 2014-04-02 12:26 | Agreed | TS-0010 | V0.1.1 |  |  | WI-0014

## Tabelle2
oneM2M IPR STATEMENT
Participation in, or attendance at, any activity of oneM2M, constitutes acceptance of and agreement to be bound by all provisions of IPR policy of the admitting Partner Type 1 and permission that all communications and statements, oral or written, or other information disclosed or presented, and any translation or derivative thereof, may without compensation, and to the extent such participant or attendee may legally and freely grant such copyright rights, be distributed, published, and posted on oneM2M’s web site, in whole or in part, on a non-exclusive basis by oneM2M or oneM2M Partners Type 1 or their licensees or assignees, or as oneM2M SC directs.