## Slide 1: WPM status report TP#34
WPM convenor, Roland Hechwartner, roland.hechwartner@t-mobile.at
2018-03-16
TP-2018-0094-WPM status report TP#34

## Slide 2: TP 34 - WI Snapshot*
44 active work items of which
  9 work items @ 100% (to be closed)
  WI-0030 - M2M Appl. & Field Domain Comp. config.
  WI-0032 - Conformance Test
  WI-0051 - Security Functions Conformance Testing
  WI-0052 - LWM2M DM & Interworking Enhancements
  WI-0055 – Product Profiles and oneM2M Features
  WI-0057 – TEF Interface
  WI-0059 – OPC-UA Interworking
  WI-0061 - Distributed Authorization
  WI-0062 - Service Layer Forwarding
Work Item Milestones reached at TP#34
  1 WIs / their deliverables reach freeze date
  1 WIs / their deliverables reach approval date
  15 WIs / their deliverables missed their earlier approval dates
1 new work item proposed at TP34
  SDT_based_Information_Model_and_Mapping_for_Vertical_Industries – approved at the mid-week TP34
Release 3 planning
  stage 3 freeze @ TP34 with exceptions to be resolved by TP35
Release 2A ratification at TP34 opening
* See work program status including progress made during TP34 in ADM-0001-Work Program Management v34.0.0.

## Slide 3: 44 active WIs*
Generic WIs
WI-0049 - Rel-1 & 2 Maintenance
WI-0050 - Rel-3 Small Technical Enhancements
WI-0079 - Rel-4 Small Technical Enhancements
REQ WG
WI-0015 - oneM2M Use Case Continuation
WI-0046 – Vehicular domain enablement
WI-0073 - App-ID Registry Function
ARC WG
WI-0031 – Optimized Group-based Operation
WI-0034 – Study of re-usable service layer contxt&Trnsct.
WI-0035 – Action Triggering
WI-0047 - DDS usage in oneM2M system
WI-0048 - OSGi Interworking
WI-0056 - Evolution of Proximal IoT Interworking
WI-0058 – Interworking with 3GPP networks
WI-0059 - OPC-UA Interworking
WI-0062 - Service Layer Forwarding
WI-0064 - Adaptation of oneM2M for Smart City
WI-0069 – Heterogen. identificat. service in oneM2M syst.
WI-0072 – Modbus interworking
WI-0076 - Lightweight oneM2M Services
WI-0080 - Edge and Fog Computing
WI-0082 - 3GPP V2X Interworking
WI-0083 - oneM2M Service Subscribers and Users
PRO WG
-
SEC WG
WI-0021 – Secure Environment Abstraction
WI-0057 - TEF Interface
WI-0061 - Distributed Authorization
WI-0065 - Trust Management in oneM2M
WI-0066 - Decentralized Authentication
WI-0068 - GlobalPlatform Interworking
WI-0077 - Attribute Based Access Control Policy
MAS WG
WI-0030 – M2M Appl. & Field Domain Comp. config.
WI-0052 - LWM2M DM & Interworking Enhancements
WI-0053 - Enhancements on Semantic Support (R3 => R4)
WI-0063 – R3 Enh. on Base Ontology & Generic IWK
WI-0070 - Disaster Alert Service Enabler
WI-0071 - oneM2M and W3C Web of Things Iwk
WI-0075 – Ind. Dom. Inf. Model Mapg. & Sem. Spt.
WI-0081 - Smart Device Template 4.0
TST WG
WI-0032 - Conformance Test
WI-0051 - Security Functions Conformance Testing
WI-0054 - Developers guide series
WI-0055 - Product Profiles & Feature Catalog
WI-0060 - Interoperability testing Release 2
WI-0074 - Conformance Test Specifications Release 2
WI-0078 - oneM2M API guide
* status in ADM-0001-Work Program Management v34.0.0.

## Slide 4: Activities since TP#33
WPM 33.1 CC & WPM 34 f2f
provided work program status
  ADM-0001-oneM2M Work Program V33.1.0
Release 3 milestones
  Discussed and propose to freeze Stage 3 at TP34, if needed allow exceptions to be solved by TP35
Release 2A
  Prepared release 2A candidate TSs, TRs; (e.g. checked with ETSI Edithelp)
  Ratified release 2A at TP#34 opening
Release 2A Control document in ADM-0012 Release_2A_Control_Document V2.0.0

## Slide 5: Items for TP Decision
TP to agree on Release 3 milestones as follows:
  Freeze of stage 3 of release 3 at TP34
    Allow exceptions to be resolved by TP35, if needed
  Ratification of release 3 post TP#37 (dedicated CC ?)
    Incl. Approval of Release 3 Control Document
    Allow sufficient time for ETSI editHelp check
TP to agree on initial Release 4 timing
  see next slide as a starting point for discussion
TP to agree on number and dates of meetings in 2019

## Slide 6: Timeline Release 3 and Release 4
Q3 2018
Q4 2018
Q1 2019
Q2 2019
Q3 2019
Q4 2019
Q1 2020
Q2 2018
TP#35
TP#36
TP#37
TP#38
?
TP#39
TP#40
TP#41
TP#42
TP#43
TP#44
TP#45
Stage 1 Freeze
Stage 2 Freeze
Stage 3 Freeze
Release 4
Tentative timeline for release 4 - Freeze Dates are provisional and a first suggestion
Assumes 6 meetings per year 2019 – dates not fixed
Q1 2018
TP#34
WG only
Stage 3 Freeze
Rel. 3
Ratification
Ratification

## Slide 7: Next Steps
Release 3 planning
  stage 3 freeze at TP34 – exceptions to be resolved by TP35
  Ratification after TP37 – dedicated CC?
    Allows sufficient time for editHelp review
Release 4 planning
  Further discuss and define scope and timing of R4
  first high-level timing of R4
    Provisional milestones for stage 1, stage 2, stage 3 and ratification suggested (see slide 6)
Update Work Program post TP#34
  document ADM-0001 oneM2M Work Program-V34.0.0
  WPM member portal

## Slide 8: Next Meetings
WPM 34.1 Conference Call
  Wed, May 9th 12:00-13:30 UTC
WPM 35 Face to Face Meeting
  Tue, May 22nd 12:30-13:30 (local time) t.b.c.