## Slide 1: WPM status report TP45 closing
WPM convenor, andyhan@hansung.ac.kr
2020-05-20

## Slide 2: WPM Status at TP45 opening
Content
WI Snapshot
WIs reaching Freeze or Approval milestone
Release 4 Timeline

## Slide 3: TP45 opening - WI Snapshot
34 active work items of which
Work Item Milestones targeted at TP#44
  5 WIs / their deliverables reach freeze date
  6 WIs / their deliverables reach approval date
  5 WIs / their deliverables missed approval/freeze dates
23 WIs target for Rel-4
2 WIs Target Rel-5
Release 4 time line update
  Stage 1 Freeze TP40 – Q2 2019 : done!
  Stage 2 Freeze TP44 – Q1 2020 : done!
  Stage 3 Freeze TP46 – Q3 2020
See full work program status @ TP45 opening in ADM-0001-Work Program Management v45.0.0.
R4+,

## Slide 4: 37 active WIs*
* status in ADM-0001-Work Program Management v45.0.0.
Release 4 candidates marked in blue
TP WIs
WI-0049 - Rel-1,2&3 Maintenance
WI-0079 - Rel-4 Small Technical Enhancements
RDM WG
WI-0015 - oneM2M Use Case Continuation
WI-0046 – Vehicular domain enablement
WI-0070 - Disaster Alert Service Enabler
WI-0075 – Ind. Dom. Inf. Model Mapg. & Sem. Spt.
WI-0081 - Smart Device Template 4.0
WI-0084 – SDT based Information Model and Mapping for Vert. Ind.
WI-0092 - Railway Domain Enablement
WI-0094- Ontologies for Smart City Services
WI-0098 - IoT for Smart Lifts
WI-0099 - Management Object Migration
TDE WG
WI-0054 - Developers guide series
WI-0060 - Interoperability testing Release 2
WI-0078 - oneM2M API guide
WI-0085 - Conformance Test Specifications Release 3
WI-0086 - Conformance Test Specifications Release 4
WI-0097 - Interoperability testing Release 3
SDS WG
WI-0053 - Enhancements on Semantic Support
WI-0058 – Interworking with 3GPP networks
WI-0064 - Adaptation of oneM2M for Smart City
WI-0069 – Heterogen. identificat. service in oneM2M syst.
WI-0072 – Modbus interworking
WI-0076 - Lightweight oneM2M Services
WI-0077 - Attribute Based Access Control Policy
WI-0080 - Edge and Fog Computing
WI-0083 - oneM2M Service Subscribers and Users
WI-0089 - Getting started with oneM2M
WI-0090 - oneM2M and Zigbee interworking
WI-0091 - oneM2M Services and Platforms Discovery
WI-0093 - Action Triggering Enhancements
WI-0095 - oneM2M System Enhancements to Support Data Protection Regulations
WI-0096 - Effective IoT Communication to Protect 3GPP Networks
WI-0100 – oneM2M and SensorThings API

## Slide 5: Freeze at TP45
* FREEZE is per TS/TR.

## Slide 6: Approval at TP45
* APPROVAL is per TS/TR.

## Slide 7: Overdue WIs
6 overdue WIs
Proposal:
WI-0054,0060,0078: approve the deliverables and close the WIs when ready.
WI-0091, WI-0093: consider update the WID milestone.

## Slide 8: Timeline Release 4
R4 Stage 1 Frozen by TP#40 – done!
R4 Stage 2 Frozen by TP#44 – done!
TP#46 R4 Stage 3 Freeze Date
Tentatively date for R4 ratification at Q1 2021
Q4 2018
Q1 2019
Q2 2019
Q3 2019
Q4 2019
Q1 2020
TP#38
TP#39
TP#40
TP#41
TP#42
TP#43
TP#44
Stage 1 Freeze
Stage 2 Freeze
Release 4
Release 3
Ratification R3
Stage 3 Freeze
Q2 2020
Q3 2020
TP#45
TP#46
Q4 2020
TP#47
TP#48
Q1 2021
R4 Appr./Rati.
TP#49
Q2 2021
achieved
planned
ratification
ratification

## Slide 9: TP45-RDM WI Status
WI# | Title | Status | Overdue | WG | Rel | TP#44 | TP#45
WI-0015 | Use Cases Collection | Active | N | RDM | Generic |  | 
WI-0046 | Vehicular domain enablement | Active | N | RDM | R4 | 91% | 91%
WI-0070 | Public Warning Service Enabler | Active | N | RDM | R4 | 40% | 40%
WI-0075 | Industrial Domain Information Model Mapping and Semantics Support | Active | N | RDM | R4 | 60% | 90%
WI-0081 | Smart Device Template 4.0 | Active | N | RDM | R4 | 90% | 95% Frozen
WI-0084 | SDT based Information Model and Mapping for Vertical Industries | Active | N | RDM | R4 | 80% | 85%
WI-0092 | Railway Domain Enablement (RAILDE) | Active | N | RDM | R4 | 45% | 50%
WI-0094 | Ontologies for Smart City Services (OSCS) | Active | N | RDM | R4 | 40% | 40%
WI-0098 | IoT for Smart Lifts | Active | N | RDM | R4 | 20% | 20%
WI-0099 | Management Object Migration | Active | N | RDM | R3 |  | 5%
WI-0101 | Advanced semantic discovery | Active | N | RDM | R4 |  | 10%

## Slide 10: TP45-SDS WI Status
Complete (no risk for Rel-4)
On track (low risk for Rel-4)
Running behind schedule (med risk for Rel-4)
Not started or stalled (high risk Rel-4)
WI | Title | SDS45
WI-0053 | Enhancements on Semantic Support | 97%
WI-0058 | Interworking with 3GPP networks | 95%
WI-0064 | Adaption of oneM2M for Smart City | 50%
WI-0069 | Heterogen. identificat. service in oneM2M syst. | 90%
WI-0072 | Modbus Interworking | 91%
WI-0076 | Lightweight oneM2M Services | 80%
WI-0077 | Attribute based Access Control Policy | 90%
WI-0080 | Edge and Fog Computing | 80%
WI-0083 | oneM2M Service Subscribers and Users | 80%
WI-0089 | Getting started with oneM2M | 22%
WI-0090 | oneM2M and Zigbee interworking | 35%
WI-0091 | oneM2M Services and Platform Discovery | 50%
WI-0093 | Action Triggering Enhancements | 80%
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations | 50%
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | 5%
WI-0100 | oneM2M and SensorThings API | 5
WI-0071 | oneM2M and W3C Web of Things Interworking | Stalled / Close
WI-0082 | 3GPP V2X Interworking | Stalled / Close
WI-0088 | M2M/IoT Application and Component Configuration | Stalled / Close

## Slide 11: TP45-TDE WI Status
Status of WIs
WI number | Title | Status | Target Release | TP#44 | TP#44(TP45)
WI-0054 | Developers’ guide series | Active |  | 97% | 97%
WI-0060 | Interoperability testing Release 2 | Active | R2 | 92% | 92%
WI-0097 | Interoperability testing Release 3 | Active | R3 | 30% | 30%
WI-0078 | oneM2M API guide | Active |  | 97% | 97%
WI-0085 | Conformance Test Specifications Release 3 | Active | R3 | 85% | 92%
WI-0086 | Conformance Test Specifications Release 4 | Active | R4 | (0) | (0)