## Slide 1: oneM2M-MEC whitepaper
JaeSeung Song (KETI)
TP-2020-0123-Status_update_on_oneM2M-MEC_whitepaper

## Slide 2: Motivation and Background
There was an interest between oneM2M and ETSI ISG MEC to support interworking
From oneM2M perspective, it would be good to place oneM2M platform instance to a place where MEC is running. The following two features allows this to happen:
  Software Campaign
  Enhanced resource announcement
Joint whitepaper work
  Started on Mid of 2019
  Targeted on End of 2019
  There was some delay and Covid-19
  Keep working on writing a whitepaper

## Slide 3: Progress & Plan
Progress on the whitepaper
  Informative sections are completed
  Sections for an architecture aspect and its descriptions are missing
  In the mean time, there is an accepted academic paper to IEEE Network Magazine
    “MEIX: Evolving Multi-Access Edge Computing for Industrial Internet-of-Things Services”
    Lionel and JaeSeung et.
Plan for the whitepaper
  Sections for the architecture will be filled with the general concept integrating oneM2M and MEC
  A draft will be shared with interesting members
  Final draft can be presented in TP 49
  Plan to publish in 1Q 2021

## Slide 4: Thank you