## Slide 1: Meeting Schedule 2021and beyond
Group Name: TP#48
Source: Roland Hechwartner, TPC, Deutsche Telekom
Meeting Date: Dec 18, 2020

## Slide 2: Summary
This document discusses the planning of oneM2M meetings in 2021 and beyond
The current meeting schedule 2021 lists four physical meetings – all except the first (TP49)
The prevailing uncertain situation due to global covid-19 outbreak and countermeasures result in an uncertainty wrt the organization of f2f-meetings, at least in the HY 1 2021
Hence, once more a contingency plan needs to be considered resp. agreed
Lessons learned / experiences made during 2020 are presented and potential meeting scenarios are discussed in this document
  Your feedback and comments are welcome
The way forward for 2021 has to be agreed – together with the meeting hosts / PT1
  2 alternative scenarios are proposed
Initiate discussion on the 2022 meeting schedule

## Slide 3: Some Lessons learned…Soft Facts
TP48 is the 4th virtual meeting
WG, guided by their cairs and vice chairs, have adopted a process to encourage efficient collaboration in e-meetings
Tool for e-voting on technical matters, for the chair and vice-chair elections is in place
Enhanced use of tools like gitlab may further improve (virtual) collaboration
pro’s:
Overall experience much better than initially expected, the model works well
High level of engagement in email discussions and offline reviews of contributions
Scheduling meetings over 1-month allowed for more time and better continuity of discussions (especially for more complex contributions)
Reduced cost for participation
…
con’s:
Web-meeting format can be difficult for many folks to get their comments heard
Time zone differences only allow for a small window of meeting time
The quality and quantity of discussions (in sessions as well as offline) and exchanges during f2f meetings can hardly be achieved in e-meetings esp. wrt new topics and solutions for complex situations.
Hurdle for newcomers to get acquainted with the group
…
Non exhaustive, based on personal opinion

## Slide 4: Some Hard Facts
Physical Meeting1
1 week + travel time
  5 meetings/y
  9 weeks average time between TP meetings
5 days meeting
44 sessions, 1 session = 90min
  40 sessions for WG - 2 slots in parallel
    [34 if Industry Day.. 42 max.]
  4 sessions for TP (no parallel session):
    1 opening/1 mid-week/2 closing
  + lunch-break sessions
    Coordination/ WPM/ Newbies
  not counting the offline discussions
+ virtual WG meetings between the TPs
Virtual Meeting1
span of 4 weeks
  5 meetings/y
  6 weeks average time between TP meetings
4*days a week, 2 sessions per day
32 sessions, 1 session = 90min
  28 sessions for WG
  2 sessions of 2h for TP
    1 opening/ 1 closing
+ virtual WG meetings between the TPs
*started with 5 days a week; initial goal: to have similar number of sessions as in f2f. 4 days a week is the current model – however for some reasons 5 d/w are utilized. 2 sessions per day were decided to best accomodate the global time difference
1 as the „typical“ lived model, not considered are associated costs to attend / host a meeting

## Slide 5: Conclusion 1
2020 showed that virtual meetings work well and allow for progress
  Virtual meetings are flexible, cost efficient and resilient
  oneM2M has been used to virtual meetings from the very beginning, however, in a different setting (e.g. interim WG meetings, non-regular virtual TPs)
  improvements of processes and (further) usage of collaboration tools in oneM2M allow increased efficiency of virtual meetings
At the same time the benefits of f2f meetings became evident
  Higher quality and quantity of discussions (in sessions / offline), exchanges
  Much easier „start“ for new delegates/companies
consider a mix of physical and virtual TPs for the future meeting planning to
  Keep the number of TP meetings/year
  Decrease the number of travels per year from 5 to x? (should we target a minimum of at least 2 f2f-meetings/year)
  Gain from the advantages of both the physical meetings and the virtual meeting
for discussion

## Slide 6: Meetings
TP#49 virtual meeting Jan 18 – Feb 10
TP#50 host InDiCo/ETSI, Dublin, April, 12.-16
TP#51, host ARIB/TTC, Japan, June 28 - July 2
TP#52 host / location t.b.d., Aug. 30.- Sep. 3
TP#53 host / location t.b.d., Nov. 29.- Dec. 3
2021
TP#44 hosted by TIA/Qualcomm. San Diego, USA, February, 17.-21. 2020
TP#45 series of virtual meetings April 20 - May 20, 2020 TTA, South Korea, April, 20.-24. ATIS, Washington,
TP#46 virtual meeting July 1 – 24, 2020 ITU-T/ETSI, Geneva, Europe, July, 6.-10. 2020
TP#47 virtual meeting Sep 28 – Oct 23, 2020 hosted by ARIB/TTC, Japan, October, 5.-9. 2020
TP#48 virtual meeting Nov 30 – Dec 18, 2020 host Indico/ETSI, Europe, Nov. 30.- Dec. 4. 2020
2020

## Slide 7: 2021 Meetings Scenario A “Yellow”
TP#50 host InDiCo/ETSI, Dublin, April, 12.-16
TP#51, host ARIB/TTC, Japan, June 28 - July 2
Scenario Yellow: merge TP50/51 in new TP#50 virtual, May 10 – June 4
Keep equal distance of 12 weeks to TP49 / TP51new
New TP#51, host t.b.d or
virtual Aug 30 – Sep 17 ?
New TP#52, host t.b.d
Source: TP-2019-0118R02-Proposed_meeting_dates_for_2021

## Slide 8: 2021 Meetings Scenario B “Blue”
TP#50 host InDiCo/ETSI, Dublin, April, 12.-16
TP#51, host ARIB/TTC, Japan, June 28 - July 2
Scenario Blue: TP#50 virtual, April 6 -22 – span less than 3 weeks
TP#51 virtual, June 21 –July 8 (or9?)
distance of 7 weeks to TP49 (8w) to TP51 (7w) TP52
TP 50
TP 51
TP 51
TP#52, Aug 30 – Sep 3; host t.b.d or
virtual Aug 30 – Sep 17 ?
Source: TP-2019-0118R02-Proposed_meeting_dates_for_2021

## Slide 9: Conclusion 2
Decide on the way forward in 2021
  Scenario A „Yellow“ = 4 meetings, 2(or 3) virtual and 2 (or 1) f2f
  Scenario B „Blue“ = 5 meetings, 3 (or 4) virtual and 2 (or1) f2f
  No change to schedule = 5 meetings, 1 virtual and 4 f2f
  Other?
Proposal for 2022
  Take into consideration Conclusion 1 to continue with a mix of physical and virtual TPs for 2022 and beyond.
  What would be a good ratio for f2f:virtual meetings?
  Decide 2022 meeting schedule at TP#49 i.e. Jan/Feb 2021
For discussion