## Slide 1: WPM status report TP55 opening plenary
WPM convener,
Andrew Min-gyu Han (andyhan@hansung.ac.kr )
2022-07-11

## Slide 2: WPM Status at TP55 opening plenary
Content
WI Snapshot
WIs reaching Freeze or Approval milestone
Release 4 Timeline / Release 5 Timeline

## Slide 3: TP55 opening - WI Snapshot
24 active work items of which
Work Item Milestones targeted at TP#55
  1 WIs / their deliverables reach freeze status
  4 WIs / their deliverables reach approval status
9 WIs target for Rel-4
11 WIs target for Rel-5
See full work program status @ TP55 in ADM-0001-Work Program Management v55.0.0.
R4+,

## Slide 4: 24 active WIs*
* status in ADM-0001-Work Program Management v52.1.0.
Release 4 candidates marked in blue, Release 5 candidates marked in green
TP WIs
WI-0049 - Rel-1 &2 &3 Maintenance
WI-0079 - Rel-4 Small Technical Enhancements
RDM WG
WI-0015 - oneM2M Use Case Continuation
WI-0094- Ontologies for Smart City Services
WI-0098 - IoT for Smart Lifts
WI-0101 - Advanced semantic discovery
WI-0104 - SDT based Information Model and Mapping for Vertical Industries – SIMVI
WI-0105 - System enhancements to support AI capabilities
WI-0109 - IPE-based Device Management with FlexContainers
TDE WG
WI-0086 - Conformance Test Specifications Release 4
WI-0103 - oneM2M API guide Rel3
WI-0106 - Interoperability testing Release 4
WI-0107 - Developers guide series
WI-0108 - Conformance Test Maintenance
SDS WG
WI-0064 - Adaptation of oneM2M for Smart City
WI-0069 - Heterogen. identificat. service in oneM2M syst.
WI-0089 - Getting started with oneM2M
WI-0090 - oneM2M and Zigbee interworking
WI-0091 - oneM2M Services and Platforms Discovery
WI-0093 - Action Triggering Enhancements
WI-0095 - oneM2M System Enhancements to Support Data Protection Regulations
WI-0096 - Effective IoT Communication to Protect 3GPP Networks
WI-0100 - oneM2M and SensorThings API
WI-0102 - System enhancements to support Data License Management

## Slide 5: WIs target for Rel-4
WI-0064, 0069 : No normative R4 work planned – Need to close?
WI-0090, 0091, 0098: Stalled

## Slide 6: WIs target for Rel-5
WI-0096, 0101, 0106, 0108 : Stalled.
WI-0100, 0107, 0109 : Good progress

## Slide 7: Freeze at TP55
* FREEZE is per TS/TR. (90% < WI < 94%)
1 WI to freeze for TP54

## Slide 8: Approval at TP55
* APPROVAL is per TS/TR. (95% < WI < 100%)

## Slide 9: Timeline Release 5
R4 Ratification : TP56 Q3 - 2022
R5 Stage 1 Freeze Date : TP#56 or TP57 – Q4 2022
R5 Stage 2 Freeze Date : TP#59 – Q2 2023
R5 Stage 3 Freeze Date : TP#xx – Q4 2023
Tentatively date for R5 ratification at TPxx + 2, Q2 2024
achieved
planned
ratification
ratification
Q2 2021
Q3 2021
Q4 2021
Q1 2022
TP#50
TP#51
TP#52
TP#53
Stage 1 Freeze
Stage 2 Freeze
Release 5
Release 4
Ratification R4
Stage 3 Freeze
Q2 2022
Q3 2022
TP#54
TP#55
Q4 2022
TP#56
Q1 2023
R5 Appr./Rati.
TP#57
Q2 2023
TP#58
Q3 2023
Q4 2023
Q1 2024
Q2
2024
Q3 2024
TP#59
TP#60