## Slide 1: WPM status report TP58 closing plenary
WPM convenor,
Andrew Min-gyu Han (andyhan@hansung.ac.kr )
2023-02-23

## Slide 2: WPM Status at TP58 Cloing plenary
Content
WI Snapshot
WIs reaching Freeze or Approval milestone
Release 5 Timeline

## Slide 3: TP58 Closning - WI Snapshot
22 active work items of which
Work Item Milestones targeted at TP#57
  1 WIs / their deliverables reach freeze status
  3 WIs / their deliverables reach approval status
4 WIs target for Rel-4
14 WIs target for Rel-5
See full work program status @ TP58 in ADM-0001-Work Program Management v58.0.0.
R4+,

## Slide 4: 22 active WIs*
* status in ADM-0001-Work Program Management v52.1.0.
Release 4 candidates marked in blue, Release 5 candidates marked in green
TP WIs
WI-0049 - Rel-1 &2 &3 Maintenance
WI-0079 - Rel-4 Small Technical Enhancements
RDM WG
WI-0015 - oneM2M Use Case Continuation
WI-0098 - IoT for Smart Lifts
WI-0101 - Advanced semantic discovery
WI-0104 - SDT based Information Model and Mapping for Vertical Industries – SIMVI
WI-0110 - Enablement of IoT in the metaverse
TDE WG
WI-0086 - Conformance Test Specifications Release 4
WI-0106 - Interoperability testing Release 4
WI-0107 - Developers guide series
WI-0108 - Conformance Test Maintenance
SDS WG
WI-0069 - Heterogen. identificat. service in oneM2M syst.
WI-0089 - Getting started with oneM2M
WI-0090 - oneM2M and Zigbee interworking
WI-0091 - oneM2M Services and Platforms Discovery
WI-0095 - oneM2M System Enhancements to Support Data Protection Regulations
WI-0096 - Effective IoT Communication to Protect 3GPP Networks
WI-0100 - oneM2M and SensorThings API
WI-0102 - System enhancements to support Data License Management
WI-0105 - System enhancements to support AI capabilities
WI-0109 - IPE-based Device Management with FlexContainers

## Slide 5: WIs target for Rel-4
WI-0090, 0091: Stalled  consider to move the WIs to R5

## Slide 6: WIs target for Rel-5
WI-0069, 0098, 0101, 0106, 107 : Stalled.

## Slide 7: Freeze at TP58
* FREEZE is per TS/TR. (90% < WI < 94%)
2 WI reach freeze status in TP58

## Slide 8: Approval at TP58
* APPROVAL is per TS/TR. (95% < WI < 100%)
None for this meeting

## Slide 9: Timeline Release 5
R5 Stage 1 Freeze Date : TP#57 – Q4 2022  TP#62 – Q4 2023
R5 Stage 2 Freeze Date : TP#59 – Q2 2023  TP#64 – Q2 2024
R5 Stage 3 Freeze Date : TP#xx – Q4 2023  TP#67 – Q4 2024
Tentatively date for R5 ratification at TP67 + @, Q2 2025
achieved
planned
ratification
ratification
Stage 1 Freeze
Stage 2 Freeze
Release 5
Stage 3 Freeze
Q2 2022
Q3 2022
TP#54
TP#55
Q4 2022
TP#56
Q1 2023
R5 Appr./Rati.
TP#57
Q2 2023
TP#58
Q3 2023
Q4 2023
Q1 2024
Q2
2024
Q3 2024
TP#59
TP#60
TP#61
TP#62
TP#63
TP#65
TP#64
TP#66
Q4 2024
TP#67
Q1 2025
Q2
2025
Q3 2025
TP#xx