## Slide 1: WPM status report TP59 closing plenary
Xavier Piednoir (ETSI Secretariat)
on behalf of WPM convenor,
Andrew Min-gyu Han (andyhan@hansung.ac.kr )
2023-04-21

## Slide 2: WPM Status at TP59 Closing plenary
Content
WI Snapshot
WIs reaching Freeze or Approval milestone
Release 5 Timeline

## Slide 3: TP59 Closing - WI Snapshot
25 active work items of which
Work Item Milestones reached at TP#59
  1 WIs / their deliverables reach freeze status
  4 WIs / their deliverables reach approval status
4 WIs target for Rel-4
17 WIs target for Rel-5
See full work program status @ TP59 in ADM-0001-Work Program Management v59.0.0.
R4+,

## Slide 4: 25 active WIs*
* status in ADM-0001-Work Program Management v59.0.0.
Release 4 candidates marked in blue, Release 5 candidates marked in green
TP WIs
WI-0049 - Rel-1 &2 &3 Maintenance
WI-0079 - Rel-4 Small Technical Enhancements
RDM WG
WI-0015 - oneM2M Use Case Continuation
WI-0098 - IoT for Smart Lifts
WI-0104 - SDT based Information Model and Mapping for Vertical Industries – SIMVI
WI-0110 - Enablement of IoT in the metaverse
TDE WG
WI-0086 - Conformance Test Specifications Release 4
WI-0103 - oneM2M API_Guide Rel 3
WI-0106 - Interoperability testing Release 4
WI-0107 - Developers guide series
WI-0108 - Conformance Test Maintenance
WI-0111 - oneM2M Architecture Icons
SDS WG
WI-0069 - Heterogen. identificat. service in oneM2M syst.
WI-0089 - Getting started with oneM2M
WI-0090 - oneM2M and Zigbee interworking
WI-0091 - oneM2M Services and Platforms Discovery
WI-0095 - oneM2M System Enhancements to Support Data Protection Regulations
WI-0096 - Effective IoT Communication to Protect 3GPP Networks
WI-0100 - oneM2M and SensorThings API
WI-0101 - Advanced semantic discovery
WI-0102 - System enhancements to support Data License Management
WI-0105 - System enhancements to support AI capabilities
WI-0109 - IPE-based Device Management with FlexContainers
WI-0112 - oneM2M Enhanced Filter and Queries
WI-0113 - Enhanced Public Warning Service Enabler

## Slide 5: WIs target for Rel-4
WI-0090, 0091: Stalled  consider to move the WIs to R5
WI# | Title | Status | Overdue | WG | Rel | TP#57 | TP#58 | TP#59
WI-0086 | Conformance Test Specifications Release 4 | Active | Y | TDE | R4 | 98 % | 98 % | 100 %
WI-0090 | oneM2M and Zigbee interworking | Active | Y | SDS | R4 | 35 % | 35 % | 35 %
WI-0091 | oneM2M Services and Platforms Discovery | Active | Y | SDS | R4 | 50 % | 50 % | 99 %
WI-0094 | Ontologies for Smart City Services (OSCS) | Active | Y | RDM | R4 | 100 % | 100 % | 100 %

## Slide 6: WIs target for Rel-5
WI-0069, 0098, 0101, 0102, 0106, 107, 109, 110 : Stalled.
WI# | Title | Status | Overdue | WG | Rel | TP#57 | TP#58 | TP#59
WI-0015 | Use Cases Collection | Active | N | RDM | Generic | n.a. | n.a. | n.a.
WI-0069 | Physical Object Heterogeneous identification and tracking services in oneM2M system | Active | Y | SDS | R5 | 90 % | 90 % | 90 %
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations (eDPR) | Active | N | SDS | R5 | 70 % | 70 % | 70 %
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | Active | N | SDS | R5 | 5 % | 5 % | 5 %
WI-0098 | IoT for Smart Lifts | Active | Y | RDM | R5 | 40 % | 40 % | 40 %
WI-0100 | oneM2M and SensorThings API | Active | N | SDS | R5 | 55 % | 70 % | 75 %
WI-0101 | Advanced Semantic Discovery | Active | N | SDS | R5 | 60 % | 60 % | 60 %
WI-0102 | System enhancements to support Data License Management | Active | N | SDS | R5 | 50 % | 50 % | 50 %
WI-0104 | SDT based Information Model and Mapping for Vertical Industries – SIMVI | Active | N | RDM | R5 | 50 % | 50 % | 65 %
WI-0105 | System enhancements to support AI capabilities | Active | N | SDS | R5 | 85 % | 85 % | 98 %
WI-0106 | Interoperability testing Release 4 | Active | Y | TDE | R5 | 0 % | 0 % | 0 %
WI-0107 | Developers guide series | Active | Y | TDE | R5 | 50 % | 50 % | 50 %
WI-0108 | Conformance Test Maintenance | Active | Y | TDE | R5 | 30 % | 40 % | 45 %
WI-0109 | IPE-based Device Management with FlexContainers | Active | Y | SDS | R5 | 85 % | 85 % | 85 %
WI-0110 | Enablement of IoT in the metaverse (MetaIoT) | Active | N | RDM | R5 | 5 % | 5 % | 5 %
WI-0111 | oneM2M Architecture Icons | Active | N | TDE | R5 |  | 0%% | 0 %
WI-0112 | oneM2M Enhanced Filter and Queries | Active | N | SDS | R5 |  |  | 0 %
WI-0113 | Enhanced Public Warning Service Enabler | Active | N | SDS | R5 |  |  | 0 %

## Slide 7: Freeze at TP59
* FREEZE is per TS/TR. (90% < WI < 94%)
1 WI reach freeze status in TP59
WI# | Title | Status | Overdue | WG | Rel | TP#57 | TP#58 | TP#59
WI-0069 | Physical Object Heterogeneous identification and tracking services in oneM2M system | Active | Y | SDS | R5 | 90 % | 90 % | 90 %

## Slide 8: Approval at TP59
* APPROVAL is per TS/TR. (95% < WI < 100%)
4 Work Items
WI# | Title | Status | Overdue | WG | Rel | TP#57 | TP#58 | TP#59
WI-0086 | Conformance Test Specifications Release 4 | Active | Y | TDE | R4 | 98 % | 98 % | 100 %
WI-0091 | oneM2M Services and Platforms Discovery | Active | Y | SDS | R4 | 50 % | 50 % | 99 %
WI-0094 | Ontologies for Smart City Services (OSCS) | Active | Y | RDM | R4 | 100 % | 100 % | 100 %
WI-0105 | System enhancements to support AI capabilities | Active | N | SDS | R5 | 85 % | 85 % | 98 %

## Slide 9: Timeline Release 5
R5 Stage 1 Freeze Date : TP#57 – Q4 2022  TP#62 – Q4 2023
R5 Stage 2 Freeze Date : TP#59 – Q2 2023  TP#64 – Q2 2024
R5 Stage 3 Freeze Date : TP#xx – Q4 2023  TP#67 – Q4 2024
Tentatively date for R5 ratification at TP67 + @, Q2 2025
achieved
planned
ratification
ratification
Stage 1 Freeze
Stage 2 Freeze
Release 5
Stage 3 Freeze
Q2 2022
Q3 2022
TP#54
TP#55
Q4 2022
TP#56
Q1 2023
R5 Appr./Rati.
TP#57
Q2 2023
TP#58
Q3 2023
Q4 2023
Q1 2024
Q2
2024
Q3 2024
TP#59
TP#60
TP#61
TP#62
TP#63
TP#65
TP#64
TP#66
Q4 2024
TP#67
Q1 2025
Q2
2025
Q3 2025
TP#xx