## Slide 1: STF 685 ESTIMED Enabling Standardized IoT deployments in MEC Environments for advanced systems Project introduction
Presented by: Joachim Koss, ETSI STF685 Leader
For: oneM2M Technical Plenary Meeting #68
10/02/2025

## Slide 2: About me
  Professional positions
    Various management positions in HW/SW Engineering, International Project and Process Management, Conformity Testing and Approval, IPR Management and Standardization
    Founder of JK Consulting & Projects, a consulting firm that supports companies in the area of Machine-to-machine (M2M), Internet of Things (IoT) technologies, product approvals, project management and in the area of Quality Management Systems
  Work in standardisation
    ETSI Board member for six years
    Vice Chairman of ETSI Technical Committee SmartM2M for four years
    Vice Chairman of oneM2M’s Technical Plenary for two years
    Leader of several ETSI Specialist Task Forces on IoT standards
    Expert in ETSI TC SmartM2M, currently with a focus on Semantic Interoperability
2
Joachim Koss JK Consulting & Projects Email: joachim.koss@jk-conpro.de Phone: +49 3379 379092 Mobile: +49 1573 2100402 LinkedIn: www.linkedin.com/in/joachim-koss-2a78a68

## Slide 3: Introducing STF685

## Slide 4: Background
  ETSI White Paper “Enabling Multi-access Edge Computing in Internet-of-Things: how to deploy ETSI MEC and oneM2M” in June 2023
  Description how the two architectures complement each other and some overall ideas on how to deploy oneM2M in a MEC environment
  ETSI project proposal “ESTIMED” aims at answering the standardization approaches addressed by the White Paper
  Proposal: build in a timely manner standardization work to address the challenges raised by the Single Market Programme 2023 and to improve the interoperability of the Internet of Things
  EC accepted ETSI proposal, commissioned ETSI by a Grant Agreement, project funding by EC/EFTA
  ETSI Call for Expertise on the project, review process, selection of 10 companies/organisations from the list of applicants
  Contracts concluded, ESTIMED project team: Specialist Task Force 685 established to perform the tasks defined in the Terms of Reference
  Start of work: 01 February 2025
4

## Slide 5: Project Organisation
5

## Slide 6: STF685 Service Providing Entities
6
Company Name
CNIT
European Digital SME
Exacta Global Smart Solutions
FSCOM
JK Consulting and Projects
Nextworks S.r.I
Samir Medjiah
Sejong University
UniMore
xFlow Research Inc.

## Slide 7: STF685 Team
7
Contact Name | Company Name | Email
Enrico Scarrone | Telecom Italia S.p.A. | enrico.scarrone@telecomitalia.it
Roland Hechwartner | Deutsche Telekom AG | roland.hechwartner@magenta.at
Dario Sabella | xFlow Research Inc. | dario.sabella@xflowresearch.com
Walter Featherstone | Apple France | w_featherstone@apple.com
Ayesha Ayub | xFlow | ayesha.ayub@xflowresearch.com
Mudassar Khan | xFlow | Mudassar.Sabeel@xflowresearch.com
Muhammad Umair Khan | xFlow | umair.anwar@xflowresearch.com
Muhammad Umair Zafar | xFlow | umair.zafar@xflowresearch.com
Ikram Ul Haq | xFlow | ikram.haq@xflowresearch.com
Mubeena Ishaq | xFlow | mubeena.ishaq@xflowresearch.com
Joachim Koss | JK Consulting and Projects | joachim.koss@jk-conpro.de
Andreas Kraft | JK Consulting and Projects | andreas.kraft@jk-conpro.de
Peter Niblett | JK Consulting and Projects | peter.niblett@jk-conpro.de
Peter Schmitting | FSCOM | peter.schmitting@fscom.fr
Yann Garcia | FSCOM | yann.garcia@fscom.fr
Samir Medjiah | Samir Medjiah | samir.medjiah@gmail.com
Giacomo Bernini | Nextworks SRL | g.bernini@nextworks.it
JaeSeung Song | Sejong University | jssong@sejong.ac.kr
Paolo Pagano | CNIT | paolo.pagano@cnit.it
Martina Troscia | CNIT | martina.troscia@pntlab-cnit.it
Mariano Falcitelli | CNIT | mariano.falcitelli@cnit.it
Kaleb Gebremichael Gebremeskel | CNIT | k.gebremeskel@studenti.unipi.it
Marwan Haruna | CNIT | marwan.haruna@cnit.it
Alexandr Tardo | CNIT | alexandr.tardo@cnit.it
Marco Picone | UNIMORE | marco.picone@unimore.it
Gabriele Casalini | Digital SME | g.casalini@digitalsme.eu
Bob Flynn | Exacta gss | bob.flynn@exactagss.com
Massimo Vanetti | Digital SME | massimovanetti@gmail.com
Pietro Piscione | Nextworks SRL | p.piscione@nextworks.it
Gabriele Scivoletto | Nextworks SRL | g.scivoletto@nextworks.it
Giada Landi | Nextworks SRL | g.landi@nextworks.it
Laurent Velez | ETSI | Laurent.Velez@etsi.org
Miguel Angel Reina-Ortega | ETSI | MiguelAngel.ReinaOrtega@etsi.org
Karen Hughes | ETSI | Karen.Hughes@etsi.org
Antoine Mouquet | ETSI | Antoine.Mouquet@etsi.org
Chantal Bonardi | ETSI | chantal.bonardi@etsi.org
Officials
Officials
Expert team (27)
Chair TC SmartM2M
Chair TC ISG MEC
Vice Chair TC ISG MEC
Chair oneM2M TP

## Slide 8: Project Objectives
  “ESTIMED” the name is the high level objective: Enabling Standardized IoT deployments in MEC Environments for advanced systems
  improve the interoperability of Internet of Things (IoT) by a combination of standardized protocols, data formats, and middleware solutions
  bring together open standards in ETSI ISG MEC (Multi-access Edge Computing) and in oneM2M on a horizontal platform for interoperable and scalable IoT systems, that is offered to edge IoT application developers via outreach activities in the ecosystem
  bring together user and industry supply side perspectives
  assess the technical implications and deployment approaches that can be tested via multiple proofs of concepts (PoCs)
  identify potential standardization gaps to carry forward in ETSI bodies
8

## Slide 9: Project Concept
9

## Slide 10: Project Phases
10

## Slide 11: STF685 Project Workplan (ToR)
11
 | Months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
 | Dec 24 | Jan 25 | Feb25 | Mar25 | Apr25 | May25 | Jun25 | Jul25 | Aug25 | Sep25 | Oct25 | Nov25 | Dec 25 | Jan26 | Feb26 | Mar26 | Apr26 | May26 | Jun26 | Jul26 | Aug26 | Sep26 | Oct26 | Nov26 | Dec 26 | Jan27 | Feb27 | Mar27 | Apr27 | May27 | Jun27 | Jul27 | Aug27 | Sep27 | Oct27 | Nov27
Task 1.1 |  | M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 1.2 |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  | M
Task 2.1 |  |  |  |  |  | D |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 2.2 |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 2.3 |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 2.4 |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 3.1 |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  | 
Task 3.2 |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  | D |  | 
Task 3.3 |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  | D |  | M
Task 3.4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  | 
Task 3.5 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D
Task 3.6 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D
Task 4.1 |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Task 4.2 |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  | M |  | D
Task 4.3 |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  | M |  | D
Task 5.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  | D
Task 5.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  | M
Task 5.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D
Task 6.1 |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  | D
Task 6.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D
Task 6.3 |  |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  |  |  | D
Task 6.4 |  |  |  |  |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  |  |  |  | M |  |  |  |  |  |  |  |  |  |  |  |  | M

## Slide 12: Work Packages (WP) and their relationship
12

## Slide 13: STF685 Deliverables (1)
13
WP No | Del No | Deliverable Name | Type | Dissemination Level | Due Date
WP6 | D6.1 | Dissemination plan | R | PU | 31-May-25
WP6 | D6.3 | Introductory White paper | R | PU | 31-May-25
WP2 | D2.1 | Analysis and selection for oneM2M and MEC implementations | R | SEN | 31-Aug-25
WP2 | D2.2 | ETSI GR MEC-DEC 050 - PWI_MECDECODE_2411_v1 (GR)- ESTIMED Use Cases & Requirements | R | PU | 30-Nov-25
WP2 | D2.3 | oneM2M Requirements - oneM2M WI -0120 | R | PU | 30-Nov-25
WP6 | D6.5 | Post-event Hackathon#1 report | R | PU | 30-Nov-25
WP1 | D1.1 | ESTIMED First Progress Report | R | SEN | 31-Dec-25
WP2 | D2.4 | Guide for selected MEC and oneM2M implementations | R | PU | 31-May-26
WP4 | D4.1 | Software artifacts of simulation for PoCs | OTHER | PU | 30-Sep-26
WP3 | D3.1 | ETSI GR MEC-DEC 051 - PWI_MECDECODE_2401_v1 (GR)- ESTIMED integration solutions | R | PU | 30-Nov-26
WP3 | D3.3 | oneM2M TR-0077 - oneM2M and MEC integration scenario and mechanisms | R | PU | 30-Nov-26
WP3 | D3.6 | White Paper on advanced oneM2M and MEC interworking using Swarm Computing | R | PU | 30-Nov-26
WP6 | D6.6 | Post-event Hackathon#2 report | R | PU | 30-Nov-26
WP1 | D1.2 | ESTIMED Second Progress Report | R | SEN | 31-Dec-26
WP6 | D6.4 | White paper on project achievements | R | PU | 31-May-27

## Slide 14: STF685 Deliverables (2)
14
WP No | Del No | Deliverable Name | Type | Dissemination Level | Due Date
WP3 | D3.2 | ETSI GS MEC-DEC 052 - PWI_MECDECODE_2402_v1 (GS)- ESTIMED Interworking and deployments | R | PU | 30-Sep-27
WP3 | D3.4 | oneM2M TS-0042 - oneM2M and MEC interworking and deployments | R | PU | 30-Sep-27
WP4 | D4.2 | Deployment scripts | R | PU | 30-Sep-27
WP3 | D3.5 | oneM2M Specification Change Requests collection | R | PU | 30-Nov-27
WP3 | D3.7 | Open Source code contribution for oneM2M and MEC implementations | R | PU | 30-Nov-27
WP4 | D4.3 | ETSI GR MEC-DEC 053 - PWI_MECDECODE_2403_v1 (GR)- ESTIMED PoC A report | R | PU | 30-Nov-27
WP4 | D4.4 | ETSI GR MEC-DEC 054 - PWI_MECDECODE_2404_v1 (GR)- ESTIMED PoC B report | R | PU | 30-Nov-27
WP4 | D4.5 | ETSI GR MEC-DEC 055 - PWI_MECDECODE_2405_v1 (GR)- ESTIMED PoC C report | R | PU | 30-Nov-27
WP4 | D4.6 | ETSI GR MEC-DEC 056 - PWI_MECDECODE_2406_v1 (GR)- ESTIMED PoC D report | R | PU | 30-Nov-27
WP5 | D5.1 | ETSI GR MEC-DEC 057 - PWI_MECDECODE_2407_v1 (GR)- ESTIMED Interoperability Test Scenarios | R | PU | 30-Nov-27
WP5 | D5.2 | ETSI GR MEC-DEC 058 - PWI_MECDECODE_2408_v1 (GR)- ESTIMED Conformance Testing | R | PU | 30-Nov-27
WP6 | D6.2 | oneM2M TR XXX XXX (Number to be assigned) Developer Guide on interworking between oneM2M and MEC | R | PU | 30-Nov-27
WP6 | D6.7 | Post-event Hackathon#3 report | R | PU | 30-Nov-27
WP6 | D6.8 | Dissemination activities reporting | R | PU | 30-Nov-27
WP6 | D6.9 | Project Promotion and Dissemination Materials | R | PU | 30-Nov-27

## Slide 15: STF685 Milestones (1)
15
Mil # | Milestone description | Cut-off date
A1 | Project Team established | 31-Jan-25
A2 | Dissemination Plans and ecosystem reach out D6.1: Dissemination plan to be sent to the EC D6.2: Introductory White paper to be sent to the EC Use cases definition and criteria for deployment scenarios selection available | 31-May-25
B | D2.1: Analysis and selection for oneM2M and MEC implementations ETSI Progress report#1 to be approved by approved by the three Reference Bodies | 31-Aug-25
C | Early PoCs :Early definition of PoCs, to be used as input for the first Hackathon and event in WP6. Means of verification: 4 early PoCs ready for the 1st Hackathon & event. Early version of application and device software ready, as support for mature PoCs. | 30-Sep-25
D1 | First set of requirements for standards interworking: D2.2: ETSI GR MEC-DEC 050 - PWI_MECDECODE_2411_v1 (GR)- ESTIMED Use Cases & Requirements published version sent to EC Early/stable drafts of D3.1:TSI GR MEC-DEC 051 and D3.3: oneM2M TR 0077, made available. D2.3: oneM2M Requirements - oneM2M WI -0120 published version sent to EC Early PoCs to be used as input for the first Hackathon D6.5: Post-event Hackathon#1 Report D1.1: First-term Progress Report with the achieved results approved by the three Reference Bodies | 30-Nov-25
D2 | D1.1: Approved by ETSI Secretariat and send to EISMEA | 31-Dec-25

## Slide 16: STF685 Milestones (2)
16
Mil # | Milestone description | Cut-off date
E | Final requirements for deployment and interoperability: D2.4: Guide for selected MEC and oneM2M implementations ETSI Progress report#2 to be approved by the three Reference Bodies | 31-May-26
F | D4.1: Software artifacts of simulation for PoCs 4 mature PoCs ready for the 2nd Hackathon Application and device software ready, as support for final PoCs | 30-Sep-26
G1 | D3.1: ETSI GR MEC-DEC 051 - PWI_MECDECODE_2401_v1 (GR)- ESTIMED integration solutions published version sent to EC Early/stable drafts of D3.2: TSI GS MEC-DEC 052 and D3.4: oneM2M TS 0042 D3.3: oneM2M TR 0077 - oneM2M and MEC integration scenario and mechanisms published version sent to EC D3.6: White Paper on advanced oneM2M and MEC interworking using Swarm Computing sent to EC D6.6: Post-event Hackathon#2 report sent to EC D1.2: Second-term Report approved by the three Reference Bodies | 30-Nov-26
G2 | D1.2: Second Progress Report approved by ETSI Secretariat and sent to EISMEA | 31-Dec-26
H | D6.6: White paper on project achievements Early/Stable drafts of D5.1: ETSI GR MEC-DEC 057 and D5.2: ETSI GR MEC-DEC 058 ETSI Progress report#3 to be approved by the three Reference Bodies | 31-May-27
I | D3.2: ETSI GS MEC-DEC 052 - PWI_MECDECODE_2402_v1 (GS)- ESTIMED Interworking and deployments published version sent to EC D3.4: oneM2M TS 0042- oneM2M and MEC interworking and deployments published version sent to EC D4.2: Deployment scripts 4 final PoCs ready for the 3rd Hackathon & event | 30-Sep-27
J | The published versions sent to EC of: D3.5: oneM2M Specification Change Requests collection D3.7: Open Source code contribution for oneM2M and MEC implementations D4.3: ETSI GR MEC-DEC 053 - PWI_MECDECODE_2403_v1 (GR)- ESTIMED PoC A report D4.4: ETSI GR MEC-DEC 054 - PWI_MECDECODE_2404_v1 (GR)- ESTIMED PoC B report D4.5: ETSI GR MEC-DEC 055 - PWI_MECDECODE_2405_v1 (GR)- ESTIMED PoC C report D4.6: ETSI GR MEC-DEC 056 - PWI_MECDECODE_2406_v1 (GR)- ESTIMED PoC D report D5.1: ETSI GR MEC-DEC 057 - PWI_MECDECODE_2407_v1 (GR)- ESTIMED Interoperability Test Scenarios D5.2: ETSI GR MEC-DEC 058 - PWI_MECDECODE_2408_v1 (GR)- ESTIMED Conformance Testing D6.2: oneM2M TR 0078 Developer Guide on interworking between oneM2M and MEC Delivery to the EC of: D6.7: Post-event Hackathon#3 report D6.8: Dissemination activities reporting D6.9: Project Promotion and Dissemination Materials Final Report approved by the three Reference Bodies and sent to EISMEA | 30-Nov-27

## Slide 17: Thank you for your attention
17
ETSI STF685 Homepage: https://portal.etsi.org/xtfs/#/xTF/685/
Contact Details:
Joachim Koss JK Consulting & Projects Email: joachim.koss@jk-conpro.de Phone: +49 3379379092 Mobile: +49 15732100402 Internet: www.jk-conpro.de