## Slide 1: STF 685 ESTIMED Enabling Standardized IoT deployments in MEC Environments for advanced systems Project status
Presented by: Joachim Koss, ETSI STF685 Leader
For: oneM2M Technical Plenary Meeting #69
02/04/2025

## Slide 2: STF 685 Meetings
Meetings held since project start
  1 Preparatory meeting
  1 STF685 Steering Committee meetings
  3 STF685 regular meetings (project coordination)
  4 STF685 Work Group meetings (technical work)
2
STF685 regular meetings planned
  The meetings take place on a regular basis, aimed in a 3-weeks cycle

## Slide 3: Achievements / Progress
Achievements since project start of expert team on 01.02.25:
  Milestone A1 achieved on 31 January 2025 (Project Team established)
  2 Work Packages (WP2, WP6) started to work Work Package Leaders and some Rapporteurs are nominated
    WP2 - Use case selection, Deployment Scenarios and Requirements definition
      D2.1 - Analysis and selection for oneM2M and MEC implementations
      D2.2 - ETSI GR MEC-DEC 050 - PWI_MECDECODE_2411_v1 (GR)- ESTIMED Use Cases & Requirements
    WP6 - Dissemination and Ecosystem
      D6.1 - Dissemination plan
      D6.3 - Introductory White Paper
3
Input to Milestone A2, 31.05.25
Input to Milestone B, 31.08.25
Input to Milestone D1, 30.11.25

## Slide 4: Announcement
4
  MEC Tech F2F#10 meeting in Sophia Antipolis MEC-Open session - Edge IoT with ESTIMED project on 29 April 2025 Goal of this open session
    provide an informative platform to the audience for sharing the ESTIMED project setup and status
    help WP2 collecting use cases from the audience suggestions
    overview and events updates of Eclipse Foundation
    Hackathons Plans discussion

## Slide 5: STF 685 Deliverables Status (1)
5
WP No | Del No | Deliverable Name | Due Date | Status | 
WP6 | D6.1 | Dissemination plan | 31-May-25 | in progress | 
WP6 | D6.3 | Introductory White paper | 31-May-25 | in progress | 
WP2 | D2.1 | Analysis and selection for oneM2M and MEC implementations | 31-Aug-25 | in progress | 
WP2 | D2.2 | ETSI GR MEC-DEC 050 - PWI_MECDECODE_2411_v1 (GR)- ESTIMED Use Cases & Requirements | 30-Nov-25 | in progress | 
WP2 | D2.3 | oneM2M Requirements - oneM2M WI -0120 | 30-Nov-25 | not started yet | 
WP6 | D6.5 | Post-event Hackathon#1 report | 30-Nov-25 | not started yet | 
WP1 | D1.1 | ESTIMED First Progress Report | 31-Dec-25 | not started yet | 
WP2 | D2.4 | Guide for selected MEC and oneM2M implementations | 31-May-26 | not started yet | 
WP4 | D4.1 | Software artifacts of simulation for PoCs | 30-Sep-26 | not started yet | 
WP3 | D3.1 | ETSI GR MEC-DEC 051 - PWI_MECDECODE_2401_v1 (GR)- ESTIMED integration solutions | 30-Nov-26 | not started yet | 
WP3 | D3.3 | oneM2M TR XXX XXX (Number to be assigned)- oneM2M and MEC integration scenario and mechanisms | 30-Nov-26 | not started yet | 
WP3 | D3.6 | White Paper on advanced oneM2M and MEC interworking using Swarm Computing | 30-Nov-26 | not started yet | 
WP6 | D6.6 | Post-event Hackathon#2 report | 30-Nov-26 | not started yet | 
WP1 | D1.2 | ESTIMED Second Progress Report | 31-Dec-26 | not started yet | 
WP6 | D6.4 | White paper on project achievements | 31-May-27 | not started yet | 

## Slide 6: STF 685 Deliverables Status(2)
6
WP No | Del No | Deliverable Name | Due Date | Status | 
WP3 | D3.2 | ETSI GS MEC-DEC 052 - PWI_MECDECODE_2402_v1 (GS)- ESTIMED Interworking and deployments | 30-Sep-27 | not started yet | 
WP3 | D3.4 | oneM2M TS XXX XXX (Number to be assigned)- oneM2M and MEC interworking and deployments | 30-Sep-27 | not started yet | 
WP4 | D4.2 | Deployment scripts | 30-Sep-27 | not started yet | 
WP3 | D3.5 | oneM2M Specification Change Requests collection | 30-Nov-27 | not started yet | 
WP3 | D3.7 | Open Source code contribution for oneM2M and MEC implementations | 30-Nov-27 | not started yet | 
WP4 | D4.3 | ETSI GR MEC-DEC 053 - PWI_MECDECODE_2403_v1 (GR)- ESTIMED PoC A report | 30-Nov-27 | not started yet | 
WP4 | D4.4 | ETSI GR MEC-DEC 054 - PWI_MECDECODE_2404_v1 (GR)- ESTIMED PoC B report | 30-Nov-27 | not started yet | 
WP4 | D4.5 | ETSI GR MEC-DEC 055 - PWI_MECDECODE_2405_v1 (GR)- ESTIMED PoC C report | 30-Nov-27 | not started yet | 
WP4 | D4.6 | ETSI GR MEC-DEC 056 - PWI_MECDECODE_2406_v1 (GR)- ESTIMED PoC D report | 30-Nov-27 | not started yet | 
WP5 | D5.1 | ETSI GR MEC-DEC 057 - PWI_MECDECODE_2407_v1 (GR)- ESTIMED Interoperability Test Scenarios | 30-Nov-27 | not started yet | 
WP5 | D5.2 | ETSI GR MEC-DEC 058 - PWI_MECDECODE_2408_v1 (GR)- ESTIMED Conformance Testing | 30-Nov-27 | not started yet | 
WP6 | D6.2 | oneM2M TR XXX XXX (Number to be assigned) Developer Guide on interworking between oneM2M and MEC | 30-Nov-27 | not started yet | 
WP6 | D6.7 | Post-event Hackathon#3 report | 30-Nov-27 | not started yet | 
WP6 | D6.8 | Dissemination activities reporting | 30-Nov-27 | not started yet | 
WP6 | D6.9 | Project Promotion and Dissemination Materials | 30-Nov-27 | not started yet | 

## Slide 7: STF685 Milestones (1)
7
Mil # | Milestone description | Cut-off date
A1 | Project Team established | 31-Jan-25
A2 | Dissemination Plans and ecosystem reach out D6.1: Dissemination plan to be sent to the EC D6.2: Introductory White paper to be sent to the EC Use cases definition and criteria for deployment scenarios selection available | 31-May-25
B | D2.1: Analysis and selection for oneM2M and MEC implementations ETSI Progress report#1 to be approved by approved by the three Reference Bodies | 31-Aug-25
C | Early PoCs :Early definition of PoCs, to be used as input for the first Hackathon and event in WP6. Means of verification: 4 early PoCs ready for the 1st Hackathon & event. Early version of application and device software ready, as support for mature PoCs. | 30-Sep-25
D1 | First set of requirements for standards interworking: D2.2: ETSI GR MEC-DEC 050 - PWI_MECDECODE_2411_v1 (GR)- ESTIMED Use Cases & Requirements published version sent to EC Early/stable drafts of D3.1:TSI GR MEC-DEC 051 and D3.3: oneM2M TR 0077, made available. D2.3: oneM2M Requirements - oneM2M WI -0120 published version sent to EC Early PoCs to be used as input for the first Hackathon D6.5: Post-event Hackathon#1 Report D1.1: First-term Progress Report with the achieved results approved by the three Reference Bodies | 30-Nov-25
D2 | D1.1: Approved by ETSI Secretariat and send to EISMEA | 31-Dec-25
Approved means by TC SmartM2M, ISG MEC, oneM2M

## Slide 8: STF685 Milestones (2)
8
Mil # | Milestone description | Cut-off date
E | Final requirements for deployment and interoperability: D2.4: Guide for selected MEC and oneM2M implementations ETSI Progress report#2 to be approved by the three Reference Bodies | 31-May-26
F | D4.1: Software artifacts of simulation for PoCs 4 mature PoCs ready for the 2nd Hackathon Application and device software ready, as support for final PoCs | 30-Sep-26
G1 | D3.1: ETSI GR MEC-DEC 051 - PWI_MECDECODE_2401_v1 (GR)- ESTIMED integration solutions published version sent to EC Early/stable drafts of D3.2: TSI GS MEC-DEC 052 and D3.4: oneM2M TS 0042 D3.3: oneM2M TR 0077 - oneM2M and MEC integration scenario and mechanisms published version sent to EC D3.6: White Paper on advanced oneM2M and MEC interworking using Swarm Computing sent to EC D6.6: Post-event Hackathon#2 report sent to EC D1.2: Second-term Report approved by the three Reference Bodies | 30-Nov-26
G2 | D1.2: Second Progress Report approved by ETSI Secretariat and sent to EISMEA | 31-Dec-26
H | D6.6: White paper on project achievements Early/Stable drafts of D5.1: ETSI GR MEC-DEC 057 and D5.2: ETSI GR MEC-DEC 058 ETSI Progress report#3 to be approved by the three Reference Bodies | 31-May-27
I | D3.2: ETSI GS MEC-DEC 052 - PWI_MECDECODE_2402_v1 (GS)- ESTIMED Interworking and deployments published version sent to EC D3.4: oneM2M TS 0042- oneM2M and MEC interworking and deployments published version sent to EC D4.2: Deployment scripts 4 final PoCs ready for the 3rd Hackathon & event | 30-Sep-27
J | The published versions sent to EC of: D3.5: oneM2M Specification Change Requests collection D3.7: Open Source code contribution for oneM2M and MEC implementations D4.3: ETSI GR MEC-DEC 053 - PWI_MECDECODE_2403_v1 (GR)- ESTIMED PoC A report D4.4: ETSI GR MEC-DEC 054 - PWI_MECDECODE_2404_v1 (GR)- ESTIMED PoC B report D4.5: ETSI GR MEC-DEC 055 - PWI_MECDECODE_2405_v1 (GR)- ESTIMED PoC C report D4.6: ETSI GR MEC-DEC 056 - PWI_MECDECODE_2406_v1 (GR)- ESTIMED PoC D report D5.1: ETSI GR MEC-DEC 057 - PWI_MECDECODE_2407_v1 (GR)- ESTIMED Interoperability Test Scenarios D5.2: ETSI GR MEC-DEC 058 - PWI_MECDECODE_2408_v1 (GR)- ESTIMED Conformance Testing D6.2: oneM2M TR 0078 Developer Guide on interworking between oneM2M and MEC Delivery to the EC of: D6.7: Post-event Hackathon#3 report D6.8: Dissemination activities reporting D6.9: Project Promotion and Dissemination Materials Final Report approved by the three Reference Bodies and sent to EISMEA | 30-Nov-27

## Slide 9: Requested Decisions

## Slide 10: Requested Decisions
10
means precondition for Milestone …
oneM2M TP is kindly asked
  to note the STF685 Status Presentation [TP-2025-0023]

## Slide 11: Thank you for your attention
11
ETSI STF 696 Homepage: https://portal.etsi.org/xtfs/#/xTF/685/
Contact Details:
Joachim Koss JK Consulting & Projects Email: joachim.koss@jk-conpro.de Phone: +49 3379379092 Mobile: +49 15732100402 Internet: www.jk-conpro.de