## Slide 1: WPM Status Report TP72
Volker Leisse (ETSI Secretariat)
(volker.leisse@etsi.org)
2025-11-14

## Slide 2: WPM Status Report TP72
WI snapshot per WG
WI status per release
Publication status

## Slide 3: WI Snapshot
50 active work items of which
7 Release independent WIs
4 WIs targeted for Rel-3
15 WIs targeted for Rel-4
18 WIs targeted for Rel-5
6 WIs targeted for Rel-6
See full work program status in ADM-0001 (to be updated)
R4+,

## Slide 4: 50 active WIs*
* status in ADM-0001 (to be updated)
WIs targeted at Release 3 and prior, Release 4, Release 5 or Release 6 – Underlined Wis new or modified at TP72
RDM WG
WI-0015 - Use Cases Collection
WI-0049 - Maintenance of Release 1, 2 and 3
WI-0070 - Public Warning Service Enabler
WI-0075 - Industrial Domain Information Model Mapping and Semantics Support
WI-0081 - Smart Device Template 4.0
WI-0084 - SDT based Information Model and Mapping for Vertical Industries
WI-0089 - Getting Started with oneM2M
WI-0091 - Services and Platforms Discovery
WI-0092 - Railway Domain Enablement
WI-0095 - System Enhancements to Support Data Protection Regulations
WI-0098 - IoT for Smart Lifts
WI-0099 - Management Object Migration
WI-0104 - SDT based Information Model and Mapping for Vertical Industries
WI-0105 - System Enhancements to Support Artificial Intelligence Capabilities
WI-0110 - Enablement of IoT in the Metaverse
WI-0116 - Maintenance of Release 2, 3 and 4
WI-0118 - Digital Twins Enablement
SDS WG (cont’d)
WI-0115 - 3GPP Interworking via NEF N33 API
WI-0117 - Small Technical Enhancements
WI-0119 - Integrating NGSI-LD API
WI-0120 - Edge Deployment Using ETSI MEC
WI-0121 - oneM2M-ROS Interworking
WI-0122 - oneM2M and Model Context Protocol
TDE WG
WI-0054 - Developers Guide Series
WI-0085 - Conformance Test Specifications
WI-0086 - Conformance Test Specifications
WI-0103 - API Guide
WI-0106 - Interoperability Testing
WI-0107 - Developer Guide Series
WI-0108 - Conformance Test Maintenance
WI-0111 - Architecture Icons
WI-0114 - Interoperability Testing
SDS WG
WI-0046 - Vehicular Domain Enablement
WI-0058 - Interworking with 3GPP Networks
WI-0064 - Adaptation of oneM2M for Smart City
WI-0069 - Physical Object Heterogeneous Identification and Tracking Services
WI-0072 - Modbus Interworking
WI-0076 - Lightweight oneM2M Services
WI-0077 - Attribute Based Access Control Policy
WI-0080 - Edge and Fog Computing
WI-0083 - Service Subscribers and Users
WI-0090 - Zigbee Interworking
WI-0093 - Action Triggering
WI-0096 - Effective IoT Communication to Protect 3GPP Networks
WI-0100 - oneM2M and SensorThings API
WI-0101 - Advanced Semantic Discovery
WI-0102 - System Enhancements to Support Data License Management
WI-0109 - IPE-based Device Management with FlexContainers
WI-0112 - Enhanced Filters and Queries
WI-0113 - Enhanced Public Warning Service Enabler

## Slide 5: Release Independent WIs
WI# | Title | Status | Target | Overdue | Lead WG | Rel | TP#70 | TP#71 | TP#72
WI-0015 | Use Cases Collection | Active | N/A | N/A | RDM |  | Cont | Cont | Cont
WI-0049 | Maintenance of Release 1, 2 and 3 | Active | N/A | Y | RDM |  | 100 % | 100 % | 100 %
WI-0054 | Developers Guide Series | Active | TP32 | Y | TDE |  | 100 % | 100 % | 100 %
WI-0104 | SDT based Information Model and Mapping for Vertical Industries | Active | N/A | N/A | RDM |  | Cont | Cont | Cont
WI-0107 | Developer Guide Series | Active | TP56 | N/A | TDE |  | 60 % | 60 % | 60 %
WI-0108 | Conformance Test Maintenance | Active | TP62 | N/A | TDE |  | 45 % | 45 % | 45 %
WI-0116 | Maintenance of Release 2, 3 and 4 | Active | N/A | N/A | RDM |  | Cont | Cont | Cont

## Slide 6: WIs targeted for Rel-3 and prior
WI# | Title | Status | Target | Overdue | Lead WG | Rel | TP#70 | TP#71 | TP#72
WI-0046 | Vehicular Domain Enablement | Active | TP47 | Y | SDS | Rel-3 | 100 % | 100 % | 100 %
WI-0058 | Interworking with 3GPP Networks | Active | TP46 | Y | SDS | Rel-3 | 100 % | 100 % | 100 %
WI-0085 | Conformance Test Specifications | Active | TP44 | Y | TDE | Rel-3 | 100 % | 100 % | 100 %
WI-0103 | API Guide | Active | TP53 | Y | TDE | Rel-3 | 50 % | 50 % | 50 %

## Slide 7: WIs targeted for Rel-4
WI# | Title | Status | Target | Overdue | Lead WG | Rel | TP#70 | TP#71 | TP#72
WI-0070 | Public Warning Service Enabler | Active | TP46 | Y | RDM | Rel-4 | 100 % | 100 % | 100 %
WI-0072 | Modbus Interworking | Active | TP46 | Y | SDS | Rel-4 | 100 % | 100 % | 100 %
WI-0075 | Industrial Domain Information Model Mapping and Semantics Support | Active | TP47 | Y | RDM | Rel-4 | 100 % | 100 % | 100 %
WI-0076 | Lightweight oneM2M Services | Active | TP45 | Y | SDS | Rel-4 | 100 % | 100 % | 100 %
WI-0077 | Attribute Based Access Control Policy | Active | TP45 | Y | SDS | Rel-4 |  |  | 
WI-0080 | Edge and Fog Computing | Active | TP48 | Y | SDS | Rel-4 | 100 % | 100 % | 100 %
WI-0081 | Smart Device Template 4.0 | Active | TP45 | Y | RDM | Rel-4 |  |  | 
WI-0083 | Service Subscribers and Users | Active | TP45 | Y | SDS | Rel-4 | 100 % | 100 % | 100 %
WI-0084 | SDT Based Information Model Mapping and Mapping for Vertical Industries | Active | TP45 | Y | RDM | Rel-4 | 100 % | 100 % | 100 %
WI-0086 | Conformance Test Specifications | Active | TP53 | Y | TDE | Rel-4 | 100 % | 100 % | 100 %
WI-0089 | Getting Started with oneM2M | Active | TP45 | Y | RDM | Rel-4 |  |  | 
WI-0092 | Railway Domain Enablement | Active | TP48 | Y | RDM | Rel-4 | 100 % | 100 % | 100 %
WI-0093 | Action Triggering | Active | TP46 | Y | SDS | Rel-4 |  |  | 
WI-0099 | Management Object Migration | Active | TP52 | Y | RDM | Rel-4 | 100 % | 100 % | 100 %
WI-0106 | Interoperability Testing | Active | TP58 | Y | TDE | Rel-4 | 30 % | 30 % | 30 %

## Slide 8: WIs targeted for Rel-5
WI# | Title | Status | Target | Overdue | Lead WG | Rel | TP#70 | TP#71 | TP#72
WI-0064 | Adaptation of oneM2M for Smart City | Active | TP44 | Y | SDS | Rel-5 | 50 % | 50 % | 50 %
WI-0069 | Physical Object Heterogeneous Identification and Tracking Services | Active | TP44 | Y | SDS | Rel-5 | 90 % | 90 % | 90 %
WI-0091 | Services and Platform Discovery | Active | TP59 | Y | RDM | Rel-5 | 50 % | 50 % | 50 %
WI-0095 | System Enhancements to Support Data Protection Regulations | Active | TP57 | Y | RDM | Rel-5 | 70 % | 70 % | 70 %
WI-0098 | IoT for Smart Lifts | Active | TP47 | Y | RDM | Rel-5 | 40 % | 40 % | 40 %
WI-0100 | oneM2M and SensorThings API | Active | TP69 | C | SDS | Rel-5 | 100 % | 100 % | 100 %
WI-0101 | Advanced Semantic Discovery | Active | TP72 | Y | SDS | Rel-5 | 60 % | 60 % | 60 %
WI-0102 | System Enhancements to Support Data License Management | Active | TP49 | Y | SDS | Rel-5 | 50 % | 50 % | 50 %
WI-0105 | System Enhancements to Support AI Capabilities | Active | TP60 | Y | RDM | Rel-5 | 90 % | 90 % | 91 %
WI-0109 | IPE-based Device Management with FlexContainers | Active | tbd | N | SDS | Rel-5 | 85% | 85% | 85%
WI-0110 | Enablement of IoT in the Metaverse | Active | TP67 | Y | RDM | Rel-5 | 5 % | 5 % | 50 %
WI-0111 | Architecture Icons | Active | TP61 | Y | TDE | Rel-5 | 60 % | 65 % | 90 %
WI-0112 | Enhanced Filters and Queries | Active | TP64 | Y | SDS | Rel-5 | 20 % | 20 % | 20 %
WI-0113 | Enhanced Public Warning Service Enabler | Active | TP62 | Y | SDS | Rel-5 | 30 % | 30 % | 30 %
WI-0114 | Interoperability Testing | Active | TP71 | Y | TDE | Rel-5 |  |  | 
WI-0117 | Small Technical Enhancements | Active | tbd | N | SDS | Rel-5 |  |  | 
WI-0118 | Digital Twins Enablement | Active | TP69 | Y | RDM | Rel-5 | 0 % | 0 % | 0 %
WI-0119 | Integrating NGSI-LD API | Active | TP71 | Y | SDS | Rel-5 | 45 % | 45 % | 45 %

## Slide 9: WIs targeted for Rel-6
WI# | Title | Status |  | Overdue | Lead WG | Rel | TP#70 | TP#71 | TP#72
WI-0090 | Zigbee Interworking | Active | TP45 | Y | SDS | Rel-6 | 35 % | 35 % | 35 %
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | Active | TP52 | Y | SDS | Rel-6 | 5 % | 5 % | 5 %
WI-0115 | 3GPP Interworking via NEF N33 API | Active | TP64 | Y | SDS | Rel-6 | 0 % | 0 % | 0 %
WI-0120 | Edge Deployment using ETSI MEC | Active | TP77 | N | SDS | Rel-6 | 5 % | 15 % | 25 %
WI-0121 | oneM2M-ROS Interworking | Active | TP74 | N | SDS | Rel-6 | 15 % | 15 % | 15 %
WI-0122 | oneM2M and Model Context Protocol | Active | TP77 | N | SDS | Rel-6 | 0 % | 15 % | 20 %

## Slide 10: Publication of TS
TS | Title | Release 3 |  | Release 4 |  | Release 5 |  | Release 6 | 
TS-0001 | Functional Architecture | V3.35.0 | TS 118 101 v3.22.0 | V4.23.0 | TS 118 101 v4.15.0 | V5.9.0 |  |  | 
TS-0002 | Requirements | V3.1.2 | TS 118 102 v3.1.2 | V4.6.2 |  | V5.4.0 |  |  | 
TS-0003 | Security Solutions | V3.17.1 | TS 118 103 v3.13.0 | V4.9.0 |  | V5.1.0 |  |  | 
TS-0004 | Service Layer Core Protocol | V3.32.0 |  | V4.23.0 |  | V5.1.0 |  |  | 
TS-0005 | Management Enablement (OMA) | V3.5.1 | TS 118 105 v3.5.1 | V4.0.1 | TS 118 105 v4.0.1 |  |  |  | 
TS-0006 | Management Enablement (BBF) | V3.6.2 | TS 118 106 v3.6.2 | V4.0.1 |  |  |  |  | 
TS-0007 | Service Components |  |  |  |  |  |  |  | 
TS-0008 | CoAP Protocol Binding | V3.9.0 | TS 118 108 v3.6.0 | V4.6.1 | TS 118 108 v4.4.1 | V5.1.0 |  |  | 
TS-0009 | HTTP Protocol Binding | V3.9.1 | TS 118 109 v3.5.0 | V4.6.1 | TS 118 109 v4.4.1 |  |  |  | 
TS-0010 | MQTT Protocol Binding | V3.1.0 | TS 118 110 v3.1.0 | V4.0.1 | TS 118 110 v4.0.1 |  |  |  | 
TS-0011 | Common Terminology | V3.0.0 |  | V4.1.1 | TS 118 111 v4.1.1 |  |  |  | 
TS-0012 | Base Ontology | V3.7.3 | TS 118 117 v3.7.3 | V4.0.0 |  |  |  |  | 
TS-0013 | Interoperability Testing | V3.4.0 | TS 118 113 v3.3.1 | V4.0.0 |  |  |  |  | 
TS-0014 | LWM2M Interworking | V3.2.0 | TS 118 114 v3.2.0 | V4.0.1 | TS 118 114 v4.0.1 |  |  |  | 
TS-0015 | Testing Framework |  |  |  |  |  |  |  | 

## Slide 11: Publication of TS (cont’d)
TS | Title | Release 3 |  | Release 4 |  | Release 5 |  | Release 6 | 
TS-0016 | Secure Environment Abstraction | V3.0.2 | TS 118 116 v3.0.2 | V4.0.0 | TS 118 116 v4.0.1 | V5.0.1 |  |  | 
TS-0017 | Implementation Conformance Statements |  |  |  |  |  |  |  | 
TS-0018 | Test Suite Structure & Test Purposes |  |  | V4.6.0 |  |  |  |  | 
TS-0019 | Abstract Test Suite & Implementation eXtra Information for Test |  |  | V4.0.0 |  |  |  |  | 
TS-0020 | WebSocket Protocol Binding | V3.0.1 | TS 118 120 v3.0.1 | V4.0.0 |  |  |  |  | 
TS-0021 | AllJoyn Interworking |  |  |  |  |  |  |  | 
TS-0022 | Field Device Configuration | V3.3.0 | TS 118 122 v3.0.2 | V4.7.1 | TS 118 122 v4.5.1 | V5.1.0 |  |  | 
TS-0023 | Home Appliances Information Model and Mapping | V3.9.0 | TS 118 123 v3.7.3 |  |  |  |  |  | 
TS-0023 | SDT-based Information Model and Mapping for Vertical Industries |  |  | V4.8.1 | TS 118 123 v4.8.1 |  |  |  | 
TS-0024 | OCF Interworking | V3.2.2 | TS 118 124 v3.2.2 | V4.0.1 | TS 118 124 v4.0.1 |  |  |  | 
TS-0025 | Product Profiles | V3.2.0 |  |  |  |  |  |  | 
TS-0026 | 3GPP Interworking | V3.6.0 | TS 118 126 v3.0.0 | V4.7.0 |  | V5.0.0 |  |  | 
TS-0027 | Security Implementation Conformance Statement |  |  |  |  |  |  |  | 
TS-0028 | Security Test Suite Structure & Test Purposes |  |  |  |  |  |  |  | 
TS-0029 | Security Abstract Test Suite & Implementation eXtra Information for Test |  |  |  |  |  |  |  | 
TS-0030 | Ontology Based Interworking | V3.0.2 |  | V4.0.1 | TS 118 130 v4.0.1 | V5.0.0 |  |  | 

## Slide 12: Publication of TS (cont’d)
TSV | Title | Release 3 |  | Release 4 |  | Release 5 |  | Release 6 | 
TS-0031 | Feature Catalogue |  |  |  |  |  |  |  | 
TS-0032 | MAF and MEF Interface | V3.0.0 |  | V4.0.0 | TS 118 132 v4.0.1 | V5.0.1 |  |  | 
TS-0033 | Interworking Framework | V3.0.0 |  | V4.0.1 | TS 118 133 v4.0.1 | V5.0.0 |  |  | 
TS-0034 | Semantics Support | V3.0.2 |  | V4.2.0 |  | V5.0.0 |  |  | 
TS-0035 | OSGi Interworking | V3.0.0 |  | V4.0.0 |  |  |  |  | 
TS-0036 | Advanced Vehicular Domain Enablement |  |  |  |  |  |  |  | 
TS-0037 | IoT Public Warning Service Enablement |  |  | V4.0.2 |  |  |  |  | 
TS-0038 |  |  |  |  |  |  |  |  | 
TS-0039 |  |  |  |  |  |  |  |  | 
TS-0040 | Modbus Interworking |  |  | V4.0.0 | TS 118 140 v4.0.0 | V5.0.1 |  |  | 
TS-0041 | SensorThings Interworking |  |  |  |  | V5.4.1 |  |  | 
TS-0042 | MEC Interworking and Deployments |  |  |  |  |  |  |  | 

## Slide 13: Publication of TR
TR | Title | Latest | Rel-3 | Rel-4 | Rel-5 | Rel-6
TR-0001 | Use Cases Collection |  |  |  |  |