## Schedule
# | Date | Time | Meeting name
1 | 2020-09-29 | 12:00 – 15:00 | SDS
2 | 2020-10-05 | 12:00 – 15:00 | SDS
3 | 2020-10-07 | 12:00 – 15:00 | SDS
4 | 2020-10-08 | 12:00 – 15:00 | SDS
5 | 2020-10-09 | 12:00 – 15:00 | SDS
6 | 2020-10-12 | 12:00 – 15:00 | SDS
7 | 2020-10-14 | 12:00 – 15:00 | SDS
8 | 2020-10-19 | 12:00 – 15:00 | SDS
9 | 2020-10-21 | 12:00 – 15:00 | SDS

## Contribs
SHORT DOC NB | SHORTNAME | SOURCE | UPLOADED | STATUS | DOC TYPE | VERS | TS/TR
SDS-2020-0278 | Corrections to TS-0004 4.2.0 | IBM | 2020-09-28 22:48 | Draft | CR | R4 | TS-0004 v 4.2.0
SDS-2020-0279 | Corrections to TS-0004 v3.18.0 | IBM |  | Draft | CR | R3 | TS-0004 3.18
SDS-2020-0272R01 | Schema updates for TS-0004 R3 | IBM | 2020-09-27 18:57 | Draft | INC | R3 | TS-0004 R3
SDS-2020-0248R04 | TS-0026-Network Monitoring Request_editorial_R4 | KDDI | 2020-09-28 00:07 | Draft | CR | R4 | TS-0026 v4.5.0
SDS-2020-0114R03 | TS-0004-attribute_level_acps_R4 | Convida | 2020-07-23 01:35 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0123R04 | TS-0004-m2m-service_user_ids_params_R4 | Convida | 2020-08-12 15:50 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0124R01 | TS-0004-m2m_service_user_resources_R4 | Convida | 2020-08-26 17:50 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0129R01 | TS-0001_primitive_profile_maintenance_R4 | Convida | 2020-08-25 14:42 | Draft (Peter to review) | CR | R4 | TS-0001
SDS-2020-0131R01 | TS-0004-primitiveProfile_procedures_R4 | Convida | 2020-08-25 14:46 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0174R02 | TS-0004-time_synchronization_beacon_R4 | Convida | 2020-07-23 01:06 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0257 | TS-0004-m2m_service_user_procedures_R4 | Convida | 2020-08-26 17:48 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0019R01 | TS-0004-nwMonitoringReq_resource_R4 | KDDI | 2020-08-11 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0209R06 | Announcement Sync Type Stage 3 R4 | Hyundai Motors & KETI | 2020-08-25 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0100R02 | TS-0008_Missing_CoAP_Status_Codes_R4 | Convida | 2020-04-12 17:02 | Revision Needed | CR | R4 | TS-0008
SDS-2020-0102R04 | TS-0009_Missing_HTTP_Status_Codes_R4 | Convida | 2020-07-04 16:40 | Revision Needed | CR | R4 | TS-0009
SDS-2020-0111R06 | GDPR feature analysis and impact to oneM2M | KETI, EGM and Hyundai Motors | 2020-09-28 00:36 | Draft | INC | R5 | TR-0062
SDS-2020-0132R02 | Consent management for GDPR | KETI, Hyundai Motors | 2020-09-28 00:45 | Draft | INC | R5 | TR-0062
SDS-2020-0133R02 | Logging for GDPR | KETI and Hyundai Motors | 2020-09-28 00:44 | Draft | INC | R5 | TR-0062
SDS-2020-0134R02 | pseudonymization and anonymization of privacy data | KETI and Hyundai Motors | 2020-07-21 21:49 | Draft | INC | R5 | TR-0062
SDS-2020-0275 | Existing data license schemes | KETI and Hyundai Motors |  | Draft | INC | R5 | TR-00
SDS-2020-0276 | Existing solution and standards for Data License | KETI and Hyundai Motors |  | Draft | INC | R5 | TR-0066 V0.0.1
SDS-2020-0277 | Data license annotation | KETI and Hyundai Motors |  | Draft | INC | R5 | TR-0066 V0.0.1

## CR Packs
TS-0001 (R2) | TS-0001 (R3) | TS-0001 (R4) | TS-0003 (R2) | TS-0003 (R3) | TS-0003 (R4) | TS-0004 (R2) | TS-0004 (R3) | TS-0004 (R4) | TS-0005(R3) | TS-0006(R3) | TS-0008 (R2) | TS-0008 (R3) | TS-0008 (R4) | TS-0009 (R2) | TS-0009 (R3) | TS-0009 (R4) | TS-0010 (R2) | TS-0010 (R3) | TS-0010 (R4) | TS-0022 (R3) | TS-0022 (R4) | TS-0026 (R3) | TS-0026 (R4) | TS-0034 (R4)
|  | SDS-2020-0249R01 | [5 empty] | SDS-2020-0175R01
|  | SDS-2020-0130R03 | [5 empty] | SDS-2020-0122R02

## WI
WI | Title | SDS39 | SDS40 | SDS41 | SDS42 | SDS43 | SDS44 | SDS45 | SDS46 | SDS47 | Comments
WI-0053 | Enhancements on Semantic Support | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% |  | Stage 3 Completed at TP46
WI-0058 | Interworking with 3GPP networks | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% |  | Stage 3 Completed at TP46
WI-0064 | Adaption of oneM2M for Smart City | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% |  | Stalled - No normative R4 work planned
WI-0069 | Heterogen. identificat. service in oneM2M syst. | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% |  | Stalled - No normative R4 work planned
WI-0072 | Modbus Interworking | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% |  | TS Completed at TP46
WI-0076 | Lightweight oneM2M Services | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% |  | Stage 2 Frozen, Stage 3 in progress
WI-0077 | Attribute based Access Control Policy | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% |  | Stage 2 Frozen, Stage 3 in progress
WI-0080 | Edge and Fog Computing | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% |  | Stage 2 Frozen, Stage 3 in progress
WI-0083 | oneM2M Service Subscribers and Users | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% |  | Stage 2 Frozen, Stage 3 in progress
WI-0089 | Getting started with oneM2M | 20% | 22% | 22% | 22% | 22% | 22% | 22% | 22% |  | Stalled - No normative R4 work planned
WI-0090 | oneM2M and Zigbee interworking | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% |  | TR work in progress
WI-0091 | oneM2M Services and Platform Discovery | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% |  | Stalled - No normative R4 work planned
WI-0093 | Action Triggering Enhancements | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% |  | Stage 2 Frozen, Stage 3 in progress
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations | SDS44: 30%; SDS45: 50%; SDS46: 55% | Rel-5 TR work in progress
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | [9 empty] | Rel-5 TR work in progress | bar: SDS39 to SDS46
WI-0100 | oneM2M and SensorThings API | [9 empty] | Rel-5 TR work in progress | bar: SDS39 to SDS46
WI-0102 | System enhancements to support Data License Management | [9 empty] | Rel-5 TR work in progress | bar: SDS39 to SDS46
WI-0071 | oneM2M and W3C Web of Things Interworking | 25% | 25% | 25% | 25% | 25% | 25% | 25% |  |  | Stalled / Close
WI-0082 | 3GPP V2X Interworking | 15% | 18% | 20% | 20% | 20% | 20% | 20% |  |  | Stalled / Close
WI-0088 | M2M/IoT Application and Component Configuration | 15% | 15% | 15% | 15% | 15% | 15% | 15% |  |  | Stalled / Close

## PRO Work Req'd
Contribution | Description | Spec | Release | Mtg Agreed | Company | TS-0004 Contribution | TS-0008 Contribution | TS-0009 Contribution | Impacts Schemas | Comments
ARC-2017-0395R03 | requestAggregationForPollingChannel-R4 | TS-0001 | R4 | 34 | Convida
ARC-2018-0206R08 | Action_Triggering_resources_procedures_from_TR-0021 | TS-0001 | R4 | 37 | Convida
ARC-2018-0214 | CR_LocationPolicy_Parent_R4 | TS-0001 | R4 | 36 | Convida
ARC-2018-0240R03 | new_[storage]_management_object_to_TS-0001 | TS-0001 | R4 | 37 | Orange
ARC-2018-0276R01 | Action_Triggering_resources_operation | TS-0001 | R4 | 37 | Huawei
SDS-2019-0108R05 | New_Attribute_in_Node_Resource(R4) | TS-0001 | R4 | 39.x | C-DOT | SDS-2019-0122R03 | N/A | N/A | Yes
SDS-2019-0035R05 | SubscriptionNotificationContentType | TS-0001 | R2 | 39.x | C-DOT | N/A | N/A | N/A | Maybe
SDS-2019-0034R06 | SubscriptionNotificationContentType | TS-0001 | R3 | 39.x | C-DOT | N/A | N/A | N/A | Maybe
SDS-2019-0272 | SubscriptionNotificationContentType | TS-0001 | R4 | 39.x | C-DOT | N/A | N/A | N/A | Maybe
SDS-2019-0134R01 | CSE_AE_registration_data_model_changes(R3) | TS-0006 | R3 | 39.x | C-DOT | N/A | N/A | N/A | Yes
SDS-2019-0135R01 | CSE_AE_registration_data_model_changes(R3) | TS-0005 | R3 | 39.x | C-DOT | N/A | N/A | N/A | Yes
SDS-2019-0236 | TS-0001 R2 CR clean-up on semantic formats | TS-0001 | R2 | 40 | KETI | SDS-2018-0002R04-TS-0004_R2_CR | N/A | N/A
SDS-2019-0234 | TS-0001 R3 CR clean-up on semantic formats | TS-0001 | R3 | 40 | KETI | SDS-2018-0001R04-TS-0004_R3_CR | N/A | N/A
SDS-2019-0235 | TS-0001 R4 CR clean-up on semantic formats | TS-0001 | R4 | 40 | KETI | N/A | N/A | N/A
SDS-2019-0237 | TS-0034 R3 CR clean-up on semantic formats | TS-0034 | R3 | 40 | KETI | N/A | N/A | N/A
SDS-2019-0213 | TS0001-Time_Series_Access_Permissions_R2 | TS-0001 | R2 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0212 | TS0001-Time_Series_Access_Permissions_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0286 | TS0001-Time_Series_Access_Permissions_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0245 | TS0001-Time_Series_Attribute_Multiplicity_R2 | TS-0001 | R2 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0246 | TS0001-Time_Series_Attribute_Multiplicity_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0287 | TS0001-Time_Series_Attribute_Multiplicity_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0257R01 | TS0001-Time_Series_Resource_Name_R2 | TS-0001 | R2 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0256 | TS0001-Time_Series_Resource_Name_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0294 | TS0001-Time_Series_Resource_Name_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0250R01 | TS0001-Time_Series_Missing_Data_Notification_R2 | TS-0001 | R2 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0249R02 | TS0001-Time_Series_Missing_Data_Notification_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0290R01 | TS0001-Time_Series_Missing_Data_Notification_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0296 | TS-0001_CR_External_Group_Identifiers_R3 | TS-0001 | R3 | 40 | KDDI | N/A | N/A | N/A | No
SDS-2019-0206R01 | TS-0001_CR_External_Group_Identifiers | TS-0001 | R4 | 40 | KDDI | N/A | N/A | N/A | No
SDS-2019-0307 | A-36.2-1_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0308 | A-36.2-1_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0309R01 | A-36.2-5_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0310 | A-36.2-5_R3 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0248R01 | TS0001-Time_Series_Attribute_Uniqueness_R2 | TS-0001 | R2 | 41 | Convida | SDS-2019-0395R01 | N/A | N/A | No
SDS-2019-0247R01 | TS0001-Time_Series_Attribute_Uniqueness_R3 | TS-0001 | R3 | 41 | Convida | SDS-2019-0394R01 | N/A | N/A | No
SDS-2019-0289R01 | TS0001-Time_Series_Attribute_Uniqueness_R4 | TS-0001 | R4 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0253R03 | TS0001-Time_Series_New_Attribute_R3 | TS-0001 | R3 | 41 | Convida |  |  |  | Yes
SDS-2019-0292R02 | TS0001-Time_Series_New_Attribute_R4 | TS-0001 | R4 | 41 | Convida |  |  |  | Yes
SDS-2019-0259R01 | TS0001-Time_Series_Subscription_R2 | TS-0001 | R2 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0258R01 | TS0001-Time_Series_Subscription_R3 | TS-0001 | R3 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0295R01 | TS0001-Time_Series_Subscription_R4 | TS-0001 | R4 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0269R01 | TS0004-Time_Series_Monitoring_R2 | TS-0001 | R2 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0252 | TS0001-Time_Series_Monitoring_R2 | TS-0001 | R2 | 40 | Convida | SDS-2019-0269R01 | N/A | N/A | No
SDS-2019-0251 | TS0001-Time_Series_Monitoring_R3 | TS-0001 | R3 | 40 | Convida | SDS-2019-0268R01 | N/A | N/A | No
SDS-2019-0291 | TS0001-Time_Series_Monitoring_R4 | TS-0001 | R4 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0360R02 | TS-0001-QoS_Resource | TS-0001 | R4 | 41 | Huawei |  |  |  | Yes
SDS-2019-0370R01 | Enable Somecast with Load Balancing | TS-0001 | R4 | 41 | Convida |  |  |  | Yes
SDS-2019-0398 | bug_fix_of_table_9_6_1_1-1_in_TS-0001 v2_24_0 | TS-0001 | R2 | 41 | BOE | N/A | N/A | N/A | No
SDS-2019-0397 | bug_fix_of_table_9_6_1_1-1_in_TS-0001 v3_16_0 | TS-0001 | R3 | 41 | BOE | N/A | N/A | N/A | No
SDS-2019-0380 | bug fix of table 9.6.1.1-1 in TS-0001 | TS-0001 | R4 | 41 | BOE | N/A | N/A | N/A | No
SDS-2019-0403 | Adding_a_new_element_XOR_to_TS-0001 | TS-0001 | R4 | 41 | CMCC | SDS-2019-0376R02 | N/A | N/A | Yes
SDS-2019-0277 | TS0001-CR-specializationID_name_R3 | TS-0001 | R3 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0278 | TS0001-CR-specializationID_name_R4 | TS-0001 | R4 | 41 | Convida | N/A | N/A | N/A | No
TS-0001 (R2) | TS-0001 (R3)
SDS-2019-0054 | ARC-2018-0315R01
SDS-2019-0131 | SDS-2019-0036R04
SDS-2019-0113R01 | SDS-2019-0053
SDS-2019-0143R02 | SDS-2019-0055
SDS-2019-0149 | SDS-2019-0112R01
SDS-2019-0152 | SDS-2019-0102
SDS-2019-0123R01
SDS-2019-0144R01
SDS-2019-0017R01
ARC-2018-318R03
SDS-2019-0151
SDS-2019-0003
TS-0034
SDS-2019-0120R02