## Schedule
# | Date | Time | Meeting name
1 | 2020-12-01 | 12:00 – 15:00 | SDS
2 | 2020-12-03 | 12:00 – 15:00 | SDS
3 | 2020-12-07 | 12:00 – 15:00 | SDS
4 | 2020-12-09 | 12:00 – 15:00 | SDS
5 | 2020-12-14 | 12:00 – 15:00 | SDS
6 | 2020-12-16 | 12:00 – 15:00 | SDS

## Contribs
SHORT DOC NB | SHORTNAME | SOURCE | UPLOADED | STATUS | DOC TYPE | VERS | TS/TR
SDS-2020-0019R11 | TS-0004-nwMonitoringReq_resource_R4 | KDDI | 2020-11-10 | Draft | CR | R4 | TS-0004
SDS-2020-0249R06 | TS-0001-nwMonitoringReq_resource_editorial_R4 | KDDI | 2020-11-10 | Draft | CR | R4 | TS-0001
SDS-2020-0248R08 | TS-0026-Network Monitoring Request_editorial_R4 | KDDI | 2020-11-10 | Draft | CR | R4 | TS-0026
SDS-2020-0322R01 | TS-0004 announceability corrections - R4 | IBM | 2020-11-19 | Draft | CR | R4 | TS-0004
SDS-2020-0324R01 | TS-0004 announceability corrections - R3 | IBM | 2020-11-19 | Draft | CR | R3 | TS-0004
SDS-2020-0318 | TS-0004_XML_construction_for_flexContainerInstance_Rel4 | Orange | 2020-11-16 | Draft | CR | R4 | TS-0004
SDS-2020-0306R01 | TS-0004 Adding flexContainer shortname_R4 | KETI | 2020-11-18 | Draft | CR | R4 | TS-0004
SDS-2020-0327 | TS-0004_AnnouncementUpdate_R3 | Andreas Kraft, DT; Bob Flynn, Chordant; Miguel Angel Reina Ortega, ETSI | 2020-11-19 | Draft | CR | R4 | TS-0004
SDS-2020-0330 | TS-0003-attribute_level_acps_R4 | Convida | 2020-11-30 | Draft | CR | R4 | TS-0003
SDS-2020-0114R05 | TS-0004-attribute_level_acps_R4 | Convida | 2020-11-30 | Draft | CR | R4 | TS-0004
SDS-2020-0329 | TR-0057_Location Policy | ETSI | 2020-11-30 | Draft | INC | R4 | TR-0057
SDS-2020-0257R04 | TS-0004-m2m_service_user_procedures_R4 | Convida | 2020-10-23 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0123R05 | TS-0004-m2m-service_user_ids_params_R4 | Convida | 2020-10-17 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0124R02 | TS-0004-m2m_service_user_resources_R4 | Convida | 2020-10-18 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0301R01 | TS-0001-service_subscription_limits_MNT_R4 | Convida | 2020-10-21 | Draft (Peter to review) | CR | R4 | TS-0001
SDS-2020-0286R04 | TS-0001-action_dependency_resources_MNT_R4 | Convida | 2020-10-04 | Draft (Peter to review) | CR | R4 | TS-0001
SDS-2020-0287R05 | TS-0004-action_dependency_resources_R4 | Convida | 2020-10-04 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0292R02 | TS-0001-software_campaign_resource_MNT_R4 | Convida | 2020-10-11 | Draft (Peter to review) | CR | R4 | TS-0001
SDS-2020-0291R02 | TS-0004-software_campaign_resource_R4 | Convida | 2020-10-11 | Draft (Peter to review) | CR | R4 | TS-0004
SDS-2020-0270 | Adding missing URL encodings for parent and child attributes to TS-0009 | Andreas Kraft (Deutsche Telekom), Andreas Neubacher (Deutsche Telekom) | 2020-09-14 | Tentatively Agreed (Need R4 Mirror) | CR | R3 | TS-0009
SDS-2020-0309 | Adding missing URL encodings for parent and child attributes to TS-0009 (R2) | Andreas Kraft (Deutsche Telekom), Andreas Neubacher (Deutsche Telekom) | 2020-10-21 | Tentatively Agreed (Need R4 Mirror) | CR | R2 | TS-0009
SDS-2020-0129R01 | TS-0001_primitive_profile_maintenance_R4 | Convida | 2020-08-25 | Revision Expected | CR | R4 | TS-0001
SDS-2020-0131R01 | TS-0004-primitiveProfile_procedures_R4 | Convida | 2020-08-25 | Revision Expected | CR | R4 | TS-0004

## CR Packs
TS-0001 (R2) | TS-0001 (R3) | TS-0001 (R4) | TS-0001 (R5) | TS-0003 (R2) | TS-0003 (R3) | TS-0003 (R4) | TS-0004 (R2) | TS-0004 (R3) | TS-0004 (R4) | TS-0005(R3) | TS-0006(R3) | TS-0008 (R2) | TS-0008 (R3) | TS-0008 (R4) | TS-0009 (R2) | TS-0009 (R3) | TS-0009 (R4) | TS-0010 (R2) | TS-0010 (R3) | TS-0010 (R4) | TS-0014 (R2) | TS-0014 (R3) | TS-0022 (R3) | TS-0022 (R4) | TS-0026 (R3) | TS-0026 (R4) | TS-0034 (R4)
|  |  | SDS-2020-0305R01 | [5 empty] | SDS-2020-0130R03
SDS-2020-0303R01

## WI
WI | Title | SDS39 | SDS40 | SDS41 | SDS42 | SDS43 | SDS44 | SDS45 | SDS46 | SDS47 | Comments
WI-0053 | Enhancements on Semantic Support | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% | 100% | Stage 3 Completed at TP46
WI-0058 | Interworking with 3GPP networks | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% | 100% | Stage 3 Completed at TP46
WI-0064 | Adaption of oneM2M for Smart City | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Stalled - No normative R4 work planned
WI-0069 | Heterogen. identificat. service in oneM2M syst. | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | Stalled - No normative R4 work planned
WI-0072 | Modbus Interworking | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% | 100% | TS Completed at TP46
WI-0076 | Lightweight oneM2M Services | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% | 90% | Stage 3 in progress
WI-0077 | Attribute based Access Control Policy | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% | 93% | Stage 3 in progress
WI-0080 | Edge and Fog Computing | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% | 90% | Stage 3 in progress
WI-0083 | oneM2M Service Subscribers and Users | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% | 90% | Stage 3 in progress
WI-0089 | Getting started with oneM2M | 20% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | Stalled - No normative R4 work planned
WI-0091 | oneM2M Services and Platform Discovery | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | Stalled - No normative R4 work planned
WI-0093 | Action Triggering Enhancements | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | Stage 3 in progress
WI-0090 | oneM2M and Zigbee interworking | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% | 35% | Rel-5 TR work in progress
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations | SDS44: 30%; SDS45: 50%; SDS46: 55%; SDS47: 65% | Rel-5 TR work in progress
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | [9 empty] | Rel-5 TR work in progress | bar: SDS39 to SDS47
WI-0100 | oneM2M and SensorThings API | SDS45: 5%; SDS46: 5%; SDS47: 15% | Rel-5 TR work in progress
WI-0102 | System enhancements to support Data License Management | SDS46: 5%; SDS47: 15% | Rel-5 TR work in progress
WI-0071 | oneM2M and W3C Web of Things Interworking | 25% | 25% | 25% | 25% | 25% | 25% | 25% |  |  | Stalled / Close
WI-0082 | 3GPP V2X Interworking | 15% | 18% | 20% | 20% | 20% | 20% | 20% |  |  | Stalled / Close
WI-0088 | M2M/IoT Application and Component Configuration | 15% | 15% | 15% | 15% | 15% | 15% | 15% |  |  | Stalled / Close

## PRO Work Req'd
Contribution | Description | Spec | Release | Mtg Agreed | Company | TS-0004 Contribution | TS-0008 Contribution | TS-0009 Contribution | Impacts Schemas | Comments
ARC-2017-0395R03 | requestAggregationForPollingChannel-R4 | TS-0001 | R4 | 34 | Convida
ARC-2018-0206R08 | Action_Triggering_resources_procedures_from_TR-0021 | TS-0001 | R4 | 37 | Convida
ARC-2018-0214 | CR_LocationPolicy_Parent_R4 | TS-0001 | R4 | 36 | Convida
ARC-2018-0240R03 | new_[storage]_management_object_to_TS-0001 | TS-0001 | R4 | 37 | Orange
ARC-2018-0276R01 | Action_Triggering_resources_operation | TS-0001 | R4 | 37 | Huawei
SDS-2019-0108R05 | New_Attribute_in_Node_Resource(R4) | TS-0001 | R4 | 39.x | C-DOT | SDS-2019-0122R03 | N/A | N/A | Yes
SDS-2019-0035R05 | SubscriptionNotificationContentType | TS-0001 | R2 | 39.x | C-DOT | N/A | N/A | N/A | Maybe
SDS-2019-0034R06 | SubscriptionNotificationContentType | TS-0001 | R3 | 39.x | C-DOT | N/A | N/A | N/A | Maybe
SDS-2019-0272 | SubscriptionNotificationContentType | TS-0001 | R4 | 39.x | C-DOT | N/A | N/A | N/A | Maybe
SDS-2019-0134R01 | CSE_AE_registration_data_model_changes(R3) | TS-0006 | R3 | 39.x | C-DOT | N/A | N/A | N/A | Yes
SDS-2019-0135R01 | CSE_AE_registration_data_model_changes(R3) | TS-0005 | R3 | 39.x | C-DOT | N/A | N/A | N/A | Yes
SDS-2019-0236 | TS-0001 R2 CR clean-up on semantic formats | TS-0001 | R2 | 40 | KETI | SDS-2018-0002R04-TS-0004_R2_CR | N/A | N/A
SDS-2019-0234 | TS-0001 R3 CR clean-up on semantic formats | TS-0001 | R3 | 40 | KETI | SDS-2018-0001R04-TS-0004_R3_CR | N/A | N/A
SDS-2019-0235 | TS-0001 R4 CR clean-up on semantic formats | TS-0001 | R4 | 40 | KETI | N/A | N/A | N/A
SDS-2019-0237 | TS-0034 R3 CR clean-up on semantic formats | TS-0034 | R3 | 40 | KETI | N/A | N/A | N/A
SDS-2019-0213 | TS0001-Time_Series_Access_Permissions_R2 | TS-0001 | R2 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0212 | TS0001-Time_Series_Access_Permissions_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0286 | TS0001-Time_Series_Access_Permissions_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0245 | TS0001-Time_Series_Attribute_Multiplicity_R2 | TS-0001 | R2 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0246 | TS0001-Time_Series_Attribute_Multiplicity_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0287 | TS0001-Time_Series_Attribute_Multiplicity_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0257R01 | TS0001-Time_Series_Resource_Name_R2 | TS-0001 | R2 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0256 | TS0001-Time_Series_Resource_Name_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0294 | TS0001-Time_Series_Resource_Name_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0250R01 | TS0001-Time_Series_Missing_Data_Notification_R2 | TS-0001 | R2 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0249R02 | TS0001-Time_Series_Missing_Data_Notification_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0290R01 | TS0001-Time_Series_Missing_Data_Notification_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0296 | TS-0001_CR_External_Group_Identifiers_R3 | TS-0001 | R3 | 40 | KDDI | N/A | N/A | N/A | No
SDS-2019-0206R01 | TS-0001_CR_External_Group_Identifiers | TS-0001 | R4 | 40 | KDDI | N/A | N/A | N/A | No
SDS-2019-0307 | A-36.2-1_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0308 | A-36.2-1_R4 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0309R01 | A-36.2-5_R3 | TS-0001 | R3 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0310 | A-36.2-5_R3 | TS-0001 | R4 | 40 | Convida | N/A | N/A | N/A | No
SDS-2019-0248R01 | TS0001-Time_Series_Attribute_Uniqueness_R2 | TS-0001 | R2 | 41 | Convida | SDS-2019-0395R01 | N/A | N/A | No
SDS-2019-0247R01 | TS0001-Time_Series_Attribute_Uniqueness_R3 | TS-0001 | R3 | 41 | Convida | SDS-2019-0394R01 | N/A | N/A | No
SDS-2019-0289R01 | TS0001-Time_Series_Attribute_Uniqueness_R4 | TS-0001 | R4 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0253R03 | TS0001-Time_Series_New_Attribute_R3 | TS-0001 | R3 | 41 | Convida |  |  |  | Yes
SDS-2019-0292R02 | TS0001-Time_Series_New_Attribute_R4 | TS-0001 | R4 | 41 | Convida |  |  |  | Yes
SDS-2019-0259R01 | TS0001-Time_Series_Subscription_R2 | TS-0001 | R2 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0258R01 | TS0001-Time_Series_Subscription_R3 | TS-0001 | R3 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0295R01 | TS0001-Time_Series_Subscription_R4 | TS-0001 | R4 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0269R01 | TS0004-Time_Series_Monitoring_R2 | TS-0001 | R2 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0252 | TS0001-Time_Series_Monitoring_R2 | TS-0001 | R2 | 40 | Convida | SDS-2019-0269R01 | N/A | N/A | No
SDS-2019-0251 | TS0001-Time_Series_Monitoring_R3 | TS-0001 | R3 | 40 | Convida | SDS-2019-0268R01 | N/A | N/A | No
SDS-2019-0291 | TS0001-Time_Series_Monitoring_R4 | TS-0001 | R4 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0360R02 | TS-0001-QoS_Resource | TS-0001 | R4 | 41 | Huawei |  |  |  | Yes
SDS-2019-0370R01 | Enable Somecast with Load Balancing | TS-0001 | R4 | 41 | Convida |  |  |  | Yes
SDS-2019-0398 | bug_fix_of_table_9_6_1_1-1_in_TS-0001 v2_24_0 | TS-0001 | R2 | 41 | BOE | N/A | N/A | N/A | No
SDS-2019-0397 | bug_fix_of_table_9_6_1_1-1_in_TS-0001 v3_16_0 | TS-0001 | R3 | 41 | BOE | N/A | N/A | N/A | No
SDS-2019-0380 | bug fix of table 9.6.1.1-1 in TS-0001 | TS-0001 | R4 | 41 | BOE | N/A | N/A | N/A | No
SDS-2019-0403 | Adding_a_new_element_XOR_to_TS-0001 | TS-0001 | R4 | 41 | CMCC | SDS-2019-0376R02 | N/A | N/A | Yes
SDS-2019-0277 | TS0001-CR-specializationID_name_R3 | TS-0001 | R3 | 41 | Convida | N/A | N/A | N/A | No
SDS-2019-0278 | TS0001-CR-specializationID_name_R4 | TS-0001 | R4 | 41 | Convida | N/A | N/A | N/A | No
TS-0001 (R2) | TS-0001 (R3)
SDS-2019-0054 | ARC-2018-0315R01
SDS-2019-0131 | SDS-2019-0036R04
SDS-2019-0113R01 | SDS-2019-0053
SDS-2019-0143R02 | SDS-2019-0055
SDS-2019-0149 | SDS-2019-0112R01
SDS-2019-0152 | SDS-2019-0102
SDS-2019-0123R01
SDS-2019-0144R01
SDS-2019-0017R01
ARC-2018-318R03
SDS-2019-0151
SDS-2019-0003
TS-0034
SDS-2019-0120R02