## Contribs
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | DOC TYPE | Release | TS/TR
SDS-2020-0295R03 | OGC-to-oneM2M Data Mapping | Deutsche Telekom | Draft | New feature | R5 | TS-0065
SDS-2021-0154 | Solution on Advanced Semantic Discovery | KETI (ETSI STF 589) | Draft | New feature | R5 | TS-0034
SDS-2021-0121R03 | TS-0004-state_processManagement_resources_R4 | Convida | Agreed | New feature | R4 | TS-0004
SDS-2021-0120R04 | TS-0001-state_processManagement_resource_MNT_R4 | Convida | Draft | New feature | R4 | TS-0001
SDS-2020-0350R03 | TS-0001-permissions_result_content_value_R4 | Convida | Draft | New feature | R4 | TS-0001
SDS-2020-0347R02 | TS-0004-permissions_result_content_value_R4 | Convida | Draft | New feature | R4 | TS-0004
SDS-2020-0114R08 | TS-0004-attribute_level_acps_R4 | Convida | Draft | New feature | R4 | TS-0004
SDS-2020-0330R03 | TS-0003-attribute_level_acps_R4 | Convida | Draft | New feature | R4 | TS-0003
SDS-2020-0301R02 | TS-0001-service_subscription_limits_MNT_R4 | Convida | Draft | New feature | R4 | TS-0001
SDS-2020-0257R06 | TS-0004-m2m_service_user_procedures_R4 | Convida | Draft | New feature | R4 | TS-0004
SDS-2020-0124R04 | TS-0004-m2m_service_user_resources_R4 | Convida | Draft | New feature | R4 | TS-0004
SDS-2020-0292R06 | TS-0001-software_campaign_resource_MNT_R4 | Convida | Draft | New feature | R4 | TS-0001
SDS-2020-0291R06 | TS-0004_software_campaign_resource_R4 | Convida | Draft | New feature | R4 | TS-0004

## CR Packs
TS-0001 (R2) | TS-0001 (R3) | TS-0001 (R4) | TS-0001 (R5) | TS-0003 (R2) | TS-0003 (R3) | TS-0003 (R4) | TS-0004 (R2) | TS-0004 (R3) | TS-0004 (R4) | TS-0005(R3) | TS-0006(R3) | TS-0008 (R2) | TS-0008 (R3) | TS-0008 (R4) | TS-0009 (R2) | TS-0009 (R3) | TS-0009 (R4) | TS-0010 (R2) | TS-0010 (R3) | TS-0010 (R4) | TS-0014 (R2) | TS-0014 (R3) | TS-0022 (R2) | TS-0022 (R3) | TS-0022 (R4) | TS-0026 (R3) | TS-0026 (R4) | TS-0034 (R4)
SDS-2021-0121R03
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SDS 50.2

## WI
WI | Title | SDS39 | SDS40 | SDS41 | SDS42 | SDS43 | SDS44 | SDS45 | SDS46 | SDS47 | SDS48 | SDS49 | SDS50 | Comments
WI-0053 | Enhancements on Semantic Support | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0058 | Interworking with 3GPP networks | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0064 | Adaption of oneM2M for Smart City | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Stalled - No normative R4 work planned
WI-0069 | Heterogen. identificat. service in oneM2M syst. | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | Stalled - No normative R4 work planned
WI-0072 | Modbus Interworking | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0076 | Lightweight oneM2M Services | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% | 90% | 93% | 97% | 97% | R4 Stage 3 wrapping up
WI-0077 | Attribute based Access Control Policy | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% | 93% | 95% | 97% | 97% | R4 Stage 3 wrapping up
WI-0080 | Edge and Fog Computing | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% | 90% | 95% | 97% | 97% | R4 Stage 3 wrapping up
WI-0083 | oneM2M Service Subscribers and Users | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% | 90% | 90% | 91% | 95% | R4 Stage 3 wrapping up
WI-0089 | Getting started with oneM2M | 20% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 25% | 30% | 30% | R4/R5 work in progress
WI-0091 | oneM2M Services and Platform Discovery | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Stalled - Push to R5?
WI-0093 | Action Triggering Enhancements | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | 91% | 93% | R4 Stage 3 in progress
WI-0090 | oneM2M and Zigbee interworking | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% | 35% | 35% | 35% | 35% | Rel-5 TR work in progress
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations | SDS44: 30%; SDS45: 50%; SDS46: 55%; SDS47: 65%; SDS48: 65%; SDS49: 65%; SDS50: 65% | Rel-5 TR work in progress
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | [12 empty] | Rel-5 TR work in progress | bar: SDS44 to SDS50
WI-0100 | oneM2M and SensorThings API | SDS45: 5%; SDS46: 5%; SDS47: 15%; SDS48: 20%; SDS49: 20%; SDS50: 20% | Rel-5 TR work in progress
WI-0102 | System enhancements to support Data License Management | SDS46: 5%; SDS47: 15%; SDS48: 30%; SDS49: 40%; SDS50: 45% | Rel-5 TR work in progress
WI-0071 | oneM2M and W3C Web of Things Interworking | SDS39: 25%; SDS40: 25%; SDS41: 25%; SDS42: 25%; SDS43: 25%; SDS44: 25%; SDS45: 25% | Stalled / Close
WI-0082 | 3GPP V2X Interworking | SDS39: 15%; SDS40: 18%; SDS41: 20%; SDS42: 20%; SDS43: 20%; SDS44: 20%; SDS45: 20% | Stalled / Close
WI-0088 | M2M/IoT Application and Component Configuration | SDS39: 15%; SDS40: 15%; SDS41: 15%; SDS42: 15%; SDS43: 15%; SDS44: 15%; SDS45: 15% | Stalled / Close