## Contribs
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | DOC TYPE | Release | TS/TR
SDS-2021-0096R01 | Add copying of label attribute when creating flexContainerInstance resources | Deutsche Telekom, Orange | Draft | New feature | R4 | TS-0004
SDS-2021-0207 | Add copying of label attribute when creating flexContainerInstance resources (TS-0001) | Deutsche Telekom, Orange | Draft | New feature | R4 | TS-0001
SDS-2021-0200R01 | TS0001_timeseries_procedures | Exacta | Draft | Change | R4 | TS-0001
SDS-2021-0201R01 | TS0004_timeseries_procedures | Exacta | Draft | Change | R4 | TS-0004
SDS-2021-0195R01 | TS-0001-Process_Management_CSF_Description_R4 | Convida | Draft | New feature | R4 | TS-0001
SDS-2021-0062R01 | TS-0001_CSEID_remoteCSE_R4 | C-DOT | Draft | Change | R4 | TS-0001
SDS-2021-0063R01 | TS-0001_CSEID_remoteCSE_R3 | C-DOT | Draft | Change | R3 | TS-0001
SDS-2021-0064R01 | TS-0001_CSEID_remoteCSE_R2 | C-DOT | Draft | Change | R2 | TS-0001
SDS-2020-0114R10 | TS-0004-attribute_level_acps_R4 | Convida | Draft | New feature | R4 | TS-0004
SDS-2020-0330R05 | TS-0003-attribute_level_acps_R4 | Convida | Draft | New feature | R4 | TS-0003
SDS-2021-0041R01 | Short names consolidation TS-0022 | Deutsche Telekom | Noted | Change | R4 | TS-0022
SDS-2021-0042R01 | Short names consolidation TS-0032 | Deutsche Telekom | Draft | Change | R4 | TS-0032
SDS-2021-0043R01 | Short names consolidation TS-0004 | Deutsche Telekom | Noted | Change | R4 | TS-0004
SDS-2021-0131 | GapsInSemanticsQuery | C-DOT | Draft | Change | R4 | TS-0001
SDS-2021-0143 | TS-0004_SparqlQueryStatusCode_R4 | C-DOT | Draft | Change | R4 | TS-0004
SDS-2021-0144R01 | TS-0004_SparqlQueryStatusCode_R3 | C-DOT | Draft | Change | R3 | TS-0004
SDS-2021-0145 | TS-0004_SparqlQueryStatusCode_R2 | C-DOT | Draft | Change | R2 | TS-0004
SDS-2021-0146 | TS-0001_Privelegs_For_Scope_Of_SemanticQuery_R4 | C-DOT | Draft | Change | R4 | TS-0001
SDS-2020-0374R04 | Allow non-confirmable messages in CoAP | IBM | Draft | Change | R4 | TS-0008
SDS-2021-0185 | Adding [credentials] specialization to TS-0022 | Deutsche Telekom | Draft | New feature | R5 | TS-0022
SDS-2021-0190 | Clarification for m2m:absRelTimestamp in TS-0004 | Deutsche Telekom, Exacta | Draft | Change | R5 | TS-0004
SDS-2021-0113 | Adding optional dataGenerationTime to contentInstance (TS-0001) | Deutsche Telekom | Draft | New feature | R5 | TS-0001
SDS-2021-0114R01 | Adding optional dataGenerationTime to contentInstance | Deutsche Telekom | Draft | New feature | R5 | TS-0004
SDS-2021-0119R02 | semantic mapping between IoT ontology and object identifiers | CMCC | Draft | New feature | R5 | TR-0033
SDS-2021-0180R03 | enum_areaNwkType_R4 | C-DOT | Noted | Change | R4 | TS-0004
SDS-2021-0188R01 | enum_areaNwkType_R4 | C-DOT | Draft | Change | R4 | TS-0004
Revision expected
SDS-2021-0181R03 | Introduction of new resource types for Advanced Semantic Discovery | JK Consulting | Noted | New feature | R5 | TS-0001
Agreed
SDS-2021-0044R04 | TS-0001_notificationEventType_for_timeSeries_R4 | ETSI | Agreed | Change | R4 | TS-0001
SDS-2021-0045R03 | TS-0004_notificationEventType_for_timeSeries_R4 | ETSI | Agreed | Change | R4 | TS-0004
SDS-2020-0361R08 | TS-0001_notificationEventType_for_timeSeries_R3 | ETSI | Agreed | Change | R3 | TS-0001
SDS-2020-0362R07 | TS-0004_notificationEventType_for_timeSeries_R3 | ETSI | Agreed | Change | R3 | TS-0004
SDS-2020-0380 | Adding missing header mapping for M2M Service User Identifier | Deutsche Telekom | Already Agreed | New feature | R4 | TS-0009
SDS-2020-0292R07 | TS-0001-software_campaign_resource_MNT_R4 | Convida | Agreed | New feature | R4 | TS-0001
SDS-2020-0291R08 | TS-0004_software_campaign_resource_R4 | Convida | Agreed | New feature | R4 | TS-0004
SDS-2021-0208 | software_MNT_Mirror | Convida | Agreed | Change | R2 | TS-0004
SDS-2021-0209R01 | software_MNT_Mirror | Convida | Agreed | Change | R3 | TS-0004
SDS-2020-0350R03 | TS-0001-permissions_result_content_value_R4 | Convida | Agreed | New feature | R4 | TS-0001
SDS-2020-0347R02 | TS-0004-permissions_result_content_value_R4 | Convida | Agreed | New feature | R4 | TS-0004
SDS-2021-0152R01 | Clarification for UPDATE of pendingNotification attribute | Deutsche Telekom, ETSI | Agreed | Change | R4 | TS-0004
SDS-2021-0193R01 | TS-0009_Missing_HTTP_RSCs_Req_Params_R4 | Convida | Agreed | Change | R4 | TS-0009
SDS-2021-0194 | TS-0008_Missing_CoAP_RSCs_Req_Params_R4 | Convida | Agreed | Change | R4 | TS-0008
SDS-2021-0196R01 | TS-0001-Session_Management_CSF_Description_R4 | Convida | Agreed | New feature | R4 | TS-0001
SDS-2021-0199R01 | TS-0004 Remove Generic Interworking Resources-R4 | IBM | Agreed | Change | R4 | TS-0004
SDS-2021-0203 | Child resource tables missing from TS-0004 Annex J-R2 | IBM | Agreed | Change | R2 | TS-0004
SDS-2021-0204 | TS-0004 Remove Generic Interworking Resources-R3 | IBM | Agreed | Change | R3 | TS-0004

## CR Packs
TS-0001 (R2) | TS-0001 (R3) | TS-0001 (R4) | TS-0001 (R5) | TS-0003 (R2) | TS-0003 (R3) | TS-0003 (R4) | TS-0004 (R2) | TS-0004 (R3) | TS-0004 (R4) | TS-0005(R3) | TS-0006(R3) | TS-0008 (R2) | TS-0008 (R3) | TS-0008 (R4) | TS-0009 (R2) | TS-0009 (R3) | TS-0009 (R4) | TS-0010 (R2) | TS-0010 (R3) | TS-0010 (R4) | TS-0014 (R2) | TS-0014 (R3) | TS-0022 (R2) | TS-0022 (R3) | TS-0022 (R4) | TS-0026 (R3) | TS-0026 (R4) | TS-0034 (R4)
| SDS-2020-0361R08 | SDS-2021-0120R05 |  |  |  |  | SDS-2021-0208 | SDS-2020-0362R07 | SDS-2021-0121R03 |  |  |  |  | SDS-2021-0194 |  |  | SDS-2021-0193R01
|  | SDS-2020-0301R02 |  |  |  |  | SDS-2021-0203 | SDS-2021-0209R01 | SDS-2020-0124R04
|  | SDS-2021-0044R04 | [5 empty] | SDS-2021-0204 | SDS-2020-0257R09
|  | SDS-2020-0292R07 | [6 empty] | SDS-2021-0044R04
|  | SDS-2020-0350R03 | [6 empty] | SDS-2020-0291R08
|  | SDS-2021-0196R01 | [6 empty] | SDS-2020-0347R02
SDS-2021-0152R01
SDS-2021-0199R01
Note on J2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SDS 50.2

## WI
WI | Title | SDS39 | SDS40 | SDS41 | SDS42 | SDS43 | SDS44 | SDS45 | SDS46 | SDS47 | SDS48 | SDS49 | SDS50 | Comments
WI-0053 | Enhancements on Semantic Support | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0058 | Interworking with 3GPP networks | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0064 | Adaption of oneM2M for Smart City | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Stalled - No normative R4 work planned
WI-0069 | Heterogen. identificat. service in oneM2M syst. | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | Stalled - No normative R4 work planned
WI-0072 | Modbus Interworking | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0076 | Lightweight oneM2M Services | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% | 90% | 93% | 97% | 97% | R4 Stage 3 wrapping up
WI-0077 | Attribute based Access Control Policy | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% | 93% | 95% | 97% | 97% | R4 Stage 3 wrapping up
WI-0080 | Edge and Fog Computing | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% | 90% | 95% | 97% | 97% | R4 Stage 3 wrapping up
WI-0083 | oneM2M Service Subscribers and Users | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% | 90% | 90% | 91% | 95% | R4 Stage 3 wrapping up
WI-0089 | Getting started with oneM2M | 20% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 25% | 30% | 30% | R4/R5 work in progress
WI-0091 | oneM2M Services and Platform Discovery | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Stalled - Push to R5?
WI-0093 | Action Triggering Enhancements | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | 91% | 93% | R4 Stage 3 in progress
WI-0090 | oneM2M and Zigbee interworking | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% | 35% | 35% | 35% | 35% | Rel-5 TR work in progress
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations | SDS44: 30%; SDS45: 50%; SDS46: 55%; SDS47: 65%; SDS48: 65%; SDS49: 65%; SDS50: 65% | Rel-5 TR work in progress
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | [12 empty] | Rel-5 TR work in progress | bar: SDS44 to SDS50
WI-0100 | oneM2M and SensorThings API | SDS45: 5%; SDS46: 5%; SDS47: 15%; SDS48: 20%; SDS49: 20%; SDS50: 20% | Rel-5 TR work in progress
WI-0102 | System enhancements to support Data License Management | SDS46: 5%; SDS47: 15%; SDS48: 30%; SDS49: 40%; SDS50: 45% | Rel-5 TR work in progress
WI-0071 | oneM2M and W3C Web of Things Interworking | SDS39: 25%; SDS40: 25%; SDS41: 25%; SDS42: 25%; SDS43: 25%; SDS44: 25%; SDS45: 25% | Stalled / Close
WI-0082 | 3GPP V2X Interworking | SDS39: 15%; SDS40: 18%; SDS41: 20%; SDS42: 20%; SDS43: 20%; SDS44: 20%; SDS45: 20% | Stalled / Close
WI-0088 | M2M/IoT Application and Component Configuration | SDS39: 15%; SDS40: 15%; SDS41: 15%; SDS42: 15%; SDS43: 15%; SDS44: 15%; SDS45: 15% | Stalled / Close