## Contribs
SHORT DOC NB | SHORTNAME | SOURCE | STATUS | DOC TYPE | Release | TS/TR
SDS-2022-0024R02 | Diagram-CR-R2 | BT | Draft | Change | R2 | TS-0003
SDS-2022-0033 | Rel 2 Ref updates 1-TS-0003 | BT | Draft | Change | R2 | TS-0003
SDS-2022-0028 | Allow non-confirmable messages in CoAP R3 | IBM | Draft | Change | R3 | TS-0008
SDS-2022-0029 | Allow non-confirmable messages in CoAP R2 | IBM | Draft | Change | R2 | TS-0008
SDS-2022-0022 | TS-0001_resourceIdentifiers_format_conversion_R3 | Miguel Angel Reina Ortega (ETSI) | Draft | Change | R3 | TS-0001
SDS-2022-0023 | TS-0004_resourceIdentifiers_format_conversion_R3 | Miguel Angel Reina Ortega (ETSI) | Draft | Change | R3 | TS-0001
SDS-2022-0009 | TS-0001_operationResult_multiplicity_R3 | Miguel Angel Reina Ortega (ETSI) | Draft | Change | R3 | TS-0001
SDS-2022-0010 | TS-0004_operationResult_handling_R3 | Miguel Angel Reina Ortega (ETSI) | Draft | Change | R3 | TS-0004
SDS-2022-0002 | CMDH_Buffering | Exacta | Draft | Discussion | R5 | TS-0022
SDS-2022-0014 | Improving Queries in Discovery and Retrieve Requests | Deutsche Telekom | Draft | Discussion | R5 | TS-0001
SDS-2022-0015 | Add lastSeenTime and lastCommunicationTime attributes to <node> | Deutsche Telekom | Draft | New feature | R5 | TS-0001
SDS-2022-0020 | Discussion_on_announcement_issues | Deutsche Telekom, ETSI | Draft | New feature | R5 | TS-0001
SDS-2022-0026 | DeviceManagementIssues | C-DOT | Draft | Discussion |  | TS-0004
Other docs
SDS-2021-0274R01 | requestAggregationForPollingChannel_R4 | Exacta | Noted | Change | R4 | TS-0004 | revision expected
SDS-2021-0253R01 | Semantic Filter result serialization type | KETI | Noted | Change | R4 | TS-0001
SDS-2021-0256R01 | Semantic Filter result serialization type (R3) | KETI | Noted | Change | R3 | TS-0001
SDS-2021-0255R01 | Semantic Query Indicator parameter clarification (R2) | KETI | Draft | Change | R2 | TS-0009 | revision expected in SDS 52
SDS-2021-0254R01 | Semantic Query Indicator parameter clarification (R3) | KETI | Draft | Change | R3 | TS-0009 | revision expected in SDS 52
SDS-2022-0008 | Improve TS-0001 clause 9.6.26.3 “Common Attributes for Announced Resources” | Deutsche Telekom | Noted | Change | R4 | TS-0001
SDS-2021-0259 | Key issue on Right to be Forgotten | Hyundai Motors, KETI | Draft | New feature | R5 | TR-0062
SDS-2021-0262R01 | gsma_reqts_001 | Exacta | Draft | New feature | R5 | TR-0063 | Not discussed
SDS-2021-0222 | TS-0004_attribute_level_ACPs_for_responses_R4 | Exacta | Draft | ? | R4 | TS-0004 | No document
SDS-2021-0115R02 | TS-0004_rateLimit_elements_multiplicity_R3 | Miguel Angel Reina Ortega, ETSI | Draft | Change | R3 | TS-0004 | Not discussed
SDS-2021-0116 | TS-0004_rateLimit_elements_multiplicity_R4 | Miguel Angel Reina Ortega, ETSI | Draft | Change | R4 | TS-0004 | Not discussed
SDS-2021-0088 | TS-0004_Fixes_for_crossResourceSubscription_R3 | Bob Flynn, Exacta; Miguel Angel Reina Ortega, ETSI | Draft | Change | R3 | TS-0004 | Not discussed
SDS-2021-0087 | TS-0001_Fixes_for_crossResourceSubscription_R3 | Bob Flynn, Exacta; Miguel Angel Reina Ortega, ETSI | Draft | Change | R3 | TS-0001 | Not discussed
SDS-2021-0049R01 | TS-0001_latest_oldest_multiplicity_R3 | Bob Flynn, Exacta; Miguel Angel Reina Ortega, ETSI | Draft | Change | R3 | TS-0001 | Not discussed
Note on A18: Karen Hughes: This was 'LEFT OPEN' during SDS 52
Note on A21: Karen Hughes: Revision expected (SDS 52)
Note on A22: Karen Hughes: Revision expected (SDS 52)
Note on A27: Karen Hughes: Not discussed during SDS 52
Note on A28: Karen Hughes: not discussed during SDS 52
Note on A29: Karen Hughes: Not discussed in SDS 52
Note on A30: Karen Hughes: Not discussed during SDS 52
Note on A31: Karen Hughes: Not discussed during SDS 52
Note on A32: Karen Hughes: Not discussed during SDS 52
Note on A33: Karen Hughes: Not discussed at TP 52

## CR Packs
TS-0001 (R2) | TS-0001 (R3) | TS-0001 (R4) | TS-0001 (R5) | TS-0003 (R2) | TS-0003 (R3) | TS-0003 (R4) | TS-0004 (R2) | TS-0004 (R3) | TS-0004 (R4) | TS-0004 (R5) | TS-0005(R3) | TS-0006(R3) | TS-0008 (R2) | TS-0008 (R3) | TS-0008 (R4) | TS-0009 (R2) | TS-0009 (R3) | TS-0009 (R4) | TS-0010 (R2) | TS-0010 (R3) | TS-0010 (R4) | TS-0014 (R2) | TS-0014 (R3) | TS-0022 (R2) | TS-0022 (R3) | TS-0022 (R4) | TS-0022 (R5) | TS-0026 (R3) | TS-0026 (R4) | TS-0032 (R2) | TS-0032 (R3) | TS-0034 (R5)
|  |  | SDS-2021-0113 | [6 empty] | SDS-2021-0114R01 | [16 empty] | SDS-2021-0185R02 |  |  |  |  | SDS-2021-0217R03
|  |  | SDS-2021-0181R08 | [6 empty] | SDS-2021-0190
|  |  | SDS-2022-0007R01 | [6 empty] | SDS-2022-0006R01

## WI
WI | Title | SDS39 | SDS40 | SDS41 | SDS42 | SDS43 | SDS44 | SDS45 | SDS46 | SDS47 | SDS48 | SDS49 | SDS50 | SDS51 | SDS52 | Comments
WI-0053 | Enhancements on Semantic Support | 30% | 40% | 50% | 75% | 90% | 95% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0058 | Interworking with 3GPP networks | 60% | 68% | 75% | 80% | 80% | 90% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0064 | Adaption of oneM2M for Smart City | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Stalled - No normative R4 work planned
WI-0069 | Heterogen. identificat. service in oneM2M syst. | 50% | 50% | 60% | 60% | 60% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | Stalled - No normative R4 work planned
WI-0072 | Modbus Interworking | 60% | 70% | 75% | 80% | 85% | 90% | 91% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | R4 - Complete
WI-0076 | Lightweight oneM2M Services | 20% | 40% | 50% | 60% | 65% | 70% | 80% | 85% | 90% | 93% | 97% | 97% | 100% | 100% | R4 - Complete
WI-0077 | Attribute based Access Control Policy | 65% | 75% | 75% | 80% | 85% | 85% | 90% | 92% | 93% | 95% | 97% | 97% | 100% | 100% | R4 - Complete
WI-0080 | Edge and Fog Computing | 20% | 35% | 45% | 55% | 65% | 70% | 80% | 85% | 90% | 95% | 97% | 97% | 100% | 100% | R4 - Complete
WI-0083 | oneM2M Service Subscribers and Users | 30% | 50% | 50% | 60% | 70% | 75% | 80% | 85% | 90% | 90% | 91% | 95% | 100% | 100% | R4 - Complete
WI-0089 | Getting started with oneM2M | 20% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 22% | 25% | 30% | 30% | 30% | 30% | R4/R5 work in progress
WI-0091 | oneM2M Services and Platform Discovery | 15% | 30% | 30% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | Stalled - Push to R5?
WI-0093 | Action Triggering Enhancements | 5% | 20% | 20% | 30% | 40% | 60% | 80% | 80% | 85% | 90% | 91% | 93% | 93% | 97% | R4 - Complete
WI-0090 | oneM2M and Zigbee interworking | 0% | 0% | 0% | 0% | 0% | 30% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | Rel-5 TR work in progress
WI-0095 | oneM2M System Enhancements to Support Data Protection Regulations | [5 empty] | 30% | 50% | 55% | 65% | 65% | 65% | 65% | 65% | 70% | Rel-5 TR work in progress
WI-0096 | Effective IoT Communication to Protect 3GPP Networks | [14 empty] | Rel-5 TR work in progress | bar: SDS39 to SDS52
WI-0100 | oneM2M and SensorThings API | SDS45: 5%; SDS46: 5%; SDS47: 15%; SDS48: 20%; SDS49: 20%; SDS50: 20%; SDS51: 25%; SDS52: 25% | Rel-5 TR work in progress
WI-0102 | System enhancements to support Data License Management | SDS46: 5%; SDS47: 15%; SDS48: 30%; SDS49: 40%; SDS50: 45%; SDS51: 45%; SDS52: 50% | Rel-5 TR work in progress
WI-0105 | System enhancements to support AI capabilities | [14 empty] | Initial concepts discussed
WI-0071 | oneM2M and W3C Web of Things Interworking | SDS39: 25%; SDS40: 25%; SDS41: 25%; SDS42: 25%; SDS43: 25%; SDS44: 25%; SDS45: 25% | Stalled / Close
WI-0082 | 3GPP V2X Interworking | SDS39: 15%; SDS40: 18%; SDS41: 20%; SDS42: 20%; SDS43: 20%; SDS44: 20%; SDS45: 20% | Stalled / Close
WI-0088 | M2M/IoT Application and Component Configuration | SDS39: 15%; SDS40: 15%; SDS41: 15%; SDS42: 15%; SDS43: 15%; SDS44: 15%; SDS45: 15% | Stalled / Close